## Overall Checklist Progress
Checklist Status
In-Ground Services Install - In-Ground Services Install - Zone 1
Trench and Backfill - QES-ITC-E01-001 | wip
Underground Conduit Installation - QES-ITC-E01-002 | wip
Cable Pit Installation - QES-ITC-E01-003 | not started
In-Ground Services Install - In-Ground Services Install - Zone 2
Trench and Backfill - QES-ITC-E01-004 | wip
Underground Conduit Installation - QES-ITC-E01-005 | wip
Cable Pit Installation - QES-ITC-E01-006 | not started
In-Ground Services Install - In-Ground Services Install - Zone 3
Trench and Backfill - QES-ITC-E01-007 | wip
Underground Conduit Installation - QES-ITC-E01-008 | wip
Cable Pit Installation - QES-ITC-E01-009 | not started
In-Ground Services Install - In-Ground Services Install - Temps
Trench and Backfill - QES-ITC-E01-010 | not started
Underground Conduit Installation - QES-ITC-E01-011 | not started
In Slab Services Install
Cast in Conduit Installation - Level 00 - Pour 1- QES-ITC-E02-001 | pass
Cast in Conduit Installation - Level 00 - Pour 2 - QES-ITC-E02-002 | pass
Cast in Conduit Installation - Level 00 - Pour 3 - QES-ITC-E02-003 | pass
Cast in Conduit Installation - Level 00 - Pour 4 - QES-ITC-E02-004 | pass
Cast in Conduit Installation - Level 00 - Pour 5 - QES-ITC-E02-005 | not started
Cast in Conduit Installation - Level 01 - Pour 1 - QES-ITC-E02-007 | pass
Cast in Conduit Installation - Level 01 - Pour 2 - QES-ITC-E02-008 | not started
Cast in Conduit Installation - Level 01 - Pour 3 - QES-ITC-E02-009 | not started
Cast in Conduit Installation - Level 02 - Pour 1 - QES-ITC-E02-010 | not started
Cast in Conduit Installation - Level 02 - Pour 2 - QES-ITC-E02-011 | not started
Cast in Conduit Installation - Level 02 - Pour 3 - QES-ITC-E02-012 | not started
Cast in Conduit Installation - Stair 1 - QES-ITC-E02-013 | not started
Cast in Conduit Installation - Stair 2 - QES-ITC-E02-014 | pass
Cast in Conduit Installation - External Slabs - QES-ITC-E02-015 | not started
Cast in Conduit Installation - Outbuildings - QES-ITC-E02-016 | not started
Cast in Conduit Installation - Level 00 - Pour 6 - QES-ITC-E02-006 | not started
Equipotential Bonding
Equipotential Bonding - Level 00 - Pour 1 - QES-ITC-E16-001 | pass
Equipotential Bonding - Level 00 - Pour 2 - QES-ITC-E16-002 | pass
Equipotential Bonding - Level 00 - Pour 3 - QES-ITC-E16-003 | pass
Equipotential Bonding - Level 00 - Pour 4 - QES-ITC-E16-004 | pass
Equipotential Bonding - Level 00 - Pour 5 - QES-ITC-E16-005 | not started
Equipotential Bonding - Level 01 - Pour 1 - QES-ITC-E16-007 | pass
Equipotential Bonding - Level 02 - Pour 1- QES-ITC-E16-008 | not started
Equipotential Bonding - Level 02 - Pour 2 - QES-ITC-E16-009 | not started
QES-ITC-E16-009 - Equipotential Bonding - Level 02 - Pour 3 | not started
QES-ITC-E16-010 - Equipotential Bonding - Stair 1 | not started
QES-ITC-E16-011 - Equipotential Bonding - Stair 2 | wip
QES-ITC-E16-012 - Equipotential Bonding - External slabs | not started
QES-ITC-E16-013 - Equipotential Bonding - Outbuildings | not started
Equipotential Bonding - Level 00 - Pour 6 - QES-ITC-E16-006 | not started
Cable Tray Installation
QES-ITC-E04-001 - Cable Tray Installation - Level 00 | not started
QES-ITC-E04-002 - Cable Tray Installation - Level 01 | not started
QES-ITC-E04-003 - Cable Tray Installation - Level 02 | not started
QES-ITC-E04-004 - Cable Tray Installation - Outbuildings | not started
Fire Sealing
QES-ITC-E13-001 - Fire Sealing - Level 00 | not started
QES-ITC-E13-002 - Fire Sealing - Level 01 | not started
QES-ITC-E13-003 - Fire Sealing - Level 02 | not started
QES-ITC-E13-004 - Fire Sealing - Outbuildings | not started
Lightning Protection
QES-ITC-E12-001 - Lightning Protection | wip
Luminaires
QES-ITC-E07-001 - Pole 1 | not started
QES-ITC-E07-002 - Pole 2 | not started
QES-ITC-E07-003 - Luminaires - Emergency & Exit Lighting - Level 00 | not started
QES-ITC-E07-004 - Luminaires - Emergency & Exit Lighting - Level 01 | not started
QES-ITC-E07-005 - Luminaires - Emergency & Exit Lighting - Level 02 | not started
QES-ITC-E07-006 - Luminaires - Emergency & Exit Lighting - Outbuildings | not started
MSB - MSB - SMSB-1
QES-ITC-E05-001 - MSB - SMSB-1- Earth Electrode | not started
QES-ITC-E05-003 - MSB - SMSB-1- Switchboard & Distribution Board Installation | not started
QES-ITC-E05-005 - MSB - SMSB-1 - Mains & Submains Installation | not started
QES-ITC-E05-011 - MSB - SMSB-1 - Cable Terminations | not started
QES-ITC-E05-015 - MSB - SMSB-1 - Final Installation Test Sheet | not started
MSB - MSB - SMSB-2
QES-ITC-E05-002 - MSB - SMSB-2- Earth Electrode | not started
QES-ITC-E05-004 - MSB - SMSB-2- Switchboard & Distribution Board Installation | not started
QES-ITC-E05-006 - MSB - SMSB-2- Mains & Submains Installation | not started
QES-ITC-E05-012 - MSB - SMSB-2- Cable Terminations | not started
QES-ITC-E05-016 - MSB - SMSB-2 - Final Installation Test Sheet | not started
MSB - MSB - MDB-SA-1
QES-ITC-E05-007 - MSB - MDB-SA-1 - Switchboard & Distribution Board Installation | not started
QES-ITC-E05-009 - MSB - MDB-SA-1 - Mains & Submains Installation | not started
QES-ITC-E05-013 - MSB - MDB-SA-1 - Cable Terminations | not started
QES-ITC-E05-017 - MSB - MDB-SA-1 - Final Installation Test Sheet | not started
MSB - MSB - MDB-SA-2
QES-ITC-E05-008 - MSB - MDB-SA-2 - Switchboard & Distribution Board Installation | not started
QES-ITC-E05-010 - MSB - MDB-SA-2 - Mains & Submains Installation | not started
QES-ITC-E05-014 - MSB - MDB-SA-2 - Cable Terminations | not started
QES-ITC-E05-018 - MSB - MDB-SA-2 - Final Installation Test Sheet | not started
MSB - MSB - MSB-SHP
QES-ITC-E05-019 - MSB - MSB-SHP - Earth Electrode | not started
QES-ITC-E05-020 - MSB - MSB-SHP - Mains & Submains Installation | not started
QES-ITC-E05-021 - MSB - MSB-SHP - Cable Terminations | not started
QES-ITC-E05-024 - MSB - MSB-SHP - Final Installation Test Sheet | not started
MSB - MSB - MSB-CP
QES-ITC-E05-022 - MSB - MSB-CP - Mains & Submains Installation | not started
QES-ITC-E05-023 - MSB - MSB-CP - Cable Terminations | not started
QES-ITC-E05-025 - MSB - MSB-CP - Final Installation Test Sheet | not started
DB - DB - DB-FPR
QES-ITC-E06-001 - DB - DB-FPR - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-002 - DB - DB-FPR - Cable Terminations | not started
QES-ITC-E06-003 - DB - DB-FPR - Final Installation Test Sheet | not started
DB - DB - DB-WPR
QES-ITC-E06-004 - DB - DB-WPR - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-005 - DB - DB-WPR - Cable Terminations | not started
QES-ITC-E06-006 - DB - DB-WPR - Final Installation Test Sheet | not started
DB - DB - DB-SUB
QES-ITC-E06-007 - DB - DB-SUB - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-008 - DB - DB-SUB - Cable Terminations | not started
QES-ITC-E06-009 - DB - DB-SUB - Final Installation Test Sheet | not started
DB - DB - DB-SMSB
QES-ITC-E06-010 - DB - DB-SMSB - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-011 - DB - DB-SMSB - Cable Terminations | not started
QES-ITC-E06-012 - DB - DB-SMSB - Final Installation Test Sheet | not started
DB - DB - DB-PFC
QES-ITC-E06-013 - DB - PFC UNIT - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-014 - DB - PFC UNIT - Cable Terminations | not started
QES-ITC-E06-015 - DB - PFC UNIT - Final Installation Test Sheet | not started
DB - DB - DB-UPS
QES-ITC-E06-016 - DB - DB-UPS - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-017 - DB - DB-UPS - Cable Terminations | not started
QES-ITC-E06-018 - DB - DB-UPS - Final Installation Test Sheet | not started
DB - DB - DB-H1
QES-ITC-E06-019 - DB - DB-H1 - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-020 - DB - DB-H1 - Cable Terminations | not started
QES-ITC-E06-021 - DB - DB-H1 - Final Installation Test Sheet | not started
DB - DB - DB-LG-1-E
QES-ITC-E06-022 - DB - DB-LG-1-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-023 - DB - DB-LG-1-E - Cable Terminations | not started
QES-ITC-E06-024 - DB - DB-LG-1-E - Final Installation Test Sheet | not started
DB - DB - DB-LG-2-E
QES-ITC-E06-025 - DB - DB-LG-2-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-026 - DB - DB-LG-2-E - Cable Terminations | not started
QES-ITC-E06-027 - DB - DB-LG-2-E - Final Installation Test Sheet | not started
DB - DB - DB-L1-1-E
QES-ITC-E06-028 - DB - DB-L1-1-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-029 - DB - DB-L1-1-E - Cable Terminations | not started
QES-ITC-E06-030 - DB - DB-L1-1-E - Final Installation Test Sheet | not started
DB - DB - DB-L1-2-E
QES-ITC-E06-031 - DB - DB- L1-2-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-032 - DB - DB-L1-2-E - Cable Terminations | not started
QES-ITC-E06-033 - DB - DB-L1-2-E - Final Installation Test Sheet | not started
DB - DB - DB-L2-1-E
QES-ITC-E06-034 - DB - DB-L2-1-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-035 - DB - DB-L2-1-E - Cable Terminations | not started
QES-ITC-E06-036 - DB - DB-L2-1-E - Final Installation Test Sheet | not started
DB - DB - DB-L2-2-E
QES-ITC-E06-037 - DB - DB-L2-2-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-038 - DB - DB-L2-2-E - Cable Terminations | not started
QES-ITC-E06-039 - DB - DB-L2-2-E - Final Installation Test Sheet | not started
DB - DB - DB-LG-C-E
QES-ITC-E06-040 - DB - DB-LG-C-E - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-041 - DB - DB-LG-C-E - Cable Terminations | not started
QES-ITC-E06-042 - DB - DB-LG-C-E - Final Installation Test Sheet | not started
DB - DB - DB-LG-K-NE
QES-ITC-E06-043 - DB - DB-LG-K-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-044 - DB - DB-LG-K-NE - Cable Terminations | not started
QES-ITC-E06-045 - DB - DB-LG-K-NE - Final Installation Test Sheet | not started
DB - DB - DB-LG-1-NE
QES-ITC-E06-046 - DB - DB-LG-1-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-047 - DB - DB-LG-1-NE - Cable Terminations | not started
QES-ITC-E06-048 - DB - DB-LG-1-NE - Final Installation Test Sheet | not started
DB - DB - DB-LG-2-NE
QES-ITC-E06-049 - DB - DB-LG-2-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-050 - DB - DB-LG-2-NE - Cable Terminations | not started
QES-ITC-E06-051 - DB - DB-LG-2-NE - Final Installation Test Sheet | not started
DB - DB - DB-L1-1-NE
QES-ITC-E06-052 - DB - DB-L1-1-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-053 - DB - DB-L1-1-NE - Cable Terminations | not started
QES-ITC-E06-054 - DB - DB-L1-1-NE - Final Installation Test Sheet | not started
DB - DB - DB-L1-2-NE
QES-ITC-E06-055 - DB - DB-L1-2-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-056 - DB - DB-L1-2-NE - Cable Terminations | not started
QES-ITC-E06-057 - DB - DB-L1-2-NE - Final Installation Test Sheet | not started
DB - DB - DB-L2-1-NE
QES-ITC-E06-058 - DB - DB-L2-1-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-059 - DB - DB-L2-1-NE - Cable Terminations | not started
QES-ITC-E06-060 - DB - DB-L2-1-NE - Final Installation Test Sheet | not started
DB - DB - DB-L2-2-NE
QES-ITC-E06-061 - DB - DB-L2-2-NE - Switchboard & Distribution Board Installation | not started
QES-ITC-E06-062 - DB - DB-L2-2-NE - Cable Terminations | not started
QES-ITC-E06-063 - DB - DB-L2-2-NE - Final Installation Test Sheet | not started
UPS - DB - DB-LG-1-U
QES-ITC-E11-001 - UPS - DB-LG-1-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-002 - UPS - DB-LG-1-U - Cable Terminations | not started
QES-ITC-E11-003 - UPS - DB-LG-1-U - Final Installation Test Sheet | not started
UPS - DB - DB-LG-2-U
QES-ITC-E11-004 - UPS - DB-LG-2-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-005 - UPS - DB-LG-2-U - Cable Terminations | not started
QES-ITC-E11-006 - UPS - DB-LG-2-U- Final Installation Test Sheet | not started
UPS - DB - DB-L1-1-U
QES-ITC-E11-007 - UPS - DB-L1-1-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-008 - UPS - DB-L1-1-U - Cable Terminations | not started
QES-ITC-E11-009 - UPS - DB-L1-1-U - Final Installation Test Sheet | not started
UPS - DB - DB-L1-2-U
QES-ITC-E11-010 - UPS - DB-L1-2-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-011 - UPS - DB-L1-2-U - Cable Terminations | not started
QES-ITC-E11-012 - UPS - DB-L1-2-U - Final Installation Test Sheet | not started
UPS - DB - DB-L2-1-U
QES-ITC-E11-013 - UPS - DB-L2-1-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-014 - UPS - DB-L2-1-U - Cable Terminations | not started
QES-ITC-E11-015 - UPS - DB-L2-1-U - Final Installation Test Sheet | not started
UPS - DB - DB-L2-2-U
QES-ITC-E11-016 - UPS - DB-L2-2-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-017 - UPS - DB-L2-2-U - Cable Terminations | not started
QES-ITC-E11-018 - UPS - DB-L2-2-U - Final Installation Test Sheet | not started
UPS - DB - DB-LG-C-U
QES-ITC-E11-019 - UPS - DB-LG-C-U - Switchboard & Distribution Board Installation | not started
QES-ITC-E11-020 - UPS - DB-LG-C-U - Cable Terminations | not started
QES-ITC-E11-021 - UPS - DB-LG-C-U - Final Installation Test Sheet | not started
Electrical Services - Level 00 - Kitchen 0.4.006
Cable Rough in - 00 - Kitchen 0.4.006 - QES-ITC-E03-001 | wip
Power Fit Off - 00 - Kitchen 0.4.006 - QES-ITC-E08-001 | wip
Electrical Services - Level 00 - Bulk Store/ Materials Management 04.005
Cable Rough in - 00 - Bulk Store/ Materials Management 04.005 - QES-ITC-E03-002 | wip
Power Fit Off - 00 - Bulk Store/ Materials Management 04.005 - QES-ITC-E08-002 | wip
Electrical Services - Level 00 - Loading Dock/Clean 0.4.004
Cable Rough in - 00 - Loading Dock/Clean 0.4.004 - QES-ITC-E03-003 | wip
Power Fit Off - Power Fit Off - 00 - Loading Dock/Clean 0.4.004 - QES-ITC-E08-003 | wip
Electrical Services - Level 00 - Body Hold 0.4.002
Cable Rough in - 00 - Body Hold 0.4.002 - QES-ITC-E03-004 | wip
Power Fit Off - 00 - Body Hold 0.4.002 - QES-ITC-E08-004 | wip
Electrical Services - Level 00 - Toilet Accessible 0.4.003
Cable Rough in - 00 - Toilet Accessible 0.4.003 - QES-ITC-E03-005 | wip
Power Fit Off - 00 - Toilet Accessible 0.4.003 - QES-ITC-E08-005 | wip
Electrical Services - Level 00 - Loading Dock/Dirty 0.4.008
Cable Rough in - 00 - Loading Dock/Dirty 0.4.008 - QES-ITC-E03-006 | wip
Power Fit Off - 00 - Loading Dock/Dirty 0.4.008 - QES-ITC-E08-006 | wip
Electrical Services - Level 00 - Store/Dirty Linen 0.4.009
Cable Rough in - 00 - Store/Dirty Linen 0.4.009 - QES-ITC-E03-007 | wip
Power Fit Off - 00 - Store/Dirty Linen 0.4.009 - QES-ITC-E08-007 | wip
Electrical Services - Level 00 - Cleaners Room 10m2 0.4.013
Cable Rough in - 00 - Cleaners Room 10m2 0.4.013 - QES-ITC-E03-008 | wip
Power Fit Off - 00 - Cleaners Room 10m2 0.4.013 - QES-ITC-E08-008 | wip
Electrical Services - Level 00 - Office/Write Up 5m2 0.4.053
Cable Rough in - 00 - Office/Write Up 5m2 0.4.053 - QES-ITC-E03-009 | wip
Power Fit Off - 00 - Office/Write Up 5m2 0.4.053 - QES-ITC-E08-009 | wip
Electrical Services - Level 00 - Airlock/Entry 0.4.012
Cable Rough in - 00 - Airlock/Entry 0.4.012 - QES-ITC-E03-010 | wip
Power Fit Off - 00 - Airlock/Entry 0.4.012 - QES-ITC-E08-010 | wip
Electrical Services - Level 00 - Store/Clean Linen 0.4.011
Cable Rough in - 00 - Store/Clean Linen 0.4.011 - QES-ITC-E03-011 | wip
Power Fit Off - 00 - Store/Clean Linen 0.4.011 - QES-ITC-E08-011 | wip
Electrical Services - Level 00 - Communications Store 0.E.014
Cable Rough in - 00 - Communications Store 0.E.014 - QES-ITC-E03-012 | wip
Power Fit Off - 00 - Communications Store 0.E.014 - QES-ITC-E08-012 | wip
Electrical Services - Level 00 - Comms Room L00 0.E.015
Cable Rough in - 00 - Comms Room L00 0.E.015 - QES-ITC-E03-013 | wip
Power Fit Off - 00 - Comms Room L00 0.E.015 - QES-ITC-E08-013 | wip
Electrical Services - Level 00 - Office/2 Person 0.4.014
Cable Rough in - 00 - Office/2 Person 0.4.014 - QES-ITC-E03-014 | wip
Power Fit Off - 00 - Office/2 Person 0.4.014 - QES-ITC-E08-014 | wip
Electrical Services - Level 00 - Central Equipment Store 0.4.010
Cable Rough in - 00 - Central Equipment Store 0.4.010 - QES-ITC-E03-015 | wip
Power Fit Off - 00 - Central Equipment Store 0.4.010 - QES-ITC-E08-015 | wip
Electrical Services - Level 00 - Store/Equipment 30m2 0.2.048
Cable Rough in - 00 - Store/Equipment 30m2 0.2.048 - QES-ITC-E03-016 | wip
Power Fit Off - 00 - Store/Equipment 30m2 0.2.048 - QES-ITC-E08-016 | wip
Electrical Services - Level 00 - Store/Pharmacy 0.4.015
Cable Rough in - 00 - Store/Pharmacy 0.4.015 - QES-ITC-E03-017 | wip
Power Fit Off - 00 - Store/Pharmacy 0.4.015 - QES-ITC-E08-017 | wip
Electrical Services - Level 00 - Pathology 0.4.016
Cable Rough in - 00 - Pathology 0.4.016 - QES-ITC-E03-018 | wip
Power Fit Off - 00 - Pathology 0.4.016 - QES-ITC-E08-018 | wip
Electrical Services - Level 00 - Staff Change Male 0.4.001
Cable Rough in - 00 - Staff Change Male 0.4.001 - QES-ITC-E03-019 | wip
Power Fit Off - 00 - Staff Change Male 0.4.001 - QES-ITC-E08-019 | wip
Electrical Services - Level 00 - Staff Change Female 0.4.000
Cable Rough in - 00 - Staff Change Female 0.4.000 - QES-ITC-E03-020 | wip
Power Fit Off - 00 - Staff Change Female 0.4.000 - QES-ITC-E08-020 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.000
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.000 - QES-ITC-E03-021 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.000 - QES-ITC-E08-021 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.003
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.003 - QES-ITC-E03-022 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.003 - QES-ITC-E08-022 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.004
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.004 - QES-ITC-E03-023 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.004 - QES-ITC-E08-023 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.007
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.007 - QES-ITC-E03-024 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.007 - QES-ITC-E08-024 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.008
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.008 - QES-ITC-E03-025 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.008 - QES-ITC-E08-025 | wip
Electrical Services - Level 00 - 4 Bed Room - Inboard Ensuite 0.2.011
Cable Rough in - 00 - 4 Bed Room - Inboard Ensuite 0.2.011 - QES-ITC-E03-026 | wip
Power Fit Off - 00 - 4 Bed Room - Inboard Ensuite 0.2.011 - QES-ITC-E08-026 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.014
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.014 - QES-ITC-E03-027 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.014 - QES-ITC-E08-027 | wip
Electrical Services - Level 00 - Lounge/ Patient Family 30m2 0.2.015
Cable Rough in - 00 - Lounge/ Patient Family 30m2 0.2.015 - QES-ITC-E03-028 | wip
Power Fit Off - 00 - Lounge/ Patient Family 30m2 0.2.015 - QES-ITC-E08-028 | wip
Electrical Services - Level 00 - 1 Bed Room Bariatric 0.2.063
Cable Rough in - 00 - 1 Bed Room Bariatric 0.2.063 - QES-ITC-E03-029 | wip
Power Fit Off - 00 - 1 Bed Room Bariatic 0.2.063 - QES-ITC-E08-029 | wip
Electrical Services - Level 00 - 1 Bed Room Bariatric 0.2.062
Cable Rough in - 00 - 1 Bed Room Bariatric 0.2.062 - QES-ITC-E03-030 | wip
Power Fit Off - 00 - 1 Bed Room Bariatic 0.2.062 - QES-ITC-E08-030 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.059
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.059 - QES-ITC-E03-031 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.059 - QES-ITC-E08-031 | wip
Electrical Services - Level 00 - Independent Assessment Suite 0.2.049
Cable Rough in - 00 - Independent Assessment Suite 0.2.049 - QES-ITC-E03-032 | wip
Power Fit Off - 00 - Independent Assessment Suite 0.2.049 - QES-ITC-E08-032 | wip
Electrical Services - Level 00 - 1 Bed Room Bariatric 0.2.054
Cable Rough in - 00 - 1 Bed Room Bariatric 0.2.054 - QES-ITC-E03-033 | wip
Power Fit Off - 00 - 1 Bed Room Bariatric 0.2.054 - QES-ITC-E08-033 | wip
Electrical Services - Level 00 - 1 Bed Room Bariatric 0.2.051
Cable Rough in - 00 - 1 Bed Room Bariatric 0.2.051 - QES-ITC-E03-034 | wip
Power Fit Off - 00 - 1 Bed Room Bariatric 0.2.051 - QES-ITC-E08-034 | wip
Electrical Services - Level 00 - 1 Bed Room Bariatric 0.2.055
Cable Rough in - 00 - 1 Bed Room Bariatric 0.2.055 - QES-ITC-E03-035 | wip
Power Fit Off - 00 - 1 Bed Room Bariatric 0.2.055 - QES-ITC-E08-035 | wip
Electrical Services - Level 00 - Disposal Room 10m2 0.2.043
Cable Rough in - 00 - Disposal Room 10m2 0.2.043 - QES-ITC-E03-036 | wip
Power Fit Off - 00 - Disposal Room 10m2 0.2.043 - QES-ITC-E08-036 | wip
Electrical Services - Level 00 - Store/General 0.2.046
Cable Rough in - 00 - Store/General 0.2.046 - QES-ITC-E03-037 | wip
Power Fit Off - 00 - Store/General 0.2.046 - QES-ITC-E08-037 | wip
Electrical Services - Level 00 - Cleaners Room 5m2 0.2.047
Cable Rough in - 00 - Cleaners Room 5m2 0.2.047 - QES-ITC-E03-038 | wip
Power Fit Off - 00 - Cleaners Room 5m2 0.2.047 - QES-ITC-E08-038 | wip
Electrical Services - Level 00 - Toilet Staff 0.2.045
Cable Rough in - 00 - Toilet Staff 0.2.045 - QES-ITC-E03-039 | wip
Power Fit Off - 00 - Toilet Staff 0.2.045 - QES-ITC-E08-039 | wip
Electrical Services - Level 00 - Interview Room 0.2.036
Cable Rough in - 00 - Interview Room 0.2.036 - QES-ITC-E03-040 | wip
Power Fit Off - 00 - Interview Room 0.2.036 - QES-ITC-E08-040 | wip
Electrical Services - Level 00 - Toilet/Accessible 0.2.037
Cable Rough in - 00 - Toilet/Accessible 0.2.037 - QES-ITC-E03-041 | wip
Power Fit Off - 00 - Toilet/Accessible 0.2.037 - QES-ITC-E08-041 | wip
Electrical Services - Level 00 - Clean Store 10m2 0.2.069
Cable Rough in - 00 - Clean Store 10m2 0.2.069 - QES-ITC-E03-042 | wip
Power Fit Off - 00 - Clean Store 10m2 0.2.069 - QES-ITC-E08-042 | wip
Electrical Services - Level 00 - Dirty Utility 14m2 0.2.035
Cable Rough in - 00 - Dirty Utility 14m2 0.2.035 - QES-ITC-E03-043 | wip
Power Fit Off - 00 - Dirty Utility 14m2 0.2.035 - QES-ITC-E08-043 | wip
Electrical Services - Level 00 - Clean Utility/Medication Room 0.2.034
Cable Rough in - 00 - Clean Utility/Medication Room 0.2.034 - QES-ITC-E03-044 | wip
Power Fit Off - 00 - Clean Utility/Medication Room 0.2.034 - QES-ITC-E08-044 | wip
Electrical Services - Level 00 - Staff Station 14m2 0.2.033
Cable Rough in - 00 - Staff Station 14m2 0.2.033 - QES-ITC-E03-045 | wip
Power Fit Off - 00 - Staff Station 14m2 0.2.033 - QES-ITC-E08-045 | wip
Electrical Services - Level 00 - Office 1 Person/NUM 0.2.031
Cable Rough in - 00 - Office 1 Person/NUM 0.2.031 - QES-ITC-E03-046 | wip
Power Fit Off - 00 - Office 1 Person/NUM 0.2.031 - QES-ITC-E08-046 | wip
Electrical Services - Level 00 - Office/Clinical Workroom 0.2.030
Cable Rough in - 00 - Office/Clinical Workroom 0.2.030 - QES-ITC-E03-047 | wip
Power Fit Off - 00 - Office/Clinical Workroom 0.2.030 - QES-ITC-E08-047 | wip
Electrical Services - Level 00 - Comms Room L00 0.E.009
Cable Rough in - 00 - Comms Room L00 0.E.009 - QES-ITC-E03-048 | wip
Power Fit Off - 00 - Comms Room L00 0.E.009 - QES-ITC-E08-048 | wip
Electrical Services - Level 00 - Dining/Recreation Therapy Room 0.2.028
Cable Rough in - 00 - Dining/Recreation Therapy Room 0.2.028 - QES-ITC-E03-049 | wip
Power Fit Off - 00 - Dining/Recreation Therapy Room 0.2.028 - QES-ITC-E08-049 | wip
Electrical Services - Level 00 - Store/Gas 0.4.017
Cable Rough in - 00 - Store/Gas 0.4.017 - QES-ITC-E03-050 | wip
Power Fit Off - 00 - Store/Gas 0.4.017 - QES-ITC-E08-050 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.001
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.001 - QES-ITC-E03-051 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.001 - QES-ITC-E08-051 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.002
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.002 - QES-ITC-E03-052 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.002 - QES-ITC-E08-052 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.006
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.006 - QES-ITC-E03-053 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.006 - QES-ITC-E08-053 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.007
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.007 - QES-ITC-E03-054 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.007 - QES-ITC-E08-054 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.010
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.010 - QES-ITC-E03-055 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.010 - QES-ITC-E08-055 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.012
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.012 - QES-ITC-E03-056 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.012 - QES-ITC-E08-056 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.014
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.014 - QES-ITC-E03-057 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.014 - QES-ITC-E08-057 | wip
Electrical Services - Level 00 - Corridor/Patient Treatment Areas 0.T.015
Cable Rough in - 00 - Corridor/Patient Treatment Areas 0.T.015 - QES-ITC-E03-058 | wip
Power Fit Off - 00 - Corridor/Patient Treatment Areas 0.T.015 - QES-ITC-E08-058 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.017
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.017 - QES-ITC-E03-059 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.017 - QES-ITC-E08-059 | wip
Electrical Services - Level 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.018
Cable Rough in - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.018 - QES-ITC-E03-060 | wip
Power Fit Off - 00 - 2 Bed Room - Inboard Ensuite Type 2 0.2.018 - QES-ITC-E08-060 | wip
Electrical Services - Level 00 - Store/Equipment 0.3.019
Cable Rough in - 00 - Store/Equipment 0.3.019 - QES-ITC-E03-061 | wip
Power Fit Off - 00 - Store/Equipment 0.3.019 - QES-ITC-E08-061 | wip
Electrical Services - Level 00 - Consult Room 0.3.017
Cable Rough in - 00 - Consult Room 0.3.017 - QES-ITC-E03-062 | wip
Power Fit Off - 00 - Consult Room 0.3.017 - QES-ITC-E08-062 | wip
Electrical Services - Level 00 - Toilet/Accessible 0.3.018
Cable Rough in - 00 - Toilet/Accessible 0.3.018 - QES-ITC-E03-063 | wip
Power Fit Off - 00 - Toilet/Accessible 0.3.018 - QES-ITC-E08-063 | wip
Electrical Services - Level 00 - Office /Write up 5m2 0.3.021
Cable Rough in - 00 - Office /Write up 5m2 0.3.021 - QES-ITC-E03-064 | wip
Power Fit Off - 00 - Office /Write up 5m2 0.3.021 - QES-ITC-E08-064 | wip
Electrical Services - Level 00 - Gymnasium/Group Therapy 0.3.016
Cable Rough in - 00 - Gymnasium/Group Therapy 0.3.016 - QES-ITC-E03-065 | wip
Power Fit Off - 00 - Gymnasium/Group Therapy 0.3.016 - QES-ITC-E08-065 | wip
Electrical Services - Level 00 - Occupational Therapy Room 0.3.013
Cable Rough in - 00 - Occupational Therapy Room 0.3.013 - QES-ITC-E03-066 | wip
Power Fit Off - 00 - Occupational Therapy Room 0.3.013 - QES-ITC-E08-066 | wip
Electrical Services - Level 00 - Airlock/Entry 0.1.000
Cable Rough in - 00 - Airlock/Entry 0.1.000 - QES-ITC-E03-067 | wip
Power Fit Off - 00 - Airlock/Entry 0.1.000 - QES-ITC-E08-067 | wip
Electrical Services - Level 00 - Waiting/Entry Foyer 0.1.001
Cable Rough in - 00 - Waiting/Entry Foyer 0.1.001 - QES-ITC-E03-068 | wip
Power Fit Off - 00 - Waiting/Entry Foyer 0.1.001 - QES-ITC-E08-068 | wip
Electrical Services - Level 00 - CafÃ©/Retail 0.1.002
Cable Rough in - 00 - CafÃ©/Retail 0.1.002 - QES-ITC-E03-069 | wip
Power Fit Off - 00 - CafÃ©/Retail 0.1.002 - QES-ITC-E08-069 | wip
Electrical Services - Level 00 - Indigenous Health Liaison Office 0.1.010
Cable Rough in - 00 - CafÃ©/Retail 0.1.002 - QES-ITC-E03-070 | wip
Power Fit Off - 00 - CafÃ©/Retail 0.1.002 - QES-ITC-E08-070 | wip
Electrical Services - Level 00 - Quiet Room 0.1.003
Cable Rough in - 00 - Quiet Room 0.1.003 - QES-ITC-E03-071 | wip
Power Fit Off - 00 - Quiet Room 0.1.003 - QES-ITC-E08-071 | wip
Electrical Services - Level 00 - Multi Purpose Room 0.1.004
Cable Rough in - 00 - Multi Purpose Room 0.1.004 - QES-ITC-E03-072 | wip
Power Fit Off - 00 - Multi Purpose Room 0.1.004 - QES-ITC-E08-072 | wip
Electrical Services - Level 00 - 1 Bed Room - Inboard Ensuite Type 2 0.2.066
Cable Rough in - 00 - 1 Bed Room - Inboard Ensuite Type 2 0.2.066 - QES-ITC-E03-073 | wip
Power Fit Off - 00 - 1 Bed Room - Inboard Ensuite Type 2 0.2.066 - QES-ITC-E08-073 | wip
Electrical Services - Level 00 - 1 Bed Room - Inboard Ensuite Type 2 0.2.067
Cable Rough in - 00 - 1 Bed Room - Inboard Ensuite Type 2 0.2.067 - QES-ITC-E03-074 | wip
Power Fit Off - 00 - 1 Bed Room - Inboard Ensuite Type 2 0.2.067 - QES-ITC-E08-074 | wip
Electrical Services - Level 00 - Laundry/Patient 6m2 0.2.020
Cable Rough in - 00 - Laundry/Patient 6m2 0.2.020 - QES-ITC-E03-075 | wip
Power Fit Off - 00 - Laundry/Patient 6m2 0.2.020 - QES-ITC-E08-075 | wip
Electrical Services - Level 00 - Staff Station 10m2 0.2.021
Cable Rough in - 00 - Staff Station 10m2 0.2.021 - QES-ITC-E03-076 | wip
Power Fit Off - 00 - Staff Station 10m2 0.2.021 - QES-ITC-E08-076 | wip
Electrical Services - Level 00 - Consult Room 0.3.001
Cable Rough in - 00 - Consult Room 0.3.001 - QES-ITC-E03-077 | wip
Power Fit Off - 00 - Consult Room 0.3.001 - QES-ITC-E08-077 | wip
Electrical Services - Level 00 - Consult Room 0.3.003
Cable Rough in - 00 - Consult Room 0.3.003 - QES-ITC-E03-078 | wip
Power Fit Off - 00 - Consult Room 0.3.003 - QES-ITC-E08-078 | wip
Electrical Services - Level 00 - Toilet/Accessible 0.1.005
Cable Rough in - 00 - Toilet/Accessible 0.1.005 - QES-ITC-E03-079 | wip
Power Fit Off - 00 - Toilet/Accessible 0.1.005 - QES-ITC-E08-079 | wip
Electrical Services - Level 00 - Parenting Room 0.1.006
Cable Rough in - 00 - Parenting Room 0.1.006 - QES-ITC-E03-080 | wip
Power Fit Off - 00 - Parenting Room 0.1.006 - QES-ITC-E08-080 | wip
Electrical Services - Level 00 - Toilet/Public 0.1.007 & 0.1.008
Cable Rough in - 00 - Toilet/Public 0.1.007 & 0.1.008 - QES-ITC-E03-081 | wip
Power Fit Off - 00 - Toilet/Public 0.1.007 & 0.1.008 - QES-ITC-E08-081 | wip
Electrical Services - Level 00 - Reception 10m2 0.1.009
Cable Rough in - 00 - Reception 10m2 0.1.009 - QES-ITC-E03-082 | wip
Power Fit Off - 00 - Reception 10m2 0.1.009 - QES-ITC-E08-082 | wip
Electrical Services - Level 00 - Interview Room/Allied Health 0.3.004
Cable Rough in - 00 - Interview Room/Allied Health 0.3.004 - QES-ITC-E03-083 | wip
Power Fit Off - 00 - Interview Room/Allied Health 0.3.004 - QES-ITC-E08-08 | wip
Electrical Services - Level 00 - Interview Room/Allied Health 0.3.005
Cable Rough in - 00 - Interview Room/Allied Health 0.3.005 - QES-ITC-E03-084 | wip
Power Fit Off - 00 - Interview Room/Allied Health 0.3.005 - QES-ITC-E08-084 | wip
Electrical Services - Level 00 - Workstation 0.3.006
Cable Rough in - 00 - Workstation 0.3.006 - QES-ITC-E03-085 | wip
Power Fit Off - 00 - Workstation 0.3.006 - QES-ITC-E08-085 | wip
Electrical Services - Level 00 - Interview Room/Allied Health 0.3.008
Cable Rough in - 00 - Interview Room/Allied Health 0.3.008 - QES-ITC-E03-086 | wip
Power Fit Off - 00 - Interview Room/Allied Health 0.3.008 - QES-ITC-E08-086 | wip
Electrical Services - Level 00 - ADL Bathroom 0.3.007
Cable Rough in - 00 - ADL Bathroom 0.3.007 - QES-ITC-E03-087 | wip
Power Fit Off - 00 - ADL Bathroom 0.3.007 - QES-ITC-E08-087 | wip
Electrical Services - Level 00 - ADL Kitchen 0.3.010
Cable Rough in - 00 - ADL Kitchen 0.3.010 - QES-ITC-E03-088 | wip
Power Fit Off - 00 - ADL Kitchen 0.3.010 - QES-ITC-E08-088 | wip
Electrical Services - Level 00 - Electronic Distribution Board 0.E.013
Cable Rough in - 00 - Electronic Distribution Board 0.E.013 - QES-ITC-E03-089 | wip
Power Fit Off - 00 - Electronic Distribution Board 0.E.013 - QES-ITC-E08-089 | wip
Electrical Services - Level 00 - Electronic Distribution Board 0.E.012
Cable Rough in - 00 - Electronic Distribution Board 0.E.012 - QES-ITC-E03-090 | wip
Power Fit Off - 00 - Electronic Distribution Board 0.E.012 - QES-ITC-E08-090 | wip
Electrical Services - Level 00 - Bay/Workstation on Wheel 0.2.042
Cable Rough in - 00 - Bay/Workstation on Wheel 0.2.042 - QES-ITC-E03-091 | wip
Power Fit Off - 00 - Bay/Workstation on Wheel 0.2.042 - QES-ITC-E08-091 | wip
Electrical Services - Level 00 - Bay/Linen 0.2.044
Cable Rough in - 00 - Bay/Linen 0.2.044 - QES-ITC-E03-092 | wip
Power Fit Off - 00 - Bay/Linen 0.2.044 - QES-ITC-E08-092 | wip
Electrical Services - Level 00 - Bay - Linen 0.2.022
Cable Rough in - 00 - Bay - Linen 0.2.022 - QES-ITC-E03-093 | wip
Power Fit Off - 00 - Bay - Linen 0.2.022 - QES-ITC-E08-093 | wip
Electrical Services - Level 00 - Bay - Mobile Equipment 0.2.025
Cable Rough in - 00 - Bay - Mobile Equipment 0.2.025 - QES-ITC-E03-094 | wip
Power Fit Off - 00 - Bay - Mobile Equipment 0.2.025 - QES-ITC-E08-094 | wip
Electrical Services - Level 00 - Bay Photocopy/Stationary 0.2.023
Cable Rough in - 00 - Bay Photocopy/Stationary 0.2.023 - QES-ITC-E03-095 | wip
Power Fit Off - 00 - Bay Photocopy/Stationary 0.2.023 - QES-ITC-E08-095 | wip
Electrical Services - Level 00 - Bay - Handwashing Type B 0.2.024
Cable Rough in - 00 - Bay - Handwashing Type B 0.2.024 - QES-ITC-E03-096 | wip
Power Fit Off - 00 - Bay - Handwashing Type B 0.2.024 - QES-ITC-E08-096 | wip
Electrical Services - Level 00 - Bay - Meal Trolley 4m2 0.2.029
Cable Rough in - 00 - Bay - Meal Trolley 4m2 0.2.029 - QES-ITC-E03-097 | wip
Power Fit Off - 00 - Bay - Meal Trolley 4m2 0.2.029 - QES-ITC-E08-097 | wip
Electrical Services - Level 00 - Bay - Handwashing Type B 0.2.026
Cable Rough in - 00 - Bay - Handwashing Type B 0.2.026 - QES-ITC-E03-098 | wip
Power Fit Off - 00 - Bay - Handwashing Type B 0.2.026 - QES-ITC-E08-098 | wip
Electrical Services - Level 00 - Electronic Distribution Board 0.E.003
Cable Rough in - 00 - Electronic Distribution Board 0.E.003 - QES-ITC-E03-099 | wip
Power Fit Off - 00 - Electronic Distribution Board 0.E.003 - QES-ITC-E08-099 | wip
Electrical Services - Level 00 - Store Equipment 14m2 0.3.000
Cable Rough in - 00 - Store Equipment 14m2 0.3.000 - QES-ITC-E03-100 | wip
Power Fit Off - 00 - Store Equipment 14m2 0.3.000 - QES-ITC-E08-100 | wip
Electrical Services - Level 01 - Plant Room 1.E.011
Cable Rough In - 01 - Plant Room 1.E.011 - QES-ITC-E03-101 | wip
Power Fit Off - 01 - Plant Room 1.E.011 - QES-ITC-E08-101 | wip
Electrical Services - Level 01 - Electronic Distribution Board 1.E.010
Cable Rough In - 01 - Electronic Distribution Board 1.E.010 - QES-ITC-E03-102 | wip
Power Fit Off - 01 - Electronic Distribution Board 1.E.010 - QES-ITC-E08-102 | wip
Electrical Services - Level 01 - GEM Terrace 1.1.072
Cable Rough In - 01 - GEM Terrace 1.1.072 - QES-ITC-E03-103 | wip
Power Fit Off - 01 - GEM Terrace 1.1.072 - QES-ITC-E08-103 | wip
Electrical Services - Level 01 - Therapy / Multipurpose Room 1.1.000
Cable Rough In - 01 - Therapy / Multipurpose Room 1.1.000 - QES-ITC-E03-104 | wip
Power Fit Off - 01 - Therapy / Multipurpose Room 1.1.000 - QES-ITC-E08-104 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.002
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.002 - QES-ITC-E03-105 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.002 - QES-ITC-E08-105 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.003
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.003 - QES-ITC-E03-106 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.003 - QES-ITC-E08-106 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.006
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.006 - QES-ITC-E03-107 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.006 - QES-ITC-E08-107 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.007
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.007 - QES-ITC-E03-108 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.007 - QES-ITC-E08-108 | wip
Electrical Services - Level 01 - 4 Bed Room - Inboard Ensuite 1.1.010
Cable Rough In - 01 - 4 Bed Room - Inboard Ensuite 1.1.010 - QES-ITC-E03-110 | wip
Power Fit Off - 01 - 4 Bed Room - Inboard Ensuite 1.1.010 - QES-ITC-E08-110 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.013
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.013 - QES-ITC-E03-111 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.013 - QES-ITC-E08-111 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.014
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.014 - QES-ITC-E03-112 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.014 - QES-ITC-E08-112 | wip
Electrical Services - Level 01 - Dining / Recreation / Therapy Room 1.1.029
Cable Rough In - 01 - Dining / Recreation / Therapy Room 1.1.029 - QES-ITC-E03-113 | wip
Power Fit Off - 01 - Dining / Recreation / Therapy Room 1.1.029 - QES-ITC-E08-113 | wip
Electrical Services - Level 01 - Comms Room 1.E.007
Cable Rough In - 01 - Comms Room 1.E.007 - QES-ITC-E03-114 | wip
Power Fit Off - 01 - Comms Room 1.E.007 - QES-ITC-E08-114 | wip
Electrical Services - Level 01 - Bay - Workstation on Wheels 1.1.031
Cable Rough In - 01 - Bay - Workstation on Wheels 1.1.031 - QES-ITC-E03-115 | wip
Power Fit Off - 01 - Bay - Workstation on Wheels 1.1.031 - QES-ITC-E08-115 | wip
Electrical Services - Level 01 - Bay - Beverage, Open Plan 4m2 1.1.028
Cable Rough In - 01 - Bay - Beverage, Open Plan 4m2 1.1.028 - QES-ITC-E03-116 | wip
Power Fit Off - 01 - Bay - Beverage, Open Plan 4m2 1.1.028 - QES-ITC-E08-116 | wip
Electrical Services - Level 01 - Bay - Handwashing, Type B 1.1.027
Cable Rough In - 01 - Bay - Handwashing, Type B 1.1.027 - QES-ITC-E03-117 | wip
Power Fit Off - 01 - Bay - Handwashing, Type B 1.1.027 - QES-ITC-E08-117 | wip
Electrical Services - Level 01 - Office - 1 Person NUM 1.1.033
Cable Rough In - 01 - Office - 1 Person NUM 1.1.033 - QES-ITC-E03-118 | wip
Power Fit Off - 01 - Office - 1 Person NUM 1.1.033 - QES-ITC-E08-118 | wip
Electrical Services - Level 01 - Office - Clinical Workroom 1.1.032
Cable Rough In - 01 - Office - Clinical Workroom 1.1.032 - QES-ITC-E03-119 | wip
Power Fit Off - 01 - Office - Clinical Workroom 1.1.032 - QES-ITC-E08-119 | wip
Electrical Services - Level 01 - Staff Station 14m2 1.1.035
Cable Rough In - 01 - Staff Station 14m2 1.1.035 - QES-ITC-E03-120 | wip
Power Fit Off - 01 - Staff Station 14m2 1.1.035 - QES-ITC-E08-120 | wip
Electrical Services - Level 01 - Clean Utility / Medication Room 1.1.036
Cable Rough In - 01 - Clean Utility / Medication Room 1.1.036 - QES-ITC-E03-121 | wip
Power Fit Off - 01 - Clean Utility / Medication Room 1.1.036 - QES-ITC-E08-121 | wip
Electrical Services - Level 01 - Dirty Utility 14m2 1.1.037
Cable Rough In - 01 - Dirty Utility 14m2 1.1.037 - QES-ITC-E03-122 | wip
Power Fit Off - 01 - Dirty Utility 14m2 1.1.037 - QES-ITC-E08-122 | wip
Electrical Services - Level 01 - Interview Room 1.1.038
Cable Rough In - 01 - Interview Room 1.1.038 - QES-ITC-E03-123 | wip
Power Fit Off - 01 - Interview Room 1.1.038 - QES-ITC-E08-123 | wip
Electrical Services - Level 01 - Toilet - Accessible 1.1.039
Cable Rough In - 01 - Toilet - Accessible 1.1.039 - QES-ITC-E03-124 | wip
Power Fit Off - 01 - Toilet - Accessible 1.1.039 - QES-ITC-E08-124 | wip
Electrical Services - Level 01 - Clean Store 10m2 1.1.040
Cable Rough In - 01 - Clean Store 10m2 1.1.040 - QES-ITC-E03-125 | wip
Power Fit Off - 01 - Clean Store 10m2 1.1.040 - QES-ITC-E08-125 | wip
Electrical Services - Level 01 - Disposal Room 10m2 1.1.042
Cable Rough In - 01 - Disposal Room 10m2 1.1.042 - QES-ITC-E03-126 | wip
Power Fit Off - 01 - Disposal Room 10m2 1.1.042 - QES-ITC-E08-126 | wip
Electrical Services - Level 01 - Cleaners Room 5m2 1.1.043
Cable Rough In - 01 - Cleaners Room 5m2 1.1.043 - QES-ITC-E03-127 | wip
Power Fit Off - 01 - Cleaners Room 5m2 1.1.043 - QES-ITC-E08-127 | wip
Electrical Services - Level 01 - Toilet - Staff 1.1.040
Cable Rough In - 01 - Toilet - Staff 1.1.040 - QES-ITC-E03-128 | wip
Power Fit Off - 01 - Toilet - Staff 1.1.040 - QES-ITC-E08-128 | wip
Electrical Services - Level 01 - Store - General 1.1.045
Cable Rough In - 01 - Store - General 1.1.045 - QES-ITC-E03-129 | wip
Power Fit Off - 01 - Store - General 1.1.045 - QES-ITC-E08-129 | wip
Electrical Services - Level 01 - Bay - Linen 1.1.046
Cable Rough In - 01 - Bay - Linen 1.1.046 - QES-ITC-E03-130 | wip
Power Fit Off - 01 - Bay - Linen 1.1.046 - QES-ITC-E08-130 | wip
Electrical Services - Level 01 - Bay - Handwashing Type B 1.1.047
Cable Rough In - 01 - Bay - Handwashing Type B 1.1.047 - QES-ITC-E03-131 | wip
Power Fit Off - 01 - Bay - Handwashing Type B 1.1.047 - QES-ITC-E08-131 | wip
Electrical Services - Level 01 - Bay - Handwashing Type B 1.1.048
Cable Rough In - 01 - Bay - Handwashing Type B 1.1.048 - QES-ITC-E03-132 | wip
Power Fit Off - 01 - Bay - Handwashing Type B 1.1.048 - QES-ITC-E08-132 | wip
Electrical Services - Level 01 - Bay - Mobile Equipment 1.1.044
Cable Rough In - 01 - Bay - Mobile Equipment 1.1.044 - QES-ITC-E03-133 | wip
Power Fit Off - 01 - Bay - Mobile Equipment 1.1.044 - QES-ITC-E08-133 | wip
Electrical Services - Level 01 - Electronic Distribution Board 1.E.008
Cable Rough In - 01 - Electronic Distribution Board 1.E.008 - QES-ITC-E03-134 | wip
Power Fit Off - 01 - Electronic Distribution Board 1.E.008 - QES-ITC-E08-134 | wip
Electrical Services - Level 01 - Plant Room 1.E.012
Cable Rough In - 01 - Plant Room 1.E.012 - QES-ITC-E03-135 | wip
Power Fit Off - 01 - Plant Room 1.E.012 - QES-ITC-E08-135 | wip
Electrical Services - Level 01 - Store - Equipment 20m2 1.1.049
Cable Rough In - 01 - Store - Equipment 20m2 1.1.049 - QES-ITC-E03-136 | wip
Power Fit Off - 01 - Store - Equipment 20m2 1.1.049 - QES-ITC-E08-136 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.050
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.050 - QES-ITC-E03-137 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.050 - QES-ITC-E08-137 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.053
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.053 - QES-ITC-E03-138 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.053 - QES-ITC-E08-138 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.054
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.054 - QES-ITC-E03-139 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.054 - QES-ITC-E08-139 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.057
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.057 - QES-ITC-E03-140 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.057 - QES-ITC-E08-140 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.058
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.058 - QES-ITC-E03-141 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.058 - QES-ITC-E08-141 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.061
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.061 - QES-ITC-E03-142 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.061 - QES-ITC-E08-142 | wip
Electrical Services - Level 01 - 1 Bed Room - 1 Bed Room - Bariatric 1.1.062
Cable Rough In - 01 - 1 Bed Room - Bariatric 1.1.062 - QES-ITC-E03-143 | wip
Power Fit Off - 01 - 1 Bed Room - Bariatric 1.1.062 - QES-ITC-E08-143 | wip
Electrical Services - Level 01 - 1 Bed Room - Special Inboard Ensuite, Type 1 1.1.065
Cable Rough In - 01 - 1 Bed Room - Special Inboard Ensuite, Type 1 1.1.065 - QES-ITC-E03-144 | wip
Power Fit Off - 01 - 1 Bed Room - Special Inboard Ensuite, Type 1 1.1.065 - QES-ITC-E08-144 | wip
Electrical Services - Level 01 - Lounge - Patient / Family 20m2 1.1.066
Cable Rough In - 01 - Lounge - Patient / Family 20m2 1.1.066 - QES-ITC-E03-145 | wip
Power Fit Off - 01 - Lounge - Patient / Family 20m2 1.1.066 - QES-ITC-E08-145 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.068
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.068 - QES-ITC-E03-146 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.068 - QES-ITC-E08-14 | wip
Electrical Services - Level 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.069
Cable Rough In - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.069 - QES-ITC-E03-147 | wip
Power Fit Off - 01 - 1 Bed Room - Inboard Ensuite, Type 2 1.1.069 - QES-ITC-E08-147 | wip
Electrical Services - Level 01 - Meeting Room 20m2 1.2.009
Cable Rough In - 01 - Meeting Room 20m2 1.2.009 - QES-ITC-E03-148 | wip
Power Fit Off - 01 - Meeting Room 20m2 1.2.009 - QES-ITC-E08-148 | wip
Electrical Services - Level 01 - Breakout Room 1.2.008
Cable Rough In - 01 - Breakout Room 1.2.008 - QES-ITC-E03-149 | wip
Power Fit Off - 01 - Breakout Room 1.2.008 - QES-ITC-E08-149 | wip
Electrical Services - Level 01 - Breakout Room 1.2.007
Cable Rough In - 01 - Breakout Room 1.2.007 - QES-ITC-E03-150 | wip
Power Fit Off - 01 - Breakout Room 1.2.007 - QES-ITC-E08-150 | wip
Electrical Services - Level 01 - Workstations 1.2.000
Cable Rough In - 01 - Workstations 1.2.000 - QES-ITC-E03-151 | wip
Power Fit Off - 01 - Workstations 1.2.000 - QES-ITC-E08-151 | wip
Electrical Services - Level 01 - Office 2 Person 1.2.010
Cable Rough In - 01 - Office 2 Person 1.2.010 - QES-ITC-E03-152 | wip
Power Fit Off - 01 - Office 2 Person 1.2.010 - QES-ITC-E08-152 | wip
Electrical Services - Level 01 - Office 2 Person 1.2.011
Cable Rough In - 01 - Office 2 Person 1.2.011 - QES-ITC-E03-153 | wip
Power Fit Off - 01 - Office 2 Person 1.2.011 - QES-ITC-E08-153 | wip
Electrical Services - Level 01 - Office 2 Person 1.2.012
Cable Rough In - 01 - Office 2 Person 1.2.012 - QES-ITC-E03-154 | wip
Power Fit Off - 01 - Office 2 Person 1.2.012 - QES-ITC-E08-154 | wip
Electrical Services - Level 01 - Office 2 Person 1.2.013
Cable Rough In - 01 - Office 2 Person 1.2.013 - QES-ITC-E03-155 | wip
Power Fit Off - 01 - Office 2 Person 1.2.013 - QES-ITC-E08-155 | wip
Electrical Services - Level 01 - Store - Photocopy / Stationery 8m2 1.2.001
Cable Rough In - 01 - Store - Photocopy / Stationery 8m2 1.2.001 - QES-ITC-E03-156 | wip
Power Fit Off - 01 - Store - Photocopy / Stationery 8m2 1.2.001 - QES-ITC-E08-156 | wip
Electrical Services - Level 01 - Meeting Room 30m2 1.2.014
Cable Rough In - 01 - Meeting Room 30m2 1.2.014 - QES-ITC-E03-157 | wip
Power Fit Off - 01 - Meeting Room 30m2 1.2.014 - QES-ITC-E08-157 | wip
Electrical Services - Level 01 - Office 1 Person 1.2.015
Cable Rough In - 01 - Office 1 Person 1.2.015 - QES-ITC-E03-158 | wip
Power Fit Off - 01 - Office 1 Person 1.2.015 - QES-ITC-E08-158 | wip
Electrical Services - Level 01 - Toilet - Accessible 1.2.004
Cable Rough In - 01 - Toilet - Accessible 1.2.004 - QES-ITC-E03-159 | wip
Power Fit Off - 01 - Toilet - Accessible 1.2.004 - QES-ITC-E08-159 | wip
Electrical Services - Level 01 - Toilet - Accessible 1.2.006
Cable Rough In - 01 - Toilet - Accessible 1.2.006 - QES-ITC-E03-160 | wip
Power Fit Off - 01 - Toilet - Accessible 1.2.006 - QES-ITC-E08-160 | wip
Electrical Services - Level 01 - Staff Room 1.2.002
Cable Rough In - 01 - Staff Room 1.2.002 - QES-ITC-E03-161 | wip
Power Fit Off - 01 - Staff Room 1.2.002 - QES-ITC-E08-161 | wip
Electrical Services - Level 01 - Toilet - Staff 1.2.005
Cable Rough In - 01 - Staff Room 1.2.002 - QES-ITC-E03-161 | wip
Power Fit Off - 01 - Staff Room 1.2.002 - QES-ITC-E08-161 | wip
Electrical Services - Level 01 - Toilet - Staff 1.2.003
Cable Rough In - 01 - Toilet - Staff 1.2.003 - QES-ITC-E03-163 | wip
Power Fit Off - 01 - Toilet - Staff 1.2.003 - QES-ITC-E08-163 | wip
Electrical Services - Level 01 - Lounge - Patient / Transit 1.1.020
Cable Rough In - 01 - Lounge - Patient / Transit 1.1.020 - QES-ITC-E03-164 | wip
Power Fit Off - 01 - Lounge - Patient / Transit 1.1.020 - QES-ITC-E08-164 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.018
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.018 - QES-ITC-E03-165 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.018 - QES-ITC-E08-165 | wip
Electrical Services - Level 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.017
Cable Rough In - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.017 - QES-ITC-E03-166 | wip
Power Fit Off - 01 - 2 Bed Room - Inboard Ensuite - Type 2 1.1.017 - QES-ITC-E08-166 | wip
Electrical Services - Level 01 - FoH Lift Lobby 1.T.004
Cable Rough In - 01 - FoH Lift Lobby 1.T.004 - QES-ITC-E03-167 | wip
Power Fit Off - 01 - FoH Lift Lobby 1.T.004 - QES-ITC-E08-167 | wip
Electrical Services - Level 01 - Toilet - Patient 1.1.021
Cable Rough In - 01 - Toilet - Patient 1.1.021 - QES-ITC-E03-168 | wip
Power Fit Off - 01 - Toilet - Patient 1.1.021 - QES-ITC-E08-168 | wip
Electrical Services - Level 01 - Staff Station 10m2 1.1.022
Cable Rough In - 01 - Staff Station 10m2 1.1.022 - QES-ITC-E03-169 | wip
Power Fit Off - 01 - Staff Station 10m2 1.1.022 - QES-ITC-E08-169 | wip
Electrical Services - Level 01 - Bay - Photocopy / Stationary 1.1.024
Cable Rough In - 01 - Bay - Photocopy / Stationary 1.1.024 - QES-ITC-E03-170 | wip
Power Fit Off - 01 - Bay - Photocopy / Stationary 1.1.024 - QES-ITC-E08-170 | wip
Electrical Services - Level 01 - Bay - Linen 1.1.023
Cable Rough In - 01 - Bay - Linen 1.1.023 / QES-ITC-E03-171 | wip
Power Fit Off - 01 - Bay - Linen 1.1.023 / QES-ITC-E08-171 | wip
Electrical Services - Level 01 - Bay - Handwashing Type B 1.1.025
Cable Rough In - 01 - Bay - Handwashing Type B 1.1.025 - QES-ITC-E03-172 | wip
Power Fit Off - 01 - Bay - Handwashing Type B 1.1.025 - QES-ITC-E08-172 | wip
Electrical Services - Level 01 - Bay - Meal Trolley 4m2 1.1.030
Cable Rough In - 01 - Bay - Meal Trolley 4m2 1.1.030 - QES-ITC-E03-173 | wip
Power Fit Off - 01 - Bay - Meal Trolley 4m2 1.1.030 - QES-ITC-E08-173 | wip
Electrical Services - Level 01 - Bay - Mobile Equipment 1.1.026
Cable Rough In - 01 - Bay - Mobile Equipment 1.1.026 - QES-ITC-E03-173 | wip
Power Fit Off - 01 - Bay - Mobile Equipment 1.1.026 - QES-ITC-E08-173 | wip
Electrical Services - Level 01 - EDB 1.E.015
Cable Rough In - 01 - EDB 1.E.015 - QES-ITC-E03-175 | wip
Power Fit Off - 01 - EDB 1.E.015 - QES-ITC-E08-175 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.001
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.001 - QES-ITC-E03-176 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.001 - QES-ITC-E08-176 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.002
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.002 - QES-ITC-E03-177 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.002 - QES-ITC-E08-177 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.003
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.003 - QES-ITC-E03-178 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.003 - QES-ITC-E08-178 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.012
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.012 - QES-ITC-E03-179 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.012 - QES-ITC-E08-179 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.010
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.010 - QES-ITC-E03-180 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.010 - QES-ITC-E08-180 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.011
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.011 - QES-ITC-E03-181 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.011 - QES-ITC-E08-181 | wip
Electrical Services - Level 01 - Corridor - Patient Treatment Areas 1.T.008
Cable Rough In - 01 - Corridor - Patient Treatment Areas 1.T.008 - QES-ITC-E03-182 | wip
Power Fit Off - 01 - Corridor - Patient Treatment Areas 1.T.008 - QES-ITC-E08-182 | wip
Electrical Services - Level 02 - Main Switch Board 2.E.016
Cable Rough In - 02 - Main Switch Board 2.E.016 - QES-ITC-E03-183 | wip
Power Fit Off - 02 - Main Switch Board 2.E.016 - QES-ITC-E08-183 | wip
Electrical Services - Level 02 - Plant Room 2.E.012
Cable Rough In - 02 - Plant Room 2.E.012 - QES-ITC-E03-184 | wip
Power Fit Off - 02 - Plant Room 2.E.012 - QES-ITC-E08-184 | wip
Electrical Services - Level 02 - UPS Room 2.E.015
Cable Rough In - 02 - UPS Room 2.E.015 - QES-ITC-E03-185 | wip
Power Fit Off - 02 - UPS Room 2.E.015 - QES-ITC-E08-185 | wip
Electrical Services - Level 02 - Palliative Care Terrace 2.1.078
Cable Rough In - 02 - Palliative Care Terrace 2.1.078 - QES-ITC-E03-186 | wip
Power Fit Off - 02 - Palliative Care Terrace 2.1.078 - QES-ITC-E08-186 | wip
Electrical Services - Level 02 - Services Riser 2.E.011
Cable Rough In - 02 - Services Riser 2.E.011 - QES-ITC-E03-187 | wip
Power Fit Off - 02 - Services Riser 2.E.011 - QES-ITC-E08-187 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.050
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.050 - QES-ITC-E03-188 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.050 - QES-ITC-E08-188 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.051
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.051 - QES-ITC-E03-189 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.051 - QES-ITC-E08-189 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.054
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.054 - QES-ITC-E03-190 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.054 - QES-ITC-E08-190 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.055
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.055 - QES-ITC-E03-191 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.055 - QES-ITC-E08-191 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.058
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.058 - QES-ITC-E03-192 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.058 - QES-ITC-E08-192 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.059
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.059 - QES-ITC-E03-193 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.059 - QES-ITC-E08-193 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.062
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.062 - QES-ITC-E03-194 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.062 - QES-ITC-E08-194 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.063
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.063 - QES-ITC-E03-195 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.063 - QES-ITC-E08-195 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.066
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.066 - QES-ITC-E03-196 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.066 - QES-ITC-E08-196 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.067
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.067 - QES-ITC-E03-197 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 - Pall Care 2.1.067 - QES-ITC-E08-197 | wip
Electrical Services - Level 02 - Lounge - Patient 2.1.016
Cable Rough In - 02 - Lounge - Patient 2.1.016 - QES-ITC-E03-198 | wip
Power Fit Off - 02 - Lounge - Patient 2.1.016 - QES-ITC-E08-198 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.015
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.015 - QES-ITC-E03-199 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.015 - QES-ITC-E08-199 | wip
Electrical Services - Level 02 - 4 Bed Room - Inboard Ensuite 2.1.011
Cable Rough In - 02 - 4 Bed Room - Inboard Ensuite 2.1.011 - QES-ITC-E03-200 | wip
Power Fit Off - 02 - 4 Bed Room - Inboard Ensuite 2.1.011 - QES-ITC-E08-200 | wip
Electrical Services - Level 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.008
Cable Rough In - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.008 - QES-ITC-E03-201 | wip
Power Fit Off - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.008 - QES-ITC-E08-201 | wip
Electrical Services - Level 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.007
Cable Rough In - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.007 - QES-ITC-E03-202 | wip
Power Fit Off - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.007 - QES-ITC-E08-202 | wip
Electrical Services - Level 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.004
Cable Rough In - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.004 - QES-ITC-E03-203 | wip
Power Fit Off - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.004 - QES-ITC-E08-203 | wip
Electrical Services - Level 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.003
Cable Rough In - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.003 - QES-ITC-E03-204 | wip
Power Fit Off - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.003 - QES-ITC-E08-204 | wip
Electrical Services - Level 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.000
Cable Rough In - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.000 - QES-ITC-E03-205 | wip
Power Fit Off - 02 - 2 Bed Room - Inboard Ensuite, Type 2 - Pall Care 2.1.000 - QES-ITC-E08-205 | wip
Electrical Services - Level 02 - Services Riser 2.E.010
Cable Rough In - 02 - Services Riser 2.E.010 - QES-ITC-E03-206 | wip
Power Fit Off - 02 - Services Riser 2.E.010 - QES-ITC-E08-206 | wip
Electrical Services - Level 02 - Bay - Handwashing, Type B 2.1.047
Cable Rough In - 02 - Bay - Handwashing, Type B 2.1.047 - QES-ITC-E03-207 | wip
Power Fit Off - 02 - Bay - Handwashing, Type B 2.1.047 - QES-ITC-E08-207 | wip
Electrical Services - Level 02 - Bay - Linen 2.1.046
Cable Rough In - 02 - Bay - Linen 2.1.046 - QES-ITC-E03-208 | wip
Power Fit Off - 02 - Bay - Linen 2.1.046 - QES-ITC-E08-208 | wip
Electrical Services - Level 02 - Bay - Handwashing, Type B 2.1.048
Cable Rough In - 02 - Bay - Handwashing, Type B 2.1.048 - QES-ITC-E03-209 | wip
Power Fit Off - 02 - Bay - Handwashing, Type B 2.1.048 - QES-ITC-E08-209 | wip
Electrical Services - Level 02 - Bay - Mobile Equipment 2.1.045
Cable Rough In - 02 - Bay - Mobile Equipment 2.1.045 - QES-ITC-E03-210 | wip
Power Fit Off - 02 - Bay - Mobile Equipment 2.1.045 - QES-ITC-E08-210 | wip
Electrical Services - Level 02 - Store - Equipment, 20m2 2.1.044
Cable Rough In - 02 - Store - Equipment, 20m2 2.1.044 - QES-ITC-E03-211 | wip
Power Fit Off - 02 - Store - Equipment, 20m2 2.1.044 - QES-ITC-E08-211 | wip
Electrical Services - Level 02 - Disposal Room 10m2 2.1.043
Cable Rough In - 02 - Disposal Room 10m2 2.1.043 - QES-ITC-E03-212 | wip
Power Fit Off - 02 - Disposal Room 10m2 2.1.043 - QES-ITC-E08-212 | wip
Electrical Services - Level 02 - Clean Store 10m2 2.1.077
Cable Rough In - 02 - Clean Store 10m2 2.1.077 - QES-ITC-E03-213 | wip
Power Fit Off - 02 - Clean Store 10m2 2.1.077 - QES-ITC-E08-213 | wip
Electrical Services - Level 02 - Cleaners Room 5m2 2.1.042
Cable Rough In - 02 - Cleaners Room 5m2 2.1.042 - QES-ITC-E03-214 | wip
Power Fit Off - 02 - Cleaners Room 5m2 2.1.042 - QES-ITC-E08-214 | wip
Electrical Services - Level 02 - Toilet - Staff 2.1.041
Cable Rough In - 02 - Toilet - Staff 2.1.041 - QES-ITC-E03-215 | wip
Power Fit Off - 02 - Toilet - Staff 2.1.041 - QES-ITC-E08-215 | wip
Electrical Services - Level 02 - Interview Room 2.1.038
Cable Rough In - 02 - Interview Room 2.1.038 - QES-ITC-E03-216 | wip
Power Fit Off - 02 - Interview Room 2.1.038 - QES-ITC-E08-216 | wip
Electrical Services - Level 02 - Toilet - Accessible 2.1.039
Cable Rough In - 02 - Toilet - Accessible 2.1.039 - QES-ITC-E03-217 | wip
Power Fit Off - 02 - Toilet - Accessible 2.1.039 - QES-ITC-E08-217 | wip
Electrical Services - Level 02 - Dirty Utility 14m2 2.1.037
Cable Rough In - 02 - Dirty Utility 14m2 2.1.037 - QES-ITC-E03-218 | wip
Power Fit Off - 02 - Dirty Utility 14m2 2.1.037 - QES-ITC-E08-218 | wip
Electrical Services - Level 02 - Clean Utility / Medication Room 2.1.036
Cable Rough In - 02 - Clean Utility / Medication Room 2.1.036 - QES-ITC-E03-219 | wip
Power Fit Off - 02 - Clean Utility / Medication Room 2.1.036 - QES-ITC-E08-219 | wip
Electrical Services - Level 02 - Staff Station 14m2 2.1.035
Cable Rough In - 02 - Staff Station 14m2 2.1.035 - QES-ITC-E03-220 | wip
Power Fit Off - 02 - Staff Station 14m2 2.1.035 - QES-ITC-E08-220 | wip
Electrical Services - Level 02 - Office - Clinical Workroom 2.1.033
Cable Rough In - 02 - Office - Clinical Workroom 2.1.033 - QES-ITC-E03-221 | wip
Power Fit Off - 02 - Office - Clinical Workroom 2.1.033 - QES-ITC-E08-221 | wip
Electrical Services - Level 02 - Office - 1 Person, NUM 2.1.032
Cable Rough In - 02 - Office - 1 Person, NUM 2.1.032 - QES-ITC-E03-222 | wip
Power Fit Off - 02 - Office - 1 Person, NUM 2.1.032 - QES-ITC-E08-222 | wip
Electrical Services - Level 02 - Comms Room 2.E.008
Cable Rough In - 02 - Comms Room 2.E.008 - QES-ITC-E03-223 | wip
Power Fit Off - 02 - Comms Room 2.E.008 - QES-ITC-E08-223 | wip
Electrical Services - Level 02 - Bay - Mobile Equipment 2.1.012
Cable Rough In - 02 - Bay - Mobile Equipment 2.1.012 - QES-ITC-E03-224 | wip
Power Fit Off - 02 - Bay - Mobile Equipment 2.1.012 - QES-ITC-E08-224 | wip
Electrical Services - Level 02 - Bay - Workstation on Wheels 2.1.031
Cable Rough In - 02 - Bay - Workstation on Wheels 2.1.031 - QES-ITC-E03-225 | wip
Power Fit Off - 02 - Bay - Workstation on Wheels 2.1.031 - QES-ITC-E08-225 | wip
Electrical Services - Level 02 - Dining / Recreation / Therapy Room 2.1.029
Cable Rough In - 02 - Dining / Recreation / Therapy Room 2.1.029 - QES-ITC-E03-226 | wip
Power Fit Off - 02 - Dining / Recreation / Therapy Room 2.1.029 - QES-ITC-E08-226 | wip
Electrical Services - Level 02 - Plant Room 2.E.007
Cable Rough In - 02 - Plant Room 2.E.007 - QES-ITC-E03-227 | wip
Power Fit Off - 02 - Plant Room 2.E.007 - QES-ITC-E08-227 | wip
Electrical Services - Level 02 - Services Riser 2.E.006
Cable Rough In - 02 - Services Riser 2.E.006 - QES-ITC-E03-228 | wip
Power Fit Off - 02 - Services Riser 2.E.006 - QES-ITC-E08-228 | wip
Electrical Services - Level 02 - FoH Lift Lobby 2.T.009
Cable Rough In - 02 - FoH Lift Lobby 2.T.009 - QES-ITC-E03-229 | wip
Power Fit Off - 02 - FoH Lift Lobby 2.T.009 - QES-ITC-E08-229 | wip
Electrical Services - Level 02 - Store - General 2.1.021
Cable Rough In - 02 - Store - General 2.1.021 - QES-ITC-E03-230 | wip
Power Fit Off - 02 - Store - General 2.1.021 - QES-ITC-E08-230 | wip
Electrical Services - Level 02 - Staff Station 10m2 2.1.022
Cable Rough In - 02 - Staff Station 10m2 2.1.022 - QES-ITC-E03-231 | wip
Power Fit Off - 02 - Staff Station 10m2 2.1.022 - QES-ITC-E08-231 | wip
Electrical Services - Level 02 - Bay - Linen 2.1.024
Cable Rough In - 02 - Bay - Linen 2.1.024 - QES-ITC-E03-232 | wip
Power Fit Off - 02 - Bay - Linen 2.1.024 - QES-ITC-E08-232 | wip
Electrical Services - Level 02 - Bay - Mobile Equipment 2.1.026
Cable Rough In - 02 - Bay - Mobile Equipment 2.1.026 - QES-ITC-E03-233 | wip
Power Fit Off - 02 - Bay - Mobile Equipment 2.1.026 - QES-ITC-E08-233 | wip
Electrical Services - Level 02 - Bay - Photocopy / Stationary 2.1.023
Cable Rough In - 02 - Bay - Photocopy / Stationary 2.1.023 - QES-ITC-E03-234 | wip
Power Fit Off - 02 - Bay - Photocopy / Stationary 2.1.023 - QES-ITC-E08-234 | wip
Electrical Services - Level 02 - Bay - Handwashing, Type B 2.1.025
Cable Rough In - 02 - Bay - Handwashing, Type B 2.1.025 - QES-ITC-E03-236 | wip
Power Fit Off - 02 - Bay - Handwashing, Type B 2.1.025 - QES-ITC-E08-236 | wip
Electrical Services - Level 02 - Bay - Handwashing, Type B 2.1.027
Cable Rough In - 02 - Bay - Handwashing, Type B 2.1.027 - QES-ITC-E03-237 | wip
Power Fit Off - 02 - Bay - Handwashing, Type B 2.1.027 - QES-ITC-E08-237 | wip
Electrical Services - Level 02 - Office - 1 Person 9m2 2.2.004
Cable Rough In - 02 - Office - 1 Person 9m2 2.2.004 - QES-ITC-E03-238 | wip
Power Fit Off - 02 - Office - 1 Person 9m2 2.2.004 - QES-ITC-E08-238 | wip
Electrical Services - Level 02 - Office - 2 Person 2.2.003
Cable Rough In - 02 - Office - 2 Person 2.2.003 - QES-ITC-E03-239 | wip
Power Fit Off - 02 - Office - 2 Person 2.2.003 - QES-ITC-E08-239 | wip
Electrical Services - Level 02 - Office - 1 Person 9m2 2.2.002
Cable Rough In - 02 - Office - 1 Person 9m2 2.2.002 - QES-ITC-E03-240 | wip
Power Fit Off - 02 - Office - 1 Person 9m2 2.2.002 - QES-ITC-E08-240 | wip
Electrical Services - Level 02 - Office - 1 Person 9m2 2.2.001
Cable Rough In - 02 - Office - 1 Person 9m2 2.2.001 - QES-ITC-E03-241 | wip
Power Fit Off - 02 - Office - 1 Person 9m2 2.2.001 - QES-ITC-E08-241 | wip
Electrical Services - Level 02 - BoH Lift Lobby 2.T.006
Cable Rough In - 02 - BoH Lift Lobby 2.T.006 - QES-ITC-E03-242 | wip
Power Fit Off - 02 - BoH Lift Lobby 2.T.006 - QES-ITC-E08-242 | wip
Electrical Services - Level 02 - Bathroom 2.1.019
Cable Rough In - 02 - Bathroom 2.1.019 - QES-ITC-E03-243 | wip
Power Fit Off - 02 - Bathroom 2.1.019 - QES-ITC-E08-243 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.017 -
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.017 - QES-ITC-E03-244 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 1 2.1.017 - QES-ITC-E08-244 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.070 -
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.070 - QES-ITC-E03-245 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.070 - QES-ITC-E08-245 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.071 -
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.071 - QES-ITC-E03-246 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.071 - QES-ITC-E08-246 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.074 -
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.074 - QES-ITC-E03-247 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.074 - QES-ITC-E08-247 | wip
Electrical Services - Level 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075 -
Cable Rough In - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075 - QES-ITC-E03-248 | wip
Power Fit Off - 02 - 1 Bed Room - Special, Inboard Ensuite, Type 2 Pall Care 2.1.075 - QES-ITC-E08-248 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.012 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.012 - QES-ITC-E03-250 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.012 - QES-ITC-E08-250 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.004 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.004 - QES-ITC-E03-251 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.004 - QES-ITC-E08-251 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.001 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.001 - QES-ITC-E03-252 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.001 - QES-ITC-E08-252 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.002 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.002 - QES-ITC-E03-253 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.002 - QES-ITC-E08-253 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.003 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.003 - QES-ITC-E03-254 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.003 - QES-ITC-E08-254 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.013 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.013 - QES-ITC-E03-255 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.013 - QES-ITC-E08-255 | wip
Electrical Services - Level 02 - Corridor - Patient Treatment Areas 2.T.010 -
Cable Rough In - 02 - Corridor - Patient Treatment Areas 2.T.010 - QES-ITC-E03-256 | wip
Power Fit Off - 02 - Corridor - Patient Treatment Areas 2.T.010 - QES-ITC-E08-256 | wip
Electrical Services - Stairs - Stair 1
Cable Rough In - Stair 1 - QES-ITC-E03-260 | wip
Power Fit Off - Stair 1 - QES-ITC-E08-260 | wip
Electrical Services - Stairs - Stair 2
Cable Rough In - Stair 2 - QES-ITC-E03-261 | wip
Power Fit Off - Stair 2 - QES-ITC-E08-261 | wip
Electrical Services - Lifts - Lift 1
Cable Rough In - Lift 1 - QES-ITC-E03-262 | wip
Power Fit Off - Lift 1 - QES-ITC-E08-262 | wip
Electrical Services - Lifts - Lift 2
Cable Rough In - Lift 2 - QES-ITC-E03-263 | wip
Power Fit Off - Lift 2 - QES-ITC-E08-263 | wip
Electrical Services - Lifts - Lift 3
Cable Rough In - Lift 3 - QES-ITC-E03-264 | wip
Power Fit Off - Lift 3 - QES-ITC-E08-264 | wip
Electrical Services - Temp Construction - Level - 00
Construction Distribution Boards | not started
Construction Wiring & Accessories | not started
Electrical Services - Temp Construction - Level - 01
Construction Distribution Boards | not started
Construction Wiring & Accessories | not started
Electrical Services - Temp Construction - Level - 02
Construction Distribution Boards | not started
Construction Wiring & Accessories | not started
Electrical Services - Temp Construction - External
Construction Distribution Boards | not started
Construction Wiring & Accessories | not started
Generator
Generator - Cable Terminations - QES-ITC-E11-002 | not started
Generator - Final Installation Test Sheet - QES-ITC-E11-003 | not started