## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Site QA
| step |  |  |  | Site Plan Cabling
ITR No.33 - Installing Underground Services | checklist |  |  |  |  | ITR 33. Installing Underground Services (Electrical)
ITR No.33 - Installing Underground Services | checklist |  |  |  |  | ITR 33C. Installing Underground Services (Comms)
ITR No.05 - Rough In | checklist |  |  |  |  | ITR No.05 - Rough In
ITP No.07 - Structured Cabling Rough In | checklist |  |  |  |  | ITP No.07 - Structured Cabling Rough In
ITR No.34 - Installing Light Pole Cages | checklist |  |  |  |  | ITR No.34 - Installing Light Pole Cages
| step |  |  |  | Temp Boards
ITP No.19 - Installation of Temporary Power Board | checklist |  |  |  |  | ZONE 1
ITP No.19 - Installation of Temporary Power Board | checklist |  |  |  |  | ZONE 2
ITP No.19 - Installation of Temporary Power Board | checklist |  |  |  |  | ZONE 3
ITP No.19 - Installation of Temporary Power Board | checklist |  |  |  |  | ZONE 4
| step |  |  |  | Temp Lighting
ITP No.14 - Construction Wiring, Installation, Test and Tag & Removal | checklist |  |  |  |  | ZONE 1
ITP No.14 - Construction Wiring, Installation, Test and Tag & Removal | checklist |  |  |  |  | ZONE 2
ITP No.14 - Construction Wiring, Installation, Test and Tag & Removal | checklist |  |  |  |  | ZONE 3
ITP No.14 - Construction Wiring, Installation, Test and Tag & Removal | checklist |  |  |  |  | ZONE 4
| step |  |  |  | Rough In
| step |  |  |  |  | ZONE 1
ITR No.10 - Cable Tray Installation | checklist | [5 empty] | ITR No.10 - Cable Tray Installation
ITR No.09 - Ground In Slab Conduits | checklist | [5 empty] | ITR No.09 - Ground In Slab Conduits
ITR No.14 - Mains and Sub Mains | checklist | [5 empty] | ITR No.14 - Mains and Sub Mains
ITR No.05 - Rough In | checklist | [5 empty] | ITR No.05 - Rough In
ITP No.07 - Structured Cabling Rough In | checklist | [5 empty] | ITP No.07 - Structured Cabling Rough In
| step |  |  |  |  | ZONE 2
ITR No.10 - Cable Tray Installation | checklist | [5 empty] | ITR No.10 - Cable Tray Installation
ITR No.09 - Ground In Slab Conduits | checklist | [5 empty] | ITR No.09 - Ground In Slab Conduits
ITR No.14 - Mains and Sub Mains | checklist | [5 empty] | ITR No.14 - Mains and Sub Mains
ITR No.05 - Rough In | checklist | [5 empty] | ITR No.05 - Rough In
ITP No.07 - Structured Cabling Rough In | checklist | [5 empty] | ITP No.07 - Structured Cabling Rough In
| step |  |  |  |  | ZONE 3
ITR No.10 - Cable Tray Installation | checklist | [5 empty] | ITR No.10 - Cable Tray Installation
ITR No.09 - Ground In Slab Conduits | checklist | [5 empty] | ITR No.09 - Ground In Slab Conduits
ITR No.14 - Mains and Sub Mains | checklist | [5 empty] | ITR No.14 - Mains and Sub Mains
ITR No.05 - Rough In | checklist | [5 empty] | ITR No.05 - Rough In
ITP No.07 - Structured Cabling Rough In | checklist | [5 empty] | ITP No.07 - Structured Cabling Rough In
| step |  |  |  |  | ZONE 4
ITR No.10 - Cable Tray Installation | checklist | [5 empty] | ITR No.10 - Cable Tray Installation
ITR No.09 - Ground In Slab Conduits | checklist | [5 empty] | ITR No.09 - Ground In Slab Conduits
ITR No.14 - Mains and Sub Mains | checklist | [5 empty] | ITR No.14 - Mains and Sub Mains
ITR No.05 - Rough In | checklist | [5 empty] | ITR No.05 - Rough In
ITP No.07 - Structured Cabling Rough In | checklist | [5 empty] | ITP No.07 - Structured Cabling Rough In
| step |  |  |  | WOOLWORTHS - Rough In
ITR No.10 - Cable Tray Installation | checklist |  |  |  |  | ITR No.10 - Cable Tray Installation
ITR No.09 - Ground In Slab Conduits | checklist |  |  |  |  | ITR No.09 - Ground In Slab Conduits
ITR No.14 - Mains and Sub Mains | checklist |  |  |  |  | ITR No.14 - Mains and Sub Mains
ITR No.05 - Rough In | checklist |  |  |  |  | ITR No.05 - Rough In
ITP No.07 - Structured Cabling Rough In | checklist |  |  |  |  | ITP No.07 - Structured Cabling Rough In
| step |  |  |  | Cut Out
| step |  |  |  |  | ZONE 1
ITR No.02 - Cutout of Ceilings & Walls | checklist | [5 empty] | ITR No.02 - Cutout of Ceilings & Walls
| step |  |  |  |  | ZONE 2
ITR No.02 - Cutout of Ceilings & Walls | checklist | [5 empty] | ITR No.02 - Cutout of Ceilings & Walls
| step |  |  |  |  | ZONE 3
ITR No.02 - Cutout of Ceilings & Walls | checklist | [5 empty] | ITR No.02 - Cutout of Ceilings & Walls
| step |  |  |  |  | ZONE 4
ITR No.02 - Cutout of Ceilings & Walls | checklist | [5 empty] | ITR No.02 - Cutout of Ceilings & Walls
ITR No.02 - Cutout of Ceilings & Walls | folder-with-checklists |  |  |  | WOOLWORTHS - Cut Out
| step |  |  |  | Fit Off
| step |  |  |  |  | ZONE 1
ITR No.18 - Light and Power Fit Off | checklist | [5 empty] | ITR No.18 - Light and Power Fit Off
ITR No.16 - Switchboard Installation and Terminate Submains | checklist | [5 empty] | ITR No.16 - Switchboard Installation and Terminate Submains
ITP No.13 - Sub-circuit Cabling Fit Off | checklist | [5 empty] | ITP No.13 - Sub-circuit Cabling Fit Off
ITP No.16 - Exit & Emergency Installating & Testing | checklist | [5 empty] | ITP No.16 - Exit & Emergency Installating & Testing
ITP No.08 - Structured Cabling Fit Off | checklist | [5 empty] | ITP No.08 - Structured Cabling Fit Off
| step |  |  |  |  | ZONE 2
ITR No.18 - Light and Power Fit Off | checklist | [5 empty] | ITR No.18 - Light and Power Fit Off
ITR No.16 - Switchboard Installation and Terminate Submains | checklist | [5 empty] | ITR No.16 - Switchboard Installation and Terminate Submains
ITP No.13 - Sub-circuit Cabling Fit Off | checklist | [5 empty] | ITP No.13 - Sub-circuit Cabling Fit Off
ITP No.16 - Exit & Emergency Installating & Testing | checklist | [5 empty] | ITP No.16 - Exit & Emergency Installating & Testing
ITP No.08 - Structured Cabling Fit Off | checklist | [5 empty] | ITP No.08 - Structured Cabling Fit Off
| step |  |  |  |  | ZONE 3
ITR No.18 - Light and Power Fit Off | checklist | [5 empty] | ITR No.18 - Light and Power Fit Off
ITR No.16 - Switchboard Installation and Terminate Submains | checklist | [5 empty] | ITR No.16 - Switchboard Installation and Terminate Submains
ITP No.13 - Sub-circuit Cabling Fit Off | checklist | [5 empty] | ITP No.13 - Sub-circuit Cabling Fit Off
ITP No.16 - Exit & Emergency Installating & Testing | checklist | [5 empty] | ITP No.16 - Exit & Emergency Installating & Testing
ITP No.08 - Structured Cabling Fit Off | checklist | [5 empty] | ITP No.08 - Structured Cabling Fit Off
| step |  |  |  |  | ZONE 4
ITR No.18 - Light and Power Fit Off | checklist | [5 empty] | ITR No.18 - Light and Power Fit Off
ITR No.16 - Switchboard Installation and Terminate Submains | checklist | [5 empty] | ITR No.16 - Switchboard Installation and Terminate Submains
ITP No.13 - Sub-circuit Cabling Fit Off | checklist | [5 empty] | ITP No.13 - Sub-circuit Cabling Fit Off
ITP No.16 - Exit & Emergency Installating & Testing | checklist | [5 empty] | ITP No.16 - Exit & Emergency Installating & Testing
ITP No.08 - Structured Cabling Fit Off | checklist | [5 empty] | ITP No.08 - Structured Cabling Fit Off
| step |  |  |  | WOOLWORTHS - Fit Off
ITR No.18 - Light and Power Fit Off | checklist |  |  |  |  | ITR No.18 - Light and Power Fit Off
ITR No.16 - Switchboard Installation and Terminate Submains | checklist |  |  |  |  | ITR No.16 - Switchboard Installation and Terminate Submains
ITP No.13 - Sub-circuit Cabling Fit Off | checklist |  |  |  |  | ITP No.13 - Sub-circuit Cabling Fit Off
ITP No.16 - Exit & Emergency Installating & Testing | checklist |  |  |  |  | ITP No.16 - Exit & Emergency Installating & Testing
ITP No.08 - Structured Cabling Fit Off | checklist |  |  |  |  | ITP No.08 - Structured Cabling Fit Off
| step |  |  |  | Commissioning
| step |  |  |  |  | ZONE 1
ITR No.12 - Switchboard Commissioning | checklist | [5 empty] | ITR No.12 - Switchboard Commissioning
ITP No.09 - Structured Cabling Testing Certified System | checklist | [5 empty] | ITP No.09 - Structured Cabling Testing Certified System
| step |  |  |  |  | ZONE 2
ITR No.12 - Switchboard Commissioning | checklist | [5 empty] | ITR No.12 - Switchboard Commissioning
ITP No.09 - Structured Cabling Testing Certified System | checklist | [5 empty] | ITP No.09 - Structured Cabling Testing Certified System
| step |  |  |  |  | ZONE 3
ITR No.12 - Switchboard Commissioning | checklist | [5 empty] | ITR No.12 - Switchboard Commissioning
ITP No.09 - Structured Cabling Testing Certified System | checklist | [5 empty] | ITP No.09 - Structured Cabling Testing Certified System
| step |  |  |  |  | ZONE 4
ITR No.12 - Switchboard Commissioning | checklist | [5 empty] | ITR No.12 - Switchboard Commissioning
ITP No.09 - Structured Cabling Testing Certified System | checklist | [5 empty] | ITP No.09 - Structured Cabling Testing Certified System
| step |  |  |  | WOOLWORTHS - Commissioning
ITR No.12 - Switchboard Commissioning | checklist |  |  |  |  | ITR No.12 - Switchboard Commissioning
ITP No.09 - Structured Cabling Testing Certified System | checklist |  |  |  |  | ITP No.09 - Structured Cabling Testing Certified System
| step |  |  |  | Temp Boards (Decommission)
| step |  |  |  |  | ZONE 1
ITP No.20 - Decommission Temporary Power Board | checklist | [5 empty] | ITP No.20 - Decommission Temporary Power Board
| step |  |  |  |  | ZONE 2
ITP No.20 - Decommission Temporary Power Board | checklist | [5 empty] | ITP No.20 - Decommission Temporary Power Board
| step |  |  |  |  | ZONE 3
ITP No.20 - Decommission Temporary Power Board | checklist | [5 empty] | ITP No.20 - Decommission Temporary Power Board
| step |  |  |  |  | ZONE 4
ITP No.20 - Decommission Temporary Power Board | checklist | [5 empty] | ITP No.20 - Decommission Temporary Power Board
| step |  |  | DLP
| step |  |  |  | Preventative Maintenance Checklist
| step |  |  |  |  | PMC 6 Month
| step |  |  |  |  | PMC 12 Month
| step |  |  |  | Exit & Emergency
| step |  |  |  |  | Initial/PC
| step | [5 empty] | Exits
| step | [5 empty] | Emergencies
| step |  |  |  |  | 6 Month
| step | [5 empty] | Exits
| step | [5 empty] | Emergencies
| step |  |  |  |  | 12 Month
| step | [5 empty] | Exits
| step | [5 empty] | Emergencies
| step |  |  | Site Induction