## Sheet1
2.1 | Supply of: - HDPE Slotted Pipe - Geofabric | A9402 L1-CHE-STD-030 Section 701 | To be type approved by MTM. Drainage Pipes to be supplied in accordance to Section 701 To be inspected upon delivery to have no damage. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets | 2.1 - Supply of: - HDPE Slotted Pipe - Geofabric | Reference - A9402 L1-CHE-STD-030 Section 701 | Acceptance Criteria - To be type approved by MTM. Drainage Pipes to be supplied in accordance to Section 701 To be inspected upon delivery to have no damage. | Method - Visual Measure Document Review | Frequency - Prior to works commencing | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets | 2.1 - Supply of: - HDPE Slotted Pipe - Geofabric
2.2 | Supply of: - LDPE Liner - Clean Stone - Bedding Sand - Beaching Rock | L1-CHE-STD-030 Section 701 | To meet L1-CHE-STD-030 requirements. Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 CHAR(AMP) Table 701.092 To be inspected upon delivery to have no damage. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets | 2.2 - Supply of: - LDPE Liner - Clean Stone - Bedding Sand - Beaching Rock | Reference - L1-CHE-STD-030 Section 701 | Acceptance Criteria - To meet L1-CHE-STD-030 requirements. Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 CHAR(AMP) Table 701.092 To be inspected upon delivery to have no damage. | Method - Visual Measure Document Review | Frequency - Prior to works commencing | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets | Reference - A9402 L1-CHE-STD-030 Section 701
2.3 | Supply of: - Riser - Standard Headwall - Class D Pit Cover | L1-CHE-STD-030 Section 705 | To meet L1-CHE-STD-030 requirements. To be supplied in accordance to Section 705 To be inspected upon delivery to have no damage. | Visual Measure Document Review | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets | 2.3 - Supply of: - Riser - Standard Headwall - Class D Pit Cover | Reference - L1-CHE-STD-030 Section 705 | Acceptance Criteria - To meet L1-CHE-STD-030 requirements. To be supplied in accordance to Section 705 To be inspected upon delivery to have no damage. | Method - Visual Measure Document Review | Frequency - Prior to works commencing | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets | Acceptance Criteria - To be type approved by MTM. Drainage Pipes to be supplied in accordance to Section 701 To be inspected upon delivery to have no damage.
Method - Visual Measure Document Review
3.1 | Primary Documentations | A4263 PTDT Form B - Track Certifier Booking Form | Approved PTDT | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Approved Permit | 3.1 - Primary Documentations | Reference - A4263 PTDT Form B - Track Certifier Booking Form | Acceptance Criteria - Approved PTDT | Method - Document review and approval | Frequency - Prior to works commencing | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off Attach: Approved Permit | Frequency - Prior to works commencing
3.2 | Pre-Commencement of Work | ITP, Quality Checklist, SWMS | All approved by relevant representative. | Document review and approval | Once (Prior to Works) | HP | SE/PE | This ITP Signed Off Attach: Approved Templates | 3.2 - Pre-Commencement of Work | Reference - ITP, Quality Checklist, SWMS | Acceptance Criteria - All approved by relevant representative. | Method - Document review and approval | Frequency - Once (Prior to Works) | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off Attach: Approved Templates | Category - HP
Responsibility - SE/PE
4.1 | Approval of IFC drawings | GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off | 4.1 - Approval of IFC drawings | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Acceptance Criteria - Approved IFC Drawings | Method - Document review and approval | Frequency - Prior to works commencing | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off | Verifying Documents - This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
2.2 - Supply of: - LDPE Liner - Clean Stone - Bedding Sand - Beaching Rock
5.1 | Survey Track Drainage Alignment CHAR(AMP) Pits | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation. | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor Surveyor | This ITP Signed Off Attach: Survey Records CHAR(AMP) Photos on site | 5.1 - Survey Track Drainage Alignment CHAR(AMP) Pits | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation. | Method - Visual Inspection Survey / Measure | Frequency - As Task Progresses | Category - HP | Responsibility - SE/PE Supervisor Surveyor | Verifying Documents - This ITP Signed Off Attach: Survey Records CHAR(AMP) Photos on site | Reference - L1-CHE-STD-030 Section 701
5.2 | Grade Existing Open Cess Drain | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Grade through existing cess drain alignment to depth indicated on design documentation. | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site | 5.2 - Grade Existing Open Cess Drain | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Acceptance Criteria - Grade through existing cess drain alignment to depth indicated on design documentation. | Method - Visual Inspection Survey / Measure | Frequency - As Task Progresses | Category - HP | Responsibility - SE/PE Supervisor | Verifying Documents - This ITP Signed Off Attach: Photos on site | Acceptance Criteria - To meet L1-CHE-STD-030 requirements. Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 CHAR(AMP) Table 701.092 To be inspected upon delivery to have no damage.
5.3 | Excavate Slotted Pipe Drainage Trench | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Excavation shall be to the depth indicated on the design documentation | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site | 5.3 - Excavate Slotted Pipe Drainage Trench | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation | Method - Visual Inspection Survey / Measure | Frequency - As Task Progresses | Category - HP | Responsibility - SE/PE Supervisor | Verifying Documents - This ITP Signed Off Attach: Photos on site | Method - Visual Measure Document Review
5.4 | Place the Following and Compact: - Bedding Sand - Geofabric - Slotted Pipe - Stone | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Bedding conforming to to Section 701.09 shall be supplied, placed and compacted. Compaction and moisture content testing to be in accordance with Section 701.20 (where applicable). Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three (3). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (b) Backfill (i) Material of nominal size 40 mm or less after compaction - Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (ii) Material of nominal size greater than 40 mm after compaction - Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. - Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Trench to be wrapped with geotextile in accordance with the manufacturers specifications and design documentation. Attach: Compaction Test Reports | Visual Inspection Survey / Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site Compaction Test Reports | 5.4 - Place the Following and Compact: - Bedding Sand - Geofabric - Slotted Pipe - Stone | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Acceptance Criteria - Bedding conforming to to Section 701.09 shall be supplied, placed and compacted. Compaction and moisture content testing to be in accordance with Section 701.20 (where applicable). Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three (3). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (b) Backfill (i) Material of nominal size 40 mm or less after compaction - Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (ii) Material of nominal size greater than 40 mm after compaction - Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. - Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Trench to be wrapped with geotextile in accordance with the manufacturers specifications and design documentation. Attach: Compaction Test Reports | Method - Visual Inspection Survey / Measure | Frequency - As Task Progresses | Category - HP | Responsibility - SE/PE Supervisor | Verifying Documents - This ITP Signed Off Attach: Photos on site Compaction Test Reports | Frequency - Prior to works commencing
5.5 | Pit, Headwall CHAR(AMP) Beaching Rock Installation | IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | All stormwater pits shall be provided with a lockable minimum Class D pit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030 | Visual Inspection Measure | As Task Progresses | HP | SE/PE Supervisor | This ITP Signed Off Attach: Photos on site | 5.5 - Pit, Headwall CHAR(AMP) Beaching Rock Installation | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 | Acceptance Criteria - All stormwater pits shall be provided with a lockable minimum Class D pit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030 | Method - Visual Inspection Measure | Frequency - As Task Progresses | Category - HP | Responsibility - SE/PE Supervisor | Verifying Documents - This ITP Signed Off Attach: Photos on site | Category - HP
Responsibility - SE/PE
6.1 | Track Certification | MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE | - Track Geometry Conformance Certificate - Track System and Component | Visual Measure Document Review | Once (upon completion of occupation works) | HP | Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure | This ITP Signed Off Attach: Relevant Conformance Certs as per acceptance criteria | 6.1 - Track Certification | Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE | Acceptance Criteria - - Track Geometry Conformance Certificate - Track System and Component | Method - Visual Measure Document Review | Frequency - Once (upon completion of occupation works) | Category - HP | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure | Verifying Documents - This ITP Signed Off Attach: Relevant Conformance Certs as per acceptance criteria | Verifying Documents - This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
6.2 | Flushing CHAR(AMP) CCTV | VR Section 701.28 VR Section 701.30 | All culverts shall be flushed clean from end to end on completion and maintained in proper working order. All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects. Attach: Flushing Record, CCTV Reports | Record Review | Each lot | HP | SE/PE | This ITP Signed Off Attach: Flushing Records, and CCTV Reports | 6.2 - Flushing CHAR(AMP) CCTV | Reference - VR Section 701.28 VR Section 701.30 | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order. All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects. Attach: Flushing Record, CCTV Reports | Method - Record Review | Frequency - Each lot | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off Attach: Flushing Records, and CCTV Reports | 2.3 - Supply of: - Riser - Standard Headwall - Class D Pit Cover
6.3 | As-Built Drawings | As-Built Drawing Management Procedure (A8197) Section 701 | IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM. Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10 | Document review and approval | Once | HP | SE/PE Supervisor | This ITP Signed Off Attach: As-Built Survey Pickup | 6.3 - As-Built Drawings | Reference - As-Built Drawing Management Procedure (A8197) Section 701 | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM. Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10 | Method - Document review and approval | Frequency - Once | Category - HP | Responsibility - SE/PE Supervisor | Verifying Documents - This ITP Signed Off Attach: As-Built Survey Pickup | Reference - L1-CHE-STD-030 Section 705
6.4 | Non-conformance Report (NCR) Closure | MTM Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP | SE/PE | This ITP Signed Off | 6.4 - Non-conformance Report (NCR) Closure | Reference - MTM Quality Management Plan | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Method - Document Review | Frequency - Once, prior to closure of this lot / element / Work area | Category - HP | Responsibility - SE/PE | Verifying Documents - This ITP Signed Off | Acceptance Criteria - To meet L1-CHE-STD-030 requirements. To be supplied in accordance to Section 705 To be inspected upon delivery to have no damage.
Method - Visual Measure Document Review
Frequency - Prior to works commencing
Category - HP
Responsibility - SE/PE
Verifying Documents - This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
3.1 - Primary Documentations
Reference - A4263 PTDT Form B - Track Certifier Booking Form
Acceptance Criteria - Approved PTDT
Method - Document review and approval
Frequency - Prior to works commencing
Category - HP
Responsibility - SE/PE
Verifying Documents - This ITP Signed Off Attach: Approved Permit
3.2 - Pre-Commencement of Work
Reference - ITP, Quality Checklist, SWMS
Acceptance Criteria - All approved by relevant representative.
Method - Document review and approval
Frequency - Once (Prior to Works)
Category - HP
Responsibility - SE/PE
Verifying Documents - This ITP Signed Off Attach: Approved Templates
4.1 - Approval of IFC drawings
Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
Acceptance Criteria - Approved IFC Drawings
Method - Document review and approval
Frequency - Prior to works commencing
Category - HP
Responsibility - SE/PE
Verifying Documents - This ITP Signed Off
5.1 - Survey Track Drainage Alignment CHAR(AMP) Pits
Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation.
Method - Visual Inspection Survey / Measure
Frequency - As Task Progresses
Category - HP
Responsibility - SE/PE Supervisor Surveyor
Verifying Documents - This ITP Signed Off Attach: Survey Records CHAR(AMP) Photos on site
5.2 - Grade Existing Open Cess Drain
Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
Acceptance Criteria - Grade through existing cess drain alignment to depth indicated on design documentation.
Method - Visual Inspection Survey / Measure
Frequency - As Task Progresses
Category - HP
Responsibility - SE/PE Supervisor
Verifying Documents - This ITP Signed Off Attach: Photos on site
5.3 - Excavate Slotted Pipe Drainage Trench
Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation
Method - Visual Inspection Survey / Measure
Frequency - As Task Progresses
Category - HP
Responsibility - SE/PE Supervisor
Verifying Documents - This ITP Signed Off Attach: Photos on site
5.4 - Place the Following and Compact: - Bedding Sand - Geofabric - Slotted Pipe - Stone
Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
Acceptance Criteria - Bedding conforming to to Section 701.09 shall be supplied, placed and compacted. Compaction and moisture content testing to be in accordance with Section 701.20 (where applicable). Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three (3). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (b) Backfill (i) Material of nominal size 40 mm or less after compaction - Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (ii) Material of nominal size greater than 40 mm after compaction - Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. - Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. Trench to be wrapped with geotextile in accordance with the manufacturers specifications and design documentation. Attach: Compaction Test Reports
Method - Visual Inspection Survey / Measure
Frequency - As Task Progresses
Category - HP
Responsibility - SE/PE Supervisor
Verifying Documents - This ITP Signed Off Attach: Photos on site Compaction Test Reports
5.5 - Pit, Headwall CHAR(AMP) Beaching Rock Installation
Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
Acceptance Criteria - All stormwater pits shall be provided with a lockable minimum Class D pit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
Method - Visual Inspection Measure
Frequency - As Task Progresses
Category - HP
Responsibility - SE/PE Supervisor
Verifying Documents - This ITP Signed Off Attach: Photos on site
6.1 - Track Certification
Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
Acceptance Criteria - - Track Geometry Conformance Certificate - Track System and Component
Method - Visual Measure Document Review
Frequency - Once (upon completion of occupation works)
Category - HP
Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
Verifying Documents - This ITP Signed Off Attach: Relevant Conformance Certs as per acceptance criteria
6.2 - Flushing CHAR(AMP) CCTV
Reference - VR Section 701.28 VR Section 701.30
Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order. All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects. Attach: Flushing Record, CCTV Reports
Method - Record Review
Frequency - Each lot
Category - HP
Responsibility - SE/PE
Verifying Documents - This ITP Signed Off Attach: Flushing Records, and CCTV Reports
6.3 - As-Built Drawings
Reference - As-Built Drawing Management Procedure (A8197) Section 701
Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM. Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
Method - Document review and approval
Frequency - Once
Category - HP
Responsibility - SE/PE Supervisor
Verifying Documents - This ITP Signed Off Attach: As-Built Survey Pickup
6.4 - Non-conformance Report (NCR) Closure
Reference - MTM Quality Management Plan
Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
Method - Document Review
Frequency - Once, prior to closure of this lot / element / Work area
Category - HP
Responsibility - SE/PE
Verifying Documents - This ITP Signed Off