## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
d4dd405f-6622-42a9-9fca-3acfd6b6882d | checklist | Internal Wet Areas (Bathrooms & Laundries waterproofing |  | Internal Wet Areas (Bathrooms & Laundries waterproofing
67d74995-0e4e-4d84-8e44-551400dc3699 | section | Details
2cf88491-13c1-4b05-a5a0-1b45e0b49b5b | checkpoint | Area Barricaded off to allow no access to internal wet areas with signs posted/visible to include date of application, 'no access waterproofing work in progress
3132d543-dfec-5fcb-b46d-d2903298e8e7 | note | attach relevant photos
421cbffc-e9e2-545e-bf60-4f7b438c9c68 | tickbox | Membrame system & methodology checked off against Landmark waterproofing details as per the Australian standard and MSDS
bc10506b-8464-54d2-ba8a-1af28dfcfe6d | tickbox | substrate clean, structurally sound & ready...
680e209f-ad0f-532a-ad60-41ff6fa34e62 | tickbox | ensure no high points..
3932cfa8-f383-58f7-8b5f-b5d7ec6e4f0e | tickbox | Holdpoint- do not proceed if above...
f3df563a-7e82-443a-8b58-318b8c0be531 | checkpoint | Apply PVC primer to all PVC drains and pipes
943a7c46-a476-5493-a811-146a2ec707e9 | note | attach relevant photos
fd046890-dcfe-42f2-a52f-bbee1beefe34 | checkpoint | Primer substrate with Trem proof 200EC as per data sheet and application guidelines
12e8f497-b90f-5d39-8d98-fabe6be7850b | note | attach relevant photos
1b178ad2-af9b-4b53-be4c-2ff8ea4b2394 | checkpoint | Install alluminium waterstops to door entries and showers as per landmarks FFL
b7a4b746-a2a0-58e2-8471-fdea15a126cc | note | attach relevant photos
35a4437f-5472-49c7-bea2-12487cc6b8d8 | checkpoint | seal all joints, gaps, cracks... with Tremflex 50 sealant- apply selected sealant as per datasheet & application guidelines
0902f628-7d42-5d85-a033-744f3953f4da | note | attach relevant photos
240dd9ce-2905-472e-85cf-1a1d95b91f3b | checkpoint | Apply 1st coat of Vulkem NEM plus on floors at the recommended thickness as per datasheet & application guidelines
63307301-a7e7-565c-bad1-6e03071a43c4 | note | attach relevant photos
e968b720-0524-4d66-b3af-9a99b33668d9 | checkpoint | Apply 2nd coat of Vulkem NEM plus on floors at the recommended thickness as per datasheet & application guidelines
5913fd88-19e6-5ea4-b236-ef173b7363af | note | attach relevant photos
a9d6df17-ceb5-4e87-adc4-4343a3fe010f | checkpoint | Waterproof walls of showers & vanity up to 1.8m ceiling at the recommended thickness as per datasheet & application guidelines
30b56806-6bd0-4d80-bfb3-246d122c1708 | checkpoint | Allow membrane to dry
bfa741d4-01de-4c2c-861c-0c27d0f7ea0a | checkpoint | flood test for a minimum of 24 hours
0f436e9e-87a1-5338-beb1-a506d0bf55de | note | attach relevant photos
0db5bacf-8614-4ef7-a505-4fb94b503548 | checkpoint | Carry out dry film thickness using positector coating thickness inspection instruction- review result against datasheet & application guidelines
804f00a0-3c41-475d-943c-d9200567261b | checkpoint | Final sign off- all general waterproofing work completed as per the above ITP
12438161-a55d-5f55-a2c6-a472fb61c5c0 | tickbox | Holdpoint- do not proceed if above...