## Sheet1
Homi Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station |  |  |  | Rev | 2 |  | Inspection and Test Codes:
Activity Title |  | Footpath Construction |  |  |  | Date | 2024-10-17 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location | [5 empty] | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-001 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Mike Robertson
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | 3235599-SP03-CA-1031 - Rev 1 New Footpath Typical Sections 3235599-SP03-CA-1032 - Rev 1 3235599-SP03-CA-1033 - Rev 1 3235599-SP03-CA-1001 - Rev 1 General Notes
Specifications: |  | NZS3910:2013 746-24-874-AC 746-22-052-PS NZS 3114:1987, part 2 Exposed Aggregate surfaces. TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction Transport New Zealand ATCOP Chapter 12: Footpaths AND Pedestrian Facilities, and RTS14 “Guidelines for Facilities for Blind and Vision-impaired Pedestrians”
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Responsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Engineer's Rep | Designer Rep
1 | PRELIMINARY AND GENERAL
1.1 | IFC Drawings and Specification |  | ACC | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification |  | Once |  | N/A | R |  | H | Sign | Date
1.2 | Method Statement & JSEA Development |  | The Downer Standards (TDS) | Prior to construction: document review. |  | Once |  | Method Statement & JSEA Completed & signed by relevant authority | H | R | R | Sign | Date
1.3 | Permit to Dig |  | DN-ZH-ST043 Ground Disturbance | Prior to construction. Permit in work package |  | Permit issued each week |  | Permit number ....................... | H |  |  | Sign | Date
1.4 | Survey Model |  | N/A | Model Review. |  | Once |  | Visual Inspection & measurement Survey Check set out as per design | H |  |  | Sign | Date
2 | MATERIAL APPROVALS
2.1 | Concrete Mix Design |  | 746-22-052-PS Section 5.2 NZS 3114:1987, part 2 Exposed Aggregate surfaces. | Mix Design approved by designer. 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. |  | Once |  | Approved Mix InEight Reference ................. | R |  | H | Sign | Date
2.2 | ATAP40/GAP40 - Material Source property testing and sampling |  | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4) |  | Once Per Year Or Every 10 000 m³ |  | IANZ Test Report | R |  | H | Sign | Date
2.3 | ATAP40/GAP40 - Production property testing and sampling |  | TNZ M/4: 2006 - 4 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control |  | Once Per Year Or Every 10 000 m³ |  | IANZ Test Report | R |  | H | Sign | Date
2.4 | ATAP40/GAP40 - Testing for layor compaction - MDD |  | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Average MDD 95% with a minimum of 92% |  | Once Per Year Or Every 5 000 m³ |  | IANZ Test Report | R |  | H | Sign | Date
2.5 | Reinforcing Steel |  | 3235599-SP03-CA-1031 - Rev 1 | SE62 - 665 Mesh Grade 500E. |  | Once |  | Mill Certificates & Approval | H |  | R | Sign | Date
2.6 | Contraction Joints |  | 3235599-SP03-CA-1031 - Rev 1 | 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. |  | Once |  | Mill Certificates & Approval | H |  | R | Sign | Date
2.7 | Tactile Indicators |  | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | 300mm x 300mm x 60mm thick yellow anti-slip precast concrete. |  | Once |  | MDS & Approval | H |  | R | Sign | Date
2.8 | Joint Sealer |  | 3235599-SP03-CA-1031 - Rev 1 | SIKAFLEX 11FC or similar approved product. |  | Once |  | MDS & Approval | H |  | R | Sign | Date
2.9 | Joint Filler |  | 3235599-SP03-CA-1031 - Rev 1 | 8mm Polystyrene joint filler . |  | Once |  | MDS & Approval | H |  | R | Sign | Date
2.1 | Stitching Reinforcing Bars |  | AT Detail FP002 | 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300 |  | As required |  | Mill Certificates & Approval | H |  | R | Sign | Date
2.11 | Geotextile |  | 3235599-SP03-CA-1031 - Rev 1 | A29 Geotextile Bidim, or similar approved product. |  | As required |  | MDS & Approval | H |  | R | Sign | Date
2.12 | Geogrid |  | 3235599-SP03-CA-1031 - Rev 1 | Tensar Triax 170 Geogrid or similar approved product. |  | As required |  | MDS & Approval | H |  | R | Sign | Date
CONSTRUCTION ACTIVITIES
3.1 | Footpath set out and excavation to subgrade |  | IFC drawings and Models 746-22-052-PS Page 9 Table 1 | Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane. NO WATER PONDING ON SUBGRADE. |  | Every 5m |  | As-Built or Stringline checksheet | H |  |  | Sign | Date
3.2 | Foundation - Subgrade Testing (Scala) |  | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1 | If caly based material is encountered - ensure subgrade has a minimum CBR of 3 Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%. |  | Every 25m² |  | Scala Test Results - CBR of 3 | H |  | R | Sign | Date
3.3 | Foundation - Subgrade Testing (Existing footpath) (Clegg) |  | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1 | If granular material is encountered - Minimum CIV of 12 |  | Every 10m |  | Clegg Test Results - min CIV 12 | H |  | R | Sign | Date
3.4 | Place Geotextile |  | 3235599-SP03-CA-1001 - Rev 1 Note 12 | An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade. A29 Bidim, ensure top, bottom and sides are coverd. |  | Per inpsection |  | Checksheet Photos | I |  |  | Sign | Date
3.5 | Undercut (If required) |  | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2 | Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed. |  | As required |  | HP Release | I |  | H | Sign | Date
3.6 | Place Geogrid (Only required for undercuts) |  | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2 | Placed above the geotextile prior to backfilling. |  | As required |  | Checksheet Photos | I |  |  | Sign | Date
3.7 | Place and compact Basecourse GAP40 |  | 3235599-SP03-CA-1001 - Rev 1 Note 9 | 100mm thick layer compacted where no undercut is required Where undercut is required: Contractor to notify Engineer. Minimum CLEGG CIV - 12. |  | Every 10 m |  | Clegg Test Results and photos | I |  |  | Sign | Date
3.8 | Timber edging |  | IFC Set out | All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick. |  | As required |  | Checksheet Photos | I |  |  | Sign | Date
3.9 | Place Reinforcing Mesh |  | 3235599-SP03-CA-1031 - Rev 1 3235599-SP03-ST-3002 Note 6.1 | 665 mesh, centrally placed. Minimum overlap of 200mm between outermost cross wires. |  | Every pour |  | Checksheet Photos | I |  |  | Sign | Date
3.1 | Place Contraction Joints |  | 3235599-SP03-CA-1031 - Rev 1 | 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. Installed every 15m. |  | Every 15m |  | Checksheet Photos | I |  |  | Sign | Date
3.11 | Place Tactilies |  | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | Tactile pavers shall be bedded on 100mm thick 20Mpa concrete. Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement. A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons |  | Per installation |  | Delivery dockets, Checksheet Photos | H |  | I | Sign | Date
3.12 | Place reinforcing Stitching Bars |  | AT Detail FP002 | Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners. 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300 |  | As required |  | Mill certificates and photos | I |  |  | Sign | Date
3.13 | Concrete Pre-Pour |  | AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge |  | Every Pour |  | Pre-Pour Checklist | H |  | I | Sign | Date
3.14 | Concrete Pour |  | AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | 2% Cross Fall Towards Carriageway. (1% min. 3% max.) 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Slump 120mm (±30mm) |  | Every Pour |  | 7 day and 28 day Concrete Test Results from supplier Slump Test Results (onsite) | W |  | W
3.15 | Concrete Finish |  | AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Exposed finish apply surface with Rugasol C. Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom ( U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm. |  | Every Pour |  | Post pour inspection checksheet | W
3.16 | Saw Cut Joints |  | 3235599-SP03-CA-1001 - Rev 1 Note 5 AT TDM | Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m. |  | Every 3m |  | Photos | W
4 | FINAL RECORDS
4.1 | Construction Record Compilation |  | N/A | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. |  | Once |  | QA Records | H |  | R | Sign | Date
4.2 | Survey Records |  | N/A | Ensure all items have been surveyed and records are assembled for asbuilting |  | Once |  | As-Built | H |  | R | Sign | Date
4.3 | Redline Drawings |  | IFC Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. |  | Once |  | IFC Mark-Up | H |  | R
4.4 | Defect, Snag and Punch List |  | DN1212-DOW-PLA-PM-0005 QMP | Update the project Defect, Snag and Punch List Register |  | If required |  | Snag Register | H |  | R | Sign | Date
4.5 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | When Required |  | NCR Forms on InEight | H |  | R | Sign | Date
Comments:
ITP APPROVAL PROCESS
Prepared By: Quality Engineer |  |  | Nas Matar |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed By: QA Manager |  |  | Cordelia Gridler-Brown |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | TBC |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  | Date:
QA Mgr./Engineer |  |  |  |  | Signed: |  | Date:
Designers Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need this in the ITP? Could we remove this? This falls under the construction work pack methodology Reply: I would leave it as you need it before you can start digging
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need to have this in the ITP? As we have set out points below?
Note on A60: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.