## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-001 Concrete Footpath | itp |  |  |  |  | DN1212-ITP-001 Concrete Footpath Rev2
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with Project specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Method Statement & JSEA Development
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Permit to Dig
label | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Model
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
label | Test Frequency - Once
label | QA Record - Visual Inspection & measurement Survey Check set out as per design
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2, NZS 3114:1987, part 2 Exposed Aggregate surfaces.
label | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer.
label | ○ 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
label | Test Frequency - Once
label | QA Record - Approved Mix
textbox | InEight Reference
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - ATAP40/GAP40 - Material Source property testing and sampling
label | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
label | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4)
label | Test Frequency - Once Per Year Or Every 10 000 m³
label | QA Record - IANZ Test Report
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - ATAP40/GAP40 - Production property testing and sampling
label | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4, NZS 4407 : 1991
label | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control
label | Test Frequency - Once Per Year
label | ○ Or Every 10 000 m³
label | QA Record - IANZ Test Report
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - ATAP40/GAP40 - Testing for layor compaction - MDD
label | Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
label | Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | ○ Average MDD 95% with a minimum of 92%
label | Test Frequency - Once Per Year Or Every 5 000 m³
label | QA Record - IANZ Test Report
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Reinforcing Steel
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - SE62 - 665 Mesh Grade 500E.
label | Test Frequency - Once
label | QA Record - Mill Certificates & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Contraction Joints
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
label | Test Frequency - Once
label | QA Record - Mill Certificates & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Tactile Indicators
label | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11
label | Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip precast concrete.
label | Test Frequency - Once
label | QA Record - MDS & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Joint Sealer
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - SIKAFLEX 11FC or similar approved product.
label | Test Frequency - Once
label | QA Record - MDS & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Joint Filler
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - 8mm Polystyrene joint filler .
label | Test Frequency - Once
label | QA Record - MDS & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Stitching Reinforcing Bars
label | Standard, Drawing or Specification Reference - AT Detail FP002
label | Construction Activity Description, Test Type and Acceptance Criteria - 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
label | Test Frequency - As required
label | QA Record - Mill Certificates & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Geotextile
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - A29 Geotextile Bidim, or similar approved product.
label | Test Frequency - As required
label | QA Record - MDS & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Geogrid
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Tensar Triax 170 Geogrid or similar approved product.
label | Test Frequency - As required
label | QA Record - MDS & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Footpath set out and excavation to subgrade
label | Standard, Drawing or Specification Reference - IFC drawings and Models 746-22-052-PS Page 9 Table 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane.
label | ○ NO WATER PONDING ON SUBGRADE.
label | Test Frequency - Every 5m
label | QA Record - As-Built or Stringline checksheet
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Foundation - Subgrade Testing (Scala)
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 9 Table 1
label | Construction Activity Description, Test Type and Acceptance Criteria - If caly based material is encountered - ensure subgrade has a minimum CBR of 3
label | ○ Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%.
label | Test Frequency - Every 25m²
label | QA Record - Scala Test Results - CBR of 3
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Foundation - Subgrade Testing (Existing footpath) (Clegg)
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 9 Table 1
label | Construction Activity Description, Test Type and Acceptance Criteria - If granular material is encountered - Minimum CIV of 12
label | Test Frequency - Every 10m
label | QA Record - Clegg Test Results - min CIV 12
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Place Geotextile
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12
label | Construction Activity Description, Test Type and Acceptance Criteria - An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade.
label | ○ A29 Bidim, ensure top, bottom and sides are coverd.
label | Test Frequency - Per inpsection
label | QA Record - Checksheet, Photos
label | DNZ Engineer - I
checkpoint | 3.5 - Undercut (If required)
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 10 Table 2
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed.
label | Test Frequency - As required
label | QA Record - HP Release
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Place Geogrid (Only required for undercuts)
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 10 Table 2
label | Construction Activity Description, Test Type and Acceptance Criteria - Placed above the geotextile prior to backfilling.
label | Test Frequency - As required
label | QA Record - Checksheet, Photos
label | DNZ Engineer - I
checkpoint | 3.7 - Place and compact Basecourse GAP40
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 9
label | Construction Activity Description, Test Type and Acceptance Criteria - 100mm thick layer compacted where no undercut is required
label | ○ Where undercut is required: Contractor to notify Engineer.
label | ○ Minimum CLEGG CIV - 12.
label | Test Frequency - Every 10 m
label | QA Record - Clegg Test Results and photos
label | DNZ Engineer - I
checkpoint | 3.8 - Timber edging
label | Standard, Drawing or Specification Reference - IFC Set out
label | Construction Activity Description, Test Type and Acceptance Criteria - All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick.
label | Test Frequency - As required
label | QA Record - Checksheet, Photos
label | DNZ Engineer - I
checkpoint | 3.9 - Place Reinforcing Mesh
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1, 3235599-SP03-ST-3002 Note 6.1
label | Construction Activity Description, Test Type and Acceptance Criteria - 665 mesh, centrally placed.
label | ○ Minimum overlap of 200mm between outermost cross wires.
label | Test Frequency - Every pour
label | QA Record - Checksheet, Photos
label | DNZ Engineer - I
checkpoint | 3.10 - Place Contraction Joints
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
label | ○ Installed every 15m.
label | Test Frequency - Every 15m
label | QA Record - Checksheet, Photos
label | DNZ Engineer - I
checkpoint | 3.11 - Place Tactilies
label | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1, Note 11
label | Construction Activity Description, Test Type and Acceptance Criteria - Tactile pavers shall be bedded on 100mm thick 20Mpa concrete.
label | ○ Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement.
label | ○ A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons
label | Test Frequency - Per installation
label | QA Record - Delivery dockets, Checksheet, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Place reinforcing Stitching Bars
label | Standard, Drawing or Specification Reference - AT Detail FP002
label | Construction Activity Description, Test Type and Acceptance Criteria - Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners.
label | ○ 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
label | Test Frequency - As required
label | QA Record - Mill certificates and photos
label | DNZ Engineer - I
checkpoint | 3.13 - Concrete Pre-Pour
label | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge
label | Test Frequency - Every Pour
label | QA Record - Pre-Pour Checklist
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.14 - Concrete Pour
label | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - 2% Cross Fall Towards Carriageway. (1% min. 3% max.)
label | ○ 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
label | ○ Slump 120mm (±30mm)
label | Test Frequency - Every Pour
label | QA Record - 7 day and 28 day Concrete Test Results from supplier, Slump Test Results (onsite)
label | DNZ Engineer - W
label | Designer Rep - W
checkpoint | 3.15 - Concrete Finish
label | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
label | ○ Exposed finish apply surface with Rugasol C.
label | ○ Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom (U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm.
label | Test Frequency - Every Pour
label | QA Record - Post pour inspection checksheet
label | DNZ Engineer - W
checkpoint | 3.16 - Saw Cut Joints
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 5, AT TDM
label | Construction Activity Description, Test Type and Acceptance Criteria - Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m.
label | Test Frequency - Every 3m
label | QA Record - Photos
label | DNZ Engineer - W
section | 4 - FINAL RECORDS
checkpoint | 4.1 - Construction Record Compilation
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Test Frequency - Once
label | QA Record - QA Records
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Records
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Redline Drawings
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Test Frequency - Once
label | QA Record - IFC Mark-Up
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Defect, Snag and Punch List
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Test Frequency - If required
label | QA Record - Snag Register
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - When Required
label | QA Record - NCR Forms on InEight
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Quality Engineer - Nas Matar
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed By: QA Manager - Cordelia Gridler-Brown
label | Reviewed By: Design Engineer - TBC
label | Reviewed By: AT Project Manager - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature