## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-001 - Pre-commencement of works | itp | ITP-001 - Pre-commencement of works
| section | 1 - Construction - General
| checkpoint | 1.1 - Design Drawings
ef78582b-cf8b-511c-a466-3d576ca0d678 | note | FREQUENCY: Prior to commencing any activity
be13fa40-00b6-596f-aca4-c9e1d2b12560 | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
35cd3411-aa98-5b31-9ebd-6cae1e6d65da | note | REFERENCE DOCUMENTS: IFC Drawings
9569fba4-5118-560c-a1f3-ee35c2513d65 | note | INSPECTION/TEST METHOD: Visual inspection
6f85d1af-6651-57bb-aa47-7d6f163da6a8 | note | RECORD OF CONFORMITY: ITP Signed
b8f00a98-a449-597f-8f8a-4b4a81d8dbc6 | note | IHP
b5f1079b-8c63-5acb-acd0-71e5f029462b | note | RESPONSIBILITY: Site Engineer / Site Foreman
282107d1-a0e1-5f23-9e23-aebc73e6b1b4 | date | Date Completed:
| checkpoint | 1.2 - Service Locating / Permits
430c54f2-321c-58e9-a7fe-269ef14e929f | note | FREQUENCY: Prior to commencing any activity
6b63ef4d-5f46-5de1-afcd-c2bfe7e5455a | note | ACCEPTANCE CRITERIA: Lodge DBYD application prior to works commence and obtain any relevant permits applicable to the works. DBYD to be renewed every 30 days.
5ee8f73d-d35b-5bcd-bd73-5e8bc2126bc2 | note | ○ All nominated/aﬀected services from the DBYD application must be located/potholed prior to commencement of works.
1eb47062-46a5-5f0e-a370-f1af7e8e6b63 | note | ○ Works identified within the vicinity of the powerlines to ensure distance exclusions are followed & spotter used, if required.
0e0a3e8d-169d-56ae-810d-35e64dc4e5f9 | note | REFERENCE DOCUMENTS: DBYD Information
26cb49a2-40af-58c0-a85b-061311158cd0 | note | INSPECTION/TEST METHOD: Visual inspection
060d7efa-7b6d-50fb-bd2e-0761eff93a72 | note | RECORD OF CONFORMITY: ITP Signed
1c2062ba-d191-545d-85be-75cb69add35b | note | IHP
e21b9616-d448-5446-b13e-c4015236e47f | note | RESPONSIBILITY: Site Engineer / Site Foreman
bc41217a-b29a-5674-b7be-c960ae6b96e1 | date | Date Completed:
| checkpoint | 1.3 - Commencement of work
12d4df68-8793-5131-a436-cd8d215467f4 | note | FREQUENCY: Prior to commencing any activity
f471d535-1b9a-56c2-b115-d75642c7e097 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence work on site before the following documents have been submitted to the Superintendent and the Superintendent has authorised release of the Hold Point:
2e636ac7-2b94-5b54-bb28-b5e3181268ee | note | (a) Public Liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
f6542d9f-ca97-5933-8231-518e27dca617 | note | (b) Health and Safety Co-ordination Plan
8ca7931f-d432-58ee-8f9d-f1050fbd7ffa | note | (c) Environmental Management Plan for initial works
c389e556-89b0-58bf-983f-8b3b6423b16e | note | (d) Project Management Plan
a2e5d44a-481c-599d-b87f-46c231ed75d2 | note | (e) Quality Management Plan
ae8207cf-3e41-5817-be36-dafe92f7fa1f | note | (f) Safety Management Plan
c362e3d9-c0a9-565c-b963-81a9dca73bb4 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 160, 166, 167, 168 & 176
5ae1bbaf-b8cc-5918-896f-74030f3a0d86 | note | INSPECTION/TEST METHOD: Visual Inspection
0bbe69bf-0131-5763-aace-7a6ee526c85a | note | RECORD OF CONFORMITY: ITP Signed
21ea7b69-b432-563b-a7fe-e36cf01f9cde | note | HP
abf1a4c5-9d70-574a-a177-04a91ec5990a | note | RESPONSIBILITY: Site Engineer
9b02bc07-8fae-5a84-bdb1-a0fe80359465 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Traffic Management
| checkpoint | 2.1 - Submission of the TMP to the Superintendent
5410b5c3-976b-5e48-908a-147df1a6a962 | note | FREQUENCY: Prior to commencing any activity
fd3b69b2-0a8a-5023-9fb6-095e2de68e78 | note | ACCEPTANCE CRITERIA: The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point.
1e68bfa3-936e-5b3b-970c-87f3ccf7fe76 | note | REFERENCE DOCUMENTS: TMP, VicRoads Standard Section 166.08
0637759c-253f-55b0-a346-e887c88351a5 | note | INSPECTION/TEST METHOD: Visual Inspection
369d4f3b-e3d1-58cc-a249-5dc75c162a3b | note | RECORD OF CONFORMITY: ITP Signed
59729f18-018b-5455-a6fb-1b6ef30733c0 | note | HP
7673bcbe-4869-5e13-a312-a2c0f496d694 | note | RESPONSIBILITY: Site Engineer
028c1518-25bd-5c51-8a09-e24bd2736a36 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Detours and Side Tracks (a) Side Tracks, (b) Detours
4f706fe0-15fa-5bcf-ac76-dae87379f88c | note | FREQUENCY: Prior to commencing any activity
7534f393-73ba-54ab-a982-e8c8634c82fd | note | ACCEPTANCE CRITERIA: Traffic shall not be diverted on to any side track until permission to use such side track has been given by the Superintendent.
15e9e411-b23f-5942-ae66-d8c023f0ca3a | note | – Permission has been given by the Superintendent and Ballarat City Council.
04c9a070-e4b7-5936-963c-4183d68897e8 | note | ○ Where VicRoads as well as the Contractor has some responsibility for the restoration of any detours or sidetracks, the Contractor shall not commence any restoration work until the Contractor has submitted details of the work to be undertaken to the Superintendent for review.
4462e449-538a-5013-8f41-23dbb2d2e8a9 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166.17 (a) & (b)
b5420330-d1e0-52c8-9323-32bf2420e980 | note | INSPECTION/TEST METHOD: Inspection
1f7f2631-bd59-51a1-9722-d13c8b4368ea | note | RECORD OF CONFORMITY: ITP Signed
dcd860d9-e028-50d5-9a2b-e9c44097959e | note | HP
de328422-4a13-5b18-8191-2ac4a63317b8 | note | RESPONSIBILITY: Site Engineer
9cee23e8-fb48-5400-ba8c-668aab7e3ca9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Traffic Management Documentation
b627f37c-5b36-527f-ba29-2eb374d655fc | note | FREQUENCY: Prior to commencing any activity
862cb4ad-1b92-5bb7-954b-ecddd09f1309 | note | ACCEPTANCE CRITERIA: Ensure all TGS plans have been reviewed and deemed acceptable for the project. Obtain MoA approval for any road impacts or closures.
729c8cc5-5bd1-5619-9712-265a4752b55d | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166
23729023-edfc-5b96-9d58-bf7e73ebc350 | note | INSPECTION/TEST METHOD: Visual Inspection
c33814d2-fd32-5536-9608-d2026db76db3 | note | RECORD OF CONFORMITY: ITP Signed
64953b9b-31b2-5dac-8308-d93ac0062e11 | note | IHP
6b8a3e63-b1e3-56ce-a7ce-808e2a3b194c | note | RESPONSIBILITY: Site Engineer / Site Foreman
33d58c8d-d693-5199-bb90-83aca5a7c05c | date | Date Completed:
| section | 3 - Health and Safety
| checkpoint | 3.1 - Occupational Health & Safety Management Implementation
4aa2c408-0efc-595a-af19-594ac40b34f7 | note | FREQUENCY: Prior to commencing any activity
d9b1c51d-f054-55c5-9c51-c3f64085e5d9 | note | ACCEPTANCE CRITERIA: Signed Safe Work Method Statement (SWMS) in place. All personnel including Subcontractors must complete Site Induction prior to arriving on site.
a97e4701-d1fb-52c9-b6ce-d7c80bc94b8d | note | REFERENCE DOCUMENTS: Site Specific SWMS
c9058d60-db3a-5a94-9286-1f18061da3f8 | note | INSPECTION/TEST METHOD: Inspection
326d4cc0-b349-5c3d-b6b1-9edfcfa9d145 | note | RECORD OF CONFORMITY: ITP Signed, SWMS
98d6f494-9ebd-5f5d-ac26-348b05b4eda5 | note | IHP
ff9136c9-c428-5c13-9878-3e73e589dbab | note | RESPONSIBILITY: Site Engineer / Site Foreman
73449734-907e-55b0-8115-498f1e1d6474 | date | Date Completed:
| checkpoint | 3.2 - Health and Safety Co-ordination Plan and Declaration
f40dff29-eb87-51ff-bd6c-32f55381a78a | note | FREQUENCY: Prior to commencing any activity
d7628394-ce6d-5d6a-a440-2f36f623cfcc | note | ACCEPTANCE CRITERIA: The Contractor shall, not less than 5 working days prior to commencing work, submit to the Superintendent:
99ee9fc5-9413-562e-a986-dad6ef75ad62 | note | (a) a reviewed Health and Safety Co-ordination Plan; and
918abdf4-b107-53c9-870a-4ba73752759f | note | (b) a signed HSCP Declaration by an OH&S consultant/advisor that the HSCP meets all the necessary requirements. The Declaration shall be in accordance with the proforma included in the appendices of this Specification.
212c3003-f418-5093-bcb4-72b54a37c553 | note | (c) a completed VicRoads HSCP Checklist with Contractor’s responses for each checklist item requirement.
7c90392b-6ca3-5683-b39e-7f00fe2950ae | note | REFERENCE DOCUMENTS: VicRoads Standard Section 168.05 (c)
ca1c2433-a237-531b-aea2-7375f2ad6fb7 | note | INSPECTION/TEST METHOD: Submission
8fd1f519-3dd5-54d7-896e-4d5186a2be52 | note | RECORD OF CONFORMITY: ITP Signed, Safety Management Plan
c4e6aae8-32a2-51c5-acda-1a0a7b0d69c8 | note | HP
87682bd1-9ccc-557c-8159-effbcb95590e | note | RESPONSIBILITY: Site Engineer
dc9a6f45-12c2-5271-9952-8702b2694cfb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Environmental Management
| checkpoint | 4.1 - Environmental Impacts, Aspects & Risk Assessment Implementation
acd6b783-e15f-5b8e-a9a8-bfc7edb67999 | note | FREQUENCY: Prior to commencing any activity
bcb924e6-3ea3-59c2-8f3c-61f40b76c231 | note | ACCEPTANCE CRITERIA: All environmental controls implemented in accordance with the Contract Environmental Impacts, Aspects & Risk Assessment.
8870f23d-f85e-55e8-9954-9be1937fba3f | note | REFERENCE DOCUMENTS: EMP & A&I
12163dd6-dc41-5217-ac62-fdc1ec4fe5bf | note | INSPECTION/TEST METHOD: Visual Inspection
2d0a449e-45c1-5094-a284-b8c6f39bbc4c | note | RECORD OF CONFORMITY: ITP Signed
947cd06b-003a-55b5-bef3-c216813116f0 | note | IHP
cd898bd0-7d6b-5fae-93a6-4e0bf81f60e4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1d5fe614-0ef2-5d11-9463-c9a0d1b3b685 | date | Date Completed:
| checkpoint | 4.2 - Environmental Management Plans
9dad0767-89cb-5d6b-b887-d9ac4745cf58 | note | FREQUENCY: Prior to commencing any activity
19d7b801-0a26-5267-9b7c-db67084efd0d | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review an Environmental Management Plan not less than 2 weeks prior to the commencement of work. Work shall not commence until:
3a950254-fc43-5ace-8953-172a1e8c0b7b | note | – the Superintendent is satisfied that the Plan meets the requirements of this specification; and
a8b812bd-98b9-5fab-9978-7f4fb2ba6cec | note | – the controls detailed in the Plan are implemented; and
d009f905-8b50-55de-8113-4cc916ea67ea | note | – the Superintendent has authorised release of the Hold Point.
f2315b8f-267a-56c1-be2c-4006ad96d5c6 | note | – Limit of works identified in applicable SWMS.
cd24dc22-2fdb-530c-b98f-d91fab435d44 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.A3, VicRoads Standard Section 177.A3
8fa5e67d-58dd-5afb-b0ac-f5d504bf732b | note | INSPECTION/TEST METHOD: Submission
1bd17015-9e55-55c7-826b-cffccb88d0b9 | note | RECORD OF CONFORMITY: EMP, ITP Signed
e5e0342b-e26b-5281-b8d6-94a70ca55d01 | note | HP
28861a54-3908-5c5b-a70a-f516dcc45a7f | note | RESPONSIBILITY: Site Engineer/Superintendent
2a2bf56d-fee3-5b8b-b67b-e29488797fce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Flora and Fauna
7fac8a2b-0982-5263-a577-d4b2df500756 | note | FREQUENCY: Prior to commencing any activity
978c5b1c-c1ad-530d-b21f-f949cfdc6d5c | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to conﬁrm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones.
36be6012-cfe3-54c4-ac3c-f38df6249c3b | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.I1, VicRoads Standard Section 177.I1(c)
7444744c-fa6f-5c2e-a237-ed89d8b718fd | note | INSPECTION/TEST METHOD: Visual Inspection
fed875ab-c809-5039-97c9-1313f862fd4b | note | RECORD OF CONFORMITY: ITP Signed, Relevant permits, No Go Zone Signage
b6771031-1a80-52da-90ae-6baccc655f0b | note | HP
e03113c3-178f-5052-bd2d-9cc7b6cfb973 | note | RESPONSIBILITY: Site Engineer
92c81c8e-1d80-5dfa-9d88-96262da22c29 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Erosion and Sediment Control
a68d9d42-29de-5f7f-877c-8d03451c9cb1 | note | FREQUENCY: Prior to commencing any activity if applicable
d98331e0-db37-5638-b170-ecd15c416182 | note | ACCEPTANCE CRITERIA: The Contractor shall provide the necessary environmental controls as nominated on the approved Environmental Management Plan and identified on site.
dd1258d4-fd17-5cf4-82c1-ca7f6f05681c | note | REFERENCE DOCUMENTS: VicRoads Standard Section 177.D1(c)
137f7a6d-4564-5a45-8c75-79e7815e8d9a | note | INSPECTION/TEST METHOD: Visual Inspection
8bc76de2-794d-5933-b0ba-53b97b2dc978 | note | RECORD OF CONFORMITY: ITP Signed
67f8a512-c74c-5195-b318-923caa1ff2e1 | note | IHP
fd257102-bdd1-5f29-8742-1f1a905a125b | note | RESPONSIBILITY: Site Engineer / Site Foreman
1a9709ec-573a-55a7-8f2a-9ce5011af90d | date | Date Completed:
| section | 5 - Stakeholder and Community Engagement
| checkpoint | 5.1 - Residents have been informed
139ef1a8-28a2-50a4-b2de-374d2201e9de | note | FREQUENCY: Prior to commencing any activity
2828fb78-2153-5f20-a26c-d296d5eb0f6f | note | ACCEPTANCE CRITERIA: Residents impacted by construction works are to be notified by letter drop of the construction taking place, the timeframe of the works and information on how the works will affect them.
00d2fb93-0fbf-5186-9a22-9d92d6d4ec80 | note | REFERENCE DOCUMENTS: Letterdrop
78facefe-203a-5c04-aac1-4e9c33511fcf | note | INSPECTION/TEST METHOD: Visual Inspection
09fe2ae5-09ad-5c03-836a-2e2e39d1dd22 | note | RECORD OF CONFORMITY: ITP Signed
3e698a02-0392-51d1-b9a9-973b9631037e | note | HP*
1335e141-aeb4-5ed3-889a-ee9c3e65b608 | note | RESPONSIBILITY: Site Engineer
016ff884-5211-5e10-a419-618f623bcfca | date | Date Completed:
| checkpoint | Final Inspection
d70498f0-3eda-5c9a-9a92-324840d75313 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
029c9a23-56e0-5cb5-9a54-440dfff06c1f | textbox | Print Name:
93f481f4-557a-5a65-98f4-95347456af1c | textbox | Position:
9502b2b9-985f-5e9d-b90d-eaf2477832f0 | date | Date:
| checklist | ITP-003 - Subgrade Preparation | itp | ITP-003 - Subgrade Preparation
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
1d0fbee8-3383-5bf9-928f-25f13f3b365d | note | FREQUENCY: Prior to commencing any activity
ba1f7c61-2f97-5f03-91bb-14241115e508 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
aa1e2b28-feab-589b-98ee-a1fa749426a9 | note | – using the correct and complete set of drawings
f5007799-9cdc-5de2-9eff-66e6d086d4e8 | note | – all drawings are the latest revision
19f4d24d-df78-5514-ba71-643f09b4147f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
be94ebdd-70ab-56e4-81ec-d7987c883398 | note | INSPECTION/TEST METHOD: Visual inspection
041ab8c5-0bfe-51e4-a348-ee870e166a83 | note | RECORD OF CONFORMITY: This ITP signed off
4b0b8624-351b-51c7-a17b-f0d3165db0cc | note | HP*
f83efd59-e753-5ebd-83f2-aaddba1ae56e | note | RESPONSIBILITY: Site Engineer / Site Foreman
fbbdd944-9f55-58d7-a2fe-5cc367d9b691 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
7586f9a9-925c-5d05-8a1f-1bedbcab4433 | note | FREQUENCY: Prior to commencing any activity
e097a3b4-41fa-55d5-ad62-700088bdfd0b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0ce74379-1a3b-51e6-9ac0-a1a5dc24f500 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
5353f9aa-d815-521b-8637-02ebdadc02f1 | note | INSPECTION/TEST METHOD: Visual Inspection
7b6644c5-fc3f-582f-af61-234beb02e3d1 | note | RECORD OF CONFORMITY: This ITP signed off
7c26c030-14c5-59d7-afeb-b4943ae4d8cf | note | HP*
d7054964-c3cb-5013-aa86-96d9d132be9d | note | RESPONSIBILITY: Site Engineer / Site Foreman
e6417e83-0f70-5407-b0b8-73c0994878d7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
d67f9718-b9b5-536f-98e4-b66fe4f6f249 | note | FREQUENCY: Prior to commencement of excavation
53087338-3691-588e-b1fd-a7b43b74bc53 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
5d4227cd-9f12-51b5-8d13-19a121834257 | note | REFERENCE DOCUMENTS: Work Procedure
adf958e8-b93b-5097-9c33-ac2fc3a945d9 | note | INSPECTION/TEST METHOD: Verify
b75b29c5-421a-5a56-8bb0-6899f6cec753 | note | RECORD OF CONFORMITY: This ITP signed
12d4be69-9241-560d-a35f-e44373fd3ebd | note | IP
fe7bddda-747e-5f01-8905-e95d47197585 | note | RESPONSIBILITY: Site Engineer/ Surveyor
f7003609-a8b5-52e2-a901-5cd848d8406e | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
8e921500-cce7-522f-ab69-f361893f12a3 | note | FREQUENCY: Each lot
68a1b683-e812-5c10-8b98-ee3c10b9777f | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
b6977cc2-9eb7-5753-b9ef-666288936b6c | note | ○ Plant and equipment shall be appropriate for the task.
4cd1cada-397b-58f7-a112-f38a91e7c504 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
1efb04ac-9935-5f46-9555-2775ada7d5d3 | note | REFERENCE DOCUMENTS: Excavation permit
56252833-75fd-58a6-b720-fd6f26c3c112 | note | INSPECTION/TEST METHOD: Verify
c8e78bc8-9c85-5d31-ae0f-aabae382137a | note | RECORD OF CONFORMITY: This ITP Signed Off
8d341e46-bd6c-54e6-a258-30695ac1053a | note | HP*
f1312e18-0514-5972-ae0c-0f13a4d3676a | note | RESPONSIBILITY: Site Engineer / Site Supervisor
cf941502-7559-5c8d-8d78-fe23cc85a5f3 | date | Date Completed:
| checkpoint | 2.3 - Subgrade Material Properties
082b5eaa-d9d3-5e30-9f7a-ea53433e1568 | note | FREQUENCY: Each Lot
8b6f9b57-ff32-54ac-83b0-d4fa393af38d | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
f41c8269-dddf-5c4a-98c5-7e5e9c63e32b | note | ○ If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
11fb1061-fc13-5c21-a272-2e4cb658e59f | note | REFERENCE DOCUMENTS: Cl 204.06e
3ef9425c-3b78-53a5-b803-cd244cb5a4c1 | note | INSPECTION/TEST METHOD: Test Point
1409e85e-ddd0-5291-b0e2-96b076c7fdd1 | note | RECORD OF CONFORMITY: Test Reports
2808a61c-79bc-5479-bc3c-a2b48deef94f | note | TP
d09a429e-bff6-592d-bc3c-cf29a95c2e0c | note | RESPONSIBILITY: Site Engineer / Site Supervisor
a83dd765-0ab8-5342-b484-b886f49e7002 | date | Date Completed:
| checkpoint | 2.4 - Inspection of Subgrade Material
788653b6-5b3b-5e62-88e6-cb7f3abe2f9a | note | FREQUENCY: Each lot
ca57755f-fa99-5d08-ae4c-db873a50bea8 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
fe3b811c-df85-5390-b630-96c018cb60e0 | note | REFERENCE DOCUMENTS: Cl 204.06c
7b93ee00-be6b-5bd6-b8aa-1e8d2ea5a7cc | note | INSPECTION/TEST METHOD: Verify
a35f6a2b-340d-5b1a-852b-25d714828147 | note | RECORD OF CONFORMITY: This ITP Signed Off
60688238-4c53-5f6c-8e32-a3db91b7644f | note | HP
75e573e4-176e-5343-958b-9cef9b52b639 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
007e943d-c8a8-53ae-8a97-df8ef375b4e7 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.5 - Material classified as silt
14b3b9e6-dfdf-5976-b348-d37005ae08dd | note | FREQUENCY: Prior to Commencing
c781522c-cb43-52f9-9808-dfbd829adb4b | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
b79e7607-2560-557b-8b5d-87c317b41d97 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b)
a2bb8ace-d6cb-5f3e-8594-d623061adafa | note | INSPECTION/TEST METHOD: Document Review
3014fca4-3687-5d43-b7da-4ba6743db4ec | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/records
2f61a3e5-b6e1-5a59-b2e9-e083ed7d4a40 | note | HP
0c823502-888c-52ca-8994-4c3e9a94665a | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
f9b807f7-6634-5bca-a664-c02e0b3ff424 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
951bd435-efd5-560e-8749-63a90b59c197 | note | FREQUENCY: Prior construction of the regulating layer
f1e5ac9d-76cf-5063-bb82-82b2e4890e9d | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
ee52dfbb-4427-55b9-a4e7-63d20b454cbb | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
45fcd720-b9cf-5447-8d1b-fde1af9be58e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
a79c65d4-57fd-5aa0-b308-96c2b9c4ebda | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
5544506a-cbd5-5f24-b991-168b3994ea18 | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
bbaeee08-6b73-50c7-b9e9-77f7b1dffe09 | note | HP
b009252f-de05-5645-a505-03ca01afffbd | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
741aa5f3-dc91-51a1-a8bb-b19c2df6b5c0 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.7 - Unsuitable Material
c028deb3-bd2b-5233-bd96-5bd526d205a8 | note | FREQUENCY: Each Lot
367d2689-e38a-5d4b-a0ca-d07640e6e5bb | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
e16bd05f-d52c-5d81-bfd6-39b13bd22524 | note | – As per RFQ Section 200, Clause 200.3, the unsuitable material shall be jointly inspected by the Superintendent to determine the extent of the rehabilitation required.
22912137-61bc-50dd-a698-6a43cc4bf8ff | note | – Backfill of excavated area shall be with Type A material.
c55c4bc7-d675-50bf-b54a-07ad89e02c47 | note | REFERENCE DOCUMENTS: 204.07(d), RFQ Section 200, Cl 200.3
5ae90706-f1f8-58b0-9ae6-67f44a8d38b1 | note | INSPECTION/TEST METHOD: Visual Inspection
a5e1476e-af9e-5422-952a-e2d076b9ce95 | note | RECORD OF CONFORMITY: This ITP Signed Off
571eead6-45a0-5d28-b21a-fa09e0eae577 | note | HP
9f653d99-d200-5c4d-ae00-b6e7478623ce | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
dd40d59c-6c89-593c-8d9b-a39c7de84cdf | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.8 - Groundwater
c89fe1f1-28d1-54fb-a49c-8f057aba14e4 | note | FREQUENCY: Each Lot
2f1f6166-b307-5fe5-80a8-3296717cdfb0 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
ce769d8b-5d86-5d6c-a78d-e9cfb9a9e9a2 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
9a346da2-fe52-5182-8660-78ed2d55155e | note | REFERENCE DOCUMENTS: 204.06 (h)
86b20980-f235-582a-a2b9-e4f4aedcc80d | note | INSPECTION/TEST METHOD: Visual inspection
3e16fb49-4505-56bb-a048-e276e0e7a039 | note | RECORD OF CONFORMITY: This ITP signed off
00ebc5df-9002-5407-84eb-ab68edcce2bd | note | HP
3afd9255-8ec4-5776-b31d-b30de1885753 | note | RESPONSIBILITY: Site Engineer/ Superintendent
cb6066ad-20c8-53a9-8e78-0f1f8cabc13b | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.9 - Subgrade Level and Shape
62ca0608-ff4b-504b-88d0-3dc96462a941 | note | FREQUENCY:
7734e078-3f1f-563c-8995-0bed248d220e | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
457b48b5-935b-5572-97f0-ac59ab00e962 | note | Scale B:
cd9fca50-1d13-5a69-bdb9-3a2a1710cbca | note | ○ Measurements per lot = 40
e4fa4549-c902-5b4f-bff6-f71af99d83cb | note | Surface level tolerances:
ff46d3b9-2de3-58d2-98ba-3fdd17acb270 | note | ○ Range x = +5, -25mm
d5ae94d4-b107-514c-93f5-95d4382a068f | note | ○ Standard Deviation = 15mm
477ba564-0eb8-5d70-b4d7-97757cfb7f35 | note | REFERENCE DOCUMENTS: 204.03(g), Table 204.031
5fc3fa81-873f-5112-b772-64531f9eb4af | note | INSPECTION/TEST METHOD: Survey
c8476226-772c-58cd-b7ce-c40021c3d8df | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
2b6df124-ee9f-5be3-a6f0-d8ec0bfffe97 | note | SCP
eb84ae28-cdfe-5286-96dc-1d447050e645 | note | RESPONSIBILITY: Site Engineer / Surveyor
0d1e147f-37ec-552b-b99d-8ea42698edf4 | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Proof Rolling
c07c4ea6-db18-514a-ad59-a14f74a09908 | note | FREQUENCY: Each Lot
2831dc8c-e5d6-5278-88dc-48f8228cfd4b | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
4ead81b1-a0ba-5d85-bbea-c77326dbd485 | note | REFERENCE DOCUMENTS: Section 173
c003997d-3dd4-579c-ad08-19c906a600bb | note | INSPECTION/TEST METHOD: Visual Inspection
101fc022-db2b-589e-9119-c86b6da63db7 | note | RECORD OF CONFORMITY: This ITP signed off
ca276e36-e2ed-5201-aafc-c8782c4479a4 | note | HP*, WP
c7f1b5c4-2a64-58a2-b66e-e2a0820c0480 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
a1e379c9-b5c9-52b1-aeb3-2089c0bfcdba | date | Date Completed:
| signoff | Signature Required
| checkpoint | 3.2 - Compaction Testing
3f7ec775-eb73-5afb-aa89-c691c796235f | note | FREQUENCY: Each Lot
5c117415-6e29-5306-be76-cbe81cf7b091 | note | ACCEPTANCE CRITERIA: Scale B
158ee682-8e96-5b70-81ee-c9c1b9016f12 | note | ○ All Type A Material = minimum mean value of density ratio = 98%
a7e81b9d-582e-5f2a-a7bd-a38bc4a9ea6c | note | ○ Ripped and re-compacted material below Cut Floor Level = minimum mean value of density ratio = 98%
13b8c96b-025b-57b6-86d3-625fa385a90d | note | REFERENCE DOCUMENTS: Table 204.131
7f144695-0276-55c3-be0c-d4ca4382d0f8 | note | INSPECTION/TEST METHOD: Test Point
d25fe6cd-2235-5cc2-9388-ae10f092cd4c | note | RECORD OF CONFORMITY: Test Records, Lot Register
c3347baa-eea8-5c41-ae59-192c5bd0abf2 | note | TP
bb2fb5f9-fa85-50d7-b29e-7694fbd66fb6 | note | RESPONSIBILITY: Site Engineer
c6adaaf9-0b28-5d4c-be02-d4c5169acf78 | date | Date Completed:
| signoff | Signature Required
| checkpoint | Final Inspection
f31ecf13-a462-519c-b0b0-6558c3496b94 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
681ee33a-2949-57b6-919c-cff447942ffe | textbox | Print Name:
342b000c-4ee3-598c-aa67-f867cf676074 | textbox | Position:
a4d645e2-8dcd-5d9e-814e-624d282d0f68 | date | Date:
| checklist | ITP-003a - Sub-Base Construction | itp | ITP-003a - Sub-Base Construction
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
79579c20-ccbd-5da1-b538-66f6be218115 | note | FREQUENCY: Prior to commencing any activity
1622f108-c836-524e-b66b-53c079a72792 | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
1c1c4d84-b157-5315-b130-5c622ddb0d98 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0b313cb7-058c-5edf-ab13-e3c271bc833c | note | INSPECTION/TEST METHOD: Visual inspection
cc57be8c-2074-5b05-b1c0-2d38273228d5 | note | RECORD OF CONFORMITY: This ITP signed
3575249f-444e-58dd-b27f-9ffb2e995897 | note | WP
fad7155b-ff9d-5b39-86b6-e8b1c108ac1a | note | RESPONSIBILITY: Site Engineer / Site Foreman
4dd3539e-c531-5dc3-9ef3-595c6084d66d | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
13b658ca-6551-5baf-8893-f0cdbbbc526a | note | FREQUENCY: Prior to commencing any activity
d09d14cb-dfb5-5557-bbd0-5fc5c3b4acec | note | ACCEPTANCE CRITERIA: Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
5da82730-22dd-5470-a3bb-22894fa2643a | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
c59c2e69-6b8d-576d-b699-7fdfd171aa34 | note | INSPECTION/TEST METHOD: Document Review
1b8cae77-6285-581e-b638-b09a3f730edf | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
60751f30-f99b-5436-8f3c-306151f593a4 | note | HP*
06609aae-4c61-5cf2-891c-d904a4e6deb8 | note | RESPONSIBILITY: Site Engineer
b3e25d8a-9f0b-5226-a6da-423300952ae9 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
2ce44622-d803-5166-92d2-9a088c32c13f | note | FREQUENCY: Prior to commencing any activity
19c08732-88c5-5f26-92fd-170cdb9d02b0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
aa63610a-b599-56ba-bbfe-fa4ac3e8260a | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
e2beeac3-2cf5-50d3-b273-74676729bc69 | note | INSPECTION/TEST METHOD: Visual Inspection
ef756af7-f132-577b-8e29-64f8f3ea3b3c | note | RECORD OF CONFORMITY: This ITP signed
a7708332-e976-5b32-8b50-f3e1bc4bb276 | note | HP*
7fc62674-4078-5454-905d-f6daa170dbf7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
87942380-f493-51b1-981e-1f21c272e03f | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Transverse Joints
edb35fd4-e058-598f-8d34-dbfecea6f054 | note | FREQUENCY: Check prior to placing material
aaf75f3b-1a52-56b2-a445-5c121588f0fc | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints
351c5e18-584d-5bb0-9798-c16d9157cd6a | note | ○ Transverse joints shall be offset from one layer to next by not less than 2 metres
3cdcf979-d252-513a-871b-706ec71e2ac2 | note | REFERENCE DOCUMENTS: Cl.304.08 (a),Cl.304.08 (c)
876c7a82-0f7e-5f47-86f3-29f97cb19fcd | note | INSPECTION/TEST METHOD: Visual Inspection
67362aeb-5c14-5fc5-8c96-0a8240ebc108 | note | RECORD OF CONFORMITY: This ITP signed off
bd59a5f9-8196-58bb-915b-5ac892155b82 | note | IP
76c1880a-d8a5-514b-9af6-d22b9efb4648 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b9720443-2388-57ad-9443-3a7bc7c4b082 | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
8710c318-28bb-5954-9410-08079befd2c7 | note | FREQUENCY: Check prior to placing material
3c0926c9-17dc-5ab8-a6b6-0177d20562cd | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
c367e7dd-b2f7-58e8-8dd2-c883c0bc5cbb | note | ○ Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
c778b40a-9122-5520-a5f0-362177df0a8a | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
16f99eb8-c9c7-570b-bb1d-48a7a06ab6f7 | note | INSPECTION/TEST METHOD: Visual Inspection
5e0537d5-657e-52bb-91b5-b52618d7c0a9 | note | RECORD OF CONFORMITY: This ITP signed off
ae2b588a-f39f-57f2-8668-caf2a666d65e | note | IP
1937fefa-e7a2-5239-afe6-2662089ab953 | note | RESPONSIBILITY: Site Engineer / Site Foreman
851f2865-2b29-5f56-9bfe-a71096779b0e | date | Date Completed:
| checkpoint | 2.3 - Lot Size
7ca07670-b402-5123-8db2-48867f6ed0a8 | note | FREQUENCY: Check prior to placing material
d122ea7a-e1e2-5ee8-aa30-7cf627951aa2 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
e29a64ec-469f-5144-9d12-31cd99b4d765 | note | REFERENCE DOCUMENTS: . Cl.304.09 (b)(ii), Table 304.121
4c6703f8-c329-505d-970f-641c8531fa32 | note | INSPECTION/TEST METHOD: Site Inspection
5b191234-899a-5783-ac9c-62aba8a8d1b4 | note | RECORD OF CONFORMITY: Signed ITP
9181ef51-8cb4-5d3e-9c05-341c600f5e04 | note | IP
7de093e5-b9b0-5090-85ff-8928eb4a8d0e | note | RESPONSIBILITY: Site Engineer / Site Foreman
83d1db4c-c418-5ef7-8190-114cbad68fea | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness
033238fc-f7ef-540c-8758-a2c9ca7aeb2b | note | FREQUENCY: Each Lot
64fd8bd4-9a8a-5e4f-bcff-e9747273cfaa | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
540bd8fd-3a3e-563f-8bc9-881b1b1a1b68 | note | REFERENCE DOCUMENTS: Cl 304.07b
fe39f3b8-3827-51ce-9941-c96686004872 | note | INSPECTION/TEST METHOD: Site Inspection
a133f09e-d925-57fb-a0ac-b4309c35cce2 | note | RECORD OF CONFORMITY: Signed ITP
c2b5a30b-d8c2-5763-babe-cbc52da1377d | note | IP
9fdfd4c3-5c99-5a35-b961-fa3fdaf33e56 | note | RESPONSIBILITY: Site Engineer
aa997459-6548-5571-a230-ee2e7254b034 | date | Date Completed:
| checkpoint | 2.5 - Proof Rolling
cf3631e1-adfa-5d65-9385-26f6ba4a23af | note | FREQUENCY: Proof Roll each layer
87d57c04-9968-5c68-9cec-6620d67dfdbd | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
18c900b3-3f3d-55b6-8ee1-20ca371ab731 | note | ○ Static > 12T
70affe28-9c96-5b4c-a30d-a1c76e747490 | note | ○ Pneumatic > 20T
8168096a-3bad-51ec-b163-21e03dc8a81c | note | REFERENCE DOCUMENTS: 173.03
5c808518-f0be-59f6-8f80-eb84dc09e5e3 | note | INSPECTION/TEST METHOD: Visual inspection
dcadf6fb-75c3-5f78-92ca-b46025eb402c | note | RECORD OF CONFORMITY: This ITP signed off
a1b44514-1e01-5bcc-8980-3c0c99cf4748 | note | HP/ WP
e4108e20-4733-58b4-aff4-2c76025f5099 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
7acbbb19-000c-56eb-9789-b9622229509a | date | Date Completed:
| signoff | Signature Required
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
3cd19c0a-3d5b-5843-b737-99db270cc8c4 | note | FREQUENCY: Prior to Testing
233efb85-571b-5787-8ee1-5ce968971e79 | note | ACCEPTANCE CRITERIA: Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
54aa1e9c-f727-53f4-909a-bf8a6990acad | note | REFERENCE DOCUMENTS: Cl.304.09, Cl.304.12, Table 304.121
97cfdca4-3547-5149-9063-e9b8463ce792 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
2d8a9ecf-6ba5-56e1-9992-6c48f322e027 | note | RECORD OF CONFORMITY: Signed ITP
87cd144d-a23e-5801-a3db-a36225c37f95 | note | AP
213d531d-ef07-563e-a2ce-3933774431ec | note | RESPONSIBILITY: Project Engineer
6e95e309-7b8d-59b8-a97d-0056d530c67f | date | Date Completed:
| signoff | Signature Required
| checkpoint | 3.2 - Compaction Testing
3de941e5-5d0a-5276-9e01-00dee32ffe9c | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
c68c39ba-18bc-5c76-a7df-d4aab0e680a4 | note | ACCEPTANCE CRITERIA: Modified Maximum Density Ratio of not less than 97% & 98% for Class 3 FCR & Class 1 FCR respectively for road pavement as per Contract Drawings 2021-01 sheet 1
a6d1a914-4924-5a0b-aa50-e999b68b4bb0 | note | REFERENCE DOCUMENTS: Contract Drawings (2021-01)
3f1ff5d0-f129-5c1f-9891-51fbe1181022 | note | INSPECTION/TEST METHOD: Test point
c6434ac8-d511-54a0-a257-f7836c47df34 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
43558c15-ea8c-58f2-8ae3-a32bb3dd9391 | note | TP
3fac5bc9-502a-5682-9e0e-f533d9cb6588 | note | RESPONSIBILITY: Site Engineer
b26e2e3f-cfc9-5512-9e7a-8cc9a0b2a6a5 | date | Date Completed:
| signoff | Signature Required
| checkpoint | Final Inspection
084a7e18-1724-5322-a8c0-54a4eb23891d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5f4a391a-7ff2-5084-a4e9-6292ac7de3d4 | textbox | Print Name:
24b8b443-49a1-596a-b8a4-1e44017617b1 | textbox | Position:
ffd7edf0-52e4-5eba-aaba-089cca114505 | date | Date:
| checklist | ITP-006 - Hot Mix Asphalt | itp | ITP-006 - Hot Mix Asphalt
| section | 1 - Construction Works
| checkpoint | 1.1 - Submission of Mix Design (Type Asphalt, mm Nominal Size)
6ce4e51b-a8cd-5a41-9144-ca0b8e611bee | note | FREQUENCY: Prior to commencing paving
40764cc3-d339-5190-816c-7a686711ada6 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix.
2e4e4e87-002a-5a75-ab2a-2b9077b95f53 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
3687622f-2778-50aa-89b8-e017a04fba87 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
50656df2-ee95-54b8-9a4b-063bf20b2836 | note | RECORD OF CONFORMITY: VR approval, Completed ITP
2e330431-d29a-554f-8430-2b23200fd2a3 | note | HP
7d4c2872-7c91-5f56-a29d-459334350232 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
32e50f61-c1e3-5f30-ab8e-2009b79b4c5e | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Implementation of all measures and controls
e0fa9f39-67c2-5ac4-a0aa-d2b97b8392c1 | note | FREQUENCY: Prior to commencing any activity
1e47a351-f29d-55f3-8e61-d7fe4bbfbf18 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
4c53398b-a6c5-56bf-9693-d030a18d5d93 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
9a8a0bc8-8f1d-57e7-94e1-06119566df1f | note | INSPECTION/TEST METHOD: Visual Inspection
9fcfabe7-6ebc-5e84-bafb-c4959aa72152 | note | RECORD OF CONFORMITY: This ITP signed off
7463f4a5-c41f-55c4-8896-14ee899534a6 | note | HP*
62eeee3e-028f-59c3-a5e0-ae4b413f495d | note | RESPONSIBILITY: Site Engineer / Site Foreman
93e25d69-e227-54cd-932f-18ce17ec40a9 | date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
919bb6c8-6609-571d-9209-005921505fac | note | FREQUENCY: Prior to commencing paving
16530470-96ca-5e11-8af6-94281336b4e3 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
d18e55f3-881d-50d3-bf4b-0bd1b1cdf465 | note | ○ Material and compaction test certificates conform for pavement
a88635a2-a22e-556e-b0ef-4bccf902153a | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
abd5c8e5-ddb9-55a7-9ee7-1701ff774725 | note | INSPECTION/TEST METHOD: Visual Inspection
4e075ea1-fe1a-5b99-bbdc-3bc2e410aef8 | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Base Course Checklist
8acac225-c896-5f70-84b0-633fc789ceb8 | note | HP
c86b25a6-6136-5f99-9f76-6b2b34576281 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
c440e075-acdc-5321-b268-fe5de3b5f9ac | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.4 - Dryback
9bdd28fa-4ae1-5d72-80b7-6410d6225a5a | note | FREQUENCY: Prior to commencing paving
93c5d512-2ca2-58e7-99ca-b3ce2c9b99a5 | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
52d7c8fa-e11e-534a-9bb3-8dede5ecbc83 | note | – 6 randomly selected test sites per lot required
548a3947-d987-5fd6-b683-d809555cbc0e | note | – If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
aae273dc-ab94-5551-a3f5-0095343ba112 | note | – If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
63454963-1708-5629-937f-195c5db43f04 | note | – Testing schedule in accordance with 310.03 (c)
52cb9ce4-143f-532a-8d1e-08e03e9828ca | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b), Table 310.031, 310.03(c), Table 310.032
23b7637c-e93b-5877-8e32-29f377c6e30e | note | INSPECTION/TEST METHOD: Verify
443c6cd5-178d-5586-8755-cb9081f9f13a | note | RECORD OF CONFORMITY: ITP Signed off
fdcb8a3a-ee42-5e9e-85ba-279ca7d61a66 | note | TP
cfa948e4-165c-57ab-9e08-075ec71f5ede | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
70d26832-afdc-5472-aca3-a54067ba2f02 | date | Date Completed:
| checkpoint | 1.5 - Ambient Conditions for Placing
febd41e4-c0c0-50d5-ba79-0a910d6ce477 | note | FREQUENCY: Prior to commencing paving
7032fc75-d43b-5663-993a-4ec4c8b090aa | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
05014729-6b00-590c-ae8b-99a1216883ef | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
3cc25af7-5445-55ff-a0d2-c0b9f4415712 | note | REFERENCE DOCUMENTS: 407.17(a)
11c02d57-3e96-520e-ad7e-18b759b4333f | note | INSPECTION/TEST METHOD: Verify
cad02170-fa02-58e5-be01-d9662d02cdb0 | note | RECORD OF CONFORMITY: Thermometer
b8aa4f87-4632-5f6c-922a-9d16ac88caf0 | note | IP
dbd7f695-c3ba-5e3c-9210-b9f4de488827 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cc136c20-0a6b-5498-be1f-75ef12c7a74a | date | Date Completed:
| checkpoint | 1.6 - Planning of Joints
fac24fcc-7ce3-5e1c-8933-ebbe7456b88c | note | FREQUENCY: Prior to commencing paving
7fff2ec9-8c7f-54c7-a70d-0a9a4a663933 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
39c1db48-a0f5-589b-beaf-ab628c3fd98d | note | ○ Transverse Joints Offset from layer to layer by at least 2m
a80157bb-3bac-5d87-bb1f-31689dab9556 | note | ○ Longitudinal Joints Offset from layer to layer by at least
e051141c-5b17-5837-bb5c-1be87c379520 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
41679541-11c1-55aa-a4bc-1cc7568589cd | note | REFERENCE DOCUMENTS: 407.21, IFC Drawings
52d3c244-2b06-5d18-b510-3f6d72ad67e4 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
7839e128-6484-5bc5-8576-e903e79509fc | note | RECORD OF CONFORMITY: Paving Plan
e76e7671-d015-598f-a38f-418f7c75564c | note | WP
ae64ac03-d5d4-5ad3-8e1d-9d43fdd74876 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
3cec5582-0109-5ccc-98f8-3cfc942bc5c9 | date | Date Completed:
| checkpoint | 1.7 - Longitudinal Joints with existing Pavement
d75be177-1ae1-5ba0-9e39-630a620a6050 | note | FREQUENCY: Prior to commencing paving
0fa02a83-3361-5699-9430-842527499a10 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
e334f8e4-6dbe-5a49-87b0-dd54e9151cb6 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
65f4209a-f98b-50a8-85ca-d1fd8ef1b7ef | note | REFERENCE DOCUMENTS: 407.21 (c)
ad8906fc-e135-5cc1-a3c1-04551a31cf17 | note | INSPECTION/TEST METHOD: Visual Inspection
85ee6460-fcb7-51aa-a917-ce58524d5b8c | note | RECORD OF CONFORMITY: ITP Signed
712edc5f-d847-535c-afa6-3cffc1a11202 | note | WP
2f6342e2-19bf-5ed1-ab32-ccbfe52084dd | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
c8f73af6-c869-576f-ae9c-e916408df538 | date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Frequency of Inspection and Testing at the Mixing Plant
8bca849b-9525-5c7d-ab1b-d82300c0d777 | note | FREQUENCY: As per Table 407.151
908bd923-d5f1-5270-afc5-c3d1ccced0ef | note | ACCEPTANCE CRITERIA: The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product.
6cb28e84-ca72-522a-8f50-5ef5b656b7c6 | note | REFERENCE DOCUMENTS: 407.151
33c29c90-820a-5377-a447-0f09003610c4 | note | INSPECTION/TEST METHOD: Test Inspection
9bb545e1-9bdb-5da0-9682-8aa368b0b151 | note | RECORD OF CONFORMITY: ITP Signed
509b27fa-7836-53dc-b4a0-48805016820e | note | TP
00930d72-441a-5869-ab67-ff7bb6773703 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
2957d5ab-b848-5bc4-8458-4e1013bcd9e5 | date | Date Completed:
| checkpoint | 2.2 - Tack Coat
a461ffe4-9c7d-5ba2-ae4a-191f676a8833 | note | FREQUENCY: Prior to commencing paving
42bcf77a-bebc-5b5d-913a-5dace1ea021e | note | ACCEPTANCE CRITERIA: As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm.
d3e5b880-bc4a-52e8-9c8d-39cbd94fb2e8 | note | ○ Tack coat to be sprayed on existing asphalt joints.
d44680ef-61ff-57c7-9a36-c26f5bde48d2 | note | ○ Tack coat must be allowed to turn from brown to black before paving.
dfec907c-76a9-511d-bea5-fd1bc5f13f4e | note | ○ If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
afd25df2-f245-514e-a77d-032f317edc45 | note | REFERENCE DOCUMENTS: 407.19, AS2150 11
68cf3ff5-d555-57c2-8873-eee10d3cc7c5 | note | INSPECTION/TEST METHOD: Visual Inspection
c0f2a74d-3d64-5d56-930e-726410bd940b | note | RECORD OF CONFORMITY: Spray area
cca8710c-eaa6-56b1-b5e6-f6f090f4512c | note | WP
bda1cc07-e68b-5bbf-bd83-ef87f1c47c59 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
26c3ba3d-ec4c-569e-82a2-710394e55076 | date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
1b7b5e32-f581-5da0-b70a-62984b40f8ea | note | FREQUENCY: Prior to commencing Paving
532001dc-1ec0-5463-9336-413e7ca1c4f7 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
b4a816e6-9d29-57a0-a661-288e3bff5ce4 | note | REFERENCE DOCUMENTS: 407.23
8ed39a01-69af-59db-9406-6a5eed0fa6ef | note | INSPECTION/TEST METHOD: Visual Inspection
ba566552-a923-5377-8357-f1020e30c6d8 | note | RECORD OF CONFORMITY: ITP Signed
17c34482-3afd-582d-bf18-0e4db1f102ad | note | HP
dfaa65d1-a98d-5801-8f0f-2304ba20ced3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
70c893d4-c0cb-5cf2-9c43-6d649ab60025 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Mix Design Confirmation
bf920119-50bf-53d5-ab75-2458e28039a1 | note | FREQUENCY: Each lot
e3c94680-62b0-56e0-a952-5f7431ac7ea4 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
fbe665a6-e6b1-54c7-b65c-e8b5664cf4ed | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
90ff38c9-4e57-5e48-9bb5-c2c830feab57 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
2e7d5a54-6d90-514b-845b-55ec7e89b1a4 | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
e4d372ba-0f20-5b4e-b547-ab7a15b18436 | note | HP*
b5e61478-d7d4-59ea-8515-193b55a739f0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d40c2f78-85b2-5b96-9ef0-3fda0b935e7b | date | Date Completed:
| checkpoint | 2.5 - Delivery of Mix
f48026cb-e855-5cf2-95b8-dfcdba90211c | note | FREQUENCY: Each load
2f7f4e16-8b1c-562e-9c50-e7cbb4995482 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
1079646e-d02b-5ee2-910c-04b5ff3b5a0f | note | REFERENCE DOCUMENTS: 407.11
21d4ac7b-2bb3-55cc-bb27-c154d5ed7d8b | note | INSPECTION/TEST METHOD: Visual Inspection
4dda9bf5-a0fb-5ad6-ac9f-90fe42c12509 | note | RECORD OF CONFORMITY: Delivery Docket
b4eda044-b447-560e-98b5-7e9d27a4860f | note | WP
ee596d85-1d9e-5f6e-9d7b-3a889802b944 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
dfec7b6f-45f7-5737-8205-1b098b3238a4 | date | Date Completed:
| checkpoint | 2.6 - Traceability
3b1be0a2-bea6-545c-9e11-4367db121c6f | note | FREQUENCY: Each lot
a4eae31b-b0e7-547b-8f87-9f52428e98f8 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
55b8f273-d8d0-5fc9-aa86-7a22636a8f85 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
5418ad85-471e-5adf-b1fe-e7726ac74699 | note | INSPECTION/TEST METHOD: Verify
dd9c9189-13b4-5309-a1ea-0fd0fabf2f52 | note | RECORD OF CONFORMITY: Daily Lot Record
8f9b7a43-4790-59b8-8b9d-e71ad752e3e8 | note | IP
4c8ac826-24a6-5d46-bf02-baa262d5148d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
136a30f7-711b-5c13-ae86-45ceb86fc7f3 | date | Date Completed:
| checkpoint | 2.7 - Layer Thickness and Level Control
bdf119d0-a340-5414-b5f1-74525548a060 | note | FREQUENCY: Regularly during paving
7cfc69c3-8b21-5539-abdc-316438363d94 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
89a438c3-d378-5abe-8229-e1797178f388 | note | REFERENCE DOCUMENTS: IFC Drawings
a4f481d6-6ddf-58af-8534-f7bdcfed89b2 | note | INSPECTION/TEST METHOD: Verify
c1549aec-0620-5f86-9ac9-afe4833fc6b6 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
387a0382-422f-55fc-be4a-bb0e1e9f1b35 | note | WP
0f5f047a-945c-56d8-9226-5e45eff1a643 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
bbdc9994-9fee-52ca-bc04-f599a34ab643 | date | Date Completed:
| checkpoint | 2.8 - Paver Stoppages
30d5823b-4a1e-5deb-8b32-7cb1b02d21c4 | note | FREQUENCY: If paver stops
7e49275e-c904-5948-8ba1-6481b1ffdf2c | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
705b2f89-559f-535d-b05e-282164050ae0 | note | REFERENCE DOCUMENTS: 407.25 (c)
676d60b4-f0dc-59f9-86da-601b6bca109c | note | INSPECTION/TEST METHOD: Verify
138f9421-efa6-5d5d-9f78-d08257cfc1e1 | note | RECORD OF CONFORMITY: Thermometer
85cffb59-586c-530c-b3a6-3d3b999070d4 | note | WP
aae4a2bd-0d57-5c63-8aaa-3a56a03069b8 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cadeb400-160f-523b-87ae-fc95dff9d2fb | date | Date Completed:
| checkpoint | 2.9 - Surface Finish of Wearing Course
2d30135d-7110-5518-a860-d277e082e39a | note | FREQUENCY: During paving and after final roll
3bf75d95-9887-55a7-a402-1dd8542c33eb | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
9b231f2e-ff47-5e95-b714-a295ea86d2fe | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
75aafbfc-fb33-577d-93ff-e8f98c541bfb | note | INSPECTION/TEST METHOD: Visual Inspection
96ce8ac2-8dab-563f-b063-e79b44e8c959 | note | RECORD OF CONFORMITY: ITP Signed
8000f7d3-ef98-5001-adbd-50b0c4b4d9da | note | WP
04a26896-34aa-5395-b2d3-d667fd353b7d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6c7244ca-b6d0-539e-900d-25f2821f6862 | date | Date Completed:
| checkpoint | 2.10 - Kerb and Channel
144d9f9d-2ab3-5c39-a4de-170a8e8acb36 | note | FREQUENCY: During paving and after final roll
ccb3a5f7-b97e-569b-89c6-a94a1a9869a7 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
e263ac10-5bc7-5b64-a825-1f7a00a93e30 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
f3fb844b-59f5-56a7-b076-978e92dbe7cb | note | INSPECTION/TEST METHOD: Visual Inspection
8b60104b-6a7a-5006-8d3f-146b239828d7 | note | RECORD OF CONFORMITY: ITP Signed
f93fe6bf-2407-5527-a225-d2174ec05216 | note | WP
bbf55836-1441-5e59-9424-15294e3b460a | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
306a4026-e3ff-506c-b20f-772fd96428f3 | date | Date Completed:
| checkpoint | 2.11 - Alignment of layers not placed against concrete edge
783191a3-26d6-5607-9503-32f1717bc7df | note | FREQUENCY: During paving and at completion of work
88dccd3e-355a-5f45-910b-a9baa4bc61b8 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
3ebe02db-f575-595c-a2de-d1f8ec3fa725 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
dfe8f615-17d4-5fd1-a74d-ce73d265a416 | note | REFERENCE DOCUMENTS: 407.29 (a)(iv), Drawings
0e3461a0-ef95-558b-884d-2ee6aabe62b4 | note | INSPECTION/TEST METHOD: Visual Inspection
84dc2fb2-7651-57e2-9d69-09571cbb210f | note | RECORD OF CONFORMITY: ITP Signed
56dd8998-d4b2-5e1b-a260-01af0523e53f | note | IP
3c117f5b-1ca9-5ffa-a3d1-6833259d7428 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
0a60d75c-a8e0-5b09-b28f-e533b797c6ed | date | Date Completed:
| checkpoint | 2.12 - Width of layers not placed against concrete edge
01562806-c6ce-532e-bcb4-bad264057784 | note | FREQUENCY: During paving and at completion of work
9aad9638-e32c-53e2-a3af-4f10d634afde | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
e9fff0a4-17c4-5ba3-a3b2-6d39baa7a333 | note | ○ The average width over any 300m shall not be less than the design or specified width
c51fc2ab-9ce5-5115-a917-ba26716699d0 | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
52eac291-bbe6-522d-a693-4bfe091cffa9 | note | INSPECTION/TEST METHOD: Visual Inspection
cd98e19c-99a0-553d-bfb1-9443f6903b8c | note | RECORD OF CONFORMITY: ITP Signed
b09e4867-780c-577f-91e1-b9655bb29c6a | note | IP
76f4ab50-ff35-5048-9304-753ba51c0e16 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d83cf146-7d7f-542b-80c0-07a069de0a4e | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
3f922d4a-3b1a-5d0c-9830-465a327fe1ff | note | FREQUENCY: Per Lot
76597802-bd74-53d5-a943-99e2a706b986 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
482f2dcf-0eb3-5584-b395-ef9a43a0090c | note | ○ 94.0% or greater Accept lot
0cca0e22-7cf2-51cb-9bde-7f44a0570f77 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
2374624a-dc25-5885-ad52-6fa03a5dac90 | note | REFERENCE DOCUMENTS: Table 407.271
0506cc60-1835-546e-a615-e36b25e17d21 | note | INSPECTION/TEST METHOD: Verify
781f543f-0c6b-5fcf-98b2-d8d508869a8c | note | RECORD OF CONFORMITY: Test Report
f84381b5-5729-52ff-97a4-313320388627 | note | TP
8fbf7144-a9e9-5d64-9344-aa3da9735e23 | note | RESPONSIBILITY: Site Engineer/ Lab Technician
42f9a568-9fec-52aa-9677-ab54867a06fd | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
17315e0d-cb61-570a-a544-0fc3f95ce397 | note | FREQUENCY: Per 4,000m2 at completion of work
bbfc8501-7c92-5cd5-9be7-4b94d1ed548c | note | ACCEPTANCE CRITERIA: Scale B: Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm
be71fd93-297f-5759-8427-6b0337c4b39b | note | ○ Minimum number of measurements per lot is 40
474e21a4-5809-510e-99bd-a06690d8ef22 | note | (ii) Kerb and Channel: Refer to Item 2.10 of this ITP
95666054-3746-5c09-956a-7b546e4695b8 | note | REFERENCE DOCUMENTS: Table 407.293, Table 407.292
4cfdceeb-4833-5c21-b4f0-92db2f886311 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
c050ba4f-7eb2-5ab3-8b8e-22bbd64d024f | note | RECORD OF CONFORMITY: Survey Conformance
4837170b-f260-554a-96a0-aae70ebfa32f | note | SCP
3db04ad9-1980-532c-b133-b0339c908d8f | note | RESPONSIBILITY: Site Engineer/ Surveyor
244cbb06-0da3-521f-af93-18a7ff49ab94 | date | Date Completed:
| checkpoint | Final Inspection
2e7def89-d6cb-553b-841b-29bc47eed33d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5b414435-7be5-52a4-8e09-72c22b02b971 | textbox | Print Name:
ba9990b0-c79a-5c06-80db-f566f80b883e | textbox | Position:
7d1529ee-cf33-5649-87f0-6c6d69d8a0cc | date | Date:
| checklist | ITP-007 - Pavement Markings | itp | ITP-007 - Pavement Markings
| section | 1 - General
| checkpoint | 1.1 - Check for correct documentation
b1c90a3c-8615-53ae-b342-dd27b63a6482 | note | FREQUENCY: Prior to commencing any activity
54d09430-165e-5871-a6eb-af38c1cd55aa | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
51b35e39-bab9-54a1-ac17-090802973551 | note | – using the correct and complete set of drawings
df27fbde-146b-513b-966d-0d4091a81b6d | note | – all drawings are the latest revision
43d933df-1851-51f7-992f-34989eeac27b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
51b67353-834a-56a1-a37a-f378bd03ea6a | note | INSPECTION/TEST METHOD: Visual inspection
ada007dd-fb3f-5f20-a479-9dd10fc74ade | note | RECORD OF CONFORMITY: This ITP signed
d4da6b3e-18dc-5d3a-8208-e115732b7bbc | note | HP*
a2a79de2-53d2-577d-827f-4a7ea63504b8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6e6184f8-0336-5543-9f14-b6234ac1f252 | date | Date Completed:
| checkpoint | 1.2 - Line marking conformance
476554aa-0a0a-5626-a57e-5a770df93783 | note | FREQUENCY: Prior to commencing any activity
72093897-bc6b-5af1-ac39-2693669b9f1b | note | ACCEPTANCE CRITERIA: Materials to be used must conform with the specification
9456c0a5-ba74-5b05-a519-8865e4646cbb | note | REFERENCE DOCUMENTS: Cl 721.A05, IFC Drawing
9f10851c-c4e3-5bcf-8c74-9ac3796ba828 | note | INSPECTION/TEST METHOD: Record Review
017a663d-4d2c-5c3e-b943-4c9480d31237 | note | RECORD OF CONFORMITY: This ITP signed
8e749043-ac23-5daa-95ba-a370f27eb1f1 | note | IP
8e739a71-7f2d-5da4-a6d5-46c03e70b3f1 | note | RESPONSIBILITY: Contractor Representative
dc1b0f72-e670-5dc9-880e-edbb5c3f890d | date | Date Completed:
| checkpoint | 1.3 - Site Preparation
9b8ebdad-3337-56e3-98a3-7837b4197550 | note | FREQUENCY: Prior to commencing any activity
7df87fd4-19af-5c92-8dd5-6341ba067ec4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings
19d10716-f935-594c-969c-992c4a36472f | note | REFERENCE DOCUMENTS: Cl 721.A06
3d9c7f40-b4f4-5242-b5eb-299d443b3395 | note | INSPECTION/TEST METHOD: Visual inspection
22e34c76-4e3b-50f5-bca5-36703669a21d | note | RECORD OF CONFORMITY: This ITP signed
be8e2b7a-c4c3-56d5-b935-b856f0522b33 | note | IP
ba318583-dcce-58ae-9a15-88c6339d3d8e | note | RESPONSIBILITY: Contractor Representative
c0a3227c-3fd2-52e4-8402-eefb2a8e8534 | date | Date Completed:
| checkpoint | 1.4 - Set-out of Pavement Markings
f6a6625b-a88d-5c0e-ab6c-736aade1f95b | note | FREQUENCY: Prior to commencing any activity
9540f926-dda0-54c0-aaf3-66f7c87e4ccc | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
bd47a7af-ec3e-5ec1-9812-312d3b132e0d | note | REFERENCE DOCUMENTS: Cl 721.A09
86d3e59d-765b-5afc-96fa-8792b3970c3c | note | INSPECTION/TEST METHOD: Visual inspection
6bff27f9-5538-5c47-a0fd-07a29256d1eb | note | RECORD OF CONFORMITY: This ITP signed
d59fa593-53bb-53f7-ad78-3e293676bb4c | note | IP
489b1383-478a-52d0-9933-dc4124058a6a | note | RESPONSIBILITY: Contractor Representative
894fa34a-5fdc-51fd-8e17-2c4e8d16ea98 | date | Date Completed:
| section | 2 - Pavement Markings
| checkpoint | 2.1 - Acceptance of Work
428fad50-95b7-5da3-9457-d3eaac5de2cc | note | FREQUENCY: Each Lot as required
f0ffeab1-021c-5c0d-a9ac-77dae65d54de | note | ACCEPTANCE CRITERIA: Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
63b48046-f39a-5661-be2c-f3b251a7cf66 | note | REFERENCE DOCUMENTS: 721.A12
a592d931-a566-5526-802e-4e163d02ecbe | note | INSPECTION/TEST METHOD: Visual Inspection
f993bf1e-9bfc-579c-ac9b-1bb690598125 | note | RECORD OF CONFORMITY: This ITP signed
2f0190f5-171a-5182-b534-0ec8672c2c72 | note | HP
0b6df03b-7236-5e7e-9a1c-c3140aa7d5f1 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
260fea90-d4b8-5132-80fe-30c549a6ca00 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Position of Markings
98770c54-edae-5264-af3a-17aa275e7a6d | note | FREQUENCY: Each Lot as required
e5685427-40d3-55e6-98c2-2b74cad28ce3 | note | ACCEPTANCE CRITERIA: All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03.
b8ca80b8-2083-5456-80f1-4ae0bef110b8 | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
cde26158-a863-5f60-a07e-1e0ee761d08b | note | REFERENCE DOCUMENTS: 721.B05
6c6afa1b-c0f7-59d6-8077-099697293ff1 | note | INSPECTION/TEST METHOD: Visual Inspection
eb83005f-f9c2-59a5-b356-46830e635099 | note | RECORD OF CONFORMITY: This ITP Signed
ce8b6253-999b-5ef5-84c4-7604833d4bea | note | HP
d8241648-573d-52f7-a3a8-96abc770f744 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
6924cfdb-1c23-5872-b230-b6c191968e29 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Installation of Linemarking
caeb90cc-84a9-5cca-9422-b05d7223df9c | note | FREQUENCY: During Construction
512f7885-de3d-55a3-b099-895f8cb09aef | note | ACCEPTANCE CRITERIA: Line marking installed as per the IFC drawings
1a97de2d-c97d-5f70-883b-4ea9d60f1861 | note | REFERENCE DOCUMENTS: IFC Drawings
640c2f05-c346-5f1e-8f31-47c6dcd64aea | note | INSPECTION/TEST METHOD: Visual inspection
ad4be330-6e0f-5cb7-bcb0-4111c6fb332e | note | RECORD OF CONFORMITY: This ITP Signed
cab4b6ea-bd27-54d9-af2f-9059f6310a90 | note | IP*
17003103-39a7-54d0-8b8b-a2b002bc5ed0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0a2a1565-bc37-531f-b8ae-578c9b99d151 | date | Date Completed:
| section | 3 - Sign Installation
| checkpoint | 3.1 - Completion Inspection
c2ae7362-933c-5aee-b2ae-6cfa9c30febf | note | FREQUENCY: Each Lot as required
adc3d06e-3d39-5777-9868-3b5eaaddc0b0 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects.
1f0bb2c4-e30f-5d2a-a4d2-3418289d1c61 | note | ○ Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles.
aa028765-6ea6-57c8-b190-3a780324d79b | note | REFERENCE DOCUMENTS:
06445729-ed3b-57d1-917f-a613fce4248a | note | INSPECTION/TEST METHOD: Visual inspection
9b8b45ba-2754-5054-b7ec-532cad0d4a73 | note | RECORD OF CONFORMITY: This ITP Signed
9cc909c1-c37c-5273-98d8-79a87c1be1ad | note | WP
8dbfeccf-4c38-586c-847f-058c7eb244e3 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
c05978f7-009c-52cd-8dc4-3ac370cee26a | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
87023afb-a755-56e8-989e-24e5fb1d7db1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3bdb8cbd-7454-5c30-8437-d82b715ad32f | textbox | Print Name:
12537109-b376-5d0c-8b50-a99ee91acc09 | textbox | Position:
a29495b2-1dd7-53fd-9bc3-dcf33dc74558 | date | Date: