## ITP Tree
87 SHELLY BEACH RD - ITP
| 1. CIVIL |  |  | 2. STRUCTURAL | 2.1 BASEMENT | PALISADE WALL | 3. FACADE | MEMBRANE AND INSULATION | GROUND FLOOR |  | 4. FITOUT | BASEMENT | APPARTMENT 1 GARAGE | FIRST FIX SERVICES AND LININGS
|  | 1.1 BUILDING FOOTPRINT | DRAINAGE/ SERVICES
[6 empty] | PILES |  |  | ROOF |  |  |  |  | SECOND FIX & FITOUT
BUILDING SUBGRADES
[6 empty] | FOUNDATIONS (CAPPING BEAMS & GROUND BEAMS) | [6 empty] | APPARTMENT 2 GARAGE | FIRST FIX SERVICES AND LININGS
[8 empty] | CLADDING | CURTAIN WALL | NORTH ELEVATION
|  | 1.2 EXTERNAL WORKS | DRAINAGE/ SERVICES
[6 empty] | INSITU COLUMNS, BEAMS & WALLS | [7 empty] | SECOND FIX & FITOUT
EAST ELEVATION
DRIVEWAY & PAVEMENT
[6 empty] | SLAB ON GRADE | [6 empty] | APPARTMENT 3 GARAGE | FIRST FIX SERVICES AND LININGS
SOUTH ELEVATION
[6 empty] | PRECAST WALLS | [7 empty] | SECOND FIX & FITOUT
WEST ELEVATION
[6 empty] | SHOTCRETE WALLS | [6 empty] | APPARTMENT 4 GARAGE | FIRST FIX SERVICES AND LININGS
[9 empty] | SUNSHADES | NORTH ELEVATION
[6 empty] | BLOCKWALLS | [7 empty] | SECOND FIX & FITOUT
EAST ELEVATION
[6 empty] | TANKING | [6 empty] | APPARTMENT 5 GARAGE | FIRST FIX SERVICES AND LININGS
SOUTH ELEVATION
SECOND FIX & FITOUT
[5 empty] | 2.2 GROUND FLOOR | FOUNDATIONS (CAPPING BEAMS & GROUND BEAMS)
WEST ELEVATION
[13 empty] | APPARTMENT 6 GARAGE | FIRST FIX SERVICES AND LININGS
PRECAST ELEMENTS
[9 empty] | GRC | NORTH ELEVATION |  |  |  | SECOND FIX & FITOUT
INSITU COLUMNS & WALLS
[10 empty] | EAST ELEVATION |  |  | APPARTMENT 7 GARAGE | FIRST FIX SERVICES AND LININGS
STEEL BEAMS AND COLUMNS
[10 empty] | SOUTH ELEVATION |  |  |  | SECOND FIX & FITOUT
SUSPENDED SLABS
[10 empty] | WEST ELEVATION |  |  | APPARTMENT 8 GARAGE | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.3 LEVEL 1 | PRECAST ELEMENTS
SECOND FIX & FITOUT
[9 empty] | RENDER | NORTH ELEVATION
PT SLABS
[13 empty] | LOBBY/ COMMONAL AREAS | FIRST FIX SERVICES AND LININGS
EAST ELEVATION
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
SOUTH ELEVATION
STEEL BEAMS AND COLUMNS
[10 empty] | WEST ELEVATION |  | APARTMENT 1 | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.4 LEVEL 2 | PRECAST ELEMENTS
SECOND FIX & FITOUT
PT SLABS
[12 empty] | APARTMENT 2 | FIRST FIX SERVICES AND LININGS
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
STEEL BEAMS AND COLUMNS
[12 empty] | APARTMENT 3 | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.5 LEVEL 3 | PRECAST ELEMENTS
SECOND FIX & FITOUT
PT SLABS
[12 empty] | APARTMENT 4 | FIRST FIX SERVICES AND LININGS
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
STEEL BEAMS AND COLUMNS
[12 empty] | APARTMENT 5 | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.6 ROOF | PRECAST ELEMENTS
SECOND FIX & FITOUT
BLOCKWALLS
[12 empty] | APARTMENT 6 | FIRST FIX SERVICES AND LININGS
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
PT SLABS
[12 empty] | APARTMENT 7 | FIRST FIX SERVICES AND LININGS
SECOND FIX & FITOUT
[12 empty] | APARTMENT 8 | FIRST FIX SERVICES AND LININGS
SECOND FIX & FITOUT
DEVELOP ITP
ITP READY FOR REVIEW
ITP UPLOADED

## 1.1 Drainage-Services
CIVIL - Drainage
Notes:
Pre-start
Locates done on site – confirm no clash with pre-existing underground services |  | comments/photos/pass fail/file uplopad
Appropriate permits in place (dig, confined space docs., etc.) |  | comments/photos/pass fail/file uplopad
GL and datum provided |  | comments/photos/pass fail/file uplopad
Upload drawings / check services depths, confirm location, filling/digging |  | comments/photos/pass fail/file uplopad
Clear work area
Trenching
Delineation of area |  | comments/photos/pass fail/file uplopad
Benching appropriate for ground conditions |  | comments/photos/pass fail/file uplopad
Safety of trenching conditions and edge protection |  | comments/photos/pass fail/file uplopad
Removal/cutting of obstruction (abandoned services, piles) |  | comments/photos/pass fail/file uplopad
Civil Eng inspection report received and close-out |  | comments/photos/pass fail/file uplopad
Installation
Confirm correct bedding material being used and spot check RL’s |  | comments/photos/pass fail/file uplopad
Pre cast manhole installation |  | comments/photos/pass fail/file uplopad
Pipes installed and correct junctions/connections |  | comments/photos/pass fail/file uplopad
Civil Eng inspection report received and close-out |  | comments/photos/pass fail/file uplopad
Backfilling
Council inspection carried out? |  | comments/photos/pass fail/file uplopad
Appropriate backfill material |  | comments/photos/pass fail/file uplopad
Backfill and compact as per Civil specs |  | comments/photos/pass fail/file uplopad
Post Backfilling
Ensure all areas level and clean with no open trenches or spoil |  | comments/photos/pass fail/file uplopad
Internal manhole works |  | comments/photos/pass fail/file uplopad
i. Splitters and benching completed | (add tick box for i,ii,iii) | comments/photos/pass fail/file uplopad
ii. Civil Eng inspection |  | comments/photos/pass fail/file uplopad
iii. Council inspection report received and close-out – as-built plan required |  | comments/photos/pass fail/file uplopad
Drainage QA received and as built |  | comments/photos/pass fail/file uplopad

## 1.1 Building Subgrades
Buildings Subgrade
Notes:
Subgrade base
Geotech Eng inspection report received- and close-out |  | comments/photos/pass fail/file uplopad
Geotech Eng Inspection of sub-base and proof rolling prior to filling |  | comments/photos/pass fail/file uplopad
Building Subgrade build-up
GL and datum provided |  | comments/photos/pass fail/file uplopad
Placement of hardfill layer compacted as per design |  | comments/photos/pass fail/file uplopad
Drainage piping installed under foundation level |  | comments/photos/pass fail/file uplopad
Platforms spot checks heights and location |  | comments/photos/pass fail/file uplopad
Subgrade Sign-off
Subgrade QA and test results received |  | comments/photos/pass fail/file uplopad
Geotech Eng Inspection of subgrade and proof rolling report received and close-out | (add tick box for i,ii,iii) | comments/photos/pass fail/file uplopad

## 1.2 Drainage-Services
CIVIL - Drainage
Same checklist as 1.1 Drainage services

## 1.2 Driveway & Pavement
Please pull up from Alberton project

## 2.1 Palisade Wall
Already on Conqa

## 2.1 Piles
Already on CONQA
Please just add a checklist for the crane piles

## 2.1 Foundation Beams (Cap & GD)
ITP Structure – Foundation Beams
Notes
1. Pre-start
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Waterproof sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks | (add tickbox for I,ii,iii,iv)
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked | (add tickbox for i,ii,iii)
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Any CAN, Engr requirements (Reo Pull-out test)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks | (add tickbox for i,ii,iii)
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets

## 2.1 Insitu Beams & Cols & Walls
1. Pre-start
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Waterproof sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Any CAN, Engr requirements (Reo Pull-out test)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets

## 2.1 Slab on Grade
ITP – Structure – Slab on Grade
Note
Pre-start
footing sign-off/QA received
Services sign-off
i. Electrical | tickbox for i.ii.iii.iv
ii. Fire
iii. Hydraulic
iv. Comms and Fibre
Subgrade sign-off/QA received
i. Backfill and blinding
GL and datum provided | tickbox for i.
Clean work area
Pre-Pour
Waterproofing sign-off/QA
i. DPM including tapes and laps | tickbox for i,ii
ii. Waterstop where applicable
Formwork signoff/QA
i. Step down/ falls | tickbox for I,ii,iii
ii. Ties, propping, seal formworks
iii. Seismic gap/expansion joints
Reo sign off/QA
GN inspection
i. Details checked | tickbox for i.ii.iii.iv.v
ii. Any CANs
iii. Check starters, scabbling, cover checked, thickenings
iv. Reinsforcement size, spacing, supports.
v. Clean formwork and ready to pour
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/safety/protection
Clear access for trucks/pump
Safe access to all areas of pour
Panel and steel protection
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Post pour
Finish
Levels
Curing agent
Saw cuts within 24h of pour and slurry removed
Pour QA received including concrete dockets

## 2.1 Precast Walls
ITP Structure – Pre-cast Panels
Pre-start
GL and datum provided
Timber guides installed – including spacers
Waterstop installed
Clean work area
Ground Beams QA received
Min days/MPa since pour
Propping onsite
Delivery Inspection
Check for damage/defects on arrival
Measurement checks in line w/ IFC SD
Panels unloaded correctly
Installation
Installed in correct location as per Struc. Dwg
Check temporary bracing as per requirements
Sample verticality check
Post Installation
As per propping design.
Check for damage to panels
Confirm all Grouting completed
Panel installation QA

## 2.1 Shotcrete Walls
ITP Structure – Shotcrete Walls
Pre-start
Ground Beams sign-off/QA received
GL and datum provided
Clean work area
Pre-pour
Service trade sign off/QA
i. attached mark-up
Formwork signoff/QA
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Check form ties and propping
iiii. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked
1. Any CAN, Engr requirements
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Pour sequence mark-up
Access/safety
Access for sprayer/pump
Check TA
Safe access to all areas of spray
Exposed reo capped
Spray / Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Post spray / pour
Checks
i. Finish
ii. Levels
Pour QA received including concrete dockets

## 2.1 Blockwalls
ITP Structure – Retaining Wall (Concrete Block)
Park Building ( Basement- LG- Ground)
Pre-start
Foundation QA
GL and datum provided
Material Testing, bricks, weep pipes
Check starters
Clean work area
Pre Block work
Reo-sign off/QA
GN Inspection
i. detail checks.
a. Any RFI's, Authority req.
During works
Foundation works including base preparation
Check reo details
Bottom clean-outs for inspection
Check set-out
Brick Layering
Drainage pipes/ weep holes
Pre-pour (blocks infill)
Reo sign off/QA
GN inspection
i. Details checked
a. Any RFIs
ii. Starters, cover checked
iii. Clean-outs free of debris and ready to inspect/pour
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/Safety
Clear access for mixers
Exposed reo capped
Safe access to all areas of work
Post pour
Checks
i. Finish
ii. Levels
iii. Alignment
Documentation QA received

## 2.1 Tanking
Please pull up from Alberton project

## 2.2 Foundation Beams (Cap & GD)
ITP Structure – Ground & Capping Beams
Notes
1. Pre-start
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Waterproof sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks | (add tickbox for I,ii,iii,iv)
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked | (add tickbox for i,ii,iii)
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Any CAN, Engr requirements (Reo Pull-out test)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks | (add tickbox for i,ii,iii)
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets

## 2.2 Precast Elements
ITP Structure – PC Walls & Planters
Pre-start
GL and datum provided
Timber guides installed – including spacers
Waterstop installed
Clean work area
Ground Beams QA received
Min days/MPa since pour
Propping onsite
Delivery Inspection
Check for damage/defects on arrival
Measurement checks in line w/ IFC SD
Panels unloaded correctly
Installation
Installed in correct location as per Struc. Dwg
Check temporary bracing as per requirements
Sample verticality check
Post Installation
As per propping design.
Check for damage to panels
Confirm all Grouting completed
Panel installation QA
ANY OTHER CHECKLIST REQUIRED FOR PLANTERS?

## 2.2 Insitu Columns & Walls
1. Pre-start
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Waterproof sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Any CAN, Engr requirements (Reo Pull-out test)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets

## 2.2 Steel Beams & Columns
ITP Structure – Structural Steel - Column and Beams
Pre-Start
RL for support beams/ Plinth
Plate support/ bolts surveyed and checked as built
Slab QA received
checked tolerances, packing space
Area clean/clear for access equipment
Safety
review weights and lifting gears inspected
taglines secured
Work space demarcation
Erection
GN inspection
i. Welds, bolts, plumb, alignment, etc. as per design
ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Post erection
Propping where required
Spot check RL’s and plumb
Primer touch-ups
Steel QA received
Grout under columns

## 2.2 Suspended Slabs
ITP Structure – Suspended Slab
Pre-start
Ea and support installed
i. QA/ signoff
Edge protection in place
Access provided
GL and datum provided
Clean work area
Pre-pour
Comflor sign-off/QA received
i. Stud testing completed
Propping sign-off/QA received
Services marked out and double mesh
Reo sign-off/QA received
GN inspection
i. Details checked
ii. Stair opening checked
iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
iv. Clean and ready to pour
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/Safety
Clear access for trucks/pump
Safe access to all areas of pour
Wash up organized
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Checked Screed to falls
Post pour
Finish
Levels
Curing agent and canvas protection (standby)
Pour QA received

## 2.2 Crane Base
ITP Structure – Foundation (Towercrane)
1. Pre-start – HOLD POINT
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked
1. Any CAN, Engr requirements ( Reo Pull-out test
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets
6. Towercrane Assembly preparation
i. ensure personell trained
ii. Verify all components
iii. Confirm to conduct trial run and check safety devices and emergency sys.
iv. Ensure load test and recorded results.
v. Confirm certification and approva and authority approvals
vi. Handing over documentations, and training certs.

## 2.3 Precast Elements
Replicate 2.3 to 2.4, 2.5 & 2.6 once the checklist review is completed
ITP Structure – PC Walls & Planters
Pre-start
GL and datum provided
Timber guides installed – including spacers
Waterstop installed
Clean work area
Ground Beams QA received
Min days/MPa since pour
Propping onsite
Delivery Inspection
Check for damage/defects on arrival
Measurement checks in line w/ IFC SD
Panels unloaded correctly
Installation
Installed in correct location as per Struc. Dwg
Check temporary bracing as per requirements
Sample verticality check
Post Installation
As per propping design.
Check for damage to panels
Confirm all Grouting completed
Panel installation QA
ANY OTHER CHECKLIST REQUIRED FOR PLANTERS?

## 2.3 PT Slabs
Replicate 2.3 to 2.4, 2.5 & 2.6 once the checklist review is completed
ITP Structure – Suspended Slab
TBC! Need to find a PT Slab template done in GN before
Pre-start
Ea and support installed
i. QA/ signoff
Edge protection in place
Access provided
GL and datum provided
Clean work area
Pre-pour
Comflor sign-off/QA received
i. Stud testing completed
Propping sign-off/QA received
Services marked out and double mesh
Reo sign-off/QA received
GN inspection
i. Details checked
ii. Stair opening checked
iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
iv. Clean and ready to pour
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/Safety
Clear access for trucks/pump
Safe access to all areas of pour
Wash up organized
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Checked Screed to falls
Post pour
Finish
Levels
Curing agent and canvas protection (standby)
Pour QA received

## 2.3 Insitu Columns
Replicate 2.3 to 2.4, 2.5 & 2.6 once the checklist review is completed
1. Pre-start
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Waterproof sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Any CAN, Engr requirements (Reo Pull-out test)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets

## 2.3 Steel Beams & Columns
Replicate 2.3 to 2.4, 2.5 & 2.6 once the checklist review is completed
ITP Structure – Structural Steel - Column and Beams
Pre-Start
RL for support beams/ Plinth
Plate support/ bolts surveyed and checked as built
Slab QA received
checked tolerances, packing space
Area clean/clear for access equipment
Safety
review weights and lifting gears inspected
taglines secured
Work space demarcation
Erection
GN inspection
i. Welds, bolts, plumb, alignment, etc. as per design
ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Post erection
Propping where required
Spot check RL’s and plumb
Primer touch-ups
Steel QA received
Grout under columns