## Sheet1
1.1 | IFC Drawings and Specification | ACC | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification | Once | N/A | R |  | H | 1.1 - IFC Drawings and Specification | Standard, Drawing or Specification Reference - ACC | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification | Test Frequency - Once | QA Record - N/A | DNZ Engineer - R | Engineer's Rep - | Designer Rep - H | 1.1 - IFC Drawings and Specification
1.2 | Method Statement CHAR(AMP) JSEA Development | The Downer Standards (TDS) | Prior to construction: document review. | Once | Method Statement CHAR(AMP) JSEA Completed CHAR(AMP) signed by relevant authority | H | R | R | 1.2 - Method Statement CHAR(AMP) JSEA Development | Standard, Drawing or Specification Reference - The Downer Standards (TDS) | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review. | Test Frequency - Once | QA Record - Method Statement CHAR(AMP) JSEA Completed CHAR(AMP) signed by relevant authority | DNZ Engineer - H | Engineer's Rep - R | Designer Rep - R | Standard, Drawing or Specification Reference - ACC
1.3 | Permit to Dig | DN-ZH-ST043 Ground Disturbance | Prior to construction. Permit in work package | Permit issued each week | Permit number ....................... | H |  |  | 1.3 - Permit to Dig | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package | Test Frequency - Permit issued each week | QA Record - Permit number ....................... | DNZ Engineer - H | Engineer's Rep - | Designer Rep - | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification
1.4 | Survey Model | N/A | Model Review. | Once | Visual Inspection CHAR(AMP) measurement Survey Check set out as per design | H |  |  | 1.4 - Survey Model | Standard, Drawing or Specification Reference - N/A | Construction Activity Description, Test Type and Acceptance Criteria - Model Review. | Test Frequency - Once | QA Record - Visual Inspection CHAR(AMP) measurement Survey Check set out as per design | DNZ Engineer - H | Engineer's Rep - | Designer Rep - | Test Frequency - Once
2.1 | Concrete Mix Design | 746-22-052-PS Section 5.2 NZS 3114:1987, part 2 Exposed Aggregate surfaces. | Mix Design approved by designer. 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. | Once | Approved Mix InEight Reference ................. | R |  | H | 2.1 - Concrete Mix Design | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2 NZS 3114:1987, part 2 Exposed Aggregate surfaces. | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer. 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. | Test Frequency - Once | QA Record - Approved Mix InEight Reference ................. | DNZ Engineer - R | Engineer's Rep - | Designer Rep - H | QA Record - N/A
2.2 | ATAP40/GAP40 - Material Source property testing and sampling | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 CHAR(AMP) 4) | Once Per Year Or Every 10 000 m³ | IANZ Test Report | R |  | H | 2.2 - ATAP40/GAP40 - Material Source property testing and sampling | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 CHAR(AMP) 4) | Test Frequency - Once Per Year Or Every 10 000 m³ | QA Record - IANZ Test Report | DNZ Engineer - R | Engineer's Rep - | Designer Rep - H | DNZ Engineer - R
2.3 | ATAP40/GAP40 - Production property testing and sampling | TNZ M/4: 2006 - 4 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control | Once Per Year Or Every 10 000 m³ | IANZ Test Report | R |  | H | 2.3 - ATAP40/GAP40 - Production property testing and sampling | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4 NZS 4407 : 1991 | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control | Test Frequency - Once Per Year Or Every 10 000 m³ | QA Record - IANZ Test Report | DNZ Engineer - R | Engineer's Rep - | Designer Rep - H | Engineer's Rep -
2.4 | ATAP40/GAP40 - Testing for layor compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Average MDD 95% with a minimum of 92% | Once Per Year Or Every 5 000 m³ | IANZ Test Report | R |  | H | 2.4 - ATAP40/GAP40 - Testing for layor compaction - MDD | Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Average MDD 95% with a minimum of 92% | Test Frequency - Once Per Year Or Every 5 000 m³ | QA Record - IANZ Test Report | DNZ Engineer - R | Engineer's Rep - | Designer Rep - H | Designer Rep - H
2.5 | Reinforcing Steel | 3235599-SP03-CA-1031 - Rev 1 | SE62 - 665 Mesh Grade 500E. | Once | Mill Certificates CHAR(AMP) Approval | H |  | R | 2.5 - Reinforcing Steel | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - SE62 - 665 Mesh Grade 500E. | Test Frequency - Once | QA Record - Mill Certificates CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | 1.2 - Method Statement CHAR(AMP) JSEA Development
2.6 | Contraction Joints | 3235599-SP03-CA-1031 - Rev 1 | 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. | Once | Mill Certificates CHAR(AMP) Approval | H |  | R | 2.6 - Contraction Joints | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. | Test Frequency - Once | QA Record - Mill Certificates CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
2.7 | Tactile Indicators | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | 300mm x 300mm x 60mm thick yellow anti-slip precast concrete. | Once | MDS CHAR(AMP) Approval | H |  | R | 2.7 - Tactile Indicators | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip precast concrete. | Test Frequency - Once | QA Record - MDS CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
2.8 | Joint Sealer | 3235599-SP03-CA-1031 - Rev 1 | SIKAFLEX 11FC or similar approved product. | Once | MDS CHAR(AMP) Approval | H |  | R | 2.8 - Joint Sealer | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - SIKAFLEX 11FC or similar approved product. | Test Frequency - Once | QA Record - MDS CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Test Frequency - Once
2.9 | Joint Filler | 3235599-SP03-CA-1031 - Rev 1 | 8mm Polystyrene joint filler . | Once | MDS CHAR(AMP) Approval | H |  | R | 2.9 - Joint Filler | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - 8mm Polystyrene joint filler . | Test Frequency - Once | QA Record - MDS CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | QA Record - Method Statement CHAR(AMP) JSEA Completed CHAR(AMP) signed by relevant authority
2.1 | Stitching Reinforcing Bars | AT Detail FP002 | 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300 | As required | Mill Certificates CHAR(AMP) Approval | H |  | R | 2.1 - Stitching Reinforcing Bars | Standard, Drawing or Specification Reference - AT Detail FP002 | Construction Activity Description, Test Type and Acceptance Criteria - 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300 | Test Frequency - As required | QA Record - Mill Certificates CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | DNZ Engineer - H
2.11 | Geotextile | 3235599-SP03-CA-1031 - Rev 1 | A29 Geotextile Bidim, or similar approved product. | As required | MDS CHAR(AMP) Approval | H |  | R | 2.11 - Geotextile | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - A29 Geotextile Bidim, or similar approved product. | Test Frequency - As required | QA Record - MDS CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Engineer's Rep - R
2.12 | Geogrid | 3235599-SP03-CA-1031 - Rev 1 | Tensar Triax 170 Geogrid or similar approved product. | As required | MDS CHAR(AMP) Approval | H |  | R | 2.12 - Geogrid | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - Tensar Triax 170 Geogrid or similar approved product. | Test Frequency - As required | QA Record - MDS CHAR(AMP) Approval | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Designer Rep - R
3.1 | Footpath set out and excavation to subgrade | IFC drawings and Models 746-22-052-PS Page 9 Table 1 | Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane. NO WATER PONDING ON SUBGRADE. | Every 5m | As-Built or Stringline checksheet | H |  |  | 3.1 - Footpath set out and excavation to subgrade | Standard, Drawing or Specification Reference - IFC drawings and Models 746-22-052-PS Page 9 Table 1 | Construction Activity Description, Test Type and Acceptance Criteria - Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane. NO WATER PONDING ON SUBGRADE. | Test Frequency - Every 5m | QA Record - As-Built or Stringline checksheet | DNZ Engineer - H | Engineer's Rep - | Designer Rep - | 1.3 - Permit to Dig
3.2 | Foundation - Subgrade Testing (Scala) | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1 | If caly based material is encountered - ensure subgrade has a minimum CBR of 3 Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%. | Every 25m² | Scala Test Results - CBR of 3 | H |  | R | 3.2 - Foundation - Subgrade Testing (Scala) | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1 | Construction Activity Description, Test Type and Acceptance Criteria - If caly based material is encountered - ensure subgrade has a minimum CBR of 3 Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%. | Test Frequency - Every 25m² | QA Record - Scala Test Results - CBR of 3 | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
3.3 | Foundation - Subgrade Testing (Existing footpath) (Clegg) | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1 | If granular material is encountered - Minimum CIV of 12 | Every 10m | Clegg Test Results - min CIV 12 | H |  | R | 3.3 - Foundation - Subgrade Testing (Existing footpath) (Clegg) | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1 | Construction Activity Description, Test Type and Acceptance Criteria - If granular material is encountered - Minimum CIV of 12 | Test Frequency - Every 10m | QA Record - Clegg Test Results - min CIV 12 | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
3.4 | Place Geotextile | 3235599-SP03-CA-1001 - Rev 1 Note 12 | An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade. A29 Bidim, ensure top, bottom and sides are coverd. | Per inpsection | Checksheet Photos | I |  |  | 3.4 - Place Geotextile | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 | Construction Activity Description, Test Type and Acceptance Criteria - An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade. A29 Bidim, ensure top, bottom and sides are coverd. | Test Frequency - Per inpsection | QA Record - Checksheet Photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | Test Frequency - Permit issued each week
3.5 | Undercut (If required) | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2 | Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed. | As required | HP Release | I |  | H | 3.5 - Undercut (If required) | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2 | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed. | Test Frequency - As required | QA Record - HP Release | DNZ Engineer - I | Engineer's Rep - | Designer Rep - H | QA Record - Permit number .......................
3.6 | Place Geogrid (Only required for undercuts) | 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2 | Placed above the geotextile prior to backfilling. | As required | Checksheet Photos | I |  |  | 3.6 - Place Geogrid (Only required for undercuts) | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2 | Construction Activity Description, Test Type and Acceptance Criteria - Placed above the geotextile prior to backfilling. | Test Frequency - As required | QA Record - Checksheet Photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | DNZ Engineer - H
3.7 | Place and compact Basecourse GAP40 | 3235599-SP03-CA-1001 - Rev 1 Note 9 | 100mm thick layer compacted where no undercut is required Where undercut is required: Contractor to notify Engineer. Minimum CLEGG CIV - 12. | Every 10 m | Clegg Test Results and photos | I |  |  | 3.7 - Place and compact Basecourse GAP40 | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 9 | Construction Activity Description, Test Type and Acceptance Criteria - 100mm thick layer compacted where no undercut is required Where undercut is required: Contractor to notify Engineer. Minimum CLEGG CIV - 12. | Test Frequency - Every 10 m | QA Record - Clegg Test Results and photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | Engineer's Rep -
3.8 | Timber edging | IFC Set out | All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick. | As required | Checksheet Photos | I |  |  | 3.8 - Timber edging | Standard, Drawing or Specification Reference - IFC Set out | Construction Activity Description, Test Type and Acceptance Criteria - All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick. | Test Frequency - As required | QA Record - Checksheet Photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | Designer Rep -
3.9 | Place Reinforcing Mesh | 3235599-SP03-CA-1031 - Rev 1 3235599-SP03-ST-3002 Note 6.1 | 665 mesh, centrally placed. Minimum overlap of 200mm between outermost cross wires. | Every pour | Checksheet Photos | I |  |  | 3.9 - Place Reinforcing Mesh | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 3235599-SP03-ST-3002 Note 6.1 | Construction Activity Description, Test Type and Acceptance Criteria - 665 mesh, centrally placed. Minimum overlap of 200mm between outermost cross wires. | Test Frequency - Every pour | QA Record - Checksheet Photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | 1.4 - Survey Model
3.1 | Place Contraction Joints | 3235599-SP03-CA-1031 - Rev 1 | 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. Installed every 15m. | Every 15m | Checksheet Photos | I |  |  | 3.1 - Place Contraction Joints | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. Installed every 15m. | Test Frequency - Every 15m | QA Record - Checksheet Photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | Standard, Drawing or Specification Reference - N/A
3.11 | Place Tactilies | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | Tactile pavers shall be bedded on 100mm thick 20Mpa concrete. Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement. A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons | Per installation | Delivery dockets, Checksheet Photos | H |  | I | 3.11 - Place Tactilies | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | Construction Activity Description, Test Type and Acceptance Criteria - Tactile pavers shall be bedded on 100mm thick 20Mpa concrete. Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement. A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons | Test Frequency - Per installation | QA Record - Delivery dockets, Checksheet Photos | DNZ Engineer - H | Engineer's Rep - | Designer Rep - I | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
3.12 | Place reinforcing Stitching Bars | AT Detail FP002 | Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners. 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300 | As required | Mill certificates and photos | I |  |  | 3.12 - Place reinforcing Stitching Bars | Standard, Drawing or Specification Reference - AT Detail FP002 | Construction Activity Description, Test Type and Acceptance Criteria - Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners. 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300 | Test Frequency - As required | QA Record - Mill certificates and photos | DNZ Engineer - I | Engineer's Rep - | Designer Rep - | Test Frequency - Once
3.13 | Concrete Pre-Pour | AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge | Every Pour | Pre-Pour Checklist | H |  | I | 3.13 - Concrete Pre-Pour | Standard, Drawing or Specification Reference - AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge | Test Frequency - Every Pour | QA Record - Pre-Pour Checklist | DNZ Engineer - H | Engineer's Rep - | Designer Rep - I | QA Record - Visual Inspection CHAR(AMP) measurement Survey Check set out as per design
3.14 | Concrete Pour | AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | 2% Cross Fall Towards Carriageway. (1% min. 3% max.) 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Slump 120mm (±30mm) | Every Pour | 7 day and 28 day Concrete Test Results from supplier Slump Test Results (onsite) | W |  | W | 3.14 - Concrete Pour | Standard, Drawing or Specification Reference - AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - 2% Cross Fall Towards Carriageway. (1% min. 3% max.) 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Slump 120mm (±30mm) | Test Frequency - Every Pour | QA Record - 7 day and 28 day Concrete Test Results from supplier Slump Test Results (onsite) | DNZ Engineer - W | Engineer's Rep - | Designer Rep - W | DNZ Engineer - H
3.15 | Concrete Finish | AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Exposed finish apply surface with Rugasol C. Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom ( U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm. | Every Pour | Post pour inspection checksheet | W |  |  | 3.15 - Concrete Finish | Standard, Drawing or Specification Reference - AT Detail FP001 3235599-SP03-CA-1031 - Rev 1 | Construction Activity Description, Test Type and Acceptance Criteria - 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Exposed finish apply surface with Rugasol C. Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom ( U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm. | Test Frequency - Every Pour | QA Record - Post pour inspection checksheet | DNZ Engineer - W | Engineer's Rep - | Designer Rep - | Engineer's Rep -
3.16 | Saw Cut Joints | 3235599-SP03-CA-1001 - Rev 1 Note 5 AT TDM | Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m. | Every 3m | Photos | W |  |  | 3.16 - Saw Cut Joints | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 5 AT TDM | Construction Activity Description, Test Type and Acceptance Criteria - Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m. | Test Frequency - Every 3m | QA Record - Photos | DNZ Engineer - W | Engineer's Rep - | Designer Rep - | Designer Rep -
4.1 | Construction Record Compilation | N/A | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Once | QA Records | H |  | R | 4.1 - Construction Record Compilation | Standard, Drawing or Specification Reference - N/A | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Test Frequency - Once | QA Record - QA Records | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | 2.1 - Concrete Mix Design
4.2 | Survey Records | N/A | Ensure all items have been surveyed and records are assembled for asbuilting | Once | As-Built | H |  | R | 4.2 - Survey Records | Standard, Drawing or Specification Reference - N/A | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting | Test Frequency - Once | QA Record - As-Built | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2 NZS 3114:1987, part 2 Exposed Aggregate surfaces.
4.3 | Redline Drawings | IFC Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Once | IFC Mark-Up | H |  | R | 4.3 - Redline Drawings | Standard, Drawing or Specification Reference - IFC Drawings | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Test Frequency - Once | QA Record - IFC Mark-Up | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer. 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
4.4 | Defect, Snag and Punch List | DN1212-DOW-PLA-PM-0005 QMP | Update the project Defect, Snag and Punch List Register | If required | Snag Register | H |  | R | 4.4 - Defect, Snag and Punch List | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register | Test Frequency - If required | QA Record - Snag Register | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | Test Frequency - Once
4.5 | Non-conformances | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. | When Required | NCR Forms on InEight | H |  | R | 4.5 - Non-conformances | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. | Test Frequency - When Required | QA Record - NCR Forms on InEight | DNZ Engineer - H | Engineer's Rep - | Designer Rep - R | QA Record - Approved Mix InEight Reference .................
DNZ Engineer - R
Engineer's Rep -
Designer Rep - H
2.2 - ATAP40/GAP40 - Material Source property testing and sampling
Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986
Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 CHAR(AMP) 4)
Test Frequency - Once Per Year Or Every 10 000 m³
QA Record - IANZ Test Report
DNZ Engineer - R
Engineer's Rep -
Designer Rep - H
2.3 - ATAP40/GAP40 - Production property testing and sampling
Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4 NZS 4407 : 1991
Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control
Test Frequency - Once Per Year Or Every 10 000 m³
QA Record - IANZ Test Report
DNZ Engineer - R
Engineer's Rep -
Designer Rep - H
2.4 - ATAP40/GAP40 - Testing for layor compaction - MDD
Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Average MDD 95% with a minimum of 92%
Test Frequency - Once Per Year Or Every 5 000 m³
QA Record - IANZ Test Report
DNZ Engineer - R
Engineer's Rep -
Designer Rep - H
2.5 - Reinforcing Steel
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - SE62 - 665 Mesh Grade 500E.
Test Frequency - Once
QA Record - Mill Certificates CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.6 - Contraction Joints
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
Test Frequency - Once
QA Record - Mill Certificates CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.7 - Tactile Indicators
Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11
Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip precast concrete.
Test Frequency - Once
QA Record - MDS CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.8 - Joint Sealer
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - SIKAFLEX 11FC or similar approved product.
Test Frequency - Once
QA Record - MDS CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.9 - Joint Filler
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - 8mm Polystyrene joint filler .
Test Frequency - Once
QA Record - MDS CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.1 - Stitching Reinforcing Bars
Standard, Drawing or Specification Reference - AT Detail FP002
Construction Activity Description, Test Type and Acceptance Criteria - 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
Test Frequency - As required
QA Record - Mill Certificates CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.11 - Geotextile
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - A29 Geotextile Bidim, or similar approved product.
Test Frequency - As required
QA Record - MDS CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
2.12 - Geogrid
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - Tensar Triax 170 Geogrid or similar approved product.
Test Frequency - As required
QA Record - MDS CHAR(AMP) Approval
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
3.1 - Footpath set out and excavation to subgrade
Standard, Drawing or Specification Reference - IFC drawings and Models 746-22-052-PS Page 9 Table 1
Construction Activity Description, Test Type and Acceptance Criteria - Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane. NO WATER PONDING ON SUBGRADE.
Test Frequency - Every 5m
QA Record - As-Built or Stringline checksheet
DNZ Engineer - H
Engineer's Rep -
Designer Rep -
3.2 - Foundation - Subgrade Testing (Scala)
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1
Construction Activity Description, Test Type and Acceptance Criteria - If caly based material is encountered - ensure subgrade has a minimum CBR of 3 Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%.
Test Frequency - Every 25m²
QA Record - Scala Test Results - CBR of 3
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
3.3 - Foundation - Subgrade Testing (Existing footpath) (Clegg)
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 9 Table 1
Construction Activity Description, Test Type and Acceptance Criteria - If granular material is encountered - Minimum CIV of 12
Test Frequency - Every 10m
QA Record - Clegg Test Results - min CIV 12
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
3.4 - Place Geotextile
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12
Construction Activity Description, Test Type and Acceptance Criteria - An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade. A29 Bidim, ensure top, bottom and sides are coverd.
Test Frequency - Per inpsection
QA Record - Checksheet Photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.5 - Undercut (If required)
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2
Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed.
Test Frequency - As required
QA Record - HP Release
DNZ Engineer - I
Engineer's Rep -
Designer Rep - H
3.6 - Place Geogrid (Only required for undercuts)
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 12 746-22-052-PS Page 10 Table 2
Construction Activity Description, Test Type and Acceptance Criteria - Placed above the geotextile prior to backfilling.
Test Frequency - As required
QA Record - Checksheet Photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.7 - Place and compact Basecourse GAP40
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 9
Construction Activity Description, Test Type and Acceptance Criteria - 100mm thick layer compacted where no undercut is required Where undercut is required: Contractor to notify Engineer. Minimum CLEGG CIV - 12.
Test Frequency - Every 10 m
QA Record - Clegg Test Results and photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.8 - Timber edging
Standard, Drawing or Specification Reference - IFC Set out
Construction Activity Description, Test Type and Acceptance Criteria - All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick.
Test Frequency - As required
QA Record - Checksheet Photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.9 - Place Reinforcing Mesh
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1 3235599-SP03-ST-3002 Note 6.1
Construction Activity Description, Test Type and Acceptance Criteria - 665 mesh, centrally placed. Minimum overlap of 200mm between outermost cross wires.
Test Frequency - Every pour
QA Record - Checksheet Photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.1 - Place Contraction Joints
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres. Installed every 15m.
Test Frequency - Every 15m
QA Record - Checksheet Photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.11 - Place Tactilies
Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11
Construction Activity Description, Test Type and Acceptance Criteria - Tactile pavers shall be bedded on 100mm thick 20Mpa concrete. Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement. A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons
Test Frequency - Per installation
QA Record - Delivery dockets, Checksheet Photos
DNZ Engineer - H
Engineer's Rep -
Designer Rep - I
3.12 - Place reinforcing Stitching Bars
Standard, Drawing or Specification Reference - AT Detail FP002
Construction Activity Description, Test Type and Acceptance Criteria - Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners. 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
Test Frequency - As required
QA Record - Mill certificates and photos
DNZ Engineer - I
Engineer's Rep -
Designer Rep -
3.13 - Concrete Pre-Pour
Standard, Drawing or Specification Reference - AT Detail FP001 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge
Test Frequency - Every Pour
QA Record - Pre-Pour Checklist
DNZ Engineer - H
Engineer's Rep -
Designer Rep - I
3.14 - Concrete Pour
Standard, Drawing or Specification Reference - AT Detail FP001 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - 2% Cross Fall Towards Carriageway. (1% min. 3% max.) 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Slump 120mm (±30mm)
Test Frequency - Every Pour
QA Record - 7 day and 28 day Concrete Test Results from supplier Slump Test Results (onsite)
DNZ Engineer - W
Engineer's Rep -
Designer Rep - W
3.15 - Concrete Finish
Standard, Drawing or Specification Reference - AT Detail FP001 3235599-SP03-CA-1031 - Rev 1
Construction Activity Description, Test Type and Acceptance Criteria - 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates. Exposed finish apply surface with Rugasol C. Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom ( U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm.
Test Frequency - Every Pour
QA Record - Post pour inspection checksheet
DNZ Engineer - W
Engineer's Rep -
Designer Rep -
3.16 - Saw Cut Joints
Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1 Note 5 AT TDM
Construction Activity Description, Test Type and Acceptance Criteria - Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m.
Test Frequency - Every 3m
QA Record - Photos
DNZ Engineer - W
Engineer's Rep -
Designer Rep -
4.1 - Construction Record Compilation
Standard, Drawing or Specification Reference - N/A
Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
Test Frequency - Once
QA Record - QA Records
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
4.2 - Survey Records
Standard, Drawing or Specification Reference - N/A
Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
Test Frequency - Once
QA Record - As-Built
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
4.3 - Redline Drawings
Standard, Drawing or Specification Reference - IFC Drawings
Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
Test Frequency - Once
QA Record - IFC Mark-Up
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
4.4 - Defect, Snag and Punch List
Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
Test Frequency - If required
QA Record - Snag Register
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R
4.5 - Non-conformances
Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference …..................
Test Frequency - When Required
QA Record - NCR Forms on InEight
DNZ Engineer - H
Engineer's Rep -
Designer Rep - R