## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
1707a231-9c5c-4aaa-99a5-2c3f6b0bf8b4 | checklist | 35.18.1 SPWB Trenching Works |  | 35.18.1 SPWB Trenching Works |  | e6909865-cb55-48d6-be7e-a863bc0073cc
d59b5141-c209-4e4d-8325-9a38a357d4fa | section | Pre Construction
4447150d-1b61-4400-becb-21577da5cb6b | checkpoint | Dial Before you dig completed and understood? This is a Hold Point.
198a11bb-234d-4a85-a12d-acb73e4a82d7 | signoff | HOLD POINT
5910e9ca-5ff3-464d-9c50-1fc9f906706c | checkpoint | Are there any Services
5186b1ca-cc11-4c3d-9c5c-63243f9e9dd2 | checkpoint | Survey Setout for portion of the works completed. Hold Point
7461ffd8-48fa-46c5-9ea1-b0ca5fc421f9 | signoff | HOLD POINT
9b4470eb-c70e-4a3c-9408-083f69516749 | checkpoint | Tree Protection in place. Hold Points X3
e52170fd-b72c-4ab8-a223-65b17a32493e | signoff | HOLD POINT
469e9122-eb85-4033-9d44-6a024c0a6835 | checkpoint | Excavation Permit Completed
5b78aa7b-f3e0-46ea-acae-ec3b6b0db545 | section | Construction
cbf33034-2696-4d4c-a0a5-90f56c1c371b | checkpoint | Preliminary Approvals Completed. Site Engineer check
5c9df9f6-d117-40ae-89ee-3932d4c26f3d | checkpoint | Clearing & Grubbing completed. Hold Point to inspect cleared Site
09820c21-fd8d-4db8-8c4b-87609659e3bd | signoff | HOLD POINT
bed8a912-4f15-4cfd-80ed-638588e6bc6a | checkpoint | Topsoil Removed
809d7086-c81c-44c2-8071-a24daf1aa526 | checkpoint | Location of Vertical bores marked
a2d22b7d-f4ee-433f-b768-4f4054083d5b | checkpoint | Trench Excavation Completed
aff5095b-1e6f-4236-b52b-cd6b4a344793 | checkpoint | Depth of Trench Every 10m Over 100m Lot
f7d26228-121b-59d9-81a0-1d0225a63541 | textbox | 0-10 (Meters)
cfb079a2-41d8-5062-8310-bd5265a85e31 | textbox | 10-20 (Meters)
35c775fb-e248-5469-8737-e9e030a3f012 | textbox | 20-30 (Meters)
32ef87d9-1d80-534b-a470-ddebff9f90a4 | textbox | 30-40 (Meters)
68c060a8-6f01-59e0-a4d8-a2fec4fe1698 | textbox | 40-50 (Meters)
f29ff198-05bd-53d1-bde9-b7d62b646b2c | textbox | 50-60 (Meters)
fba9abe2-0a30-55ac-bea1-176f868013fb | textbox | 60-70 (Meters)
59713e25-bc2c-5ddf-b744-e5b4bac460ff | textbox | 70-80 (Meters)
c66a7a05-0d37-57dc-aaa6-8b732659ca18 | textbox | 80-90 (Meters)
b8ba37ef-5a46-524b-9a93-41ccb0f1b2dc | textbox | 90-100 (Meters)
5745e4d8-f8de-420f-b3a6-242dad558aa7 | checkpoint | Excavation Sign Off (Hold Point)
c87c202b-61b6-4422-a7ac-6c058aac2cec | signoff | HOLD POINT
991a42b9-cb25-4e55-bbf9-557a82c7973e | checkpoint | Sleeve placed for Vertical Bore
16813735-2ada-4e97-8fe7-db3aeb52acc6 | checkpoint | Trench backfilling with coarse gravel (>40mm) to design height of trench pipework? Hold Point (check against Design Height Register)
4aef6c39-0c6c-4daf-bba1-d08c02c5f691 | signoff | HOLD POINT
3bcaaba6-41b5-4cb3-863d-b3f1ed07d02b | checkpoint | Gravel Sign off prior to pipework (Hold Point)
c8a47acf-ae53-44e3-bd59-0f1d039c5a66 | signoff | HOLD POINT
8dc9179b-e6c5-41c4-8116-875f2ed25b43 | checkpoint | Vertical Bore ITC completed?
4b701f47-46e2-403f-aeac-8d3c0f5a49aa | checkpoint | Inspection of completed Gas interception Pipework. Hold Point
0dcbbca7-0a44-4e0b-a7a1-c69a7d3d7331 | signoff | HOLD POINT
6d09533f-694f-4135-a306-e0ac4083eec4 | checkpoint | Pipe Work Sign Off (Hold Point)
3bdfbd24-898a-4e07-ad95-3d142edd12f5 | signoff | HOLD POINT
bd05ecf3-0a99-4996-837e-2d43b6106bf2 | checkpoint | Trench backfilling with coarse gravel (>40mm) to finished design height. Hold Point.
880f1862-e47a-464a-aa3c-d238a1b772f3 | signoff | HOLD POINT
eb58953c-8608-41d0-a7d7-10c9091b3194 | checkpoint | Completed Gravel Sign Off (Hold Point)
208b6496-b9de-427b-a4e8-d978f5d60406 | signoff | HOLD POINT
8dccdd8e-574a-47dd-9b81-23479fab6860 | checkpoint | Testing of Coarse gravel. Plan with Site Engineer.
1761e615-00f3-4199-88c4-5522cd464fdc | checkpoint | Installation of vertical risers. As per jointing methodology with Site Engineer.
db2ea843-274f-4357-b05e-274f35952854 | checkpoint | Geotextile installation completed. Hold Point
91a239a3-c593-4ac9-a95f-3034b648add2 | signoff | HOLD POINT
4dbb535b-9895-40e2-a28c-52f9807d8560 | checkpoint | Geotextile Sign Off (Hold Point)
335e6b0c-e210-4c4a-8011-1829b4dc9fdd | signoff | HOLD POINT
6cea3e05-fd97-48cc-b1fe-fbc97eda7387 | checkpoint | Survey completed for top of coarse gravel. Hold Point
d1a8b3be-9c64-4f36-9488-4a371d517559 | signoff | HOLD POINT
d808aae5-8689-4a6e-8cad-692bf034f4f6 | checkpoint | Survey Sign off
7d5b5c3f-6e61-49bc-8a12-3e0fd4ff14d4 | signoff | SURVEY Sign off
6a645e46-3470-446a-b499-1c6953fb5eb6 | checkpoint | Placement of capping material completed.
acf8eee8-90a0-4914-a8ff-821741eb7f1d | checkpoint | Testing of capping material completed. Refer to Testing Plan.
0274f5e6-89ea-449a-9065-0e8836b1ac5d | checkpoint | Survey of capping material.
5e9b09fc-91e5-49b4-ad06-82e25d01bcec | checkpoint | Capping Sign Off (Hold Point)
80951d67-d6d9-4ec2-8fda-72a8e60b6a8c | signoff | HOLD POINT
2d32225e-300a-44f9-9078-0868bb046603 | section | Daily Log and Notes from Trench Work
0bd40c25-509e-4a6e-8754-7b3ba16436eb | checkpoint-no-value | Details
a397e23d-e1d6-5c08-8398-dfd43a9e784c | number | How Many Days of Excavation per Lot
de45f1a4-ccea-42a7-a0b2-78d6fa63153a | checkpoint | Was there Weather that affected the trench