## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Earthworks - 101 - Rev B | itp |  |  |  | Yes | ITP - Earthworks - 101 - Rev B | 37cc6425-ba5f-42cf-abb6-51bfe648c651
checkpoint-group |  |  | section | 3.01 General
checkpoint-status |  |  | checkpoint | 3.01.01 - Precondition Surveys
label | 69cd2420-d366-54eb-958b-47ee6ba30c3b |  | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
label | 8a300e3e-8b0d-50e1-92a8-acacc9470272 |  | note | Standard / Specification - PS 2.13
label | 4012ae1e-5742-5bb3-bd88-9891dd0da569 |  | note | Verifying Document - Precondition Survey
label | 5ee54bf7-4881-50be-9cbd-b6ca24fbed29 |  | note | Frequency - Prior to the Contractor taking possession of the Site.
label | 4ee5ad50-8a49-5ef9-b2ce-6829404da63e |  | note | Verification Activity: Activity - H
label | 042a86d8-9388-5bf2-bc39-fae98a19ea53 |  | note | Verification Activity: By - PM
checkpoint-group |  |  | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
checkpoint-status |  |  | checkpoint | 4.01.01 - Source Property Tests and Sampling
label | c970b435-1a5a-5b52-9c63-6d3dc47a7b24 |  | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
label | 5fddf01b-636b-5c1b-9e0f-f9d479c784a9 |  | note | Standard / Specification - PS 15.7.3 Appendix XIII
label | c05f86e5-078b-56d0-a84d-743d12ed7c80 |  | note | Verifying Document - IANZ Lab Reports
label | 0d61936a-619a-5486-b002-fd3bb8ecd191 |  | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
label | 6c36e154-7375-5049-8d17-38c7ea3fb8aa |  | note | Verification Activity: Activity - HP
label | 3ce79e68-2cd7-57fc-8b23-187278275664 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
label | 0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce |  | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
label | 3a7cfff1-f254-5419-911c-e86cf81791ad |  | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
label | bac60110-709f-58ca-825f-eef1d568b6fe |  | note | Verifying Document - IANZ Lab Reports
label | 28d0819b-7509-50e5-aaad-6484fe8c56af |  | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
label | 93ed1431-f321-5f8b-8125-d991cf43a90b |  | note | Verification Activity: Activity - HP
label | 5eecf011-989a-5420-a82b-eb0149a57904 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.03 - Production Property Test Sampling
label | 6c461bdf-e882-525f-a094-2bcc190ce2e7 |  | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
label | 4c2ef108-068a-59d0-b3de-60b2a95c6c7f |  | note | Standard / Specification - PS 15.7.3 Appendix XIII
label | 6a814afb-0be7-53e5-8592-2862e1a765fd |  | note | Verifying Document - IANZ Lab Reports
label | efce84d9-b1b2-5d89-991c-9da04e5ba923 |  | note | Frequency - 0-400 M3 – 2 Tests
label | f89666dd-0f56-5b39-b7d2-2694b08c1b13 |  | note | ○ 400-1,500M3 – 3 Tests
label | ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d |  | note | ○ 1,500-4,000M3 – 4 Tests
label | 8473fabf-bde7-5cc9-8e93-e31e0d9d300b |  | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
label | fd98181f-7bd9-5f53-8201-bb0c6813a688 |  | note | Verification Activity: Activity - H
label | 29935793-de84-5fc9-9e9a-dc726b88856e |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 4.03.02 - Insitu Property Test Sampling
label | 42f927b1-749d-53b4-a100-ea6d5ff0ba1b |  | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
label | 19a1cd4f-97f9-5ea3-8a93-2e2396d8b506 |  | note | Standard / Specification - PS 15.7.3 Appendix XIII
label | ff7a2735-75a6-51cf-9a4a-0860007ad974 |  | note | Verifying Document - IANZ Lab Reports
label | 42bbd9ef-2e1d-53d9-878b-206b20635eff |  | note | Frequency - Prior to use
label | 05b8ee26-1d22-5b51-9ff7-74d041afdd54 |  | note | Verification Activity: Activity - HP
label | 05079142-0924-5a49-9ae4-ca339608863e |  | note | Verification Activity: By - ENG
label | bd794abb-aef0-59fe-b613-fc27f9274d0b |  | note | Comments / Closeout Details - Frequency TBC as not provided
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.04 Type A3 (Site Won Landscaping Fill)
checkpoint-status |  |  | checkpoint | 4.04.01 - On Site track-able Testing
label | 8fefcbaf-cb68-5917-9433-3d41137b8e4e |  | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
label | b4914206-8d0b-5414-9502-17ae4fad6e1c |  | note | Standard / Specification - PS 15.7.3
label | e51abaca-32b0-57d1-8544-f906b25a9fc0 |  | note | Verifying Document - Visual Site Record
label | aaf6e6a1-d9e9-5a27-86da-31e404a8a62d |  | note | Frequency - Prior to Sampling
label | d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 |  | note | Verification Activity: Activity - W
label | 21e39c46-937e-5756-bf3a-0fa20897c108 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
label | da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 |  | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
label | 75366e9f-f170-5da4-8e90-2ba29431f456 |  | note | Standard / Specification - PS 15.7.3, PS 15.13
label | 01c254a6-d804-5850-b1b7-daee29774ece |  | note | Verifying Document - IANZ Lab Reports
label | cd00113d-ee85-5286-956b-580960ae86ae |  | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
label | 9895d0dc-5a1e-556b-b3a4-f60bb935b694 |  | note | Verification Activity: Activity - HP
label | 803e0adb-6908-539d-91c5-5f291f829291 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.04.03 - Insitu Property Test Sampling
label | b2e3a0b7-200b-54bc-8753-e33bdade2178 |  | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
label | da342694-bd84-565c-b303-933f704abeb3 |  | note | Standard / Specification - PS 15.7.3
label | 3f8b0f56-e239-5878-82f3-25bd301b0188 |  | note | Verifying Document - IANZ Lab Reports
label | 54187772-fb0a-5304-b22d-e6fef5571033 |  | note | Frequency - Prior to use
label | 5f2c876f-b40e-5944-91db-1b5c4f101bfd |  | note | Verification Activity: Activity - HP
label | 10ebcf48-ad4b-5c4f-ac90-4d24da87969d |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.05 Topsoil
checkpoint-status |  |  | checkpoint | 4.05.01 - Topsoil
label | c48a7814-415e-5bf0-90db-a1b8443b9fdd |  | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
label | e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad |  | note | Standard / Specification - PS 15.7.3
label | cf04a554-dfc6-58b4-9613-62ac16fdabb9 |  | note | Verifying Document - Site Record
label | ee11df60-1ce5-585b-8998-69594136d238 |  | note | Frequency - During Stripping
label | e137dc49-6b12-5bed-ab75-30d89abce352 |  | note | Verification Activity: Activity - I
label | 11dd70c8-b8f1-5205-a62a-89a0d37a59b0 |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 4.06 Earthworks General
checkpoint-status |  |  | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
label | 01a812e1-2a2b-5d7f-a9f9-4d80c94b831d |  | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
label | c17089c8-cde6-5780-af0b-4d44cfe037e4 |  | note | Standard / Specification - PS 15.10.9
label | 3752352a-df5a-53b2-8094-118f73546c7d |  | note | Verifying Document - Datasheet
label | 8e7145b3-d717-57d4-8b68-f84837bcbada |  | note | Frequency - Prior to use
label | 6f3350cc-a5e3-5922-90ec-ceba1cff1e25 |  | note | Verification Activity: Activity - R
label | ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 5.01 Site Clearance
checkpoint-status |  |  | checkpoint | 5.01.01 - Site Clearance
label | 76735cd9-4858-55a6-aa06-101f02518612 |  | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
label | e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 |  | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
label | f35896e9-18bd-51fb-84bd-a516fea07908 |  | note | Verifying Document - Site Record
label | 1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 |  | note | Frequency - Prior to excavation
label | 553d21dc-d656-5d11-a678-49e9091a7776 |  | note | Verification Activity: Activity - I
label | b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 5.01.02 - Dump Site Approval
label | 165908c4-435f-5b36-8fd9-df3fab4ecdd9 |  | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
label | e22c6756-65e9-50b5-b8f9-e78161c44d04 |  | note | Standard / Specification - NZTA F/1 - 9.4
label | 55d5c387-b48b-5e7f-9757-2749a36ece54 |  | note | Verifying Document - Site Record
label | f84ff3ba-d111-577e-814d-2f3b3ff0c62e |  | note | Frequency - Prior to Stockpiling
label | 73737f8f-3ed5-5230-a5fa-7d12fd1ac08c |  | note | Verification Activity: Activity - HP
label | 74ce0d35-f379-5262-b7f4-46543d42148d |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.03 - Mulching
label | 7c25105e-22ed-5c83-8240-5f58fa89da29 |  | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
label | 39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 |  | note | Standard / Specification - PS 14.1.1
label | 54411dec-bc57-5533-afb7-0f38308d0bf6 |  | note | Verifying Document - Site Record
label | d3575c48-3185-5f98-b1fe-4784265e23ac |  | note | Frequency - During Clearing
label | 449c8392-36d0-5a80-8ce1-30049ce1eaa6 |  | note | Verification Activity: Activity - R
label | 07fddfa0-d1c0-5767-bf10-aa4ad5673f63 |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 6.01 General Earthworks
checkpoint-status |  |  | checkpoint | 6.01.01 - Earthworks Methodology
label | c228e36c-639a-5d64-84a6-17b814e6f41b |  | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
label | 0b682de4-c8ae-51d1-9923-ecbfc85690dd |  | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
label | b50a3242-4781-56d2-9c29-2bfa07bedacd |  | note | Verifying Document - Approved Methodology
label | 9b77a527-c1c2-52d4-bf08-2baf8fe48a93 |  | note | Frequency - Prior to Earthworks
label | 00c15935-b738-5367-8878-db856c582b87 |  | note | Verification Activity: Activity - HP
label | 2e554e60-d952-5dd6-861b-a558370ee856 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.02 - Temporary Excavation Approval
label | 8b4c1814-1483-57a0-a93e-7cf0f5129205 |  | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
label | 33ca796d-57e5-58de-b34f-c32e6163735c |  | note | Standard / Specification - PS 15.13
label | c6d3b217-5879-5d04-b9ab-a032084546f6 |  | note | Verifying Document - Engineers Approval
label | de2c1bd3-ac7a-562d-817a-3f4a0bb05767 |  | note | Frequency - Prior to Excavation.
label | cd18a545-923b-5871-b92c-dee9402f4e29 |  | note | Verification Activity: Activity - HP
label | b2515f22-7df2-58c2-ac65-fe920a60c040 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.03 - Temporary Works Design
label | 6bf13ae3-7a65-50e5-8ee5-356f37e5f99f |  | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
label | 34321cd1-593b-53a3-963f-41929191a96b |  | note | Standard / Specification - PS 15.13
label | 725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 |  | note | Verifying Document - Approved Design
label | e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c |  | note | Frequency - Prior to Excavation.
label | 2ac192cb-bf2e-52c2-b62a-50c4c4697492 |  | note | Verification Activity: Activity - HP
label | e421222d-e59e-5ba2-9fce-d91b87b2c1cd |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.04 - Temporary Stockpiles
label | baf815d3-1ef3-59b4-94ad-daf49ffc72eb |  | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
label | 18b30793-18bf-5c62-9ab2-12c0e2ba5c49 |  | note | Standard / Specification - PS 15.6.5
label | cc98758a-ecad-5043-bcc8-3a0f6433d90f |  | note | Verifying Document - Engineers Approval
label | 58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c |  | note | Frequency - Prior to stockpiling
label | 08cfbbd5-6e1b-5ca2-872e-ed4df362935a |  | note | Verification Activity: Activity - HP
label | 8f11b887-eb69-534b-b326-59012efc3a5c |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.05 - Surplus Material
label | 02f14ce9-3ef4-562b-b104-58d1241b50c7 |  | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
label | c85b74b4-9183-55a7-ae2f-345297038e49 |  | note | Standard / Specification - PS 15.1
label | ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f |  | note | Verifying Document - Engineers Approval
label | a960256b-958b-5eb6-af8e-bc4d99728fb0 |  | note | Frequency - Each Occurrence
label | 52fea67b-14ca-5826-8d8a-c11dc3466cf4 |  | note | Verification Activity: Activity - HP
label | 4b1848f4-9510-5def-95f4-d24b7a6c808e |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.06 - As-Builts
label | db708295-8b31-57be-bec5-77dab4401720 |  | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | a24bef18-ed19-5402-9911-8d0aa41611d7 |  | note | Standard / Specification - PS 15.11.7
label | 44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f |  | note | Verifying Document - Survey Records
label | b240b2d4-ab96-5982-84a2-2fd25825db00 |  | note | Frequency - During Earthworks
label | f0563e63-58d2-5281-99f2-223329a109a7 |  | note | Verification Activity: Activity - D
label | 0379ef52-f0a4-5de8-b838-16ad532332f7 |  | note | Verification Activity: By - SV
checkpoint-group |  |  | section | 6.02 Cutting and Subgrade
checkpoint-status |  |  | checkpoint | 6.02.01 - Cut slope inspections
label | f0c9e4d3-35fc-5484-b867-873378bcdcc6 |  | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
label | a5050965-657c-5cb4-ba54-29f7a81a36c0 |  | note | Standard / Specification - PS 15.10.2, PS 15.13
label | 0ca6644d-27bc-50cb-82c3-e9215beabdf8 |  | note | Verifying Document - Engineers Approval
label | ee095220-c54a-544f-8c85-d2e244c4a0fd |  | note | Frequency - Each Occurrence
label | 6854b9e5-08d8-53bf-b4c4-25cc08b491a4 |  | note | Verification Activity: Activity - HP
label | 3b8c7bd6-7173-5f1c-9873-a15adf5e3876 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.02 - Dewatering
label | 45ad7851-3863-514c-bd5d-d0013775f8f7 |  | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
label | 10bf3c53-35d3-54c6-aa6d-417ba63dc5da |  | note | Standard / Specification - PS 15.10.18
label | fbd2f8c6-64ab-5c47-af05-cb3418296a2c |  | note | Verifying Document - Site Records
label | bc3137ea-86db-5fc7-b231-fea3db637513 |  | note | Frequency - Ongoing
label | f642d9fb-44aa-5900-a964-19c664e82209 |  | note | Verification Activity: Activity - S
label | 83904629-984d-510e-b1a8-050717dedc6a |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
label | f3d10b4e-addd-5538-a957-2a37e0034faf |  | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
label | 2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b |  | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
label | 8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 |  | note | ○ Shear Vane Average minimum su: > 60kpa
label | 4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e |  | note | ○ Shear Vane Single test minimum su: > 50kpa
label | 3ff01897-8d7b-537a-9e0a-bdedcefe185a |  | note | ○ SCALA: Minimum 3 blows per 100mm penetration
label | 630d469c-d4b6-528c-8e3d-4302c9510b53 |  | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
label | 0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 |  | note | Verifying Document - Shear Vane or Scala Report
label | 85d3bae8-7bf8-56b3-9602-213fb78a5576 |  | note | Frequency - 4 test per 400M2
label | 55a69f30-35b2-5c05-9282-92604524f101 |  | note | Verification Activity: Activity - I
label | 8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.02.04 - Undercut Subgrade Compaction
label | f841e758-4cd2-5891-b08c-751a3c88b535 |  | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
label | 8fb02c88-5c79-5b58-a1dd-92a07552b833 |  | note | Standard / Specification - PS 15.10.4
label | a629293c-385f-5bce-b059-933f4c7d43dd |  | note | Verifying Document - Site Records
label | 2a96cae7-3c6a-51cb-9454-6091224f2d6f |  | note | Frequency - Prior to Backfilling
label | 4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 |  | note | Verification Activity: Activity - S
label | 9afabe93-cf7b-5ea2-9907-09925e3a24f2 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.02.05 - Soft Road Subgrade Areas
label | 6fd65fab-6193-5462-afeb-d69af1a8db96 |  | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
label | d76e99d9-c656-55e3-acb1-1c1df46f6945 |  | note | Standard / Specification - PS 15.10.4
label | 1be23212-e8df-5d9f-8313-9a5254ebe069 |  | note | Verifying Document - Notice
label | 1c0d6418-f406-5f50-950c-5444425f50bf |  | note | Frequency - When Encountered
label | 34656019-18b2-5fea-94d4-d598e2a8138a |  | note | Verification Activity: Activity - S
label | c035f040-40a1-576d-b193-c59e6a453dad |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.02.06 - Daily Earthwork Grading and Rolling
label | 8984ac7d-e1bb-57c5-a681-dc58d56356d3 |  | note | Acceptance / Conformance Criteria - Earthwork materials on site are sensitive to overworking in wet conditions. It is critical that all fill surfaces are graded and rolled at the end of each day’s work to prevent any ponding, erosion and potential softening of the structural fill.
label | 416ec768-064f-530b-a57e-145a8c004c54 |  | note | Standard / Specification - PS 15.6.4
label | bf95fb32-c647-53aa-b7f4-0e546b27403b |  | note | Verifying Document - Site Records
label | 24c2a60d-45ac-58c8-a99d-a8a30e9dd85e |  | note | Frequency - Daily
label | 49f92057-be72-5671-9aa9-7b3b87593047 |  | note | Verification Activity: Activity - R
label | 9ed53212-1e6c-58c5-a68f-c2728e7742fc |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.02.07 - Finished Surfaces
label | 9bec837e-b683-55ad-bd75-4a248c626262 |  | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
label | a6991efb-ab9a-5b99-bf23-cb2f8b77c50b |  | note | Standard / Specification - PS 15.6.8
label | be65fa83-a107-5342-9c6d-a54c8b435c69 |  | note | Verifying Document - Survey Records
label | 887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 |  | note | Frequency - Each Finished Surface
label | 157d7177-0edf-5110-9131-f02c3d9f1433 |  | note | Verification Activity: Activity - D
label | 1fe43a96-441d-52f3-9c61-b1ddff480ba2 |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
label | b64008e4-8e18-5171-b4ca-a72a0d91c282 |  | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
label | 677d8b3a-9fe5-5e7f-9e11-0862609e0580 |  | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
label | 9841c2a6-be7e-500d-bcca-506f57b64c31 |  | note | Verifying Document - Engineers Approval
label | 4e231911-13ab-5ecd-9b53-75b332d5bfb0 |  | note | Frequency - Prior to filling with 24h notice
label | c10bf413-07c4-5174-9e14-7c2fbcd9358d |  | note | Verification Activity: Activity - HP
label | 950b4e24-66ad-5e1f-946a-4eebbe8609ed |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.03 Filling General
checkpoint-status |  |  | checkpoint | 6.03.01 - Compaction Trials
label | 082af659-e5a1-5e55-bb14-86dcfa2c12cc |  | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
label | b932f253-0659-5483-8431-149e22a51f34 |  | note | Standard / Specification - PS 15.10.15
label | 0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 |  | note | Verifying Document - Trial Results
label | 5fa74afb-d11f-58b9-9267-b51498af3937 |  | note | Frequency - During Works before placement of each material.
label | 103d17fd-0df9-56e9-949a-dda4690eb715 |  | note | Verification Activity: Activity - R
label | 66efe4f8-ef07-5b70-852c-a42dccaab6c1 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 6.03.02 - Daily Earthwork Grading and Rolling
label | df995618-ec5c-52ac-bb34-bf80d218c209 |  | note | Acceptance / Conformance Criteria - Earthwork materials on site are sensitive to overworking in wet conditions. It is critical that all fill surfaces are graded and rolled at the end of each day’s work to prevent any ponding, erosion and potential softening of the structural fill.
label | 6e1990f4-1944-52f9-adc1-c56f6e23f059 |  | note | Standard / Specification - PS 15.6.4
label | dd521587-27b0-51b0-a5d0-24e9fa01953b |  | note | Verifying Document - Site Records
label | 442378b2-795b-5196-893f-c29d3d69eee0 |  | note | Frequency - Daily
label | 77503a2a-7c81-5b30-9e68-1ed134c05d3d |  | note | Verification Activity: Activity - R
label | 61621d38-6e44-5229-bb6a-1d9f4d0cb4e7 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.03.03 - Surface Scarifying
label | 0ed24745-c07b-583e-bab1-918484a3fcf6 |  | note | Acceptance / Conformance Criteria - Prior to commencement of filling operations, the previously graded and rolled surface shall be scarified or worked to prevent the formation of sub-standard, or weak layers within the fill.
label | f2acaa3e-a613-5262-ab61-2eb45808fb66 |  | note | Standard / Specification - PS 15.6.4
label | e3c95049-7b0f-5e5d-b815-97e54766a6ce |  | note | Verifying Document - Site Records
label | 9ba4ab12-463b-5cf6-83b5-2ff13e36ec88 |  | note | Frequency - Prior to commencement of filling operations
label | a886b71a-9ea3-532b-aa9d-0e0d3d2038e2 |  | note | Verification Activity: Activity - R
label | 14af5504-d32e-597d-9485-05036e84c49f |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.03.04 - Geotextile on Undercut to Waste and Backfill
label | b66a3f7f-c101-55fc-a488-65023d32f225 |  | note | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
label | 39fe306a-53bb-58ff-84b4-d25744279b95 |  | note | Standard / Specification - PS 15.10.9
label | 2215bfc9-484e-5f67-adce-6df3c540172a |  | note | Verifying Document - Site Records
label | 2d33a3f7-a446-54bb-a02a-dbae2920cdbb |  | note | Frequency - Prior to Backfilling undercuts
label | 8477f682-7f40-53b2-9c76-46de57fde771 |  | note | Verification Activity: Activity - R
label | f661c483-12d8-5268-8d41-625af8658963 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.03.05 - Conditioning
label | d74afa4d-f935-570e-94d3-8483c0bf8c68 |  | note | Acceptance / Conformance Criteria - Prior to compaction, the fill materials shall be spread uniformly in horizontal layers and, if necessary, uniformly conditioned to an appropriate water content by aeration and drying or wetting and/or by blending and mixing suitable “wet” and “dry” materials and/or by lime and/or cement treated. Where drying of the soils is required, the Contractor shall disc the soil and allow it to dry uniformly to its full depth before compaction.
label | bfe2829b-4969-5002-be23-7f6c1135e726 |  | note | Standard / Specification - PS 15.10.13
label | bd9340b3-fae2-5a14-9f43-f8ec2baa64b6 |  | note | Verifying Document - Survey Records
label | dfba2370-1846-5844-b67a-07f1a1549078 |  | note | Frequency - Prior to compaction
label | 575e4689-c914-502d-b256-d7853a600a03 |  | note | Verification Activity: Activity - R
label | e7b8c790-811c-5f65-bcef-84b37c54a358 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.03.06 - Weaving or Pumping
label | bd1991d0-5093-5804-aff8-c52b44e7385d |  | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
label | e605ba42-46c5-5a4e-888c-2477e598e0b8 |  | note | Standard / Specification - PS 15.10.16
label | d39f9c2c-ed77-5b28-9068-8d5502076351 |  | note | Verifying Document - Site Records
label | 68e095e6-4a9f-530e-83a7-48b3803bce4c |  | note | Frequency - When encountered
label | 27e7c1ea-82b6-5046-a56c-510159c3d998 |  | note | Verification Activity: Activity - S
label | ed838f5a-7bf1-5227-8006-76b8f7af37f3 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.03.07 - Finished Surfaces
label | 3070b6ed-33d2-59d9-86fa-a87d75982015 |  | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
label | 3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f |  | note | Standard / Specification - PS 15.6.8
label | 816b2da5-1e05-56ee-b0d4-f4dad76d85e7 |  | note | Verifying Document - Survey Records
label | 41c5a73c-3d7a-5d08-99a6-a6c30a41296c |  | note | Frequency - Each Finished Surface
label | d8403246-e1a7-5f1e-a63f-c616a6f86317 |  | note | Verification Activity: Activity - D
label | 6183135d-77a3-5020-94fc-7c8fb634a0f3 |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
label | 929f9aa7-dcab-55ef-848e-e713dd5186b9 |  | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
label | a0d0e862-2504-55af-b439-f3f7356c1fcf |  | note | Standard / Specification - PS 15.13
label | 51f6149e-c97b-5a09-af39-5267730b4dd8 |  | note | Verifying Document - Engineers Approval
label | 1d64599f-c05f-5017-bfc2-421633c38bf0 |  | note | Frequency - Prior to placing topsoil or track rolled fill.
label | ec8638c9-6512-5db2-95d2-d6d3f35119b8 |  | note | Verification Activity: Activity - HP
label | 72c74c91-2072-5a09-8013-ca846e10480a |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
checkpoint-status |  |  | checkpoint | 6.04.01 - Imported Structural Fill Layers
label | 6878fdaf-0bcd-5db1-a513-1fc0df376bbf |  | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
label | 8b06cea0-2762-5a10-b343-8660f98e0189 |  | note | Standard / Specification - PS 15.10.14
label | 1a89ef0a-9801-51bc-aee0-85e181a5627d |  | note | Verifying Document - Site Records
label | 30797fec-d05d-5e1d-9407-2ca3ce812dbc |  | note | Frequency - Each Layer
label | e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 |  | note | Verification Activity: Activity - R
label | d72c325b-87d7-5b7a-abca-566cc22d1211 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.02 - Surface Scarifying
label | fe1a94d5-5552-5cca-8c7c-16926a35b5f8 |  | note | Acceptance / Conformance Criteria - When the fill operation has ceased in any area for more than 8 hours, then immediately before recommencing the fill operation, the fill surface shall be scarified to a depth of 100mm, conditioned and compacted to achieve the required standard of compaction.
label | e615373f-2db6-5207-8ff1-239417fb42e4 |  | note | Standard / Specification - PS 15.10.14
label | 218828ab-54bc-5918-a6a9-f99ba5b8e165 |  | note | Verifying Document - Site Records
label | 22690e79-2427-5d90-9229-00235a53b51e |  | note | Frequency - Each Occurrence
label | 82437048-2ef3-576b-9f29-aa94afe252e6 |  | note | Verification Activity: Activity - R
label | b22a0b72-7ef7-5e4c-bbb6-d4c65442a668 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
label | 33972346-eaf4-5b1b-adab-39ff4c57e4e4 |  | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
label | 8d53921a-09d5-5ddd-b361-6ff29682cbca |  | note | ○ Minimum CIV = 18
label | c3c1296c-564e-5332-8f97-a1742c8a6a85 |  | note | ○ Average CIV= 20
label | b21d6bc2-fa63-5bc1-8d96-b05121b299af |  | note | Standard / Specification - Appendix XIII
label | 9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 |  | note | Verifying Document - Clegg Results
label | edfa4ec3-1fcc-5df9-ba9c-81716eabe644 |  | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
label | c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb |  | note | Verification Activity: Activity - I
label | e91737f2-9daa-590c-ba83-c4825556312f |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.04 - Non-Structural Fill Zone - Strength – Clegg Impact Value (CIV)
label | 9edd37d7-9376-551e-84f9-b888b8840c61 |  | note | Acceptance / Conformance Criteria - A1 Imported Non-Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
label | 5b2f902a-75e1-52ba-831a-286d435423d5 |  | note | ○ Minimum CIV = 10
label | 0d47f6a9-9a9c-5830-a715-20e29444a71c |  | note | ○ Average CIV = 12
label | cd8cbc5d-5199-51fe-8b4d-b38294c9026a |  | note | Standard / Specification - Appendix XIII
label | f92cde20-aba2-55da-8996-95fb4f00d9cf |  | note | Verifying Document - Clegg Results
label | 3987cf23-05e1-5604-91fa-7c85db88248f |  | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
label | 7cd5ddd4-8c1e-52f1-aeba-5f314cce96f9 |  | note | Verification Activity: Activity - I
label | 6c04cc44-a270-5c2c-903f-8ca50b667f73 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
label | 8538573c-cf3b-5d93-9368-25bca6185db5 |  | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
label | 0859020c-bdbe-53a9-aa8e-86fa06eb9044 |  | note | ○ Average >95% Of In-Situ MDD
label | d1330c35-522e-5ba6-999b-78f42cdedb3c |  | note | ○ Minimum >92% Of In-Situ MDD
label | f71ac2b1-40f1-5836-9882-b3e5ee872755 |  | note | Standard / Specification - Appendix XIII
label | 69d85f65-b61d-579d-940f-2b691894d755 |  | note | Verifying Document - NDM Results
label | 8ab19fa7-6aa1-5a12-b545-cf914fee74be |  | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | e2147c12-4568-5322-b418-283ae63070af |  | note | Verification Activity: Activity - I
label | 09a8aad4-3fc9-597d-b419-c865f36b4acc |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.06 - Solid Density
label | 0419e26d-8e73-55d6-8166-f030f49ff305 |  | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
label | 6b8338ea-3136-54bc-aec4-0e1145900e7a |  | note | Standard / Specification - Appendix XIII
label | 06771a40-5a5a-5d5d-8674-41bfaeebf1b9 |  | note | Verifying Document - Solid Density Lab Report
label | 69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da |  | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
label | 19c9408e-b96a-516b-b78e-a5dd3fe8565c |  | note | Verification Activity: Activity - I
label | 5540bb1d-6af1-5d75-a199-fe2a1662c21b |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.07 - Organic Content
label | f09d0ff0-01ec-50cb-9988-3a078371cb3d |  | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
label | 5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 |  | note | Standard / Specification - Appendix XIII
label | ea12d870-db9e-5048-94de-56f316678975 |  | note | Verifying Document - Site Records
label | 4b4f2a35-1e50-5341-80c6-541a73664b53 |  | note | Frequency - Ongoing
label | f77c9bbc-fb8f-5e0f-86c9-c66a4643254e |  | note | Verification Activity: Activity - I
label | dbb35f07-7f2f-5414-a8b4-c69adbcef37c |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.04.08 - Completed Fill Approval
label | cb670aff-3430-5d2c-ac3e-1482548f09ee |  | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
label | e3ea5880-55a7-54a4-9ee9-9323b972ab79 |  | note | Standard / Specification - PS 15.13
label | eb4e4dcc-9679-50a0-8275-a70670f63fd0 |  | note | Verifying Document - Engineer Approval
label | 5b1465a0-9c5b-51b0-8b4b-9694e85f2324 |  | note | Frequency - Prior to Pavement Construction
label | a3b40c94-fe59-5b33-bcda-878d287d2995 |  | note | Verification Activity: Activity - HP
label | 696e1611-579b-5ae6-b3d8-5701063db1b8 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.05 LANDSCAPE FILL
checkpoint-status |  |  | checkpoint | 6.05.01 - Cohesive Fill Layers
label | c352122b-b969-515a-bd14-4ee2d6d77a2c |  | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work.
label | eb2c9836-d46b-5735-a171-5b7c260a8373 |  | note | Standard / Specification - PS 15.10.16
label | 16c87f21-2b6f-5a9e-950f-ce52726911a4 |  | note | Verifying Document - Site Records
label | f997564b-0a06-59cc-aaf8-0d04c169bb65 |  | note | Frequency - Each Layer
label | 48daa9bc-dbe2-5457-aa35-ebb3d2f05eee |  | note | Verification Activity: Activity - R
label | a63751f3-0140-5d7c-80c1-864752f123ce |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.02 - Fill surfaces Sealing
label | a578d34e-40e1-5c0c-b225-25282dfa3822 |  | note | Acceptance / Conformance Criteria - All fill surfaces shall be sealed at the end of each day’s work.
label | 275dad26-4948-57bc-bc5d-25291c4dfe04 |  | note | Standard / Specification - PS 15.10.16
label | bf910f9a-c5f9-5501-bd00-480e205a15ef |  | note | Verifying Document - Site Records
label | cd655ab2-4234-580a-b1d2-e5f8d0f9c64b |  | note | Frequency - Each Day
label | 5b4f0479-5692-504d-98b2-93cf71280de9 |  | note | Verification Activity: Activity - R
label | a00280e8-d9ac-5f5e-86c0-a351a10dc28a |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
label | 8e28b866-fa38-519b-918f-3d14bb22ecfb |  | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
label |  |  | note | ○ Average Maximum Air Voids < 8%
label |  |  | note | ○ Single Test Maximum Air Voids< 10%
label | b6a6dfee-f164-5998-9bdb-0af48b5f824e |  | note | Standard / Specification - Appendix XIII
label | bebdea1e-dece-5fe9-9b48-a107125b16b9 |  | note | Verifying Document - NDM Results
label | e003f7a2-352b-5d80-9fd5-e44eddfe06fe |  | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | 3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 |  | note | Verification Activity: Activity - R
label | da65e1bd-770b-59ad-9793-ebeab9e626dd |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.04 - Non-structural Fill – Shear Strength (SU)
label |  |  | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
label |  |  | note | ○ Average Minimum Su > 60kPa
label |  |  | note | ○ Single Test Minimum Su > 50kPa
label |  |  | note | ○ Scala: Minimum 2 Blow Per 100mm up to 1.0m deep
label |  |  | note | ○ Shear vanes and scala's not applicable where cohesive soils are mixed with granular material
label |  |  | note | Standard / Specification - Appendix XIII
label |  |  | note | Verifying Document - Shear Vane or Scala Results
label |  |  | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.05 - Non-Structural Fill - MDD
label |  |  | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
label |  |  | note | Standard / Specification - Appendix XIII
label |  |  | note | Verifying Document - NDM Results
label |  |  | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
label |  |  | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
label |  |  | note | Standard / Specification - TNZ F1 Section 10.5.1
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Formation level
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.07 - Organic Content
label |  |  | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
label |  |  | note | Standard / Specification - Appendix XIII
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Ongoing
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.08 - Water content
label |  |  | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
label |  |  | note | Standard / Specification - Appendix XIII
label |  |  | note | Verifying Document - Water Report
label |  |  | note | Frequency - Every NDM
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
label |  |  | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
label |  |  | note | Standard / Specification - Appendix XIII
label |  |  | note | Verifying Document - Lab Report
label |  |  | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 6.05.10 - Topsoil Placement Inspection
label |  |  | note | Acceptance / Conformance Criteria - Inspect the cut surfaces prior to the placement of topsoil and planting - tolerance of +/- 50mm
label |  |  | note | Standard / Specification - PS 15.13
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Prior to Topsoil
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.06 Settlement Monitoring
checkpoint-status |  |  | checkpoint | 6.06.01 - Settlement Monitoring Methodology
label | 55cd879c-55fc-5cf6-ac3c-be63cb59295d |  | note | Acceptance / Conformance Criteria - The Contractor shall submit details of their proposed monitoring equipment and installation methodology within their Earthworks Management Plan for the Engineer’s Approval.
label | e81a1f0f-e781-525e-8c33-4e23315d1115 |  | note | Standard / Specification - PS 15.12.5
label | 3d5ed6b8-8e4c-545a-9b90-7b60919dd913 |  | note | Verifying Document - Approved EMP
label | ef9455b2-30f0-545d-a18d-d1e03ec6a2d5 |  | note | Frequency - Prior to Works
label | bbd43815-e554-5e0c-8e5b-3ca67662ee30 |  | note | Verification Activity: Activity - HP
label | 258d068c-dd4d-5efc-a8bb-531c5d1e9410 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.06.02 - Supply, Install, Survey and Remove and Monitoring Equipment
label | f3fece7f-2a75-51d9-ab8c-3818abf85f3f |  | note | Acceptance / Conformance Criteria - The Contractor shall install geotechnical instrument systems in the positions shown in the Contract Drawings unless otherwise instructed by the Engineer.
label | f5b4da39-18a7-50fa-81bb-119512aa3245 |  | note | Standard / Specification - PS 15.12
label | f2f8a813-1fd2-5f2e-8fb2-868eac6068eb |  | note | Verifying Document - Site Records
label | 51df963b-9897-5abb-94e9-92f9a247955d |  | note | Frequency - Prior to Construction
label | 68391c45-455a-5051-9344-65d8f1c811eb |  | note | Verification Activity: Activity - I
label | 160f22c6-6304-5fea-b1ab-230125cb63ef |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 6.06.03 - Instrument Reading Notice
label | 6f87da36-7041-5714-aab1-a9d1a3d4eb69 |  | note | Acceptance / Conformance Criteria - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
label | e3bc3f60-11df-5986-8e49-8f95bf3b526c |  | note | Standard / Specification - PS 15.12.5
label | d1a19be7-e1d3-5547-8909-138345432d0b |  | note | Verifying Document - Site Records
label | 1f9dbbe2-04ff-5485-ae11-50ba7690ec6a |  | note | Frequency - Prior to Survey
label | fe3add51-08eb-5bf7-8e2f-9257106320fe |  | note | Verification Activity: Activity - HP
label | 78d1467f-a870-5168-8aca-e0fc839d8ecc |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.06.04 - Base Readings, Responsibility and Ownership
label | 26de447a-be80-5db7-9fed-a5598df339e2 |  | note | Acceptance / Conformance Criteria - Following installation, the Contractor shall undertake testing to demonstrate the instruments are working properly. The Contractor shall submit records of each of the instruments showing location, soil conditions encountered, installation details and initial readings. Construction will not be permitted until the Engineer is satisfied that the instruments are working correctly.
label | 3dac7c57-2fd9-5583-b22e-1c9daad809d8 |  | note | Standard / Specification - PS 15.12.2
label | 57fbadc8-856e-59ea-9c0b-6a4ad79abd98 |  | note | Verifying Document - Site Records
label | 887d2697-0438-5748-9d92-50071d9dcfaf |  | note | Frequency - Prior to Construction
label | 172ad8cb-f559-5105-bb7d-9fce0c280ca5 |  | note | Verification Activity: Activity - HP
label | e13218bd-7f4d-5ce9-9578-5fc34d2a157d |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.06.05 - Pin Protection
label | 05377e32-4d4d-5ac9-85e7-88b011824a6c |  | note | Acceptance / Conformance Criteria - The Contractor shall ensure the Pins are protected and not disturbed in any way once constructed. The Contractor shall also install settlement survey stations at locations protected from Construction traffic and works.
label | 5d18b3db-6402-5696-83e5-db181b003227 |  | note | Standard / Specification - PS 15.12.5
label | 05cd1b8f-838a-5ded-9ab1-8a0bccdc8b88 |  | note | Verifying Document - Site Records
label | 89614663-9ee1-5f54-80d8-09f62996a296 |  | note | Frequency - Ongoing
label | 96cac559-a2d0-5e18-bd1c-8c5f91f83364 |  | note | Verification Activity: Activity - R
label | 3f8e7bef-6f86-5244-b41d-7c1991bd3106 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 6.06.06 - Monitoring
label | 1d838e30-c9ec-58bc-8841-43d057802429 |  | note | Acceptance / Conformance Criteria - Following the active fill of the embankment, the Contractor shall read all monitoring pins bi weekly. Monitoring frequency may be reduced to weekly intervals when there is no active earthworks in that area, and while waiting for embankment to settle.
label | ab916766-b8ca-5614-a3be-61f3ef5ce0a5 |  | note | Standard / Specification - PS 15.12.5
label | 5a8987e1-beb5-5285-9626-14c6d4b752e3 |  | note | Verifying Document - Survey Records
label | 6fa587b6-07fd-53aa-b98e-c9e5af40fc7a |  | note | Frequency - Bi Weekly following Embankment Filling
label | a7929d20-4291-5176-920f-7926ba3c34af |  | note | Verification Activity: Activity - R
label | c2010ee4-fd12-508a-ae38-dccfae200836 |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 6.06.07 - Engineers Review
label | d77b11fc-070b-50e1-8629-958659ff4f44 |  | note | Acceptance / Conformance Criteria - The Engineer will review the results of the settlement monitoring to assess completion of the preconsolidation period. This period is anticipated to be less than 3 months.
label | cf3d110b-7081-5043-99cf-c1c5e1e82116 |  | note | Standard / Specification - PS 15.12.5
label | 88313476-05c6-574c-be37-84b542b7c1ff |  | note | Verifying Document - Survey Records
label | aba9f8b6-25d1-5e33-9124-ff7cef034c4a |  | note | Frequency - Ongoing
label | 53867a85-e95a-5618-87e7-f9eec85edf34 |  | note | Verification Activity: Activity - R
label | 49b6db7c-780d-5c5a-b85b-ffd17e3d8432 |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 6.06.08 - Pore Water Dissipation
label | 75ceb013-f0cb-5b7e-af80-af6640b2d53d |  | note | Acceptance / Conformance Criteria - Review of settlement pins data to confirm sufficient pore water dissipation has occurred in the soft soil layer.
label | 1e5ba5db-1e50-52e5-a141-a55015b8ec11 |  | note | Standard / Specification - PS 15.13
label | 6d539e72-2e15-54ff-a874-531eefc30c8a |  | note | Verifying Document - Engineers Approval
label | bde27891-0f79-54b4-bce1-6e40158e43bd |  | note | Frequency - Prior to completing Monitoring
label | 1f4973ca-c9c2-5289-b401-f542f7e282e3 |  | note | Verification Activity: Activity - HP
label | c3e2a4d3-85b0-50f8-aab3-5c691c2e24f6 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.06.09 - Settlement Monitoring Termination
label | f89d107c-7f62-5edf-ba7c-a0e330bfb041 |  | note | Acceptance / Conformance Criteria - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
label | 2d0e1d42-bc4c-5ffc-a6ec-30a5d4d6670d |  | note | Standard / Specification - PS 15.12.7, PS 15.13
label | 95432c0f-587e-557b-a06a-d2c1de6b3656 |  | note | Verifying Document - Engineers Approval
label | e1dd00fe-0aed-5bbc-9759-328a6cb6ca36 |  | note | Frequency - Prior to completing Monitoring
label | f1a09b53-7a5d-50a9-8933-50232be4a599 |  | note | Verification Activity: Activity - HP
label | adfba00d-f5d8-5f2d-a739-d023b0e4a01c |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT