## Enabling Works
Site Location |  |  | Aspiring Avenue RAB
Enabling Works - Footpath, Kerb and channel
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Materials
2 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Everysite | Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 | Inprocess Inspection | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
3 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | Inprocess Inspection | FH concrete QA sheet, Photos | Site Engineer
CIVIL WORKS | [8 empty] | =
4 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
5 | Tactiles |  | TDM Technical Standards - FP0010 | Each PX | Warning TGSI tiles should have 150mm concrete slab underneath | Inprocess Inspection, Measurement | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
5.1 |  | Visual | NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | Inprocess Inspection` | Photos | Site Engineer
5.2 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Edge of warning indicators to set back 300mm from the face of the kerb or lane. | Inprocess Inspection | Photos | Site Engineer
5.3 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing | Inprocess Inspection | Materials Dockets | Site Engineer
6 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | Inprocess Inspection | Photos | Site Engineer
6
7 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Yeswanth Vemula | Initial | YV |  | Date: | 2023-05-01
Approving Delegate |  | Daniel Tat | Initial | DT |  | Date: | 2023-01-27

## Concrete Speedtable (hidden)
|  |  |  | Process Control Plan |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Halsey- Maich RAB |  | FH Engineer |  | SS
|  |  |  | Procedure: | Raised Pedestrian Crossing |  | FH Manager |  | DT
Inspection & Test Plan / Checklist
Detailed Location |  |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
Halsey-Maich RAB
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer/MSQA Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | H | Ensure that Sub-Contract and Supplier Agreements are signed | Prior to commencement | Document Review | Signed Subcontractor and Supplier Agreements | Subcontract and Supplier Agreements | Site Engineer
2.1 |  | H | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by CAR manager for each site and works are only completed within the approved dates.. | TMP on MyWorksites/On Site | Site Engineer
2.2 |  | H | Ensure all Sub-Contractors and Suppliers go through FH induction | On site daily | Induction | Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation | Hazard ID and Pre-starts to safety team | Site Engineer
3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Prior to commencement | Document Review | IFC drawings have been received by Contractor | Check Drawing Register | Site Engineer | Design Engineer
4 | Installation of Erosion and Sediment Controls | H | Ensure that Erosion & Sediment Control in place | Prior to commencement | Visual Inspection | Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence | Environmental Controls Audit | Environmental Manager/Site Engineer
5 | Survey Setout | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey + Smart Level | Consistency with Construction Drawing | Site Photos post surveying | Site Engineer
6 | Locate Existing Services by Hand Digging | H | Ensure all services conflicting with the line of trench has been exposed by hand digging | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | Digging and excavation checklist, service planes,As-Built Drawings Doc. Review | Site Engineer
7 | Material Compliance | H | LESA dowels to be used at all construction joints at 600mm clearance | Prior to pouring concrete | Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer
7.1 |  | H | 0.25mm polythene layer placed across all surface area at bottom of raised table | Prior to pouring concrete | Visual Inspection, Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer
7.2 |  | H | 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer. | Prior to pouring concrete | Visual Inspection | CIV >=25 | Delivery Dockets / Photos | Site Engineer
7.3 |  | H | Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
7.4 |  | H | All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder | Prior to pouring concrete | Concrete Delivery Dockets | Delivery Docket added to QA folder | Concrete Delivery Dockets | Site Engineer
8 | Temporary Works (Formwork) | W | Formwork to be set to correct line and level | Prior to pouring concrete | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
8.1 |  | H | Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15) | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.2 |  | H | Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.3 |  | H | Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.4 |  | H | Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road | Prior to pouring concrete | Measurement | Designer to inspect gradient level | Site photos / Concrete Formwork Checklist | Site Engineer | MSQA Engineer
8.5 |  | H | The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured | Prior to concrete pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
9 | Reinforcing | H | All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint | Prior to pouring concrete | Measurement | Concrete Inspection Record | Site photos/Concrete Formwork Checklist | Site Engineer | MSQA Engineer
10 | Concreting | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection | Engineer will be notified via email/SMS at least 24 hours before required for inspection | Email / SMS | Site Engineer
10.1 |  | W | Vibrator to be used throughout concrete pour | When pouring concrete | Visual Inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer
10.2 |  | H | Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top. | At completion of pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
11 | Curing | M | Concrete will be left for 48 hours minimum to cure before traffic is allowed on it. | Post Pour | Monitoring the time allowed for curing | 48 hours minimum have passed | Concrete Formwork Checklist | Site Engineer
12 | Remove formwork | W | Remove formwork after 48 hours | Post Curing | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer
13 | Asphalt- Concrete extension slab/ Toe | H | Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003 | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer
13.1 |  | H | 200mm thick 50MPa Concrete with two layers of 663 mesh | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer
13.2 |  | W | Tack Coat between AC and Concrete slab | Post Curing | Visual inspection | Photos + Delivery Docket added to QA folder | Site photos | Site Engineer
13.3 |  | W | 50mm thick DG10 / Mix 7 | Post Curing | Measurement | Photos + Delivery Docket added to QA folder | Site photos,delivery dockets | Site Engineer
14 | Lot Number QA File | W | Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file | At completion of Lot | Document Review | All QA files compiled and sumbitted to client | QA records | Site Engineer
14.1 |  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review | Delivery Dockets to be included in QA file | QA records | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer

## Stormwater
[7 empty] | Approved |  | Signature
|  |  |  | Contract Name: | Aspiring Avenue/Thomas Road Intersection |  | FH Engineer |  | YV
|  |  |  | Procedure: | Storm water Drainage |  | FH Quality Manager |  | DT
Inspection & Test Plan / Checklist
Job No:
Detailed Location:
Halsey- Maich RAB
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits & Services | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer
|  | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols | B4u dig plans & GPR report attached | Site Engineer
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep.
4 | Survey Set out | H | Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files | Survey Receipt. | Site Engineer
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP | Manufacturers Data Sheets, Delivery Dockets | Site Engineer
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. | As-built Drawings. Doc. Review | Site Engineer
7 | Trenching & Excavation | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016) | Prestart RCP | Site Engineer
|  | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | Site Engineer
|  | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | Site Engineer
8 | Bedding for Concrete Pipe Laying & Manhole & Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | Site Engineer
9 | Pipe Position Tolerance | M |  | At any point of pipe | ` | Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design. | FH Drainage Line Record, Survey Data. | Site Engineer
10 | Trench Backfill - Placing & Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm | Construction Photos | Site Engineer
11 | As-Built Drawings | W | Red pen marked-up As-Built of every 'Issued for Construction' AT drawings | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | Site Engineer | Engineers Rep.
Comments:
|  |  | Daniel Tat |  | Signature: |  |  | Date:
QA checked By Quality Manager:
[5 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep:

## Traffic Islands
ITP - Aspiring Ave RAB
Site Location |  |  | Aspiring Avenue RAB
Traffic Islands
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Everysite | Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint | Inprocess Inspection | FH concrete QA sheet, photos. | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Construction Drawings | Survey Receipt. | Site Engineer
3 | Concrete Island | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | Kerbs to be haunced with 20MPa Concrete | Inprocess Inspection | Photos | Site Engineer
|  | QA FORM | TDM Technical Standards - IS0001 & IS0003 | Each Site | Basecourse to be 150mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer
4 | Concrete Infil | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 180mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Asbuilts
5 | As built information | Drawings | = | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET | = | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Yeswanth Vemula | Initial | YV |  | Date: | 2023-05-01
Approving Delegate |  | Daniel Tat | Initial | DT |  | Date:

## Pavement
[7 empty] | Approved |  | Signature
|  |  |  | Contract Name: | Aspiring Avenue/Thomas Road Intersection |  | FH Engineer
|  |  |  | Procedure: | Pavement Construction |  | FH Quality Manager |  | DT
Inspection & Test Plan / Checklist
Job No:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Precom
1 | Permits & Services | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer
|  | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols | B4u dig plans | Site Engineer
|  | H | Approved TMP | Prior to any construction commencing | = | Approved TMP and WAP onsite befor establishing traffic management | TMP Plans | Site Engineer
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep.
SAC Pavement & Surfacing
4 | Bitumen | H | NZTA M/1 | Passing all tests listed in Table 1 of NZTA M/1 | Testing | Passing all tests listed in Table 1 of NZTA M/1 | IANZ Lab results | Site Engineer
5 | Asphalt Mix Design | H | JMF approved |  | Review | AUSTROADS |  | Site Engineer
6 | Production Tests | M | NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P (M/10 Table 5.1)/ | 1 set every 300t | Review | NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature | IANZ Lab results | Site Engineer
7 | Check Weather Reports | W | No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius | Weather call the day before | Visual | Forecast and thermometer | Radar and Asphalt QA | Site Engineer | Design Engineer
8 | Pre-Seal Inspection | H | Surface finish | Continuous | Visual | The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp | Sealing QA | Site Engineer
9 | Tack Coat | M | Minimum residual binder application of 0.3l/m2 | Each Run | Testing & Visual | Each spray of bitumen | Asphalt QA | Site Engineer
10 | Construct 50MM PMB AC14 | M | NZTA M/10 NDM and Stringline | Each Run | Testing & Visual | Construct 50mm PMB AC14 . - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10 | Asphalt QA | Site Engineer
11 | Construct 50MM HF AC14 | M | NZTA M/10 NDM and Stringline | Each Run | Visual | Construct 50mm PMB AC14 in 1layer | Asphalt QA | Site Engineer
12 | Two coat Grade 3/5 racked -in seal Grade 4 Membrane | M | Construct a two-coat Grade 3/5 racked in seal or G4 membrane (min residual bitumen application rate of 1l/m2) | Continuous | Testing & Visual | Tank dip tests before and after application to confirm application rate. Additional PTR rolling to imbed the aggregates into the bitumen | Chipseal QA Photos | Site Engineer
16 | Construct 80MM AC 20 | M | NZTA M/10 NDM and Stringline | Each Run | Testing & Visual | Construct 80 MM AC20. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10 | Asphalt QA | Site Engineer
17 | Benkelman Beam deflection testing - (If Required) | M | NZTA M/10 NDM and Stringline | Each Run | Testing & Visual | where Benkelman Beam deflection is greater than 2.4mm and less than 3.0 mm, excavate further 70mm depth, place an ARG GEOGRID on top of exposed subbase and replace with 70mm AC20 Asphalt and static roll. | Asphalt QA | Site Engineer
18 | Clegg Hammer testing | M | Design is approved and Drawings are of the latest revision. | Every 10 M intervals | Testing & Visual | CIV>=32 | Asphalt QA/Photos | Site Engineer
19 | Surface Finish | W | TNZ P/9P | Each Lot | Visual | Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate | Photos | Site Engineer
20 | Reinstatement of Linemarking and RRPM's | M | NZTA M7 approved (Class B or C as required for anticipated traffic level) | Every site | Visual | *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated | Photos | Site Engineer
Comments:
[5 empty] | Signature: |  |  | Date:
QA checked By Quality Manager:
[5 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep:

## Round about
Halsey- Maich RAB
Roundabout
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Construction
1 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Drawings | Survey Receipt. | Site Engineer
2 | Concrete Roundabout - Central Island | QA FORM/ Drawings | Construction Drawings | Each Site | Standard precast kerb to be hand-laid with 120mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Basecourse , with CBR>5 | Inprocess Inspection | Photos | Site Engineer
|  | QA FORM/ Drawings | Construction Drawings | Each Site | Central island to have 150mm GAP 65 Granular base course on removed pavement surface. | Inprocess Inspection | Photos | Site Engineer
3 | Concrete Infill - Central Island | QA FORM | Construction Drawings | Each Site | 180mm depth of 20MPa Unreinforced Concrete with 3kg/m3 red oxide and Broom Finish | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
4 | Apron | QA FORM/ Drawings | Construction Drawings | Each Site | Slip formed 25Mpa fibre reinforced concrete for roundabout edging | Inprocess Inspection | Photos | Site Engineer
|  | QA FORM/ Drawings | TDM Technical Standards - IS0007 | Each Site | Kerbs to be sitted on 300mm Min AP40 Sub Basecourse , with CBR>5 | Inprocess Inspection | Photos of smart level/ Asbuilts | Site Engineer
|  | QA FORM/ Drawings | Construction Drawings | Each Site | Apron to have 2% min fall towards the road and 2 m wide throughout. | Inprocess Inspection | Photos of smart level/ Asbuilts | Site Engineer
|  | QA FORM/ Drawings | TDM Technical Standards - IS0007 | Each Site | Apron to have 50mm thick AC14 HF with 0.25mm Polythene layer on top below concrete | Inprocess Inspection | Photos of smart level/ Asbuilts | Site Engineer
|  | Concrete Dockets | Construction Drawings | Each Site | 195mm depth of 40 Mpa concrete with 4kg/m3 Black oxide and Broom Finish | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Asbuilts
7 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
7 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Cimyona | Initial | CV |  | Date: | 2022-02-04
Approving Delegate |  | Daniel Tat | Initial | DT |  | Date: | 2022-02-04

## Signage
Halsey- Maich RAB
Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT - | Survey Receipt | Site Engineer
Materials
2 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Every site | All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers. | Inprocess Inspection | Dockets/Photos | Site Engineer
3 | Pole, Impact recovery post and Ground Socket | QA FORM | TDM Technical Standards | Every site | Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep | Inprocess Inspection | Dockets/Photos | Site Engineer
Construction
4a | Ground Socket | QA FORM | TDM Technical Standards | Each Socket | The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket. | Inprocess Inspection | Dockets/Photos with tape measurement | Site Engineer
4b | Pole and Impact recovery post | QA FORM | TDM Technical Standards | Each Post or pole | All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation | Inprocess Inspection | Dockets/Photos | Site Engineer
5 | Signs/Belisha Disk | QA FORM | TDM Technical Standards | Each Sign | All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately. | Inprocess Inspection | Dockets/Photos | Site Engineer
Asbuilts
#REF! | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | YV |  | Date: | 2023-03-30
Approving Delegate |  | Nithin Thomas | Initial | SS |  | Date: | 2023-03-30