## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Site Establishment
CHECK-003 Site Establishment | checklist |  |  | Tier 2: Site Establishment Checklist
CHECK-002 Site Inspection | checklist |  |  | Tier 2: Site Inspection Checklist
| step |  |  | Tier 1: Daily Prestart
CHECK-006 Daily Prestart | checklist |  |  | Tier 2: 26/03/2024
CHECK-006 Daily Prestart | checklist |  |  | Tier 2: 27/03/2024
| step |  |  | Tier 1: Toolbox Talks
FORM-001 Tool Box Talks | checklist |  |  | Tier 2: 26/03/2024
FORM-001 Tool Box Talks | checklist |  |  | Tier 2: 27/03/2024
010SAF_08 SWMS | checklist |  |  | Tier 1: SWMS
| step |  |  | Tier 1: Dry Fire
| step |  |  | Tier 2: Conduits in Slab
ITPS-012 In Slab Conduit Installation | checklist |  |  | Tier 3: Zone 1
ITPS-012 In Slab Conduit Installation | checklist |  |  | Tier 3: Zone 2
ITPS-012 In Slab Conduit Installation | checklist |  |  | Tier 3: Zone 3
| step |  |  | Tier 2: Rough In
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 1
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 2
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 3
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 4
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 5
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 6
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 7
| step |  |  | Tier 2: Fit Off
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 1
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 2
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 3
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 4
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 5
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 6
ITPS-003 Fire Alarm and EWIS Installation | checklist |  |  | Tier 3: Zone 7
| step |  |  | Tier 2: Alarms and EWIS Commissioning
ITPS-004 Fire Alarm and EWIS Commissioning | checklist |  |  | Tier 3: Zone 1 & 2
ITPS-004 Fire Alarm and EWIS Commissioning | checklist |  |  | Tier 3: Zone 3
ITPS-004 Fire Alarm and EWIS Commissioning | checklist |  |  | Tier 3: Zone 4 & 5
ITPS-004 Fire Alarm and EWIS Commissioning | checklist |  |  | Tier 3: Zone 6 & 7
| step |  |  | Tier 2: Fire Panel Fit Off
ITPS-016 Fire and EWIS Panel Installation | checklist |  |  | Tier 3: MFIP
ITPS-016 Fire and EWIS Panel Installation | checklist |  |  | Tier 3: SFIP Substation
ITPS-016 Fire and EWIS Panel Installation | checklist |  |  | Tier 2: EWIS Panel Fit Off - MECP
| step |  |  | Tier 1: Wet Fire
| step |  |  | Tier 2: Fire Sprinkler Rough In
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 1
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 2
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 3
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 4
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 5
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 6
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 7
| step |  |  | Tier 2: Fire Sprinkler Fit Off
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 1
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 2
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 3
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 4
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 5
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 6
ITPS-008 Sprinkler Installation | checklist |  |  | Tier 3: Zone 7
| step |  |  | Tier 2: Fire Sprinkler Commissioning
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 1
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 2
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 3
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 4
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 5
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 6
ITPS-009 Sprinkler System Commissioning | checklist |  |  | Tier 3: Zone 7
| step |  |  | Tier 2: Fire Sprinkler Pressure Test
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 1
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 2
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 3
| step |  |  | Tier 2: Fire Hydrant Installation
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 1
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 2
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 3
| step |  |  | Tier 2: Fire Hydrant Pressure Test
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 1
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 2
ITPS-011 Pipework Pressure Testing | checklist |  |  | Tier 3: Zone P/T 3
ITPS-014 Diesel Fire Pumpset Installation and Commissioning | checklist |  |  | Tier 2: Fire Pumpset Installation
ITPS-015 GM Tank Installation | checklist |  |  | Tier 2: Fire Tank Installation