## Table 1
Project | 21/22 Pavment Rehabs SH30 Ruato Rock Bluff - RS158 / RP10494 - 11033 Waka Kotahi NZTA | [12 empty] | ITP No.:
Client | [13 empty] | Revision : | 1
Description of Work | Cement modified / Overlay M4AP40
Prepared By | Akshad Patle |  |  | Reviewed By | John Kahu |  |  | Approved By | [5 empty] | Date: | 2023-03-15
Current Version:
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C, E or Sp |  |  |  | Y/N | Y/N | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
1. Procurement
Design
What do we need to do to comply with the specification? e.g. approval of materials such as concrete etc. | Geometric Design | Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual | Principal Approval | Contractor and Principal peer review | per design revision | Contract / Rehab Manager |  | C or S |  | C | E | Y
| Pavement Treatment Design | Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Principal Approval | Contractor and Principal peer review | per design | Contract / Rehab Manager | Approvals Register - Pavement Rehabilitation Design Report | C or S |  | C | E | Y
Materials: GAP 65 Pre‐treatment Material
| Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | C or S |  |  | S | N | N
| Source Property Test | CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Soaked CBR ≥ 40 | Soaked CBR test (NZS:4407:2015:3.15) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | N | Y
| Production Property Test | Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Sand Equivalent Test (NZS:4407:2015, 3.6) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | N | Y
Materials: M/4 AP40 Basecourse Material
| Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet
| Source Property Test | Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | less than 10% fines passing 2.36mm sieve size under a load of 130kN | Curshing Resistance Test (NZS 4407:1991, Test 3.10) | One test for every 10,000m³ of source material | Quality Controller/ Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y | Y
|  | Weathering Quality Index (3.3.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | AA, AB, AC, BA, BB or CA | Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | One test for every 10,000m³ of source material | Quality Controller/ Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y | Y
|  | California Bearing Ratio (3.3.3) ‐ TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Soaked CBR ≥ 80% | California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | One test for every 10,000m³ of source material | Quality Controller/ Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y | Y
| Production Property Test | Sand Equivalent (4.2.1.1) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006 | Quality Controller/ Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y | Y
|  | Broken Face Content (4.2.2) ‐ TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Broken Face Test (NZS:4407: 1991, Test 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006 | Quality Controller/ Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y | Y
|  | Particle Size Distribution (4.2.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006 | Quality Controller/ Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y | Y
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C, E or Sp |  |  |  | Y/N | Y/N | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
Materials: Cement
| Stabilising Agent Selection | Cement (4.1.2) - TNZ B/5: 2008 | GP | Visual inspection of supplier docket | per truck load | Quality Controller/ Supervisor | Supplier Docket Supplier Cert | Sp or S |  | Sp or S | C | Y | Y
Materials: Water
| Water draw for stabilising | Water (5.0.0) - TNZ B/5: 2008 | Free from impurities justified by use of municipal water supply | Visual inspection of hydrant use form | per truck load | Quality Controller/ Supervisor | Hydrant use form | Sp or S |  | Sp or S | C | Y | Y
2. Pre-Implementation
What planning and documentation is needed before we commence operations | Work Pack complete and held on site | ..\Work Pack | [5 empty] | C |  | C | C | N | Y
| Communication Plan implemented | ..\4.5 CSCMP | [5 empty] | C |  | C | C | N | Y
| Are any consents /approvals required, including for taking water. | Hydrant Use form | Forms available for applicable days | Visual inspection and recording | Daily as required | Supervisor | Hydrant Use Form | S |  | S |  | N | Y
| Quality Control forms on site | RQP, ITP, Scala Penetrometer Test Records, Material test sheets etc. | Visual Confirmation |  | Daily as required | Supervisor |  |  | C |  |  | N | N
| Person(s) on site with authority to stop work if quality of final outcome is compromised for any reason | QMP | At least one nominated staff member on site at all times |  |  | Site Supervisor, Quality Controller, Engineer | Pre-start sheets, timesheets | C or S |  | S |  | N | N
| On site Prestart Meeting | Site design information - Earthworks plan - design drawings. | Visual confirmation and walk over - confirm associated works -verify extent of works - verify digouts or additonal items | Visual inspection and recording- variation approval process | Prior to any phyusical work engagement | Supervisor | Design alteration variation ACCPETANCE | S |  | S | E | Y | Y
| Records Management (i.e. it is known what documented records are to be kept) | ITP and QMP state what quality documentation is required | Filled in and Signed ITP | Visual inspection, recording and approval | As per hold points in collaboration with the programme | Quality Controller | ITP | C |  | C | E | Y | Y
2. Temporary Works (including Traffic Management, Environmental and Health and Safety Controls)
What do we need to do to comply with the drawings? e.g. erection of formwork, traffic management etc . | Traffic Management Approved / Implemented (copy in Job Pack on-site) | Site Specific TMP, COPTTM, Higgins TTM SOP, SCR Form | Passing SCR audits | Visual inpsection and recording |  | STMS | Site Specific TMP, SCR | C | C | C | C | N | Y
| Environmental controls in place (Seal of Existing Catchpits or storm water line) | HSE Audit, JSEA |  |  |  | Site Supervisor | HSE Audit, JSEA | C | C | C | C | N | Y
| Health and Safety controls in place (e.g. Isolate work area) | HSE Audit, JSEA |  |  |  | Site Supervisor | HSE Audit, JSEA | C | C | C | C | N | Y
| Standard Operating Procedures / JSEAs available on site | HSE Audit |  |  |  | Site Supervisor | HSE Audit | C | C | C | C | N | Y
| Any service covers or utilities identified and protected to Service Authorities expectations | PTW Process, B4UDIG | Work always undertaken under live PTW | Visual inpsection and recording | Weekly | Permit Issuer | PTW | C | C | C | C | N | Y
3. Stripping Existing Pavement and 250mm Pavement Layer ; Test Pits for Confirming SG @ RP 10.822m
What do we need to do to comply with the specification, drawings, and quality requirements during the construction process? e.g. placement of materials such as concrete, asphalt or fill material and required testing. | Saw Cut Exiting Pavment @ RP 10494 (Start) & RP 11033 (END) | SH30 - RS158 / RP 10494- 11033 - RUATO ROCK BLUFF DRAWINGS Sheet C01 & C05 | Visual Confirmation | Saw Cutter | Start and End of Site | Quality Engineer/Supervisor | Photographs | C | C | C | C | N | Y
| To confirm the requirement of Pre- treatment Repair | SH30 RUATO ROCK BLUFF - Design Report | Verifiy scala result against treatment type | Scala Penetrometer on Excavation Floor | As required | Quality Controller/ Supervisor | Scala sheet test result | C | C | C | E | Y | Y
4. Construction - Granular make up and In-situ Modification
| Plant and Machinery Seletion | Plant and Equipment (6.0.0) - TNZ B/5: 2008 | Cement Spreading Truck, Direct Injection Stabilising Mill, Vibratory Single Drum Roller and either; 1 Smooth Double Drum and 1 PTR or 1 Combination Roller | Visual Inspection | Pre-establishment | Supervisor | Daily Site Record | S |  | S | E | Y | Y
| Weather including temperature | Weather Limitations (7.1.1) - TNZ B/5: 2008 | Ambient air temp ≥5˚ C, Wind speed ≤25km/h, Rainfall ≤0mm | Visual Inspection, Met Service /Windy | Throughout process | Supervisor | Daily Site Record, Metservice | S |  | S | E | Y | Y
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C, E or Sp |  |  |  | Y/N | Y/N | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
What do we need to do to comply with the specification, drawings, and quality requirements during the construction process? e.g. placement of materials such as concrete, asphalt or fill material and required testing. | Spreading of Cement | Spreading of Cement (7.3) - TNZ B/5: 2008 | Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate | Mat test (1m² canvas) and Average Usage Test | per 400m² and upon emptying the spreader | Supervisor | Mat Test Form and truck dockets | S or Sp |  | S | E | Y | Y
| Addition of Water | Addition of Water (7.5) - TNZ B/5: 2008 | 90-100% OWC | Nuclear Densometer Testing prior to Stabilisation | ≥1 per 1000m² lot | Supervisor | NDM Record | S |  | S | C | Y | Y
| Cut Depth | Control of cut depth (7.6.1) - TNZ B/5: 2008 | -5mm and +15mm of design stab depth | Physical Measure and Visual Record | ≥1 per 200m of cut length | Supervisor | Photographs and Daily Site Record | S |  | S | C | Y | Y
| Tie in points: Existing Vehicle entrance points , Existing Dish Channel, Existing Valve @RP 10640 including start and end points | Austroads Guide to Road Design Part 3: Geometric Design, NZ3910 Variations TNZ State Highway Geometric Design Manual | Principal Approval | Physical Measure and Visual Record | Pre-physical work commencement | Supervisor | Design alteration variation ACCPETANCE | S |  | S | E | Y | Y
| Longitudinal Joints | Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008 | The greater of 100m or 50% of layer thickness | Visual Record | per sucessive cut | Supervisor | Photographs, Daily Site Record and Stabilising Plan | S |  | S | C | N | Y
| Continuity of Layer | Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008 | Longitudinal overlap 1m | Visual Record | per sucessive cut | Supervisor | Photographs, Daily Site Record and Stabilising Plan | S |  | S | C | N | Y
| Stabilised Material Particle Size | Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008 | No excessive breakdown of stabilised material | Visual Record | within 20m per sucessive cut | Supervisor | Photographs | S or C |  | S or C | C | N | Y
| Establish Compaction Target | Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Formal Agreement | Plateau Density Testing | 1 time, or additional tests when material changes visually (Recommend a minimum of 1-2 tests per section) | Supervisor | NDM Record | S or C |  | S or C | C | N | Y
| Compaction Acceptance | Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005 | Mean value ≥ 98% and Minimum Value ≥ 95% | Nuclear Densometer Testing | ≥ 5 tests per 1000m² lot | Supervisor | NDM Record | S or C |  | S or C | C | N | Y
| Control Testing | Control testing during and after construction (7.7.2) - TNZ B/5: 2008 | Nil | Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | when agreed | Supervisor | Test Report | S or C |  | S or C | E | N | N
| Surface Smoothness | Surface shape (7.8) - TNZ B/5: 2008 | ± 10mm deviation | 3m Straight Edge | during construction and prior to seal | Supervisor | Photographs | S |  | S | E | Y | Y
| Surface Shape | Surface shape (7.8) - TNZ B/5: 2008 ; Superelevation RP 10500 - 10800 = 10 % & 10900 - 10970 = 6% | Between -5mm and +15mm | String lines or Survey Asbuilt | during construction and prior to seal | Supervisor | String Sheet/Survey Asbuilts | S |  | S | E | Y | Y
| Cross Fall | Crossfall (7.9) - TNZ B/5: 2008 | 0.5% ≤ X ≤ ‐0.5% | 3m straight edge or Survey Asbuilt | during construction and prior to seal | Supervisor | Cross Fall Records/Survey Asbuilts | S | C | S | E | Y | Y
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C, E or Sp |  |  |  | Y/N | Y/N | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
| Surface Finish | Surface finish (7.10) - TNZ B/5: 2008 | Tightly bound matrix post sweep | Visual inpsection | prior to seal | Supervisor | Pre-seal inspection sheet | C | C and E | C or S | E | Y | Y
| Pre-sealing Requirements | Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005 | ≤80%, however 65% is ideal | Nuclear Densometer Testing | if required, ≥5 tests per 1000m² lot | Quality Controller | NDM Record | C | E | S | E | Y | Y
5. Chip Sealing 2/4 - 2 Coat Chipseal with Catonic Emulsion or 180/200 Binder
5.1. Procurement What do we need to do to comply with the specification? e.g approval of materials such as concrete etc. | Chipseal Resurfacing
| Binder - Penetration Grade | TNZ M/1 | Table 1 | Property Test | Annual | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C C C C C C C C C |  | C C C C C C C C C | N N N N N N N N | N N | Y Y N N N N N N
| Binder - Polymer Modified Emulsion | Higgins Internal Specification | % PMB Required, PH, Residue by Evaporation, Viscosity | Property Test | 1/100,000 litres supplied
| Source Property -Coarse Aggregate - Crushing Resistance | TNZ M6, RNZ 9805:2009 | <10% fines under 230kN minimum | Sample Test - Crushing Resistance | 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Surfacing Project Manager | [5 empty] | Y Y Y Y Y Y Y
| Source Property -Coarse Aggregate - Weathering Resistance |  | AA or BA | Weathering Quality Index
| Production Property - Skid Resistance | NZTA T/10 | Meet Skid performance Requirement | Aggregate Perfomance Method | Each Site
| Production Property - Cleaness Value | NZTA P/17, M/6 | G2 - 89 min, G3 - 87 min, G4 - 85 min | Sample Test - Cleaness Value | Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
| Production Property - Particle Size/Shape |  | As per Table 2 and 3 NZTA M/6 | Sample Test - Particle Size/Shape
| Production Property - Broken Faces |  | 98% | Sample Test - Broken Faces
| Chipseal Designs | EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | Client Approval | Review | Annual |  | EBOP NOC Design Report Acceptance |  |  |  | N |  | N
5.2. Construction What do we need to do to comply with the specification, drawings, and quality requirements during the construction process? e.g placement of materials such as concrete or fill material and required testing. | Chipseal Resurfacing
| Finalise Sprayrate | EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | N/A | Review | Each Site | Surfacing Supervisor | Site/Spray Instruction | C |  | C | C | N | Y
| Check weather | N/A | Not foggy or raining or wet surface. Base Temp ≥ 10ºC and rising. No rain forecast | Weather Forecast | Prior to establishment each day | Surfacing Project Manager | Daily Report, Chip Sealing Quality and Site Record | S |  | S | C | N | Y
| Ensure limits of site are marked | EBOP NOC Design Report | Visual Inspection | Visual | Prior to start sealing each site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Establish TTM | TMP | Comply with TMP | Visual | Each Site | Surfacing Supervisor / STMS | Daily Diary / STMS Record | C |  | C | C | N | Y
| Sweep surface clean of deleterious material | P/17 | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Record ATP's on site | N/A | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Confirm correct treatment(s) and chip | EBOP NOC Design Report | Details/chip correct | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | Y | N
| Cutback Bitumen Blend | RNZ 9803_0513 | +/- 2PPH Cutter, +ve for Adhesion agent presence | Sample and test | 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Surfacing Project Manager, Surfacing Supervisor | IANZ Report's | C |  | C | C | N | Y
| Bitumen Application Rate | E/2 Certificate, Seal Design / Spray Instruction | Current E/2 Certificate +/- 4% per Spray Run | Test, Review | Per Sprayer, Per Site | Surfacing Supervisor/ Supervisor | E/2 Certificate. Spray Sheets | C |  | C | C | N | Y
| Chip Application Rates | Chipsealing in NewZealand | As per Chipping Guide | Visual | Each Site |  | Chip application check sheet. Chip Sealing Quality and | C |  | C | C | N | Y
| Rolling | Chipsealing in NewZealand | Mimimum as per CS in NZ - Bit volume / 3600 | Visual | Each Site |  | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Cleanup | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site |  | Chip Sealing Quality and Site Record | C |  | C | C | Y | N
| Post Sweeping | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site |  | Site Record | C |  | C | C | Y | N
| Linemarking and RRPM Reinstated | MOTSAM | Matches previous linemarking - within 48hours of sealing | Visual | Each Site |  | Site Record | C |  | C | C | N | Y
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C, E or Sp |  |  |  | Y/N | Y/N | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
| Removal of TTM | TMP | Comply with TMP | Record | Each Site | STMS/ Supervisor | STMS Record / Daily Report | C |  | C | C | N | Y
5.3. Post Construction | Chipseal Resurfacing
| Resurfacing Construction Completion report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Each Site | Resurfacing Construction Completion report | Daily Report / STMS Record | C |  | C | C | N | Y
| Chipseal Post-Verification Testing and Report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Each Site | Surfacing Manager | Chipseal Post- Verification Testing and Report | C |  | C | C | Y | N
6. Close Out
What do we need to do to handover to the Client or next work activity? | Post Construction Walkover |  | Formal Agreement | Visual Inspection | Post seal sweep | Quality Controller, Supervisor and Engineer | Meeting Minutes | C | C, S and E | C | E | Y | Y
| Pavement Rehabilitation Construction Completion Report | Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14- 001_601 Maintenance Specification | Engineer Approval | Visual Inspection | ≤2 months of 1st Coat Seal | Contract Manager/ Quality Control | Signed Report | C | C, S and E | C | E | Y | Y
S – Subcontractor C – Contractor E – Engineer/Principal Representative Sp – Supplier Quality Control Records Compiled by: Name: Reviewed / Approved by: Name: Role: Role: Signature: Signature: Date: Date