## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | QMP |  |  |  |  | Yes | QMP | 144e53bf-b2f7-41a7-ade5-e8ccd2613d25
checkpoint-status |  |  | checkpoint | QMP
checklist-flat |  |  | checklist | Verified Program |  |  |  |  | Yes | Verified Program | 1af391ff-6854-4bc7-9333-1338307d668c
checkpoint-status |  |  | checkpoint | Verified Program
checklist-flat |  |  | checklist | Production and Testing ITPs |  |  |  |  | Yes | Production and Testing ITPs | 7395ac36-901e-4308-acb9-dc025ceb5b8d
checkpoint-status |  |  | checkpoint | Production and Testing ITPs
checklist-sectioned |  |  | checklist | ITP - Pavement Rehabilitation, Cement modified generic |  |  |  |  | Yes | ITP - Pavement Rehabilitation, Cement modified generic | 8211b0d7-711a-493e-b32c-54fe32ca3a1b
checkpoint-group |  |  | section | 1. Procurement
checkpoint-status |  |  | checkpoint | Geometric Design
label | 23daf0e6-5980-5234-9c9c-e471610e8e9a |  | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design
label | 56af718b-440b-5c41-85d2-884c7440787b |  | note | TNZ State Highway Geometric Design Manual
label | fa641f6c-6362-5cc6-823f-eb59ebfd66b0 |  | note | Acceptance Criteria - Principal Approval
label | d95124bd-9d48-5201-8fdf-5011d2cbb303 |  | note | Method - Contractor and Principal peer review
label | b3eeb8cf-387b-5f22-8707-fcb656a939d4 |  | note | Frequency - per design revision
label | 6bc00443-b0aa-5a2d-afea-449317440a93 |  | note | Conduct - C or S
label | f1423ef5-5298-5a6f-af48-1b96745c247f |  | note | Produce Record - C
label | e6111f50-18a0-5e34-8596-97bfaca1efcc |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Pavement Treatment Design
label | a920dc16-3ea3-52b0-8d82-52dd8b9de056 |  | note | Controlling Documents - Austroads Guide to Pavement Technology
label | 1fdbd713-156d-50a6-a3c8-08239e9bc5b3 |  | note | New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
label | 5a860fcb-e3af-5c7f-ad91-c739ad7f898d |  | note | Acceptance Criteria - Principal Approval
label | f2b4b5ed-9b19-5325-adf7-c440f35b058f |  | note | Method - Contractor and Principal peer review
label | b5cb49b3-de51-5354-abd5-b74f3b36ffab |  | note | Frequency - per design
label | 35f7a04c-7dcd-59aa-a459-62d081b6ff0d |  | note | Conduct - C or S
label | a79f40cd-d51f-5fcc-a4f6-fd7d3008c8c1 |  | note | Produce Record - C
label | 5146ce22-11a1-5633-a0a0-6e6e4d621cc0 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Aggregate Sampling
label | cc42f583-805f-54b1-82ce-1834c1637c5f |  | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
label | 262b03f9-deb7-5536-b79e-ecd4989670d3 |  | note | Verifying Document - Sampling Worksheet
label | 15b95cb7-3c4c-5bb0-b692-a051f677c60e |  | note | Conduct - C or S
label | ee10aec3-237a-5d0e-b87e-ce1cd7de3925 |  | note | Approval - S
checkpoint-status |  |  | checkpoint | Source Property Test
label | 741e3e05-8b7f-5157-9436-5a6d316cb133 |  | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
label | 9071d0b4-ec10-5091-b408-730b2c17afca |  | note | Acceptance Criteria - Soaked CBR ≥ 40
label | 3bf37e92-d2d2-5e39-884b-e67fa51dfb55 |  | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
label | 7e8e8f7f-a947-5fa3-a07d-cbc691a76d23 |  | note | Responsible Person - Supervisor
label | 915f2b94-f5d9-5278-a8ef-5a3b21644dc1 |  | note | Verifying Document - Test Report
label | 05646849-d0c7-544e-acf0-ab070d5e55ff |  | note | Conduct - Sp or C or S
label | f9cb9837-dd44-5c75-9485-435e71cc041f |  | note | Produce Record - Sp or S
label | 8da8546d-90d7-57a3-8f31-4997c600fe9e |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Production Property Test
label | 1958a4d8-35d9-5af9-a1fc-0781a369f8f3 |  | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
label | 9c3fb33d-e573-55e1-a2fb-d0a3c6f5c97a |  | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
label | 2265c70c-1907-5182-92ee-8983671864cb |  | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
label | 8583d81a-38e8-5d93-8d82-8d86f11c36cd |  | note | Responsible Person - Supervisor
label | 88901877-21d4-54d1-8a75-0d47e2aa1142 |  | note | Verifying Document - Test Report
label | 64f73317-7d6f-511a-81c0-3ba2a24b2416 |  | note | Conduct - Sp or C or S
label | 2dde12bc-23fc-519c-935c-935586f70537 |  | note | Produce Record - Sp or S
label | b40476d8-2e6a-5dd7-a77b-28a042dbc6d4 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Aggregate Sampling
label | 122345f9-1685-5096-a8a4-25156a318ac0 |  | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
label | 75fce1c9-bfb6-553a-8b3c-0846cd327710 |  | note | Verifying Document - Sampling Worksheet
checkpoint-status |  |  | checkpoint | Source Property Test
label | 64e1a29c-0ffb-521d-8455-025ed95a09fd |  | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
label | 7dc27a84-986e-5f90-8a19-e747c66b4614 |  | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
label | 126d844a-a739-52d5-8846-2788ff4767de |  | note | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
label | 940a5dda-136a-5298-9821-408a312603f0 |  | note | Frequency - One test for every 10,000m³ of source material
label | 62a265aa-9506-532f-881d-a64f599090ac |  | note | Responsible Person - Quality Controller
label | 56437e86-4c65-53c3-9de3-5be34547f238 |  | note | Verifying Document - Test Report
label | 83e4977f-9473-5bf1-b840-4a1e39a8c861 |  | note | Conduct - Sp or C or S
label | d2fb076a-d350-578a-82df-2f88e8b6561c |  | note | Produce Record - Sp or S
label | 4bac2861-5ee3-5df7-9a5f-13b55bac3d14 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Source Property Test
label | c7ecd514-76a5-5ac1-9014-aeaa03a136f4 |  | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
label | 9ee9b218-f425-5271-8c1f-7e7eb17dff7f |  | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
label | 59f64ea1-0290-5cb3-8bff-125617cb7aaa |  | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
label | 25c289ef-c65d-55f2-a79e-835185ea6cc3 |  | note | Frequency - One test for every 10,000m³ of source material
label | f3a9f57f-3e47-5da8-b02c-6a2a10972ab7 |  | note | Responsible Person - Quality Controller
label | a2ab7b59-7cfb-5d1e-abd9-537fecb5a7c0 |  | note | Verifying Document - Test Report
label | cb4ca2e2-4a95-5af9-a20a-ea7d818ffc53 |  | note | Conduct - Sp or C or S
label | d4849851-4474-5cb8-87d6-7058126c981d |  | note | Produce Record - Sp or S
label | 709b0886-f0f4-568e-a844-136c617adaf1 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Source Property Test
label | 50973de9-53af-5738-909a-adda36e73e2e |  | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006,
label | 493ec83d-85a5-5d13-845d-f27c44114f90 |  | note | NZS 4402: 1986 Test 4.1.3,
label | 7b8df431-d13c-5675-bd3a-b084c9a5d27e |  | note | NZS 4407: 1991 Test 3.15
label | 13f1ba93-73b0-5a90-a503-fafecb5a7cd4 |  | note | (California Bearing Ratio Test)
label | 4280800b-8b56-5b01-a03f-80e76bae7e4a |  | note | Acceptance Criteria - Soaked CBR ≥ 80%
label | 8939421c-090e-5def-ac92-cdd6d8ba19f0 |  | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
label | 81feafd9-c53e-5280-a7d4-7390bf3087a6 |  | note | Frequency - One test for every 10,000m³ of source material
label | f422e47b-9c9a-59ff-b141-967ccaaab0ab |  | note | Responsible Person - Quality Controller
label | 1072c4d9-cde6-56af-9f1b-0fecad219d8a |  | note | Verifying Document - Test Report
label | d0fb3d0b-7b24-5072-b0d2-f32bc233dd92 |  | note | Conduct - Sp or C or S
label | 2c5f2197-a679-5024-9d87-ac220155f93a |  | note | Produce Record - Sp or S
label | d4c6817f-f4e7-546c-8e27-660ebf54e50f |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Production Property Test
label | ab66f585-ed41-5351-b893-cdb24f4b6c4e |  | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006
label | 3f812ab1-1058-5dd2-b53e-38594eee3813 |  | note | NZS 4407: 1991 Test 3.6 or
label | 909a4000-367c-5199-8cf9-2f979ad5eb57 |  | note | Clay Index (4.2.1.2) - TNZ M/4: 2006,
label | 8886a70b-4c16-5116-bc11-7c3e1cd4b65a |  | note | NZS 4407: 1991, Test 3.5 or
label | ed46665f-1933-5f95-a92e-8af632534130 |  | note | Plasticity Index (4.2.1.3) - TNZ M/4: 2006,
label | 0c99d82c-9629-5b2f-af13-c4c48b1cb786 |  | note | NZS 4407: 1991 Test 3.4
label | 58c76dd7-8df5-535c-9df6-38152e0e7dcd |  | note | Acceptance Criteria - Sand Equivalent ≥40; or
label | e949d827-41c4-577d-8d08-0045c57f8730 |  | note | Clay Index ≤3; or
label | b507b2a2-a614-5af0-a200-538d8d2f2d3b |  | note | Plasticity Index ≤5
label | 5c291ad3-f6e3-5682-9c63-91c40dcfc815 |  | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or
label | dda5df13-766d-5812-bd07-60a1a5cd5e81 |  | note | Clay Index Test
label | b7466020-d7b9-58d1-8498-3dbfb7211bc5 |  | note | (NZS:4407: 1991, 3.5); or
label | 5b6fe145-52a2-5068-8d27-35a2888fab5f |  | note | Plasticity Index Test
label | 6d3b344f-d4ac-5999-8261-d336055ab19f |  | note | (NZS 4407:1991, 3.4)
label | 53bb0088-9a37-59bd-a830-446202009b2c |  | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
label | fa9b19d1-181b-5ae8-be98-1799103d6c8e |  | note | Responsible Person - Quality Controller
label | 8fd0e4ee-a1d3-5721-a169-d79e8e9d5097 |  | note | Verifying Document - Test Report
label | f2f8d449-2c41-58f3-9b4b-1d5e3302328a |  | note | Conduct - Sp or C or S
label | c649d521-b56f-513e-95f3-073d2b9b0040 |  | note | Produce Record - Sp or S
label | d8ec158c-2a8f-5bc2-a3a5-dfe0cf1ce3fd |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Production Property Test
label | 88687629-76d9-51a9-8410-96dc53f69eca |  | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
label | 28f25aa5-9db1-583f-b56c-bacad667f934 |  | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
label | f1ff14af-81be-56f4-8677-26b4b80eda63 |  | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
label | 2430f651-4961-56ee-9432-566ea899ddb9 |  | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
label | a4fc1129-d2d9-57d6-b67f-1855893afd05 |  | note | Responsible Person - Quality Controller
label | f22ae790-0751-5e9d-af35-f5e929e5ac40 |  | note | Verifying Document - Test Report
label | a84f4c7a-79a8-53f8-ae50-b3087597a71c |  | note | Conduct - Sp or C or S
label | aef67428-bd89-52e8-b3f5-cf231c8456e0 |  | note | Produce Record - Sp or S
label | 56ca0436-c0c2-5110-989b-5e3c46182159 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Production Property Test
label | 5c722765-77f1-58f5-8942-da986b8b94f2 |  | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
label | fdcc847d-7d9d-5676-bbdc-aeaf4834ebcb |  | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
label | 94de280f-1a93-5813-a62e-b3d85ec3abaf |  | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
label | 1b7b05ee-d383-5e00-8380-7098e03182d6 |  | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
label | 30706776-cb3d-5e02-ae23-054fba1cd24c |  | note | Responsible Person - Quality Controller
label | c3cc79b6-a908-5250-8d85-0ca6c02a484f |  | note | Verifying Document - Test Report
label | f3f5502f-372b-5d34-86e0-91dfdf2065c2 |  | note | Conduct - Sp or C or S
label | 8f802276-5bb0-518d-b5e0-978d4cc19956 |  | note | Produce Record - Sp or S
label | 7bff03b8-a026-5964-bdd2-b7fa24a1e4a5 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Stabilising Agent Selection
label | 70dcd3d5-a82a-52d2-9c78-a71d9c69be65 |  | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
label | b64d9add-7bd3-5e62-b9d6-a61b39928f4d |  | note | Acceptance Criteria - GP
label | 61ec4fa7-4a56-51cc-84f5-d20b2b002139 |  | note | Method - Visual inspection of supplier docket
label | c8491ba8-b4d1-5d8f-8b46-ddc0c431348c |  | note | Frequency - per truck load
label | 3a328fd8-2536-5ac4-8961-7c0d8fd0bdf9 |  | note | Responsible Person - Quality Controller
label | 051f15a6-1d8b-5827-b8fb-96b71f0add4e |  | note | Verifying Document - Supplier Docket Supplier Cert
label | afd8d568-6c62-5291-af3c-0a570a4fa102 |  | note | Conduct - Sp or S
label | e5cf148a-8a34-51dc-a10d-ba5495661f0c |  | note | Produce Record - Sp or S
label | ae3fdd51-48fa-57b9-9cde-7249e12a7ed9 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Water draw for stabilising
label | 89870684-1914-5840-8254-97d8c53b9b2b |  | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
label | f47bba05-2e23-50f3-8a39-19d8ac536086 |  | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
label | e9f38b0b-6a95-5f71-a2d5-6d40209d6b7c |  | note | Method - Visual inspection of hydrant use form
label | 9f9080b3-7d90-506c-92a5-f85a6e5b561c |  | note | Frequency - per truck load
label | 54cd115a-0fac-5740-96a7-9f3cc87a758a |  | note | Responsible Person - Quality Controller
label | fe7f8ae7-bb3d-59ac-9629-5c39dfafa185 |  | note | Verifying Document - Hydrant use form
label | 49e97a82-41b9-5ddc-979f-276a634a122d |  | note | Conduct - Sp or S
label | e3d35f23-5f9f-5681-b790-431f3d1e6530 |  | note | Produce Record - Sp or S
label | e412bb73-ca25-5599-a637-04bc6d084ba7 |  | note | Approval - C
checkpoint-group |  |  | section | 2. Pre-Implementation
checkpoint-status |  |  | checkpoint | Work Pack complete and held on site
label | e05b42c2-5cfa-5f5e-aafa-ece248b48d33 |  | note | Controlling Documents - ..\Work Pack
label | 204aaeb7-a365-5fc6-a99d-f89320b270a2 |  | note | Conduct - C
label | 292d5208-7898-550e-a3c4-90b7e30cb791 |  | note | Produce Record - C
label | 0f747e60-2ff7-5699-a8d8-7e98771deffb |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Communication Plan implemented
label | c9162a58-e9c6-56f4-abd0-1e185cbfb11b |  | note | Controlling Documents - ..\4.5 CSCMP
label | 27bccb62-836b-57dd-bc4c-9195c484700d |  | note | Conduct - C
label | 10364ed0-155a-5d2f-9d42-8e26320bb78c |  | note | Produce Record - C
label | 0abf1e41-0f2a-5c7e-9ad6-840c612b4f5b |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Are any consents /approvals required, including for taking water.
label | 1501e1a3-6b5e-5481-a7de-865d129355cd |  | note | Controlling Documents - Hydrant Use form
label | 999a7bc8-c0a1-58b2-9fea-458e9ae5c0e5 |  | note | Acceptance Criteria - Forms available for applicable days
label | a66c2c73-0fee-56fa-8058-33a74c60d3b2 |  | note | Method - Visual inspection and recording
label | ac267f59-0224-5f3b-8d33-a180b8aec30f |  | note | Frequency - Daily as required
label | fee9a705-bd95-577e-9c3a-a7f2a244bb52 |  | note | Responsible Person - Supervisor
label | ab15f582-1e52-5345-ba97-b48c50f7dea6 |  | note | Verifying Document - Hydrant Use Form
label | 398ad660-ab3b-5991-a878-f611a359a411 |  | note | Conduct - S
label | 47713c6a-a882-5592-b795-8068ec657ce9 |  | note | Produce Record - S
checkpoint-status |  |  | checkpoint | Quality Control forms on site
label | 10207b03-85e4-5b8d-82d2-45af3ee643d0 |  | note | Controlling Documents - RQP, ITP, Scala Penetrometer Test Records, Material test sheets etc.
label | 44e03621-f775-5a87-b6cb-483bf2ca96c1 |  | note | Acceptance Criteria - Visual Confirmation
label | 59ed82a6-1d7f-5549-80e1-db622f842a0c |  | note | Witness - C
checkpoint-status |  |  | checkpoint | Person(s) on site with authority to stop work if quality of final outcome is compromised for any reason
label | a8f581dd-094d-50dc-a13a-621d1e55f325 |  | note | Controlling Documents - QMP
label | 49427b1c-327b-5770-b69e-ed12a3acb1cb |  | note | Acceptance Criteria - At least one nominated staff member on site at all times
label | 1f5682ce-ea59-5114-8d16-e48878674b03 |  | note | Responsible Person - Site Supervisor, Quality Controller, Engineer
label | 5ae8886e-3ccd-5fb4-9fce-4cd76c7af966 |  | note | Verifying Document - Pre-start sheets, timesheets
label | 78eaa47e-7ee3-5a70-9b62-10e1fd10f15e |  | note | Conduct - C or S
label | 0cab0a76-2909-53ef-9f89-85314295f204 |  | note | Produce Record - S
checkpoint-status |  |  | checkpoint | Records Management (i.e. it is known what documented records are to be kept)
label | d6349ef0-eaa4-501b-a3b9-4ebd728d447f |  | note | Controlling Documents - ITP and QMP state what quality documentation is required
label | d12f3dad-a085-5717-8d87-f27989d51f1f |  | note | Acceptance Criteria - Filled in and Signed ITP
label | e5b5eadb-2348-50a5-a663-1112be63afaa |  | note | Method - Visual inspection, recording and approval
label | eede3cfe-3dac-5cce-aa38-c872d2c29a4f |  | note | Frequency - As per hold points in collaboration with the programme
label | 26e3d35f-ac6c-5f6f-afa0-6d31eb8ea90d |  | note | Responsible Person - Quality Controller
label | d34ae252-136c-5952-b048-b18529f31384 |  | note | Verifying Document - ITP
label | f38230d3-08ef-5375-b540-3900efde45fa |  | note | Conduct - C
label | c3a55091-3351-5532-8d1c-c29413c81df1 |  | note | Produce Record - C
label | c34ed24f-18ef-5b34-b048-36e7b1df3df0 |  | note | Approval - E
checkpoint-group |  |  | section | 2. Temporary Works (including Traffic Management, Environmental and Health and Safety Controls)
checkpoint-status |  |  | checkpoint | Traffic Management Approved / Implemented (copy in Job Pack on-site)
label | 9e38439d-6f9c-5158-ade0-16358d36a8f0 |  | note | Controlling Documents - Site Specific TMP, COPTTM, Higgins TTM SOP, SCR Form
label | 684334fd-4279-53b4-90df-78b917522215 |  | note | Acceptance Criteria - Passing SCR audits
label | dc9631f0-bb79-51bd-82a0-867a8587074d |  | note | Method - Visual inspection and recording
label | 3f81d287-1670-550d-93d6-961e7d25c351 |  | note | Responsible Person - STMS
label | 7b7d1bc9-35e9-54bc-95e5-e3551d898087 |  | note | Verifying Document - Site Specific TMP, SCR
label | 1015ef44-6cc5-5311-973a-a34c2a201bd1 |  | note | Conduct - C
label | 29b69568-c344-55a0-9764-0366014459eb |  | note | Witness - C
label | 9f25d3d6-2ff4-531b-b007-51bf9b672ed9 |  | note | Produce Record - C
label | 91d613ae-2949-5197-b99b-25b5bee5d9f4 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Environmental controls in place?
label | 2b6a2655-308a-59b8-99ae-9eafb79ea950 |  | note | Controlling Documents - HSE Audit, JSEA
label | b8c5bb13-fed1-5518-b6ee-b2dfa4c4157f |  | note | Responsible Person - Site Supervisor
label | b8b0170c-2cc4-58bc-9f49-65d57f0bef9a |  | note | Verifying Document - HSE Audit, JSEA
label | ebc3bd11-c0c5-5425-9be6-cd9fb352e0d7 |  | note | Conduct - C
label | 7f849acf-26ab-57a0-b2b9-3e4cc574ad19 |  | note | Witness - C
label | ca049235-b36c-5428-be9d-87cd844aad7b |  | note | Produce Record - C
label | c0d844d5-b683-597c-8912-b87717d97223 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Health and Safety controls in place (e.g. Isolate work area)
label | a3cb0aca-5d23-5ca4-905a-a049592b13e1 |  | note | Controlling Documents - HSE Audit, JSEA
label | 47a70285-2685-5680-8464-350c32b17544 |  | note | Responsible Person - Site Supervisor
label | abf19f6f-c5d6-5fdd-ba6e-245e8bb435bc |  | note | Verifying Document - HSE Audit, JSEA
label | 49a02dd7-2f83-5b92-b489-5a2cd80c76e7 |  | note | Conduct - C
label | 6f739ad9-df4f-59ac-aa0b-ca77303f49be |  | note | Witness - C
label | 648c17b1-e0b1-5f50-9ebc-208039ed0689 |  | note | Produce Record - C
label | 3b090e12-8960-5066-b9fe-a8a1301bf665 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Standard Operating Procedures / JSEAs available on site
label | 9ed2c9d1-7483-5cf4-866e-15c51258ee19 |  | note | Controlling Documents - HSE Audit
label | e0d394c2-e007-54c8-bd12-c918489d166a |  | note | Responsible Person - Site Supervisor
label | 1f18c8dc-1d10-5add-8b4c-8b284b40bc60 |  | note | Verifying Document - HSE Audit
label | 525300b5-5235-52e0-a2d9-13fef275ad6b |  | note | Conduct - C
label | 91dd910f-0efe-534a-84aa-e1ec5282e272 |  | note | Witness - C
label | 3d04c9bc-aeb2-5f44-9ad3-f34326920176 |  | note | Produce Record - C
label | 7457f46e-bfe4-5244-8e1c-2a9888a818f4 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Any service covers or utilities identified and protected to Service Authorities expectations
label | 0b3fc37b-d54c-591f-b12b-30e8ae307929 |  | note | Controlling Documents - PTW Process, B4UDIG
label | 7749fa8d-80f0-53a0-8ee2-9f425bb66469 |  | note | Acceptance Criteria - Work always undertaken under live PTW
label | f5f440c2-fee1-5bf3-8fc4-c8859625ff64 |  | note | Method - Visual inspection and recording
label | bc8836f6-b568-5175-9457-f19c4a0b3724 |  | note | Frequency - Weekly
label | 074a43e6-bf57-5264-81f8-d93d922569b7 |  | note | Responsible Person - Permit Issuer
label | c39337f3-ea31-5f44-bdd9-329bb9b12b28 |  | note | Verifying Document - PTW
label | fe1bbbc8-bf5a-5840-b007-b308d4bad88e |  | note | Conduct - C
label | 0103728a-7b1b-5cd9-bf04-b10cbd7802de |  | note | Witness - C
label | 8beac278-9ac3-53e6-a1e4-ced8b629f090 |  | note | Produce Record - C
label | ac4b57d2-19c1-5155-919f-06e11c56333f |  | note | Approval - C
checkpoint-group |  |  | section | 3. Construction - Drainage
checkpoint-status |  |  | checkpoint | Drainage identification and placement
label | 92ad4f2a-0011-5648-9ec2-34d42773f256 |  | note | Controlling Documents - Review design with Client
label | e2ff12b2-1779-5af4-bd11-d9cee8a90dbd |  | note | Acceptance Criteria - Visual agreement with Client
label | 17c2f1c7-a5d0-5820-b1f9-b3ebeecd390a |  | note | Method - Visual inspection and recording
label | 7c78b1e7-8d6c-5f92-9e38-c219bda2560b |  | note | Frequency - As required
label | d8223deb-1fdc-536b-afad-d9bcdeda23fa |  | note | Responsible Person - Supervisor/pm
label | 4beaf26b-2ec9-5744-a941-a51f9852cbf5 |  | note | Verifying Document - Production notes
label | e9cff1f8-ab7d-57af-a197-f6c66ebf021b |  | note | Conduct - S
label | 7a9ab55d-cc5c-50fb-b4c7-23c0edf770aa |  | note | Witness - C
label | 6118e0a5-09f0-5ede-9b3d-9d403521d764 |  | note | Produce Record - S
label | dc10a466-9190-5c81-bb10-9fe86e515637 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Excavate trenches and placement of drainage
label | 39369fe8-d955-54c9-b7f4-86430754cb53 |  | note | Controlling Documents - Higgins SOP - culvert installation
label | 452fd16b-a8cc-55e2-8423-1aabe6ddeee1 |  | note | Acceptance Criteria - Relative fall > 1%
label | a5f352a3-e5b3-5283-b443-4a1d668872e1 |  | note | Method - Digital level
label | c6cb5d26-6f1e-51f0-ac26-9c61d2ac1c14 |  | note | Frequency - As required
label | 8fa9b952-e601-5c44-bcb8-f9614db8e9a3 |  | note | Responsible Person - Quality Controller
label | 64d202ae-5baf-5d6c-aa9d-34b86bb26624 |  | note | Verifying Document - Drainage QA form
label | c34b34d4-9f75-56fa-874b-1cb426b1e137 |  | note | Conduct - S
label | 5ae97c1e-2c2a-5c81-8c93-8c557d305072 |  | note | Witness - C
label | 5c2182c9-0717-5f09-8213-9076eeb58fad |  | note | Produce Record - S
label | 164c5086-f464-5234-98d1-6b887d25a1ac |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Drainage materials and aggregates
label | 099cdf22-7016-532a-8e7c-bc44b9b25f17 |  | note | Controlling Documents - B2
label | fdc56bb0-31d2-5cdc-be6d-768b6779b4d0 |  | note | Acceptance Criteria - Sieve test
label | 4a06a0d8-255c-5a01-91de-706c250ab8d0 |  | note | Method - Lab result
label | 2596fdf1-d15c-5a09-873c-cc239a5d09be |  | note | Responsible Person - Quality Controller
label | 1cea4e39-dc78-55e6-8903-cd0202f3530a |  | note | Verifying Document - Drainage QA form
label | 8ea5e17a-1bd0-5129-91f6-566c7b189db3 |  | note | Conduct - S
label | 226b72b9-a912-5e2c-ba45-177f170ea9f8 |  | note | Witness - C
label | 9109c188-4f4d-59be-9640-14a33ead536a |  | note | Produce Record - S
label | c80d4b9e-79ac-526d-8c1b-2c82e1b5be29 |  | note | Approval - C
checkpoint-group |  |  | section | 4. Construction - Pre-treatment Digouts
checkpoint-status |  |  | checkpoint | Pre-treatment Repair Method Selection
label | 8a1a35a1-378a-54c8-a2ca-a806761e0f34 |  | note | Controlling Documents - Site specifics to be confirmed
label | c9a650e0-f91c-5d0d-a33f-2dc4e80ba8a2 |  | note | Acceptance Criteria - Verify scala result against treatment type
label | b156f592-e24d-57ac-a2ca-f0972a373b29 |  | note | Method - Scala Penetrometer on Excavation Floor
label | 81b46ba9-6542-5f4b-a93b-693203cf4c6b |  | note | Frequency - As required
label | 4f297912-40d3-5fd4-998c-e07170f1e974 |  | note | Responsible Person - Quality Controller
label | 44adbec9-354b-5efd-9cbe-fa7c1584d20b |  | note | Verifying Document - Scala sheet test result
label | 20d3e81f-5c14-5fc4-bd76-d547d0bc1616 |  | note | Conduct - S
label | c10294c4-51ff-5630-9ffa-c4520a164ac5 |  | note | Witness - C
label | d28a8317-1f25-5087-a161-5de63271b10d |  | note | Produce Record - S
label | 3cf9c3d3-35ed-57fc-8eb4-14098275a033 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Excavation floor drainage
label | 27127dd7-c29f-5138-9566-a275ed9648a0 |  | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
label | cc94d1fa-12c7-5d5d-bf98-4332ccaefd2f |  | note | Acceptance Criteria - 4-8% toward edge of seal
label | 2a3b0083-7445-5d20-9a76-ebac836e9fcf |  | note | Method - Digital level
label | b3f6f136-f5fa-5d7a-894a-520f6e4a4e0e |  | note | Frequency - As required
label | e0e7738d-f255-595a-ab7f-4d81f0b5f6e7 |  | note | Responsible Person - Quality Controller
label | c98f8997-1827-5e73-a1a3-257cbd24760e |  | note | Verifying Document - Dig out QA form
label | 0db11486-d249-5d26-8aee-b74a82ccc0eb |  | note | Conduct - S
label | 9d70d0e0-4629-5c56-99b5-1f71703c305d |  | note | Witness - C
label | b0d16d59-3d08-5cd6-ab2a-013f04adbe29 |  | note | Produce Record - S
label | 5f02a89c-7e8d-5c43-97ab-c33544ed585f |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Base Course material hardness
label | 180f434a-9aff-5964-b229-743ff7c2dba4 |  | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
label | 7a536855-2284-5193-b6e1-03c878065422 |  | note | Acceptance Criteria - ≥45 Clegg
label | f12946ad-8cb6-5d48-98ac-30851462df47 |  | note | Method - Clegg Hammer
label | 0cc96726-49bf-5488-a91b-54258ee7bf7a |  | note | Frequency - 2 per patch
label | 72ceba3e-f5cc-537e-9c82-2ecf48f3b7d3 |  | note | Responsible Person - Quality Controller
label | 2b6153cd-2fe0-5b99-8759-e5e9f876c1c8 |  | note | Verifying Document - Clegg hammer form
label | 93a2e25b-7ed0-5512-a5f2-f31dea5351e4 |  | note | Conduct - S
label | 8b9b3bb3-6468-5727-b3de-0cfce259edd6 |  | note | Witness - C
label | 3ea046a5-b547-5faf-a59d-41c3e8480836 |  | note | Produce Record - S
label | 3d4ae4f6-9124-5ff1-bdce-8890d5b66061 |  | note | Approval - C
checkpoint-group |  |  | section | 5. Construction - Granular make up and In-situ Modification
checkpoint-status |  |  | checkpoint | Plant and Machinery Selection
label | eab2ab0a-74de-5a6d-b3d4-e33bb72c3e42 |  | note | Controlling Documents - Plant and Equipment (6.0.0) - TNZ B/5: 2008
label | 57af197f-3957-5877-8559-97601e011807 |  | note | Acceptance Criteria - Cement Spreading Truck, Direct Injection Stabilising Mill, Vibratory Single Drum Roller and either; 1 Smooth Double Drum and 1 PTR or 1 Combination Roller
label | e1cf4264-6d9b-5844-866c-2957e35b9dbb |  | note | Method - Visual Inspection
label | 089ce533-9409-51df-a2df-e4c02fc36310 |  | note | Frequency - Pre-establishment
label | a301eddd-af12-5cfd-aaf8-aad66c36473c |  | note | Responsible Person - Quality Controller
label | e34cb9bf-61b0-556b-9c1c-e0e3bdea64c7 |  | note | Verifying Document - Daily Site Record
label | 21f6b842-740c-509a-8bce-3a3b5b5876f7 |  | note | Conduct - S
label | 044cc412-7beb-5112-898b-5ab132021117 |  | note | Produce Record - S
label | abae606a-0313-57e0-8618-1f441ad66914 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Weather including temperature
label | fe1a2f8b-3c0c-582f-bb72-ce8ef8b0534c |  | note | Controlling Documents - Weather Limitations (7.1.1) - TNZ B/5: 2008
label | 3de2d282-22ed-5e0a-bd29-f434236b85d3 |  | note | Acceptance Criteria - Ambient air temp ≥5˚ C, Wind speed ≤25km/h, Rainfall ≤0mm
label | 548ebe26-1330-5d58-ad39-cf8d514c9245 |  | note | Method - Visual Inspection, Met Service
label | 7432174a-36f5-5fe6-b701-f619c5318f7a |  | note | Frequency - Throughout process
label | df98fbaa-77d2-5bb7-b598-54f24b25e73d |  | note | Responsible Person - Quality Controller
label | 0c540aac-1097-535d-bb07-a847897d1d85 |  | note | Verifying Document - Daily Site Record, Metservice
label | 7b126a26-091c-5774-9425-08dbed24a3bc |  | note | Conduct - S
label | 299b2034-fffd-5aa1-a126-824e754c0d91 |  | note | Produce Record - S
label | 1cd235eb-a784-5b3c-9d59-c6c81d181df4 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Spreading of Cement
label | 779ce055-d1b1-5bfc-88d7-89b33adbdeab |  | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
label | 92a0c94a-cf72-5e6b-825a-4cc08fe4cee9 |  | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
label | d1387c95-fbef-59a1-a5ff-87ccbaedac56 |  | note | Method - Mat test (1m² canvas) and Average Usage Test
label | 50207a19-65aa-5a36-b159-18968e8957e6 |  | note | Frequency - per 400m² and upon emptying the spreader
label | 03865fe2-724c-5d89-9c4c-9aed8fa13cc5 |  | note | Responsible Person - Quality Controller
label | 7097a712-c10e-5199-ac65-cc485a0d37cf |  | note | Verifying Document - Mat Test Form and truck dockets
label | 077a42ee-8a68-5d87-82ac-8974d62d462d |  | note | Conduct - S or Sp
label | 57d16403-8ff0-580d-a90d-7a36cd33afa3 |  | note | Produce Record - S
label | 7205f251-7da2-5eb1-8af6-f60dd463dccf |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Addition of Water
label | 09563d34-bbe0-5548-b2c9-94771d72c9f6 |  | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
label | c25e7440-70c5-545e-9e43-4421c8974582 |  | note | Acceptance Criteria - 90-100% OWC
label | c478b4af-4c45-5aac-8f71-ddee1b9f711c |  | note | Method - Nuclear Densometer Testing prior to Stabilisation
label | 2b554c7c-0228-5bfc-91ce-d4265c868ee8 |  | note | Frequency - ≥1 per 1000m² lot
label | 5ca1ae5c-d5c5-5d91-afaa-b36e8c80c9f9 |  | note | Responsible Person - Quality Controller
label | bf6c18d4-3448-54dd-85a0-eb22d6c5032c |  | note | Verifying Document - NDM Record
label | 5f2185e1-d77e-59d0-8fe3-dcfddcbac7c6 |  | note | Conduct - S
label | c4072f41-7961-5821-b842-1d1aee1fde71 |  | note | Produce Record - S
label | ce58f37e-13fc-5476-8150-069c4331e8f9 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Cut Depth
label | ae4f0923-b2ec-530d-8e7d-029565896dd4 |  | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
label | 896b8101-29e5-5ecf-b81e-d891d36950af |  | note | Acceptance Criteria - -5mm and +15mm of design stab depth
label | da6934c4-da65-5e54-b2cf-7bb83d99b208 |  | note | Method - Physical Measure and Visual Record
label | 012d7c0d-127b-5bc1-ad9a-8f55425675b2 |  | note | Frequency - ≥1 per 200m of cut length
label | 29196fd5-8eee-5b86-9cca-521a02901476 |  | note | Responsible Person - Quality Controller
label | e036ffff-f3eb-5e46-a315-787ef0d0680f |  | note | Verifying Document - Photographs and Daily Site Record
label | 5b1bc5f7-1fcd-5905-9f7e-7fea69dfffbe |  | note | Conduct - S
label | c733de5f-fbb8-5e68-a017-75af32a06b6b |  | note | Produce Record - S
label | 4f3f6d8d-bd46-5051-8a0d-50e4fcf70a0c |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Longitudinal Joints
label | 60198ac2-ce10-5714-9f08-c711a3012320 |  | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
label | 3ba46e61-853d-5325-b887-65aaffd640c7 |  | note | Acceptance Criteria - The greater of 100m or 50% of layer thickness
label | 0a7a86a4-be48-5420-889e-9a52191aa7ec |  | note | Method - Visual Record
label | 5eba05c5-83f0-52de-b5aa-bc2c317d7cfd |  | note | Frequency - per successive cut
label | 8aa1a230-a6fd-5242-ad3d-592735fc6f27 |  | note | Responsible Person - Quality Controller
label | 8331d570-d05f-54c8-92c7-eba2f1c530ec |  | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
label | 12defcd1-fc53-546f-92a7-1ea54c7d5328 |  | note | Conduct - S
label | 85328c64-b73e-51f6-a704-f0d5ee993b1c |  | note | Produce Record - S
label | 7938acba-9e06-5a0d-90a5-f7f2f696a0c8 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Continuity of Layer
label | 99fe71c5-3150-53c5-b996-c38c5d2acdc9 |  | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
label | f4e6bb8d-6a66-5841-9bd5-1e31c8173199 |  | note | Acceptance Criteria - Longitudinal overlap 1m
label | 0ad48dac-008f-5de0-95e7-5eb76475bdeb |  | note | Method - Visual Record
label | 4e4867ab-7c1c-5cec-a33c-182d795ff6dd |  | note | Frequency - per successive cut
label | 7c983f5d-1550-58f9-8fdb-eef7d808e4d9 |  | note | Responsible Person - Quality Controller
label | a192c250-4b7f-5b99-82e6-f6822cfa63fa |  | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
label | 0db0f717-0751-550e-b76c-32afceeb8aba |  | note | Conduct - S
label | 07151af7-0f92-5a24-b607-f13636129cbc |  | note | Produce Record - S
label | db78d226-ea73-58d4-abd8-8accdd107da7 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Stabilised Material Particle Size
label | a2df3fcb-ed3e-50f5-9b16-010ef735c615 |  | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
label | 74dc9588-afe5-5314-990b-ef4a45edb073 |  | note | Acceptance Criteria - No excessive breakdown of stabilised material
label | 0b2300ac-1dd0-5de0-9cef-4e738fe0eab7 |  | note | Method - Visual Record
label | ce4c8a17-89ca-5d14-a59d-694debd353f3 |  | note | Frequency - within 20m per successive cut
label | b89493ed-e111-5642-b7e4-2f89dfa18101 |  | note | Responsible Person - Quality Controller
label | 5d11bfdd-0278-5343-a3c7-680d44e278b3 |  | note | Verifying Document - Photographs
label | 20feea77-15ae-5798-871e-88421907933e |  | note | Conduct - S or C
label | f15b7d56-f7f2-599e-9a3e-9ba3d0199cda |  | note | Produce Record - S or C
label | 52bb278b-7ff4-53c7-a962-5ba2c591e836 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Establish Compaction Target
label | 59c72fa2-a4d9-5be1-bacc-d3db55dcea84 |  | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
label | 67122a60-5f6c-5f98-bd22-18055ebf7c41 |  | note | Acceptance Criteria - Formal Agreement
label | 50cf8cac-cf2a-5e9e-a517-1e2cd8ea299e |  | note | Method - Plateau Density Testing
label | 0170797d-f42b-553e-842c-cf406f58a47d |  | note | Frequency - 1 time, or additional tests when material changes visually (Recommend a minimum of 1-2 tests per section)
label | c0938476-acc2-5240-9c0d-140453eb1620 |  | note | Responsible Person - Quality Controller
label | 0e12526c-3d69-5471-86f7-dff4ee66d58f |  | note | Verifying Document - NDM Record
label | 435cd426-fbcf-507c-a429-c74ff7a1cc5d |  | note | Conduct - S or C
label | 4a1e8751-03f5-539f-a497-bee86dd3cdbd |  | note | Produce Record - S or C
label | 30534eff-03dd-548f-a98b-b3aa7f7042eb |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Compaction Acceptance
label | a50d0450-166b-58ac-a030-815e8efe67c2 |  | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
label | 9dc387a9-27d0-5831-b345-d577b5e268f2 |  | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
label | e954345a-8557-5f02-ab7c-c4d57e157429 |  | note | Method - Nuclear Densometer Testing
label | d7b4283a-3c1b-5d4f-b089-82f6bceaf1e1 |  | note | Frequency - ≥ 5 tests per 1000m² lot
label | cc4a0219-758e-5e9d-9dcd-367a3163e6dc |  | note | Responsible Person - Quality Controller
label | 7630e42d-75a0-59a8-bcd2-014d1b254d70 |  | note | Verifying Document - NDM Record
label | 1b4871d2-c753-5317-bc8c-086bb4523b16 |  | note | Conduct - S or C
label | 0d4e501e-6f11-5bee-a956-95c87e0003e8 |  | note | Produce Record - S or C
label | aa628863-92d7-5a12-98e9-f95ffc2fafdd |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Control Testing
label | 167f584f-f910-5138-9c90-8d15f8772fee |  | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
label | 899cb87d-a328-5d26-8c86-4313f1795f54 |  | note | Acceptance Criteria - Nil
label | 7e0f2986-87db-5cf6-8892-8ce87ac950b7 |  | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
label | 95d4658b-35d4-53ca-a811-2114df48c274 |  | note | Frequency - when agreed
label | c4e2260b-53a9-54d0-9162-ddd6f1c12954 |  | note | Responsible Person - Quality Controller
label | b23f9564-d41c-51e1-9e57-2043c64ea46e |  | note | Verifying Document - Test Report
label | 6ebc6c2d-3f51-52e6-9a36-86c4ca0b2d37 |  | note | Conduct - S or C
label | 962b85e0-2750-5ede-a36b-6f6ad7900b0a |  | note | Produce Record - S or C
label | af6638e7-a950-5a94-b490-a52cbbfbcbe1 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Surface Smoothness
label | 546d0d2f-0530-51a4-beeb-50f370dae915 |  | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
label | ff4f1ab2-f023-597f-9b8d-694d118aac68 |  | note | Acceptance Criteria - ± 10mm deviation
label | e43d4e7d-4d5b-5ea6-93be-b7afb622d5a3 |  | note | Method - 3m Straight Edge
label | 9eb8dfe0-a2fe-5811-b1a5-35675fee7576 |  | note | Frequency - during construction and prior to seal
label | e216fb85-c163-593f-be07-7c640fd1c07c |  | note | Responsible Person - Supervisor
label | 4f061c65-c08f-5f5f-a762-569a6759dd3d |  | note | Verifying Document - Photographs
label | e44b67db-2eed-5547-9b3d-e21b0e1d9f93 |  | note | Conduct - S
label | 3076c3db-c553-5744-af7d-b013b6f986d7 |  | note | Produce Record - S
label | 85532d8b-1bb7-56d6-aa46-2c996bf2cbe5 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Surface Shape
label | b8eb2a25-ec3e-5ddf-ad6e-6435ed9b77ef |  | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
label | 014db4a7-a51b-5bed-8532-aedfd585f92f |  | note | Acceptance Criteria - Between -5mm and +15mm
label | a57ff17b-a15a-5a44-8d8d-579c83226f75 |  | note | Method - String lines or Survey As Built
label | 30c65329-5d26-5242-b08f-ad1882727cc8 |  | note | Frequency - during construction and prior to seal
label | 2aa48e48-4b8d-544d-a7cd-7aa31dd5fa97 |  | note | Responsible Person - Supervisor
label | 6c9619ec-2d7b-59e6-8b86-49611e96b944 |  | note | Verifying Document - String Sheet/Survey As Builts
label | b5804a9c-15aa-5f70-b377-c395255bf883 |  | note | Conduct - S
label | 353ec70e-d1f0-5276-89e4-a3fb27b6e15b |  | note | Produce Record - S
label | 34bcb6d6-872e-545a-bc8e-16b7aab427df |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Cross Fall
label | 62ee53ac-0029-5e5b-ab65-0a1f99c39399 |  | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
label | 1070836a-ae26-5c21-93f1-d265a7fc116a |  | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
label | 0d72304a-9ee1-5f37-bd51-c53761bed7aa |  | note | Method - 3m straight edge or Survey As Built
label | 5a5738d8-30c3-5df0-acb8-78c1074efa0a |  | note | Frequency - during construction and prior to seal
label | b45c6bd9-2dba-542e-9f2c-0e7a9639beb1 |  | note | Responsible Person - Supervisor
label | d09aaa62-3430-5c1c-9bde-b7567d1ec67b |  | note | Verifying Document - Cross Fall Records/Survey As Builts
label | 06f43bba-4bc9-5f9c-b23c-3183eed35804 |  | note | Conduct - S
label | 5ac5588c-755b-5871-bfee-9e6291d42482 |  | note | Witness - C
label | e0ce1ed5-65e6-5c81-9d83-9fdee24a0b1a |  | note | Produce Record - S
label | 49ac7de1-13c6-54cb-8134-9f3726bb2377 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Surface Finish
label | eff60613-9167-529d-a613-03983050e10f |  | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
label | b9766024-69a7-5a58-936f-144c08b48407 |  | note | Acceptance Criteria - Tightly bound matrix post sweep
label | 38f9b670-8a9f-5d2b-8836-78e5fa10302c |  | note | Method - Visual inspection
label | 812e13ec-e6ca-5d73-b223-b3dbb5a4f08d |  | note | Frequency - prior to seal
label | 0196b742-fd0f-5bd1-8392-5179e61e66fe |  | note | Responsible Person - Supervisor
label | f78259a1-4160-5fda-bcc4-7c1c8a7013fd |  | note | Verifying Document - Pre-seal inspection sheet
label | 8a4a0c99-b590-5d44-b643-af207fb76415 |  | note | Conduct - C
label | 83fd7b34-8604-54a3-ae99-8e498534ca3f |  | note | Witness - C and E
label | 320b2915-4ae3-5f5f-8e72-5ba157129770 |  | note | Produce Record - C or S
label | 119fc0d3-4b7b-5310-873c-edd7e9d90550 |  | note | Approval - E
checkpoint-status |  |  | checkpoint | Pre-sealing Requirements
label | 197aed84-7954-5531-9685-e78192cad3c9 |  | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008,
label | 69db532f-c4bd-5295-851a-44987e0a3dbf |  | note | Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
label | 06c49834-f875-5296-a012-531496eb5243 |  | note | Acceptance Criteria - ≤80%, however 65% is ideal
label | 40e875b1-b314-5766-8728-fccccc6f5fc1 |  | note | Method - Nuclear Densometer Testing
label | 7d9ba89f-347d-5d3d-96d4-c795d722e0ed |  | note | Frequency - if required, ≥5 tests per 1000m² lot
label | 57c3aaf3-cd64-5ad7-8f0c-62d221c375d2 |  | note | Responsible Person - Quality Controller
label | d839ca46-d145-5a93-bc98-1df334dcb349 |  | note | Verifying Document - NDM Record
label | 1b864631-4fc6-5d88-a91d-e74b4809af62 |  | note | Conduct - C
label | f832235d-5478-57b6-b265-495d78f5b400 |  | note | Witness - E
label | 5da84be2-2f4b-5491-ae1f-735ffd91125f |  | note | Produce Record - S
label | d713e3db-2de1-55f5-8872-43835a4d09f4 |  | note | Approval - E
checkpoint-group |  |  | section | 6.1. Procurement (Chip Seal Resurfacing)
checkpoint-status |  |  | checkpoint | Binder - Penetration Grade
label | c8eed71a-04c0-5c7e-b2c1-7cf96643c0a8 |  | note | Controlling Documents - TNZ M/1
label | 8b32eef4-525b-5e29-8698-7a54c27dd84c |  | note | Acceptance Criteria - Table 1
label | 1dbe47a3-9dd7-5525-88ea-f7ec0f30f814 |  | note | Method - Property Test
label | 491a2e94-cbbe-58e3-9800-7e43c1277dc7 |  | note | Frequency - Annual
label | a70cf99c-1704-5f6b-962d-b415b788fb39 |  | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | 7d3205c7-1ba0-5794-87ba-2954db422b9a |  | note | Verifying Document - IANZ Report's
label | 43eefaa3-44c2-580d-a238-371dcb86c9ca |  | note | Conduct - C
label | 1d16de17-d09d-55eb-ba05-24d083320936 |  | note | Produce Record - C
label | 471a056d-3154-5102-93d2-fa4b9e84d22a |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Binder - Polymer Modified Emulsion
label | d47d414a-719c-5d14-8fce-c757ce61556e |  | note | Controlling Documents - Higgins Internal Specification
label | 4050a639-ea42-5805-9d38-17ca36a19c49 |  | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
label | 86724cf2-714e-5b0a-a46d-75fa88c35e62 |  | note | Method - Property Test
label | 75deb3fd-eabc-538e-b6ff-2e91f0c05eaa |  | note | Frequency - 1/100,000 litres supplied
label | e32d5363-9d36-5dd5-beae-a895ed711b82 |  | note | Conduct - C
label | 4c6f031e-234e-561b-84f6-a2a99ee5acb8 |  | note | Produce Record - C
label | 95daeb04-309e-55b6-be37-3ad344fe940f |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
label | ca704e10-3256-55fd-a0d3-b8bf2faa48ce |  | note | Controlling Documents - TNZ M6
label | 3e340514-90be-5242-964c-7650c992078f |  | note | RNZ 9805:2009
label | 816ed67b-2238-5115-b780-80240594da7f |  | note | Acceptance Criteria - <10% fines under 230kN minimum
label | ade7d123-d0a3-58df-a1ac-c717ef1a8e0a |  | note | Method - Sample Test - Crushing Resistance
label | 56751622-de55-5171-a7c8-695924ce7d41 |  | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
label | 30f7f63b-5c73-56f3-8a42-50f17e6a1793 |  | note | Responsible Person - Surfacing Project Manager
label | d96724e2-e701-5dda-9651-fb1e7de29ead |  | note | Conduct - C
label | 536e30cd-cad5-5cf8-a00e-c7b280ccee1f |  | note | Produce Record - C
label | 9e5dc714-bb35-589b-86ee-1cb23484d961 |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
label | dec2efe7-fd96-5319-bafb-517c217c89af |  | note | Acceptance Criteria - AA or BA
label | 78c5f70b-fda6-58e3-ac4a-f87c6dca8a24 |  | note | Method - Weathering Quality Index
label | ea1b14ee-4fd5-53ac-af16-ef6e9264f85b |  | note | Conduct - C
label | 6a03b210-7c88-5d96-8a4e-d1aba496c76a |  | note | Produce Record - C
label | cdab389e-a653-5aaa-975b-d3be8a0aef10 |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Production Property - Skid Resistance
label | 34d12fa7-aa14-518e-8819-b3d3a466b735 |  | note | Controlling Documents - NZTA T/10
label | 053971d2-37b7-5684-b962-b22c502c40f9 |  | note | Acceptance Criteria - Meet Skid performance Requirement
label | 9625f79f-1c27-523d-8c07-934f88e2b5bf |  | note | Method - Aggregate Performance Method
label | fa0d76ae-e06d-554d-8a85-37f234738fd8 |  | note | Frequency - Each Site
label | 324646de-dc38-5498-9555-115b5fcf6bf7 |  | note | Conduct - C
label | 0cc32584-1397-5572-86c2-674037d02610 |  | note | Produce Record - C
label | 7c5273f6-9e36-5a19-95a8-0a5569265cee |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Production Property - Cleanness Value
label | d2320f4b-87da-5b8b-83cf-bec5ca3146ad |  | note | Controlling Documents - NZTA P/17, M/6
label | 35012be5-f7d0-5e3c-90c5-3ade81b4c06d |  | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
label | 517bea58-fad9-579d-b2bf-984a8464dba0 |  | note | Method - Sample Test - Cleanness Value
label | 7c99254c-3a5b-5279-95f5-0c845d5dc77b |  | note | Frequency - Per Stockpile
label | b4d53dd2-8ded-5048-befe-640c32f1299f |  | note | <100m3 - 1 Sample
label | bc79fa54-e407-5596-896f-890344f7a7e1 |  | note | 100-500m3 - 2 Samples
label | 866f5428-fdf2-5630-be19-5007b58d75ea |  | note | >500m3 3 Samples
label | 32584941-042b-54f6-b8cd-d0fef9ee7014 |  | note | Conduct - C
label | 8e798841-f432-5769-ba44-2d9c9f064baa |  | note | Produce Record - C
label | 25f9f1b1-e998-57f0-a639-de914d31f6ea |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Production Property - Particle Size/Shape
label | 66e71881-5beb-5896-8da7-a42542699d63 |  | note | Acceptance Criteria - As per Table 2 and 3 NZTA M/6
label | 0158a40d-45cf-5122-80f6-504dbd98b917 |  | note | Method - Sample Test - Particle Size/Shape
label | 7eff8023-9792-58dc-9479-37b7b2ec4f9b |  | note | Conduct - C
label | bbac334c-843f-50fa-b634-a306e7ca701d |  | note | Produce Record - C
label | 40181668-e860-5177-b4f9-0fa3132f1dee |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Production Property - Broken Faces
label | 135aacde-7288-5fb4-8779-67014447a48f |  | note | Acceptance Criteria - 0.98
label | 5f97faf3-5183-54c2-a630-949019eb5127 |  | note | Method - Sample Test - Broken Faces
label | 1dfa7caf-2c3f-5324-8550-4d5107f5faea |  | note | Conduct - C
label | 54ffe832-65e3-5517-9b29-6707e57dba32 |  | note | Produce Record - C
label | 77ef3cc9-553b-534f-a932-b0ba7ed06496 |  | note | Approval - N
checkpoint-status |  |  | checkpoint | Chip Seal Designs
label | ff0bae9c-ef1f-5a10-a86b-d4f6b02f8d21 |  | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
label | 5ce4fd5e-701a-5192-bad0-8c35b76ae05f |  | note | Acceptance Criteria - Client Approval
label | 245744b7-6976-54c8-938e-a963aa6dac65 |  | note | Method - Review
label | 15844307-8e27-58e4-8101-58756d30ee98 |  | note | Frequency - Annual
label | 9f097b21-0cec-54c5-99fe-a11d9288eb02 |  | note | Verifying Document - EBOP NOC Design Report Acceptance
label | c081694e-f17c-5780-90fb-1b874e78d8f9 |  | note | Conduct - C
label | efb7bbb0-35e1-5464-82fd-79fbf3d4cb38 |  | note | Produce Record - C
label | 5425a4a8-7315-58e5-bca9-1927a91cde89 |  | note | Approval - N
checkpoint-group |  |  | section | 6.2. Construction (Chip Seal Resurfacing)
checkpoint-status |  |  | checkpoint | Start spraying Temp >10°C
label | 2fa505af-4779-5d55-96c2-2e6e73ec59a9 |  | note | Controlling Documents - NZTA P/17
label | 59563562-b5ea-554d-ae80-409c7fd83bbb |  | note | Acceptance Criteria - Start >10°C
label | a0c6384e-49a7-5fb9-a295-1bbe9fa629c5 |  | note | Frequency - Per site
label | 080ba78e-261f-54d9-9345-c3a7b9206422 |  | note | Responsible Person - Site Foreperson / Site QA
label | 445fdd50-dce2-5df7-9265-d65cd3f29c6b |  | note | Verifying Document - Spray Sheet
label | 22428573-b6d8-5ab5-b875-b08fd59861ca |  | note | Conduct - C
label | 140cfdf6-3b98-5a22-99f7-855a430ee918 |  | note | Produce Record - C
label | 9a77ff0c-652d-57b3-96b4-e8876d283d16 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Binder application variation
label | d105ca1e-cf9d-57ae-b2b9-ed8553de1a2d |  | note | Controlling Documents - NZTA P/17
label | f08b6058-54ef-5cb8-a43c-8c413fbf04fd |  | note | Acceptance Criteria - +/- 4% (spray rate)
label | ef832bd6-f965-5e99-9d50-f19352fb737f |  | note | Frequency - Per site
label | a02837cf-455d-53a7-a3c5-42303c2860b1 |  | note | Responsible Person - Site Foreperson / Site QA
label | 63009873-6549-5852-b58c-8bb135c8c8aa |  | note | Verifying Document - Spray Sheet
label | 88191725-43b1-544e-b21d-db3f03c02c84 |  | note | Conduct - S
label | 034c5910-8567-5bab-baa4-818ca8b454a9 |  | note | Produce Record - S
label | 286e6eb4-30d6-5222-80b9-5c636b6ff88a |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Sealing chip application
label | 6700002c-2098-58c7-a4e2-b6c19ad91c55 |  | note | Controlling Documents - NZTA P/17
label | 55588f24-2a28-5b33-b1e8-96a408ca7d7e |  | note | Acceptance Criteria - Full and even coverage of sprayed area
label | 7cb22e35-9334-5fae-b6c0-eff75d2b6d19 |  | note | Frequency - Per site
label | 337808f1-35aa-5525-b385-fa7e7f831e35 |  | note | Responsible Person - Site Foreperson / Site QA
label | b64c6fd4-2343-5c6a-a37a-5638901fb005 |  | note | Verifying Document - Post-seal Inspection Form
label | 821dffd3-f1a5-573b-afec-20f8b8748fb2 |  | note | Conduct - C
label | 10a66b31-9e4e-5e9b-8dc5-47c0dd58cdcc |  | note | Produce Record - C
label | 69ec8cfc-f905-56d5-a1fa-1a45ac69c635 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | PTR Rolling pattern
label | 0d25254b-2933-5cc1-9c30-aa5ddaf7d603 |  | note | Controlling Documents - NZTA P/17
label | 269496eb-274d-5d54-998c-143f0b4738b0 |  | note | Acceptance Criteria - Initial rolling completed along with traffic-rolling under controlled TTM
label | aa0556f6-0546-5ec5-bbee-1383522d6738 |  | note | Frequency - Per Site
label | 6e42871e-160d-5abe-ad14-ff974b248b89 |  | note | Responsible Person - Site Foreperson
label | 9601a552-cd9f-546f-9e31-acd2e4e068bb |  | note | Verifying Document - Post-seal Inspection Form
label | abfb9eac-70d7-588b-9b39-18dfa073ca63 |  | note | Conduct - C
label | 2bd3f990-6655-583c-b2e7-76c0d976f5d0 |  | note | Produce Record - C
label | 8a8ac96d-2f3b-533d-91c5-80cf74278563 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Trafficking
label | 7fc276ad-d89b-5ffb-8d79-37da199daa9b |  | note | Controlling Documents - Chapter 11 - Chipsealing in NZ
label | 4726e498-ee3e-52b8-b148-f62a8b2073fc |  | note | Acceptance Criteria - Initial rolling completed along with traffic-rolling under controlled TTM
label | b8333da8-97db-583b-8372-d2c3a40d4d50 |  | note | Frequency - Per Site
label | 40530a06-d7a5-5b1a-94b0-00141e854b4a |  | note | Responsible Person - Site Foreperson / STMS
label | 56550f31-c87f-53e0-9d2f-c15d7624ce59 |  | note | Verifying Document - Post-seal Inspection Form
label | a9627f44-329e-5a9f-ae60-9e83547de829 |  | note | Conduct - C
label | 6ded0161-a737-58c1-b77a-3216d2f4c090 |  | note | Produce Record - C
label | 77d0d536-7f45-5fed-94c6-2006ae590d04 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Tagging for line marking
label | bfca921e-605c-544a-bd55-dfa36a323548 |  | note | Controlling Documents - Chapter 11 - Chipsealing in NZ
label | 61190d37-2f41-5c60-8bed-fde40afbee0c |  | note | Acceptance Criteria - Pre-seal Visual check
label | 13b9fcbd-e0e0-5930-a50b-3480f5569cb3 |  | note | Frequency - Per site
label | b328be30-5170-572a-b791-5ae4bf60faff |  | note | Responsible Person - Site Foreperson
label | b78aabd7-eeb3-541e-8160-3dc2c5683744 |  | note | Verifying Document - Post-seal Inspection Form
label | 04e5f64f-714f-512c-b730-f53024f25cdf |  | note | Conduct - C
label | c5f89d5a-3c39-570b-9cf3-7e920c5fb317 |  | note | Produce Record - C
label | e4832b06-c321-5fab-8ed2-f2d31506c05c |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Post-Sealing Surfacing Condition
label | c3800a60-de6f-56f3-bb22-ad0ef18522e0 |  | note | Controlling Documents - QMP
label | b60367fe-b9ed-51b6-bc15-db4163c7fb9a |  | note | Acceptance Criteria - Visual check
label | 097ba107-598c-5c11-b6b8-5a03519e7837 |  | note | Frequency - Per site
label | 28d20919-3c26-54b6-850c-8f66d65623f0 |  | note | Responsible Person - Site Foreperson
label | a90e434a-f6da-59a0-86ef-d38bbae8ff90 |  | note | Verifying Document - Post-seal Inspection Form & Photograph
label | 09ac524c-e8cb-52c1-8741-8b4819508904 |  | note | Conduct - C
label | aea65367-4aef-5b67-a5e0-79febad4c6f7 |  | note | Produce Record - C
label | 7ed315dc-188c-50d2-b412-e5ac4ef7b1e5 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
label | 8215621b-05e4-5fc6-99a7-8b6e1bee4c3a |  | note | Acceptance Criteria - Current E/2 Certificate
label | 300bad08-8984-5084-aaa5-a8159bbee143 |  | note | #ERROR!
label | 23392ed1-f49f-5344-bab8-5511d82b0a2f |  | note | Method - Test, Review
label | 36681c60-edc1-5b99-bf0c-5e626bf1c0c4 |  | note | Frequency - Per Sprayer, Per Site
label | 9af839b8-3ccf-53a7-a7db-c8b958c8c2e2 |  | note | Responsible Person - Surfacing Supervisor
label | ae3c51c6-ab48-5f0e-95d5-ddafe97c2406 |  | note | Verifying Document - E/2 Certificate. Spray Sheets
label | c9c0955d-0618-5c76-bae9-145d1bad296e |  | note | Conduct - C
label | 744f8d33-60f5-5e7f-9428-71ef481b239d |  | note | Produce Record - C
label | 45293c68-563f-5521-b6fc-0c6cb5ca9105 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Line Marking and RRPM Reinstated
label | 9b4fbdde-4677-5221-8653-bf0b9929cbb3 |  | note | Controlling Documents - MOTSAM
label | 5212daae-2420-51d1-beec-c9625589449a |  | note | Acceptance Criteria - Visual check
label | b1e20833-cf5c-551d-8847-0fac01d61988 |  | note | Frequency - Per site
label | 39fd9953-9c0b-5d43-b981-c5728089cabb |  | note | Responsible Person - Project Manager
label | 6d7bd652-11ae-542c-ad25-4a1eb95d2824 |  | note | Verifying Document - Photograph
label | fab56455-5ebc-579e-b5f1-ee419db197db |  | note | Conduct - C
label | d479d0c6-2942-5341-8d4d-81db53b5dc55 |  | note | Produce Record - C
label | 843ddc5e-3482-5885-a42a-6b816960f732 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Matches previous Line Marking - within 48 hours of sealing
label | 6ff9acf3-9712-5465-9c97-a21e6ef3b079 |  | note | Controlling Documents - MOTSAM
label | 79a5bee6-ca28-53dc-930d-aee3f6722bec |  | note | Acceptance Criteria - Visual check
label | b97db8b8-cef3-5950-9b31-298333dc8f5b |  | note | Frequency - Per site
label | ba3a1b18-c274-520a-8333-c818c921abc0 |  | note | Responsible Person - Project Manager
label | a93f5f76-2492-5cdc-a4a4-64abc9514334 |  | note | Verifying Document - Photograph
label | ac6593fe-9d6a-53ed-9c21-5d16e84e259c |  | note | Conduct - C
label | f7cd3393-72dd-54bb-b8ab-2dd604044d50 |  | note | Produce Record - C
label | 5356bef3-38f8-5020-888e-cb6497fc24e2 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Spray Sheet/s Checked & Supplied for Claiming
label | ae80ccc8-933f-54f6-845e-b133b155f106 |  | note | Controlling Documents - QMP
label | b64237ed-6b17-5240-820f-52895d44bd4b |  | note | Acceptance Criteria - Spray sheet data verified against design/programme
label | a2e2324f-f4d9-58a6-be6f-3837c5115f44 |  | note | Frequency - Per site
label | 7cf4c11c-4781-537f-8f04-d1b612934392 |  | note | Responsible Person - Project Manager
label | 7280791d-9cb9-58d6-b698-42d0f708b179 |  | note | Verifying Document - Spray Sheet/s
label | ca667949-3d43-5056-9586-1900b4856adc |  | note | Conduct - C
label | b9171473-1722-571d-904d-b21e9f55f3d2 |  | note | Produce Record - C
label | baaa4c2c-7ecd-5784-9545-cef1d300f735 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Collect & Upload RAMM data
label | 07b7d154-fbaf-55d2-8bf7-9107f05503d8 |  | note | Controlling Documents - Comply with Waka Kotahi format
label | cc8bea09-bb78-52b1-a576-9d09c8451111 |  | note | Acceptance Criteria - Correct data supplied
label | ede5cfc5-db37-5216-9f4f-275b9985c42c |  | note | Frequency - Per site
label | a4aa5746-bef5-53e9-8300-0867e3c8f8ff |  | note | Responsible Person - Renewals Manager
label | f5b3d78d-47c3-56b1-8c7d-1ce210bee59e |  | note | Verifying Document - Spray Sheet/s & Photographs
label | 6ed7bbf9-7090-514b-8b4d-e4058bd157d1 |  | note | Conduct - C
label | 243153e0-b41c-5b6e-9426-955953f66c0f |  | note | Produce Record - C
label | 2fc5adce-3237-5129-b44f-128b01265c21 |  | note | Approval - C
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 7c90afe4-6220-53e6-a1f0-1c019dba9531 |  | note | Controlling Documents - TMP
label | 151e0f6d-d8c7-5e1a-869e-d4ae00b83378 |  | note | Acceptance Criteria - Comply with TMP
label | 90da0291-aea1-5fcb-b795-72afb818be1f |  | note | Frequency - Each Site
label | f15a57e4-ea39-51c2-8134-9b035dc2b022 |  | note | Responsible Person - STMS/ Surfacing Supervisor
label | bd0cdb52-79fb-5d86-8727-1e98177f90f2 |  | note | Verifying Document - STMS Record / Daily Report
label | 1ad55394-4e80-5127-87b9-c9d765fa3338 |  | note | Conduct - C
label | 2f7f9327-27d0-5260-b0ad-b07390f9694d |  | note | Produce Record - C
label | d75df27e-3856-5c91-92ea-0f18abd8859f |  | note | Approval - C
checkpoint-group |  |  | section | 7. Close Out
checkpoint-status |  |  | checkpoint | Pavement Rehabilitation Construction Completion Report
label | 45f1c205-3c10-5c20-b1ce-11a6b542b125 |  | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
label | 19c4adbf-662b-532c-beb6-c2f2c6d3e246 |  | note | Acceptance Criteria - Engineer Approval
label | 6cbb20d2-690f-59dc-acf0-5b0a8cd7c4dd |  | note | Method - Visual Inspection
label | 7b3091c2-b175-5051-8bf9-dd77a494fe58 |  | note | Frequency - ≤2 months of 1st Coat Seal
label | f8200d5b-fc9d-5157-8994-105b938c4ad6 |  | note | Responsible Person - Quality Controller/ Contract Manager
label | d2372fe6-504a-5e66-83c2-836cc932f406 |  | note | Verifying Document - Signed Report
label | 7e3ae063-462a-5fe0-b2dd-5e1ca8c44edc |  | note | Conduct - C
label | 786cd607-960f-59a2-9e2e-dc82abdb6b70 |  | note | Witness - C, S and E
label | c9b57d5f-8d8b-523a-b4b5-8a6eeb38fb6d |  | note | Produce Record - C
label | 60523ceb-af9a-50de-9d3e-a4a127ef21eb |  | note | Approval - E
checklist-flat |  |  | checklist | Approved JMF |  |  |  |  | Yes | Approved JMF | 8ac71f70-40b1-42f7-82bd-850237aaf41a
checkpoint-status |  |  | checkpoint | Approved JMF
checklist-sectioned |  |  | checklist | ITP - Resurfacing | itp |  |  |  | Yes | ITP - Resurfacing | 8fefdcf2-f1dd-45f2-a008-3e617d011fd2
checkpoint-group |  |  | section | 1.0 Pre-Work
checkpoint-status |  |  | checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
label | 2206b41c-d0e3-553e-a630-d6f970d2b090 |  | note | H
label | 376ea47a-b31a-5fa8-ad3e-d10a526d0a89 |  | note | Reference or Specification - Design Report
label | ca0a57dd-4c42-5fc3-a9c2-f07521ea10ea |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | affa38d7-153f-56a2-8d04-5d2f8bd0af4d |  | note | How Often? Each site
label | 842e26ca-67b8-59a8-95b8-2b6e9df84603 |  | note | Records Required - Copy of Approved Design Report
label | 0f470ee3-ee75-5ef7-b460-551189a9dbd8 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved JMF for Pre-Level Mix (if required)
label | 96355c61-9d41-5472-a535-0005854ab9a1 |  | note | H
label | c40e764d-def6-5acf-b2b8-963bc51a4ae4 |  | note | Reference or Specification - Design Report
label | 6e85b06f-52d3-5c56-ac67-b7c17209f38e |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | 21f584f4-01dd-566a-b895-65266d264889 |  | note | How Often? Each site
label | db5f468e-029c-5c6e-aec9-51528f5f569f |  | note | Records Required - Copy of Approved Design Report
label | 822e5804-7374-589e-9ada-189150ddbd5a |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved JMF for Wearing Course Mix
label | 3cb3f29a-301b-59dd-8f5b-a83acb8b9d7f |  | note | H
label | 37cae36c-3d77-5f29-9a22-46c06f30fd27 |  | note | Reference or Specification - Design Report
label | e969011c-623a-5a46-941f-129450142506 |  | note | Method/Test Required - Confirm approved JMF dates in Design Report
label | 226c5367-56c0-5fdb-aacb-638c65428efd |  | note | How Often? Each site
label | 893a48db-69df-5bdb-8788-19059311f227 |  | note | Records Required - Copy of Approved Design Report
label | 56c43060-a36c-53e0-8e23-3119ec87d7e2 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Approved Design Report
label | 337d13d1-d82a-57b4-9d8d-4dcc857e5903 |  | note | H
label | 88172857-3e01-5547-b97d-1988c273f1e6 |  | note | Reference or Specification - Design Report
label | 0af9a51f-c16c-58d8-a2f3-8bb1c224bc29 |  | note | Method/Test Required - Confirm document on-site
label | a2eac3fe-6560-56f5-b12a-961c09abea0e |  | note | How Often? Each site
label | 3acad867-a6d7-53fb-9fe0-738334dd6d45 |  | note | Records Required - Copy of Approved Design Report
label | 3ca6d6f7-1a8a-5667-a654-b327f77e73b0 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Treatment of affected Service Covers (to be raised or protected)
label | 67e37a52-c6fc-51ba-a888-6eb26913bfba |  | note | H
label | 11d6c3c1-fb01-5737-af82-78978d9f560b |  | note | Reference or Specification - Job sheet
label | 5c2ccb51-8db2-5733-bae8-0dc05d8ba209 |  | note | Method/Test Required - Confirm plan in place
label | 7e1aa2c1-12b1-5b13-abe2-e706fda56ce0 |  | note | How Often? Each site
label | 60fcfb27-b059-5773-866c-e648735118b5 |  | note | Records Required - Job Sheet record
label | d7896c0d-8321-5929-9447-aecd888fcf55 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Stakeholder Management Requirements met
label | dbe01c22-49bc-5150-8cc3-74b0f8b1be94 |  | note | H
label | f23968fb-20a7-561e-aad7-b575448bf38c |  | note | Reference or Specification - CSCMP
label | 7f50c371-8440-50d5-b999-ae1e9b596eab |  | note | Method/Test Required - Confirm requirements followed
label | d41a5033-cab4-5b9a-bec7-7ac9dd6a514c |  | note | How Often? Each site
label | 36ed58f0-6e52-5be8-adc3-f0becc045e38 |  | note | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | 570f2568-ffad-599a-9026-5ab71d11a205 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | 1d396e89-637f-5f37-ae3b-86d94d1ce65e |  | note | H
label | 1dc8bef1-4243-5f01-8e73-26ca484937cd |  | note | Reference or Specification - QMP
label | 5de9d5dc-65a3-5aa5-92ee-79c187d72dfc |  | note | Method/Test Required - Brief all team members on day’s work plan
label | 0714015a-017b-5c1b-82a0-78e2021869a7 |  | note | How Often? Each site
label | 77bb0492-2ca5-561c-b149-8fde1ed90ec6 |  | note | Records Required - Daily diary
label | 619c6412-7701-584b-bc60-760ef4800fde |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | Confirm if any environmental protection is required
label | 4caccc3e-6f93-57f6-a54b-c9e815740036 |  | note | H
label | a96cfb35-dfad-5835-a3ae-077115b1dbdd |  | note | Reference or Specification - ESMP
label | 232082d8-79bd-5182-8e57-a65e1de83c30 |  | note | Method/Test Required - Record decision
label | 05bc419f-e496-561d-b25a-117c2274d19c |  | note | How Often? Each site
label | 6d9e03f6-a623-5e6c-81a1-7344fee09d74 |  | note | Records Required - Job Sheet record
label | 885965ed-d865-5f22-b770-5dcc0ef3f6e7 |  | note | Responsibility - Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Ambient Conditions - Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
label | 3e2796e5-422e-5762-af05-6a3e4224fa6e |  | note | H
label | 49c2d762-8095-5bbe-8aee-ba5bcb8ef9a3 |  | note | Reference or Specification - NZTA M10: 2020 9.5.2
label | 8a690283-280b-5227-89e1-9d19674c4f19 |  | note | Method/Test Required - Temperature Gun Check
label | 23c1fc4a-7b25-5f26-b810-234b36cb4a43 |  | note | How Often? Each site
label | bdf321f7-a28d-5ac6-b8ea-0b63fcf95a3d |  | note | Records Required - Job Sheet record
label | 9d2a9abb-dcf3-5967-b863-d0a7c7347f1c |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Job start, identify risks and controls, communicated to team
label | af7890d6-9a05-58e4-96d9-2fd31e8fb76c |  | note | H
label | 302bafc9-bc63-51c4-833d-de1e1100443c |  | note | Reference or Specification - HSMP
label | 52631a86-5df0-5538-b0cd-4f145e7296c0 |  | note | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | ece4b107-8480-531e-9f4e-66ff3cb4008e |  | note | How Often? Each site
label | 58d2ed09-4af9-5c2e-b36a-9e6a9bc34bc2 |  | note | Records Required - Hazard ID form
label | 0eb44db5-32c9-5abf-bf1c-6159cca9bec9 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Establish traffic management to plan
label | a83d7f61-4e3c-5a5a-8ca4-e7405cc93d57 |  | note | H
label | 8e1d9c0c-ec3d-53cc-ba43-b0b4128e82c9 |  | note | Reference or Specification - TMP
label | 4fc4688f-5a07-5b07-a7b3-b14954401a68 |  | note | Method/Test Required - Site audit post set up
label | f13b3bf9-9bf1-513a-8d5d-a9634bf6f92a |  | note | How Often? Each site
label | 299ec372-2c30-5fcf-80e9-06d8f2938e78 |  | note | Records Required - TTM diary
label | 7cf8ebca-68da-5ea0-8e05-eeb6e481a3a3 |  | note | Responsibility - STMS
checkpoint-status |  |  | checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | 9e045253-daf4-5393-9d69-ca1e881ea60d |  | note | H
label | 2f782b51-4387-56a2-81d2-4030e637b2e1 |  | note | Reference or Specification - Design Report
label | c0bf009d-675c-5fe7-ab38-cfca0399d0f1 |  | note | Method/Test Required - Record as-built site dimensions
label | 94ec6e8a-0381-5dd2-92c5-6059714e2669 |  | note | How Often? Each site
label | fe8bcc43-1558-57d7-9ee3-63e30b1d6f40 |  | note | Records Required - Job Sheet record
label | 8f04b532-7516-5058-bf0a-a9fb9213a96e |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Identification of Services; Service Plans on Site; Shallow Services Marked
label | cf865470-54d5-5b59-9a60-a185a5135c33 |  | note | H
label | f11c8385-35e1-5894-96c7-fd1c6f2f0398 |  | note | Reference or Specification - SOP
label | 74128de0-4028-5665-9a08-d68f1fe4a0da |  | note | Method/Test Required - Confirm document on-site / Visual check
label | 1ac45e59-34b6-575e-87de-236f9b36458e |  | note | How Often? Each site
label | 1b232b6c-bf5f-5277-aa39-f7638bb3548a |  | note | Records Required - Job Sheet record
label | ab5d4c6b-4e8a-5c94-9c60-027ce7fdfc80 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Record & photograph environmental protection measures installed
label | 502f07b8-a3d7-50ee-9896-b7e97f61e67c |  | note | I
label | ba235174-5971-537d-903d-de33798a3686 |  | note | Reference or Specification - ESMP
label | 52d1e394-0e42-54e6-8d9c-7d7e2613d912 |  | note | Method/Test Required - Record temporary measures
label | 4e4d1109-4f70-57b4-8408-9d7489d0a770 |  | note | How Often? Each site
label | 80b7f4fd-8153-5f3b-9e55-88c0156220b5 |  | note | Records Required - Job Sheet record & photograph
label | d0b0ab46-ed5f-5a47-adf6-2e2a1ef32f25 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 3.0 Milling (If Required)
checkpoint-status |  |  | checkpoint | Milling undertaken to correct depth - +/- 5mm nominal thickness
label | 2e880ef4-359d-5c81-a506-21dc2572ce83 |  | note | I
label | 34b5999e-cff3-58d9-84fb-9315cd4494b5 |  | note | Reference or Specification - Design Report
label | 8c46f4f7-de4f-5670-a4d0-bd728965b655 |  | note | Method/Test Required - Dip checks
label | 1e7dd2e2-4759-5d36-bc82-831d10eff52a |  | note | How Often? Per site
label | c43c7f65-02fb-502b-8daf-caa76657e593 |  | note | Records Required - Job Sheet record
label | 87bf2549-baf9-5936-9e71-ae9bc5d8c79d |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Exposed Basecourse waterproofed / levelled
label | 47e4f073-1d8a-5a48-896b-f99d83e1221a |  | note | I
label | d0d7e596-53fa-5725-b845-3dfb2a19d942 |  | note | Reference or Specification - QMP
label | 85577660-9190-52b7-b280-8d60a8a67486 |  | note | Method/Test Required - Acceptable / Unacceptable
label | 245b86ec-1216-59a5-a9f4-42956a6d3108 |  | note | How Often? Per site
label | cea254db-eb83-5816-accb-7489074d9534 |  | note | Records Required - Job Sheet record
label | 31cc612a-ab04-534f-a7fc-8e3a5dc7b2fe |  | note | Responsibility - Site Supervisor
checkpoint-group |  |  | section | 4.0 Membrane (If Required)
checkpoint-status |  |  | checkpoint | Application as per Design Requirements (Chip size / binder application rate)
label | 5cd7db54-be27-58fd-985b-e3e8de595a98 |  | note | I
label | acabcd08-5bec-5ac3-b764-6bbc5dce2785 |  | note | Reference or Specification - Design Report
label | a5d748da-5e81-5ae5-bcee-e594acfe8138 |  | note | Method/Test Required - Spray Sheet/s
label | 44a57b29-dcef-587b-9f93-62cfe8aa6fa1 |  | note | How Often? Per site
label | 3a5f35c9-517a-534f-8867-12b8f1fb9e2b |  | note | Records Required - Job Sheet record
label | dd8fd798-cf90-53a2-845b-8ebb1b79fa74 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 5.0 Strengthening Repairs (If Required)
checkpoint-status |  |  | checkpoint | Delivery temperature - +/- 30 degrees from recommended mixing temperature
label | 4f1b387b-2c2a-5ab0-9fb9-7736328830e1 |  | note | T
label | df2b56e4-3c07-56f6-a530-97e4c3cfa593 |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | 23dd68ad-6f7d-5673-8079-24cbbc077520 |  | note | Method/Test Required - Temperature Gun Check - Acceptable/Unacceptable
label | 5747e0c8-8c85-5e31-a31c-e00bedc48d73 |  | note | How Often? Per load
label | fd0c5e6e-a48e-5f80-95f7-352dabd2fd76 |  | note | Records Required - Job Sheet record
label | 4b151498-be03-5f8f-b5d7-66f75766dca2 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Structural Asphalt Layer Thickness - Each Layer >55mm with ±10mm nominal thickness
label | 00f1f4c5-af96-5780-bf18-a7b1a6523c77 |  | note | T
label | b0874908-b094-5557-b6ab-25ba77e88504 |  | note | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
label | c1b170b9-7105-5cbb-acfa-637b61c29f7b |  | note | Method/Test Required - Dip checks during paving process / Cores
label | 003fe724-9273-54d6-8314-6a6512f9b488 |  | note | How Often? One test per patch & / or One test per 300m2
label | 44faa9c8-2906-563e-8ba5-ba96e516d243 |  | note | Records Required - Job Sheet record & photograph
label | 69cbea48-73cd-5440-856e-fe2467ad374b |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids
label | a4674e5a-649b-593d-a267-1eb9e54a7220 |  | note | T
label | 0f095c28-bea1-576c-a490-855faaf628f9 |  | note | Reference or Specification - Paving SOP
label | f68e6b0a-aef0-5cca-a9a5-576685e01088 |  | note | Method/Test Required - NDM for Quality Control Only
label | 6063fc31-2178-55b2-9a73-81178eba9bf4 |  | note | How Often? One test per patch & / or One test per 50m2
label | ec7b7780-ba1c-5d14-8260-0fc4072a7af4 |  | note | Records Required - Job Sheet record & photograph
label | c5e6a4d1-5949-5934-94d3-bff99966f25c |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 6.0 Pre-Levelling (If Required)
checkpoint-status |  |  | checkpoint | Delivery Temperature - +10 / -30 degrees from recommended mixing temperature
label | 672ec022-fce7-5afa-9831-82a7c242fd06 |  | note | T
label | 12ba052c-619c-5646-aaa0-c35c71ecd8a1 |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | 9b014056-08e5-5463-ba1e-416797ff503d |  | note | Method/Test Required - Temperature Gun Check
label | 4091019c-6afd-59e5-93b4-1e2c86875c39 |  | note | How Often? Per load
label | 94118284-5c3f-514c-b346-e286df3f46a4 |  | note | Records Required - Job Sheet record
label | 8137f2dd-ccbd-5e26-812c-f9cba3c9f12d |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
label | 928c3c7e-4eae-55da-aa64-5b92a8792ca5 |  | note | T
label | f0e7a9bd-1933-5177-841d-6bb59984b8fb |  | note | Reference or Specification - Design Report
label | 22128586-f4f1-5b16-b996-6ca403661c19 |  | note | Method/Test Required - Dip checks during paving process / Cores
label | 85331183-7935-585d-85c5-ad76a014ba92 |  | note | How Often? Every 15m
label | 8098af5e-9bca-5ba5-b42b-3f0c3e98ff45 |  | note | Records Required - Stringline Sheet record & photograph
label | e9c7d65f-3c3f-5295-a0bb-13c9709d5a09 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-group |  |  | section | 7.0 Wearing Course
checkpoint-status |  |  | checkpoint | Delivery temperature - +10 / -30 degrees from recommended mixing temperature
label | f2c8cad6-3b11-5355-abf1-eaabf3be129e |  | note | T
label | 74528bde-d000-5bc4-b3f4-cbb4f81c7966 |  | note | Reference or Specification - NZTA M10: 2020 Notes
label | eefa4d76-20c0-5b2e-baa7-8af7b9405906 |  | note | Method/Test Required - Temperature Gun Check
label | 8c78f34d-12ea-5fb7-863a-05039e26bcc5 |  | note | How Often? Per load
label | 9436f9da-b4c9-5879-ac9a-f6832f63d918 |  | note | Records Required - Job Sheet record
label | 1ea33632-98e8-5e4e-a8f6-6342114af7a0 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | -5mm / +10mm nominal thickness specified in Design Report; If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
label | ffae70f6-4274-5a9e-b0c6-3ca4eefc68bb |  | note | T
label | 75addc95-21ab-5a6f-b030-9364070fbc9f |  | note | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
label | 30df4787-ecb4-5bba-b80b-b2776eb7c3a4 |  | note | Method/Test Required - Dip checks during paving process / Stringline Sheet
label | 297852b2-2851-5062-92b7-b270cce1c520 |  | note | How Often? Every 15m
label | c509acdc-d1b0-505c-b358-acfedff96e7b |  | note | Records Required - Stringline Sheet record & photograph
label | d96acfb8-5d1a-51f4-9829-81aba96a6aee |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids (1)
label | 33a13f5f-64f8-51b7-984a-961f4c315a67 |  | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset (1)
label | d85edd41-2f8e-59b6-b2e7-859f96de1faa |  | note | T
label | 4296959a-719a-547c-b106-1c20c884e949 |  | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | c12a5f19-dbc8-55d7-b35a-b5adbe28a982 |  | note | Method/Test Required - 150mm Diameter Cores where: 1. >30 tonnes 2. >=35mm lift thickness
label | cf181920-7fc6-53ff-baff-28e316c4c247 |  | note | 100mm Diameter Cores where: 1. >30 tonnes, 2. >=35mm and <40mm lift thickness
label | ed6175e8-0e83-5841-b68d-cdd1d6e95482 |  | note | NDM (only where accepted by the Engineer in writing along with the testing plan.)
label | eb46026e-0818-58bf-b6bb-fd12ce115123 |  | note | How Often? Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
label | 62932d39-86e6-59ba-8418-ed7b577712e4 |  | note | Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
label | eac9a6bd-05ce-59ca-bdbb-6c871a0d1f95 |  | note | NDM (only where accepted by then Engineer as per agreed testing plan.)
label | 26d40d6b-06a1-5578-9f71-e914a099cbd6 |  | note | Records Required - IANZ Accredited Laboratory
label | be2c3dba-e541-56f4-8b5f-b25e70309031 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Compaction and Air Voids
label | 009bba04-96c4-5fc4-9475-19eaf87cd4e4 |  | note | Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
label | 5370ce52-89c5-5e64-93fa-09afcd96eb5a |  | note | T
label | 88970b0f-bcd9-58d7-9f58-851ffe570f09 |  | note | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | 183be702-4efb-584e-bd43-72eadfa82434 |  | note | Method/Test Required - NDM for Quality Control Only
label | 52aef13e-ef53-5a60-86e4-b8dd66ea678c |  | note | How Often? Every 20m alternating wheel tracks
label | 417727c4-9209-5782-883b-681ddf1e28de |  | note | Records Required - Job sheet Record
label | a1f2ab54-179b-50be-99b8-0b9c3f762107 |  | note | Responsibility - Site Supervisor / Site QA
checkpoint-status |  |  | checkpoint | Post construction surface condition
label | 565b6726-9be0-500a-a24f-d3f491f20fd0 |  | note | I
label | e61f501d-0afa-5053-a3cd-ffbec443a0b5 |  | note | Reference or Specification - Design
label | 213a0b7b-ac84-5849-8e55-e84edfcad32d |  | note | Method/Test Required - Acceptable / Unacceptable
label | bdb03da0-7169-59ee-8fea-a1ff2b4be169 |  | note | How Often? Per site
label | 75915582-9cca-56f6-87f0-c07bbfbef0dc |  | note | Records Required - Job Sheet record
label | 5ff1a08a-3721-5e11-bef1-1d0bac918a10 |  | note | Responsibility - Site Supervisor
checkpoint-status |  |  | checkpoint | Supervisor to provide an update regarding site completion per shift
label | 6c359ad0-682d-5f35-b414-f0599a455190 |  | note | H
label | 3b4a1da4-d8d9-59e5-bbd5-116c5eb078cc |  | note | Reference or Specification - Design
label | af896fa1-d940-5018-8294-8da248bd7bdb |  | note | Method/Test Required - Acceptable / Unacceptable
label | 50f10cf0-2dbb-599a-bf8e-1e59b7cb0ae8 |  | note | How Often? Per site
label | b2c004cc-a7c5-5d13-a46c-8be516128c85 |  | note | Records Required - Email
label | 59015451-7907-5b7f-b65c-e94e0e5fb7a6 |  | note | Responsibility - Site Supervisor
checkpoint-group |  |  | section | 8.0 Post-Construction
checkpoint-status |  |  | checkpoint | Linemarking and RRPM Reinstated - Matches previous linemarking - within 48 hours of sealing
label | c89e92d0-d50e-58b4-be3f-1d0610947037 |  | note | H
label | 41aeef3c-677f-5dfa-a1d1-14de1b332e69 |  | note | Reference or Specification - MOTSAM
label | f9915846-9e2c-5994-8b94-ba0b40c1cd52 |  | note | Method/Test Required - Visual check
label | a4e58d1c-f153-5ee5-9076-06c3782b81cd |  | note | How Often? Per site
label | bd3a188f-3a0e-51f0-a0c7-12701c3ad56e |  | note | Records Required - Job Sheet record & photograph
label | 94c724c2-c0c6-551d-8f09-a9325f4050e2 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | As-Built records – structural patches
label | 22f58c3e-7cd4-5a5d-90ab-5767f2fab9df |  | note | H
label | d2c1f388-7a52-54c3-8146-9708721367e8 |  | note | Reference or Specification - Design
label | 3799eeaf-2730-57f0-8c1f-dda585bb657b |  | note | Method/Test Required - Record as-built patch dimensions & RPs
label | a548255d-3195-5935-8881-56342f74a1f2 |  | note | How Often? Per site
label | 96766b65-794f-525a-961f-04f9b9a6df2a |  | note | Records Required - Job Sheet record & photograph
label | cba2ec15-858c-5340-97b2-b17c9f002d1d |  | note | Responsibility - Project Manager / Site QA
checkpoint-status |  |  | checkpoint | Collect RAMM data
label | df8d213e-d829-511e-9c3a-f8d340b6714c |  | note | H
label | c8be74f2-a3ca-52c3-bb82-bd005960196f |  | note | Reference or Specification - Comply with Waka Kotahi format
label | a58015ca-dd26-5d9a-99b7-027bc2bbbff0 |  | note | Method/Test Required - Correct data supplied
label | 81e2e29f-5d1f-5456-85cd-e33227ee1129 |  | note | How Often? Per site
label | 16f2adc5-8ceb-591b-adf4-43282de224ae |  | note | Records Required - Job Sheet record + As-Builts + photographs
label | 3d79e30c-1fc5-5922-9db9-58e4e3e39e8d |  | note | Responsibility - Project Manager / Site QA
checkpoint-status |  |  | checkpoint | Compaction as per sample test results
label | 0d6495c4-715b-5bb9-a144-aefe9cd059a0 |  | note | H
label | 6351a0b0-c1e4-5c7d-b80e-e06b99da1efe |  | note | Reference or Specification - JMF Design Compaction
label | 786c4aa5-b663-5e21-8b06-7007da440370 |  | note | Method/Test Required - Mean ≥95% ; Minimum ≥92%
label | b3a83b80-9d1a-5c78-92e2-2854252f7fbe |  | note | How Often? Every 20m alternating wheel tracks
label | ee2764a8-2625-501a-a8d3-0b90a7f69fec |  | note | Records Required - Post-Verification Testing and Report from IANZ Accredited Lab
label | aae94182-9bd7-50b8-86f6-68873ddb6545 |  | note | Responsibility - Project Manager
checkpoint-group |  |  | section | 9.0 Out Of Season Paving
checkpoint-status |  |  | checkpoint | Out of Season Paving
label | b3555ee3-2077-5614-8835-4ac4fe242217 |  | note | H
label | 4ffa7979-a375-50bd-a9fe-f03a693eebdf |  | note | Reference or Specification - Winter Surfacing Site Note
label | b920417d-bbaa-5c7b-ac1b-c4134bfa6c56 |  | note | Method/Test Required - Waka Kotahi Approval
label | d36a6ada-a389-5ca3-8aa9-6f3bfca8aca8 |  | note | How Often? Per Applicable Site
label | 59eb161a-9f0e-5866-9640-d71e169a9f3e |  | note | Records Required - Copy of Waka Kotahi Approval on-site
label | dd6cf1ff-c6f3-5bc8-a5cb-d63c85367e93 |  | note | Responsibility - Project Manager / Site Supervisor
checkpoint-status |  |  | checkpoint | Dispatching Temperature compliance
label | 10aad9ca-5331-5b98-8110-cff467939dcd |  | note | T
label | 46ff0729-c533-59d8-b0fb-d3fe9a385088 |  | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | 76179902-2af7-512b-9e0b-9da04cf40d2a |  | note | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
label | 0bdaca13-3d60-5f3b-8e6d-a07d29939dc6 |  | note | How Often? Per Load
label | 9cc5c9cc-ff49-50fd-be4b-8a00722a28ea |  | note | Records Required - Job Sheet record
label | 16038e4e-18d6-569b-babf-419114c39f29 |  | note | Responsibility - Asphalt Plant Manager
checkpoint-status |  |  | checkpoint | Arrival and Compaction Temperature: 110-170°C - To be recorded when mix is tipped into the paver.
label | d863dc72-21d0-514c-ab28-e7082ac98e33 |  | note | Manager to be notified if temperature falls below:
label | 049c442a-7624-511d-8a2c-c1500d2f09bf |  | note | SMA9.5 134°C
label | de93256b-b27e-53ed-a512-cf11f04be34c |  | note | SMA12.5 134°C
label | 940dc724-6fee-5535-b4c5-a35481a9a04b |  | note | SMA11 134°C
label | aaf25a0b-d59a-50fc-b54f-bcde1c269a0a |  | note | AC20 145°C
label | d7974f37-7ec7-5132-b6c7-4433aad6961f |  | note | AC14 142°C
label | 626dff8c-7a0d-5840-adab-b71184554720 |  | note | If temperature falls below 110°C mix will not be used
label | aca99e1e-1e26-5896-84a0-e1aaf528fef3 |  | note | T
label | d78f4110-0d6c-5e0b-8162-f13b9bde811a |  | note | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | d6f2ec19-7497-55bc-96a5-632c60e057c1 |  | note | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
label | 580bef94-b676-5c32-adad-58d8b53b557e |  | note | How Often? Per Load
label | 065b8d56-34d7-52bc-8c02-5b70ab39b3ba |  | note | Records Required - Job Sheet record
label | 5fb255e2-3645-56e5-9eef-24a21ac35f8f |  | note | Responsibility - Site Supervisor / Site QA
checklist-sectioned |  |  | checklist | ITP - Resurfacing Physical Works | itp |  |  |  | Yes | ITP - Resurfacing Physical Works | da62f677-d6d6-48fd-82cb-6c70537311d5
checkpoint-group |  |  | section | 1.0 Pre-Works (Off Site)
checkpoint-status |  |  | checkpoint | Stakeholder Management Requirements met
label | cdbfdb4a-d24b-5cc3-8174-8645ac4ad163 |  | note | H
label | 50bbdd45-eb78-5ecd-9322-c3ecb496aada |  | note | Reference or Specification: CSCMP
label | 4cbff717-c5be-51df-9575-55723a8e9dda |  | note | Method/Test required: Confirm requirements followed
label | 117f8001-ab2d-503a-ada2-95cdeae542ff |  | note | How Often? Each site
label | 658aa158-24ea-5c2d-be74-af1631414747 |  | note | Records Required: Copy of stakeholder notification / Photographs of VMS Boards
label | 7673e013-0850-5f5a-8ed8-a647f703e3a4 |  | note | Responsibility: Project Manager / Renewals Manager
checkpoint-status |  |  | checkpoint | Confirm if any environmental protection is required
label | b34c7fb8-cc8c-5849-95e5-b77c64e097af |  | note | I
label | 243a7e07-82bc-51ee-b441-9836c4bdd7a5 |  | note | Reference or Specification: ESMP
label | f2ce81e5-7384-5a65-8ece-1b72fa3927af |  | note | Method/Test required: Record decision
label | 54597b4e-0af4-5023-8478-1d719181dcb3 |  | note | How Often? Each site
label | 99a2a15b-7adb-5cba-83b5-f40e4784b1c9 |  | note | Records Required: Pre-seal Inspection Form
label | 5964959e-b1b9-562c-bca0-d2f79ffc7f18 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | a3d6c656-a3f4-523b-864a-b3d7637204e1 |  | note | H
label | 22c408f8-fa9c-5281-b96f-7be6f7735ac4 |  | note | Reference or Specification: QMP
label | 5f838ea5-5868-5503-b93f-a3119836a32f |  | note | Method/Test required: Brief all team members on day’s work plan
label | 02a584c4-70f4-5fef-b7b6-ac01101cc0f3 |  | note | How Often? Each site
label | fd7aba74-aa34-59e2-9ad9-d2b2cacb86c2 |  | note | Records Required: Pre-seal Inspection Form
label | 2062912c-f538-5849-8cf8-6e3e44b6b716 |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Pre-Construction (On Site)
checkpoint-status |  |  | checkpoint | Job start, identify risks and controls, communicated to team
label | e6d149ae-f116-5a8d-9e78-15db3a3b2288 |  | note | H
label | b4acb78c-9aa1-58a7-8b67-61c1319dc563 |  | note | Reference or Specification: HSMP
label | 99d9085f-1b63-5fbd-bf97-bdf1bed99ca5 |  | note | Method/Test required: Record all risks and controls on Hazard ID following Team discussion
label | 9797f6bd-1c62-5f2d-b301-75cde1afe59b |  | note | How Often? Each site
label | 52341539-4f26-5a34-832f-fd5fff39beaf |  | note | Records Required: Hazard ID form
label | 61b3a9a4-0522-50d6-bc14-fa40c40d3189 |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Establish traffic management to plan
label | 0f493a92-8a60-5824-b6b3-95f27a427d7e |  | note | H
label | ac58de1f-2941-551b-ae2a-3e0a1151ca54 |  | note | Reference or Specification: TMP
label | 9725cd06-6c03-541b-86c4-d0d2b41bc5c1 |  | note | Method/Test required: Site audit post set up
label | 9a78cc7f-8c51-5c58-886b-f51a55ee1bc7 |  | note | How Often? Each site
label | 97fcc26d-98c1-54cf-91e8-c6e601165184 |  | note | Records Required: TTM Diary
label | 4f4b72e3-2ec4-528a-a13d-e9e90159ecbf |  | note | Responsibility: STMS
checkpoint-status |  |  | checkpoint | Confirm site is on approved programme
label | 534d5581-1913-5a69-9da3-7fe548a43035 |  | note | H
label | dc75f533-266c-5ee6-a6e6-10052ac2dc48 |  | note | Reference or Specification: Approved Programme
label | 83127d40-9123-5301-a8f9-0ed1755e6f11 |  | note | Method/Test required: Record as-built site dimensions
label | 2c210442-a7dd-5cb4-9bcc-40f6e1e9dcd8 |  | note | How Often? Each Site
label | e9c1b3f2-dcc3-5bb8-95bc-f8a09f5a5822 |  | note | Records Required: Pre-seal Inspection Form
label | decec038-6802-5740-b436-0af349833260 |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
label | 3c1afa8e-5218-5ac8-934e-c2a032a5ad3d |  | note | H
label | d098261c-50e2-5a67-8e17-e51c2c195be4 |  | note | Reference or Specification: Approved Programme
label | 064a72f6-bee8-5307-9880-a054b15c482f |  | note | Method/Test required: Record as-built site dimensions
label | ad445598-39c2-5533-943a-c4909417c17c |  | note | How Often? Each Site
label | bc436c36-69a2-5cbd-8a74-e814d0c8012e |  | note | Records Required: Pre-seal Inspection Form
label | a7b79433-be25-5bb1-a1ad-da253c304e60 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Stockpiled sealing chip is clean and suitable for sealing
label | d17b3bbd-7393-589a-9ae8-ebd751d472d9 |  | note | H
label | 2dbdb2d4-2b72-5638-971d-e7ce55f4703a |  | note | Reference or Specification: QMP
label | 77da869d-0497-5ef2-89cf-4e11ad3e148d |  | note | Method/Test required: Acceptable/Unacceptable
label | f00fee48-495f-5153-b90c-9669e4845b23 |  | note | How Often? Each Stockpile
label | 64403bb0-86a8-5b25-83b6-a81005d02c20 |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | e97de4b1-7f3a-593c-b6fd-8abcb164d37a |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
label | 50664fb8-d6b6-53ad-9393-f74ae7577333 |  | note | H
label | 97066233-9ffb-5ef0-969d-2db61c6b930e |  | note | Reference or Specification: QMP
label | 5ce4fa85-b74c-506b-ade1-13f622078eb9 |  | note | Method/Test required: Acceptable/Unacceptable
label | 52a2f23b-2019-55d6-81e5-bd9ddf18cbae |  | note | How Often? Each Stockpile
label | cf069fea-3338-50aa-8fde-254814f3358b |  | note | Records Required: Pre-seal Inspection Form
label | 39c54daf-cd50-5b77-b750-78d68b0faeca |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Record & photograph environmental protection measures installed
label | 8ed2474a-a321-5fdd-b715-723d4b301806 |  | note | I
label | 744bf317-6a11-59c3-91d2-b8b1170cc984 |  | note | Reference or Specification: ESMP
label | 56cdcb7c-bb2c-5b48-8158-39e87167f631 |  | note | Method/Test required: Record temporary measures
label | 32764105-bfec-5960-b815-a344880e096f |  | note | How Often? Each site
label | 5750ea02-81d1-585a-b088-6416e9f5edd4 |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | dca434d7-b224-5495-bf5b-162973e83d9b |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Binder application rate
label | 26ac55df-5697-5d02-bfa2-5ed7e99b60cc |  | note | T
label | 24060e91-7b06-51a9-a74b-debd2e15610f |  | note | Reference or Specification: Seal Design / Spraying Instructions
label | 82677a5b-81fb-543d-b6ba-ea25a2bf907a |  | note | Method/Test required: Confirm seal design requirements from programme
label | b2f97d7e-aee7-5ce8-b256-d3760c534722 |  | note | How Often? Per site
label | e7d153e3-e851-585c-9800-88fddecefe2a |  | note | Records Required: Spray Sheet
label | d3fdf202-f295-53a6-b940-ffe441038793 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Pre-Sealing surface condition
label | a8f808df-b9af-5562-9a3a-a2beebebf2b1 |  | note | I
label | 1ae7ae28-d524-5cd8-825b-7246fccb79c5 |  | note | Reference or Specification: QMP
label | 7540d5cf-5a7e-5668-acea-522c9a1db232 |  | note | Method/Test required: Acceptable/Unacceptable
label | db0c2e38-988c-5a0b-9f3f-6580d26423af |  | note | How Often? Per Site
label | 4e17fdc0-9327-574a-aea7-0654d908bbdf |  | note | Records Required: Pre-seal Inspection Form & Photograph
label | 255848e4-7bbc-5e42-9ea3-ec56fa7cf681 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-group |  |  | section | 3.0 Construction
checkpoint-status |  |  | checkpoint | Start spraying Temp >10°C
label | 01336111-0af4-57a7-bed0-cf5b2ce88e20 |  | note | T
label | f1bc9e01-dbda-5a06-ae80-6597e1c375d3 |  | note | Reference or Specification: NZTA P/17
label | c9dc2a97-1487-5c6b-9a5a-6ff1ee44caaa |  | note | Method/Test required: Start >10°C
label | 20626384-7370-586f-b3f6-90fd5bf8e45e |  | note | How Often? Per site
label | bd9af927-6c24-526d-a043-f65d7e8e05a8 |  | note | Records Required: Spray Sheet
label | 01c53d0e-982a-544e-92cd-17e56ea9e4bd |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Binder application variation
label | d5f15e87-0a9d-5122-a9d6-121603950276 |  | note | T
label | 2525a921-6bc0-5cc1-a280-ee9323867de4 |  | note | Reference or Specification: NZTA P/17
label | 22f3f8f5-49a8-5044-9b66-15b74be23d38 |  | note | Method/Test required: +/- 4% (spray rate) ; '+/- 50l (tank dip)
label | aee9410e-dce0-5d13-abbc-3caee6c1931f |  | note | How Often? Per site
label | 32a5eec4-d4e1-5254-bc3b-2e66dd1caf72 |  | note | Records Required: Spray Sheet
label | cc206622-80a3-51e1-bae3-8eb2a6065078 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | Sealing chip application
label | c811bbff-d316-5660-a2fd-f37a40f0f48a |  | note | I
label | 1d1a1683-53b3-5445-9517-8d65c1f0f190 |  | note | Reference or Specification: NZTA P/17
label | 39aecca8-8070-545d-ab43-a8f661baa761 |  | note | Method/Test required: Full and even coverage of sprayed area
label | b404cf64-dbcb-5226-8ce1-9e50baff72c8 |  | note | How Often? Per site
label | 5e2a5aef-edce-5410-aece-7d16d486ca7a |  | note | Records Required: Post-seal Inspection Form
label | 1db84468-050f-5370-907c-70f1c7392024 |  | note | Responsibility: Site Foreperson / Site QA
checkpoint-status |  |  | checkpoint | PTR Rolling pattern
label | 255c3fb6-536b-52ee-b8cb-fce74f5287c3 |  | note | I
label | 21086bce-46fe-525a-8f81-ecde439379fe |  | note | Reference or Specification: NZTA P/17
label | 5db6abbb-e11c-5992-b5e5-c9e31d8bc35d |  | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
label | 6d5a234d-009e-5a25-b63a-0ac7840752ec |  | note | How Often? Per Site
label | 543a7248-17d0-5815-a691-62bf51d1cc4c |  | note | Records Required: Post-seal Inspection Form
label | ba3f9ae0-9877-5b27-937e-36518fcad1c0 |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Traffickating
label | c2ff3134-1a8d-5126-bf6e-7ac62a8485ae |  | note | I
label | 0ad0d532-4b20-5448-a4d7-04c01a3f09c2 |  | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
label | 41778075-be09-5bd5-92e0-2cfe587e87f3 |  | note | Method/Test required: Initial rolling completed along with traffic-rolling under controlled TTM
label | 8f8963a2-654c-5f55-abdc-d73a98756db0 |  | note | How Often? Per Site
label | 578d1904-8009-54d9-8f8d-7f3848e9a031 |  | note | Records Required: Post-seal Inspection Form
label | 6ed84a04-c4a1-5377-8d97-91d54d4cd462 |  | note | Responsibility: Site Foreperson / STMS
checkpoint-status |  |  | checkpoint | Tagging for line marking
label | 3a740848-78f2-5a3f-944f-e9696e1eb965 |  | note | I
label | 95b3ecb0-9a83-5def-a6f5-56ca030cc34c |  | note | Reference or Specification: Chapter 11 - Chipsealing in NZ
label | ea95e64b-b91e-56ab-abeb-87e4a9e45ab0 |  | note | Method/Test required: Pre-seal Visual check
label | 6d9492c4-b48a-51ae-8b1f-549b8e7fd44d |  | note | How Often? Per site
label | 491317cb-f9ca-521d-b85e-003e988ec69f |  | note | Records Required: Post-seal Inspection Form
label | bafff7b6-826d-5f95-86dc-77e1ecc665e7 |  | note | Responsibility: Site Foreperson
checkpoint-status |  |  | checkpoint | Post-Sealing Surfacing Condition
label | dd5b1df1-a9d8-5326-b017-7d845c140298 |  | note | I
label | 9e8d6acf-3143-5a1a-8346-fc18655c90b5 |  | note | Reference or Specification: QMP
label | fe662e7a-771c-5aaa-a68e-924be69d139c |  | note | Method/Test required: Visual check
label | ce1645f1-ad03-561f-b374-aabcbfe053e2 |  | note | How Often? Per site
label | a2d0bceb-fa49-5576-8976-238b851957ea |  | note | Records Required: Post-seal Inspection Form & Photograph
label | ce2c78a1-615c-50bd-acb8-03b36d53fc4e |  | note | Responsibility: Site Foreperson
checkpoint-group |  |  | section | 4.0 Post-Construction
checkpoint-status |  |  | checkpoint | Linemarking and RRPM Reinstated, Matches previous linemarking - within 48 hours of sealing
label | bcce04e9-05a5-5c90-9c44-85bf7b603357 |  | note | H
label | 53725ac3-5e7c-5d53-bd7d-76d183dd3305 |  | note | Reference or Specification: MOTSAM
label | 308889cd-5efb-5e7b-9130-434e714cdaa3 |  | note | Method/Test required: Visual check
label | 0f5785ad-92c1-5362-8424-d6a953d14f6f |  | note | How Often? Per site
label | a069e844-ca12-5d8f-91ce-9a5163f47402 |  | note | Records Required: Photograph
label | 4379108f-f0ea-5f3d-bb1c-012fca74f6c4 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Spray Sheet/s Checked & Supplied for Claiming
label | 658e7f1f-939c-5684-8b83-27ed1965928c |  | note | H
label | 6249776e-51d9-53d4-8aac-d298f5790102 |  | note | Reference or Specification: QMP
label | 51ee2afc-24db-5d82-9c9d-ccd97b92d7b1 |  | note | Method/Test required: Spray sheet data verified against design/programme
label | dcecb69e-8a12-5eeb-b4f7-274c2c5fbb25 |  | note | How Often? Per site
label | 99dc1304-c1a9-55b0-9574-1942c4210baa |  | note | Records Required: Spray Sheet/s
label | 09f63ad2-b8e4-5161-aa9c-327b5528db36 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Collect & Upload RAMM data
label | 8d7e45a9-f108-51cd-99b1-f741ead63676 |  | note | H
label | b36ed547-f582-5ba3-90c0-c2a4d8f80729 |  | note | Reference or Specification: Comply with Waka Kotahi format
label | 2220a9f0-a4f9-5f10-9f95-a9d346648f04 |  | note | Method/Test required: Correct data supplied
label | e365a772-6213-54ec-9f7d-e756043dd338 |  | note | How Often? Per site
label | af37524f-28de-51b7-a956-5d7a36648d47 |  | note | Records Required: Spray Sheet/s & Photographs
label | 51c17567-73e0-57fc-afc7-084a52a4d876 |  | note | Responsibility: Renewals Manager
checkpoint-group |  |  | section | 5.0 Out Of Season Sealing
checkpoint-status |  |  | checkpoint | Out of Season Sealing
label | 641b7c62-e616-5ef6-ad60-6fbabffb3ebe |  | note | H
label | dd2a6469-f6e4-58ae-b8df-93162484b08a |  | note | Reference or Specification: Winter Surfacing Site Note
label | ad196084-e963-5a54-8570-10038bb7e4da |  | note | Method/Test required: Waka Kotahi Approval
label | a8a8ec4e-81d6-54a2-ad6f-45b7d30a32d1 |  | note | How Often? Per Applicable Site
label | 3e49c9a4-ea4a-5d95-8307-1ab0b247421d |  | note | Records Required: Copy of Waka Kotahi Approval on-site
label | 48bc0663-71f2-5cc5-b7bd-a8e73bbe755a |  | note | Responsibility: Project Manager / Renewals Manager
checklist-sectioned |  |  | checklist | ITP - Granular Rehab |  |  |  |  | Yes | ITP - Granular Rehab | db966afa-080b-41c3-be49-2a8b7e9f1033
checkpoint-group |  |  | section | 1.0 AP 40 M4 – Raw Aggregate Testing
checkpoint-status |  |  | checkpoint | Sand equivalent, or
label | ce69a728-c599-5cec-b99c-64a7b1b0d060 |  | note | T
label | ad716045-053e-5607-a59c-4421336ae6c2 |  | note | Reference or Specification: Design
label | 62cef0cc-f12a-5059-b24d-8d629fafb218 |  | note | Method/Test required: ≥35 Unit of measure?
label | b4109b10-eb05-59a2-8c2f-d23f7a804dcb |  | note | How Often? 1 sample per 500m3
label | 951e56ec-963a-5dba-be4b-fcf3307dcc31 |  | note | Records Required: Test Report
label | 45bae04d-3828-566f-b03a-98c2bcc02409 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Clay Index (passing 0.075 mm), or
label | a6289f85-c843-52b9-bddb-b49fa9139848 |  | note | T
label | d0f9af63-f86d-51a8-ae7f-491062bb4f73 |  | note | Reference or Specification: Design
label | 0838be70-19b8-53d0-a65a-a03257f0f969 |  | note | Method/Test required: <=3 Unit of measure?
label | bd72d7dc-6e4b-5948-a384-f1b58a8719d2 |  | note | How Often? 1 sample per 500m3
label | 6919e779-47e1-564f-9357-0d2e693e2839 |  | note | Records Required: Test Report
label | 4c1d77b6-c5a7-59dc-b831-6a7234ebecef |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Plasticity Index
label | ee378919-17b5-5907-bd14-6331b4227c3c |  | note | T
label | 0e4b0798-7946-57ec-a40a-07c11fd42fa0 |  | note | Reference or Specification: Design
label | 02d708c6-b257-51cc-98a5-a89e54c653b3 |  | note | Method/Test required: <=3 Unit of measure?
label | 3a7f36df-de52-5e65-bb74-f4cc1dd046db |  | note | How Often? 1 sample per 500m3
label | 8bb65a34-ac61-5b29-abe7-af358b583e25 |  | note | Records Required: Test Report
label | b1cf7f7b-66fd-59f8-a4b5-9bfe36182dae |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Particle size distribution
label | 60d29f41-860c-502b-a48d-49aeb4d4fc20 |  | note | T
label | f8b36724-246e-56ec-a73c-16ba3cba9b44 |  | note | Reference or Specification: Design
label | b3e81397-38ee-53e6-8a38-d4175e667cef |  | note | Method/Test required:
label | c970ae93-50ae-5878-bff2-86049064582f |  | note | • 100% passing 63mm
label | dc323022-448c-5f71-9859-e8e51adb54f8 |  | note | • 40% ≥ 65%passing 19mm
label | 352712d9-523c-53cf-b808-8904fd2ea8da |  | note | • ≤ 10% passing 0.425mm425µm
label | cb5c14b2-5bcd-565d-b558-728689d9fb6f |  | note | How Often? 1 sample per 250m3
label | 69d68354-e340-5dc4-8c00-dbc8b412a35e |  | note | Records Required: Test Report
label | 0dd8316e-c580-5151-89cb-1d30e9fff193 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Solid Density
label | d7185f64-a55d-5c04-b793-2b4e40fde087 |  | note | T
label | 3a8f5a73-d4c7-5694-b2b5-3e8ea77d3448 |  | note | Reference or Specification: NZTA B/2 7.5
label | 378c1a7c-c036-5c2c-b529-a1a8261c8a11 |  | note | Method/Test required:
label | 9175eb7d-0c3e-5a26-ba7f-8945efc234e8 |  | note | • Unit of measure?
label | 3f9dd623-a633-5791-b021-42c424f093e5 |  | note | • Tolerance?
label | 57cf72a0-66d4-51fd-929c-331419749e66 |  | note | How Often? 1 test
label | ef1f43e0-22d2-542c-b4be-7adf6e2c3c53 |  | note | Records Required: Test Report
label | 57e63228-0779-5341-a83a-7edcd5604e1b |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Determination of MDD & OWC
label | 17562201-f80b-5bd8-82aa-09694982dceb |  | note | T
label | 2a4d9850-0317-596b-bfd9-ea118792df47 |  | note | Reference or Specification: NZTA B/2 7.5
label | d60cb53a-2967-5a73-9cc1-f732aa49e8ed |  | note | Method/Test required:
label | 9a547c82-e655-5987-b7b4-cc37713de689 |  | note | • Unit of measure?
label | 95a19683-33fb-5b56-b8a5-44debb6f4820 |  | note | • Tolerance?
label | ef183e83-0621-558c-a069-0fd6b32dd76a |  | note | How Often? 1 test
label | 26c35729-54fb-5210-bdd5-83444589010f |  | note | Records Required: Test Report
label | e124a433-48c3-50b5-b0c3-b7d68bb4a69d |  | note | Responsibility: Project Manager
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | Stakeholder notifications undertaken
label | 23215615-9bd1-553c-9321-e6b3d1f38b51 |  | note | H
label | 44c46434-666f-5d13-983c-45d3cb127056 |  | note | Reference or Specification: CSCMP
label | 40274952-286a-5fbd-a6d2-bde64240a8fa |  | note | Method/Test required: Stakeholder notification emails and letter drops
label | c6cc75d9-6eaf-5a01-8246-19c2fdf8da51 |  | note | How Often? Each site
label | aee599c1-e71d-5e52-902e-16908271ee8a |  | note | Records Required: Evidence of notifications
label | 50fcc313-354d-5463-814f-82afa08c3a66 |  | note | Responsibility: Network Manager
checkpoint-status |  |  | checkpoint | Mark-out of services and Permits in place
label | 95c80e26-4009-56c5-9422-42c4339390c8 |  | note | H
label | d2cf0e53-cc07-5921-b621-8947a177f323 |  | note | Reference or Specification: HSMP
label | ebb45c53-01bf-571c-9810-cc5dae536d38 |  | note | Method/Test required: Physical mark-out of all services and signed permits
label | 03bea957-76f4-5d08-b659-1c4f3c5f44c0 |  | note | How Often? Each site
label | 72cf1c1c-1246-5044-addc-6abffcbf3f2d |  | note | Records Required: Signed permit
label | 6a1d3921-303e-5871-8239-105dc0931b56 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Job start, identify risks and mitigations, communicate to team
label | 078fb512-e0a4-5a40-8bf8-01beed709d09 |  | note | H
label | e17a0c58-4344-5750-b30c-ddcee3990944 |  | note | Reference or Specification: HSMP
label | ae4e10c0-ba2c-5211-981d-47066b6d7599 |  | note | Method/Test required: Record all hazards on JSEA and brief team
label | eecd5f5f-a6ba-5d5b-9011-417ad0058d31 |  | note | How Often? Each morning
label | 82b7fe10-8f0c-5a68-917b-0ca1b4bed124 |  | note | Records Required: Job start form
label | e9594c5a-7dd4-5236-85e3-18880d60b001 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Set up traffic management to plan
label | e14b900d-731d-5697-abd5-39fba73c353f |  | note | T
label | f44e9224-6a6e-5101-bf06-705d22f9a575 |  | note | Reference or Specification: TMP
label | c2df49d6-878b-5098-8f94-6d0a145428f2 |  | note | Method/Test required: Perform Site audit post-set up
label | 618450f6-5404-55ad-9969-b5e98cabe419 |  | note | How Often? Each site
label | d0e9bd02-78fb-5901-a8e9-eac51607e42c |  | note | Records Required: Daily Diary
label | 1967e463-9a78-5782-8b4b-65429604cc3b |  | note | Responsibility: STMS
checkpoint-status |  |  | checkpoint | Assess environmental requirements of site and install sediment and erosion control measures if required
label | 400370eb-b6a5-5e98-ae40-08fa0136c907 |  | note | I
label | 486031be-e296-56eb-8bff-841b728acda8 |  | note | Reference or Specification: ESMP
label | df70acd6-4ce3-59f2-86c4-bdb2ab8bac3c |  | note | Method/Test required: Identify areas at risk and install control measures
label | 6838c9de-7e5a-5f3c-bf5b-a6169c11b89b |  | note | How Often? Each site
label | 5cab5010-72ad-54ce-9530-02b235006622 |  | note | Records Required: Daily diary
label | b785ea96-80bb-5c59-b09c-7206f39bb704 |  | note | Responsibility: Supervisor
checkpoint-group |  |  | section | 3.0 Basecourse Inlay
checkpoint-status |  |  | checkpoint | Cement Spread Rate
label | 42117727-5208-58c5-94d0-7ba990fb56a0 |  | note | H
label | bff4a659-22bd-5cb3-a502-8d85e0a60878 |  | note | Reference or Specification: NZTA B/5
label | bc5f6032-9112-579c-a1b9-b51a8bd0ae27 |  | note | Method/Test required:
label | 0e17e85a-b73c-53f1-b3df-8909a0f15e62 |  | note | • ±0.5kg/m2
label | 76e2a5e0-3298-5917-ab80-0a6c3b517973 |  | note | • Weigh mat: Every 400m²
label | 3eab6b5b-9284-5416-a65a-71869807ed3b |  | note | • Average usage test: Within ±2.5% of the specified rate
label | 7456e484-9709-5cbb-ad55-a88ab42cb8f2 |  | note | How Often? Upon emptying the spreader and bulk tanker
label | 9fc3768b-8cfb-58a8-b23c-e6b97b1f1cb1 |  | note | Records Required: Cement Sheet
label | 8b67d880-7be5-5275-9f0f-dc33379cf72f |  | note | Responsibility: Stabilizing Supervisor
checkpoint-status |  |  | checkpoint | Hoe and stabilise to design depth
label | b08607db-732a-5664-9609-cbf86eeacbae |  | note | I
label | 06041f66-fb75-5185-84fa-c46772163bd8 |  | note | Reference or Specification: NZTA B/5
label | 7632f830-b456-5aa1-867b-828adfe1234a |  | note | Method/Test required: -0mm / +20mm
label | baae4376-2de3-5739-b88e-b5b810e7b626 |  | note | How Often? Per run
label | 7258cad2-a043-539c-8be8-3222fc3e129b |  | note | Records Required: Cement Sheet
label | 78679d38-a130-51a7-987a-b6e4e3d9b2e7 |  | note | Responsibility: Stabilizing Supervisor
checkpoint-status |  |  | checkpoint | Overlap longitudinal joints
label | 13c3ab62-82a4-509b-8734-70e1d12c3006 |  | note | I
label | 5f791713-8334-58a7-9294-bdc15a6c4809 |  | note | Reference or Specification: NZTA B/5
label | 628ff46a-b7e6-50b3-a082-873e22776a5f |  | note | Method/Test required: Record hoe-depth setting
label | 5752032c-3f65-5c19-8da5-b01000d6173d |  | note | How Often? Per run
label | a93531cf-cef8-5108-8cd0-e40708183f35 |  | note | Records Required: Stringline Sheet
label | 6bc7634d-22cb-58f5-a965-7ce15bde1662 |  | note | Responsibility: Stabilizing Supervisor
checkpoint-status |  |  | checkpoint | Plateau density test
label | 3ca24cc3-87ae-50b6-98b7-dc4997c7d8e2 |  | note | T
label | 081f23ad-45f7-5f91-9a1a-3f6fae111002 |  | note | Reference or Specification: NZTA B/5
label | 1e26e019-24c5-5b74-8f6c-2454edcf5f8d |  | note | Method/Test required: 200mm overlap
label | f7e20c71-ce9b-5ec6-81ae-be8fed027788 |  | note | How Often? 20m centres each side
label | 8a704a06-cafa-55eb-a340-35a348ed542a |  | note | Records Required: Plateau Density Sheet
label | 01257f69-3e4a-5a18-a6f7-e64f1aeb9c8a |  | note | Responsibility: Quality Engineer
checkpoint-status |  |  | checkpoint | Confirm layer thickness
label | 268e0654-1918-5cb7-8736-14f8cb2f2c75 |  | note | T
label | 52344fc3-1783-5be9-8944-8ca97d448c2d |  | note | Reference or Specification: NZTA B/5
label | eb8fa5fc-32a8-57aa-9824-72b021d5b789 |  | note | Method/Test required: Nuclear Densometer
label | 25d9bef4-5b03-5b75-b87a-75923e884ea8 |  | note | How Often? 20m alternating wheel tracks
label | d687525f-b21c-5bde-b19a-fae9cf4b9cab |  | note | Records Required: Plateau Density Sheet
label | e2c46515-5972-58b4-a5b7-47372587c5bf |  | note | Responsibility: Quality Engineer
checkpoint-status |  |  | checkpoint | Compaction as per sample test results
label | 0d85bd6c-10d2-500b-adf1-dafd103cd386 |  | note | H
label | ee1b2554-601e-52cf-9962-a87fd5faae83 |  | note | Reference or Specification: NZTA B/5
label | ff324ec8-3077-5bf6-a3d0-36b8a4ebd1f3 |  | note | Method/Test required:
label | c1158d7d-d552-5a67-896f-ebd1376f23a5 |  | note | • Mean ≥95%
label | 4fc4ac05-0853-5deb-8915-2341c6851742 |  | note | • Minimum ≥92%
label | f732b3a2-a83b-5e18-a2bd-3ad4d97e0ea5 |  | note | How Often? Every 20m alternating wheel tracks
label | 4c9d227b-c887-5e63-8b77-aabbf38d2927 |  | note | Records Required: NDM Sheet
label | 02eb0d4a-e4fa-5ea2-b504-61e87245e4de |  | note | Responsibility: IANZ Accredited Lab
checkpoint-status |  |  | checkpoint | Impact hammer test
label | 0461cd19-d306-53e5-89c5-c32d1aefb0e1 |  | note | H
label | 7f39a19c-3ea8-5812-b98f-76fa1634e4de |  | note | Reference or Specification: Spec?
label | 2df1a697-901c-561f-bfa8-7d659c8893cd |  | note | Method/Test required: ≥70 CIV
label | bcbd3ef6-417c-52cf-a4da-4152bd35ebe8 |  | note | How Often? Every 20m alternating wheel tracks
label | f37c0916-1534-5779-bf52-5ef56897a5a2 |  | note | Records Required: Clegg Sheet
label | 5f40e634-c746-5e8c-ad85-b87eb289264e |  | note | Responsibility: IANZ Accredited Lab
checkpoint-status |  |  | checkpoint | Confirm surface levels
label | 51934aa2-5659-5604-8dd4-1e86e68e62df |  | note | T
label | 6e23f4c3-a613-5b71-9262-c3b2d39d0101 |  | note | Reference or Specification: NZTA B/2 5.1
label | 04d3fbe0-b0e8-5193-83e7-595235bda13c |  | note | Method/Test required: -5mm / +15mm
label | ecba9a9c-1eb1-5742-922e-5b1f0be51dbf |  | note | How Often? Every 20m, full width
label | 9c7c1827-fd43-534f-a429-be2a5f8ca55a |  | note | Records Required: Stringline Sheet/As-Builts
label | 1b76c7e1-c608-569e-a26c-c1a00c934ae1 |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Surface Finish
label | d3588765-1aeb-5935-839b-1a09c15802a4 |  | note | T
label | 12822f3e-c52a-5717-bdf1-e8b8a7d5e2c3 |  | note | Reference or Specification: NZTA B/2 5.1
label | c59676e4-1726-5303-8e91-87045bf942fc |  | note | Method/Test required: -5mm / +15mm
label | ba769c71-81eb-50ba-a332-1398113054db |  | note | How Often? Every 20m, full width
label | edb5af76-9cd4-54bd-aec4-af0b7edd4cdf |  | note | Records Required: Stringline Sheet/As-Builts
label | e86ce6fe-e0dd-5f4f-a276-3a3fa15e27af |  | note | Responsibility: Project Manager
checkpoint-status |  |  | checkpoint | Confirm surface levels
label | 3f61ab98-e188-57e4-906b-9b6163516d10 |  | note | H
label | 7583a3d3-1d80-5311-a165-2057dbbf5906 |  | note | Reference or Specification: NZTA B/2
label | bddd53b5-1dc5-5f0f-8dfc-1e68be8740ca |  | note | Method/Test required: On-Site Inspection
label | 05164b95-b3f3-57ba-8e05-c1e976a4c0b2 |  | note | How Often? Per site
label | 100be1c6-d322-5991-ba0d-2e6f5cfd189d |  | note | Records Required: Inspection between BECA/Higgins Staff
label | cd911ee0-e8e8-5cef-838f-26f375ddc6c8 |  | note | Responsibility: Renewals Manager
checkpoint-status |  |  | checkpoint | Surface Finish
label | 3c99e71b-8b41-5303-b86a-3c0774901386 |  | note | H
label | bb45cc1e-08c1-54df-b448-2fdb48c83600 |  | note | Reference or Specification: NZTA B/2
label | 0b78398c-bff0-54bb-ba41-7f6a84ed1365 |  | note | Method/Test required: On-Site Inspection
label | 787a82f4-31b9-535f-8444-a84c12e57128 |  | note | How Often? Per site
label | ff8de13c-611c-52e4-8c96-e610b37e8865 |  | note | Records Required: Inspection between BECA/Higgins Staff
label | c4261e22-e3c1-542e-a470-91ceb7d77a53 |  | note | Responsibility: Renewals Manager
checkpoint-group |  |  | section | 5.0 Aggregate Testing – Sealing Chip
checkpoint-status |  |  | checkpoint | Crushing Strength
label | a852e6d6-92de-5d93-927b-24296af73fb2 |  | note | T
label | 1a67d1eb-d5e3-511d-a42b-aef096625f5a |  | note | Reference or Specification: NZTA M/6 3.2
label | a3e5672c-429a-5a6c-8a02-82c4202cad12 |  | note | Method/Test required: <10% fines passing 2.36mm under 230 KN load
label | 2391c29b-21c6-55d2-abcf-51df95924414 |  | note | How Often? 1 Test
label | 4fc6571e-92c0-5d3a-afe1-09eb4496d7ad |  | note | Records Required: Test Report
label | 1f84c44d-ab0e-5b39-8a4c-b2d817cab78f |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Weathering Quality
label | 8c292de0-11d5-511e-805e-cf1c804ca0cf |  | note | T
label | 087f13a1-3bb3-57fe-8728-1158d8bccc08 |  | note | Reference or Specification: NZTA M/6 3.3
label | 27da9846-1198-5f67-8e33-1dfe6c663f6d |  | note | Method/Test required: AA or BA
label | 5b1cd088-984d-53f3-8d60-9c713179019b |  | note | How Often? 1 Test
label | b0482dae-5050-53bb-8d84-dd52f786ec1a |  | note | Records Required: Test Report
label | 09a3f2e5-f547-5aa4-a384-7dbb2efea7f4 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | a67a9e25-0f56-54a7-bd34-861020da906d |  | note | T
label | da45191a-8eed-5778-97fe-d3470b80a631 |  | note | Reference or Specification: NZTA M/6 3.5
label | 86293b8e-ba4f-5c05-8e69-d9e375b99928 |  | note | Method/Test required: PSV Required = 52 min
label | 20f592ec-11f9-5d10-bd60-2ade23589d29 |  | note | How Often? 1 Test
label | 10a97dd4-886d-5e6c-8993-2330e54b1790 |  | note | Records Required: Test Report
label | b039c768-bb3c-5c18-8e57-3df53280449a |  | note | Responsibility: Accredited PSV Testing Agency
checkpoint-status |  |  | checkpoint | Cleanliness
label | 06b739cc-f4bf-5806-b553-468bb5354550 |  | note | T
label | 27e74b13-c0f1-5841-8582-af4d9012d60b |  | note | Reference or Specification: NZTA M/6 4.1.1
label | 8cff71d3-60f5-5356-aa50-f28abbf45208 |  | note | Method/Test required:
label | 355b3bde-d99a-512a-b005-cc1f5d101642 |  | note | • Grade 5 – 89 min
label | 0d81f4cb-b18c-5c99-8279-3f4d7ef85051 |  | note | • Grade 3 – 87 min
label | 758669ac-f922-5da5-b263-c85182f048c3 |  | note | • Grade 4 – 85 min
label | 8680abf9-e9ec-593d-a5c0-9d560bd60a60 |  | note | How Often? 1 Test
label | 067bb561-a99f-5dae-a455-0598076f3438 |  | note | Records Required: Test Report
label | 4a2c7123-b1dc-57ab-9452-ba53457f3708 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Grading
label | 56f750ab-bd4b-58bd-8437-26d3c9a1b7b5 |  | note | T
label | 1a295f33-9f9b-50c4-9735-f06def6e01b5 |  | note | Reference or Specification: NZTA M/6 4.2.1
label | b7e4e3de-8c6d-5237-b9ef-1ad3beb98347 |  | note | Method/Test required: See NZTA M/6 4.2.1
label | b375432a-1c97-51f2-98f0-c1467f7bffc7 |  | note | How Often? 1 Test
label | 612b1b2c-1b98-561c-913d-c9cdbadb1dec |  | note | Records Required: Test Report
label | 353d8af3-05df-5ae1-8dc3-7b5355fad575 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-group |  |  | section | 6.0 Chipseal Control
checkpoint-status |  |  | checkpoint | Confirm viscosity of bitumen
label | 896b6d4a-c855-5e8d-b6f3-f3e1631f9760 |  | note | T
label | 1eb45214-4706-5708-9f82-3c65fe2a67da |  | note | Reference or Specification: NZTA M/1 Table 1
label | d85aa5d4-4f90-5bc9-83c6-34c99e8d4d0d |  | note | Method/Test required: Viscosity PaS at 60°C
label | adcf85fc-9fac-516a-8e77-33f135d3218a |  | note | How Often? 1 Test
label | 165b1375-06bf-5ceb-8122-6bf1f109cc78 |  | note | Records Required: Construction
label | 1dd9a24f-9240-5a73-9b63-121c211638d4 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Confirm penetration grade of bitumen
label | d8ca1c4b-cdb5-5a92-beaf-77b72d3dcecb |  | note | T
label | 4ff06caa-2afd-59de-8b9f-0e2f40db9c47 |  | note | Reference or Specification: NZTA M/1 Table 1
label | a6045246-3959-5d47-86c1-5ec3838e8e3e |  | note | Method/Test required: Penetration at 25°C,100g, five seconds
label | 0612141c-6529-5174-baf0-53bd7f01e77e |  | note | How Often? 1 Test
label | 511580f3-d9e0-5d6f-878d-863a4938e4c0 |  | note | Records Required: Construction
label | ffb0367f-bd6c-545e-a253-e4e670a456c5 |  | note | Responsibility: IANZ accredited laboratory
checkpoint-status |  |  | checkpoint | Spray bitumen, then place chip *and roll – refer design for chipseal Grade
label | 636f4ca1-dcf0-55f3-a3e3-4205a6c0f076 |  | note | I
label | d2e76f2f-fdf4-52b6-ae4e-2dbeb1a8e2af |  | note | Reference or Specification: NZTA M/1 Table 1
label | 7b247478-5d85-5eb6-b57c-d1552f6391eb |  | note | Method/Test required: Visual Check
label | 915ca07f-6b2d-5f7f-9485-85574c4819a7 |  | note | How Often? On-Site
label | 6c88f6fa-f3e3-5be4-8153-44172cfd4a03 |  | note | Records Required: Visual check
label | 321289db-d346-5960-ad4c-8eb827ad0e68 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Check for excessive "windows"
label | 8f462d93-91c6-5a15-aadc-f1099d85794f |  | note | I
label | efa58039-37f4-536e-8ad9-d216abb153fb |  | note | Reference or Specification: NZTA M/1 Table 1
label | dde88c9f-4384-5b52-80eb-a5e43fa2d774 |  | note | Method/Test required: Visual Check
label | 143ffa11-15c0-5b49-a49a-fbec80cefc10 |  | note | How Often? On-Site
label | f8e8a7b4-2d76-5203-a641-fc92ac20b6a9 |  | note | Records Required: Visual check
label | e51f9c18-c7cd-55a0-929f-aa56f2cbf177 |  | note | Responsibility: Supervisor
checkpoint-group |  |  | section | 7.0 Site Close-out
checkpoint-status |  |  | checkpoint | Field Quality Review
label | 9393e35b-95d5-505a-b765-3b1387fb02b4 |  | note | I
label | 474a86e2-8d5f-5ce2-b90b-1cdddc5a344b |  | note | Reference or Specification: QMP
label | 14d1d9b1-6c9e-55c3-ba49-f6bcdb00676a |  | note | Method/Test required: Verification of Work Standards
label | 46f702d1-4cfd-5fdd-9e18-efcdef1c200a |  | note | How Often? 10% of sites
label | 7a94ece2-317f-5cbe-9104-6234286e20e0 |  | note | Records Required: Record in Audit Field of RAMM Contractor
label | 9e1cdbab-4f2d-5896-a962-4cd6fd93812c |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Collect RAMM Data
label | 843a7b8c-0ff1-59ca-bae1-405f585d07c5 |  | note | I
label | c4a1e74b-e6df-5699-b369-a154cfb072a0 |  | note | Reference or Specification: SHDOM / Data Quality Plan
label | 8684986b-d193-5125-b9bf-d1ecff0d3ba7 |  | note | Method/Test required: L1 Accredited Personnel
label | 29b75f49-55e5-565e-8f44-f677abeefa87 |  | note | How Often? All Jobs
label | c04d590f-6209-5bc5-98e1-353b1fb99b96 |  | note | Records Required: SHDOM Specs
label | 1c89e1e4-7723-5f71-9405-c072c13d2208 |  | note | Responsibility: Foreman / Supervisor
checkpoint-status |  |  | checkpoint | Verify RAMM Data
label | 9b13ab29-7ccc-522c-9a7f-6d3ed37cb255 |  | note | I
label | 4698340b-39d7-5c55-8d85-47c535fb998a |  | note | Reference or Specification: SHDOM / Data Quality Plan
label | 662959b9-6420-5989-a4ac-8519f7d202af |  | note | Method/Test required: Level 2 Accredited Personnel
label | ec1acc2e-4074-559c-a4c9-a5e430cc33c4 |  | note | How Often? All Jobs
label | 3c9a8adb-563a-5df0-8542-a9d9b660ca5b |  | note | Records Required: SHDOM Specs
label | c011a5c1-ced8-5f0e-8ec7-3d3a9875ba13 |  | note | Responsibility: Renewals Manager
checklist-flat |  |  | checklist | Approved Design Report |  |  |  |  | Yes | Approved Design Report | e0639135-48eb-4c56-999f-3e1a72be6ef2
checkpoint-status |  |  | checkpoint | Approved Design Report