## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement Rehab - Rotorua Airport | itp |  |  |  | Yes | ITP - Pavement Rehab - Rotorua Airport
section | 1. Procurement
checkpoint | Geometric Design
label | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
label | Acceptance Criteria - Principal Approval
label | Method - Contractor and Principal peer review
label | Frequency - per design revision
label | Responsible Person - Contract / Rehab Manager
label | Conduct - C or PE
label | Produce Record - C
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Pavement Treatment Design
label | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
label | Acceptance Criteria - Principal Approval
label | Method - Contractor and Principal peer review
label | Frequency - per design
label | Responsible Person - Contract / Rehab Manager
label | Verifying Document - Approvals Register - Pavement Rehabilitation Design Report
label | Conduct - C or PE
label | Produce Record - C
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Material Geo Fabric: on the Sub grade (Digout Floor) - Geofabric for drainage improvement on Sub Grade
label | Controlling Documents - TNZ F1 Specification
label | Acceptance Criteria - Pincipal Approval Picture for Docket over Roll
label | Frequency - once per material change
label | Responsible Person - Sub Contractor
label | Verifying Document - Picture for Docket over Roll
label | Conduct - SC
label | Witness - PE
label | Produce Record - PE
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Materials: GAP 65 Pre‐treatment Material (for Type 1, 2‐SB & 3‐SB Only ) - Aggregate Sampling
label | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
label | Verifying Document - Sampling Worksheet
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
checkpoint | Materials: GAP 65 Pre‐treatment Material (for Type 1, 2‐SB & 3‐SB Only ) - Source Property Test
label | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
label | Acceptance Criteria - Soaked CBR ≥ 30%
label | Method - Soaked CBR test (NZS:4407:2015:3.15)
label | Responsible Person - Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: GAP 65 Pre‐treatment Material (for Type 1, 2‐SB & 3‐SB Only ) - Production Property Test
label | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
label | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
label | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
label | Responsible Person - Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
label | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
label | Verifying Document - Sampling Worksheet
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
label | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
label | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
label | Method - Crushing Resistance Test (NZS 4407:1991, Test 3.10)
label | Frequency - One test for every 10,000m³ of source material
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
label | Controlling Documents - Weathering Quality Index (3.3.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
label | Acceptance Criteria - AA, AB, AC, BA, BB or CA
label | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
label | Frequency - One test for every 10,000m³ of source material
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
label | Controlling Documents - California Bearing Ratio (3.3.3) ‐ TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
label | Acceptance Criteria - Soaked CBR ≥ 80%
label | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
label | Frequency - One test for every 10,000m³ of source material
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
label | Controlling Documents - Sand Equivalent (4.2.1.1) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) ‐ TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
label | Acceptance Criteria - Sand Equivalent ≥39; or Clay Index ≤3; or Plasticity Index ≤5
label | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
label | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
label | Controlling Documents - Broken Face Content (4.2.2) ‐ TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
label | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
label | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
label | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
label | Controlling Documents - Particle Size Distribution (4.2.3) ‐ TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
label | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
label | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
label | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) ‐ TNZ M/4: 2006
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Test Report
label | Conduct - SP
label | Witness - PE
label | Produce Record - SP
label | Approval - E
label | Witness Point - Y
checkpoint | Materials: Cement - Stabilising Agent Selection
label | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
label | Acceptance Criteria - GP
label | Method - Visual inspection of supplier docket
label | Frequency - per truck load
label | Responsible Person - Quality Controller/ Project Engineer
label | Verifying Document - Supplier Docket Supplier Cert
label | Conduct - Sp
label | Witness - E
label | Produce Record - Sp / PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Materials: Water - Water draw for stabilising
label | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
label | Acceptance Criteria - Free from impurities justified by use of municipal water supply
label | Method - Visual inspection of hydrant use form
label | Frequency - per truck load
label | Responsible Person - Sub Contractor
label | Verifying Document - Hydrant use form
label | Conduct - SC
label | Witness - PE
label | Produce Record - PE
label | Approval - C
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Sub Soil Drain Materal - Sub Soil Drain Pipe
label | Controlling Documents - Sub Soil Drainage Contruction F/2 Specification
label | Acceptance Criteria - Principal Approval High Density Corrugated Punched Pipe of Iplex Nexus Flo/Marley Brand Class 500 Blue Strip, SN 4 ‐ 110 Dia
label | Method - Visual inspection and Certificate from Supplier
label | Frequency - once per material type
label | Responsible Person - Sub Contractor
label | Verifying Document - Docket Picture
label | Conduct - SC
label | Witness - PE
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Sub Soil Drain Materal - Drainage geo fabric
label | Controlling Documents - Certificate from the supplier/Docket
label | Acceptance Criteria - Principal Approval Bidim A14 Class Min
label | Method - Docket photograph
label | Frequency - one per mateial approval
label | Responsible Person - Sub Contrctor
label | Verifying Document - Docket Picture
label | Conduct - SC
label | Witness - PE
label | Approval - E
holdpoint | HOLD POINT
section | 2. Pre-Implementation
checkpoint | Work Pack complete and held on site
label | Controlling Documents - ..\Work Pack
label | Conduct - SC
label | Produce Record - SC
label | Approval - PE
label | Witness Point - Y
checkpoint | Communication Plan implemented
label | Controlling Documents - ..\4.5 CSCMP
label | Conduct - SC
label | Produce Record - SC
label | Approval - PE
label | Witness Point - Y
checkpoint | Are any consents /approvals required, including for taking water.
label | Controlling Documents - Hydrant Use form
label | Acceptance Criteria - Forms available for applicable days
label | Method - Visual inspection and recording
label | Frequency - Daily as required
label | Responsible Person - Sub Contractor
label | Verifying Document - Hydrant Use Form
label | Conduct - SC
label | Produce Record - SC
label | Witness Point - Y
checkpoint | Quality Control forms on site
label | Controlling Documents - RQP, ITP, Scala Penetrometer Test Records, Material test sheets etc.
label | Acceptance Criteria - Visual Confirmation
label | Frequency - Daily as required
label | Responsible Person - Supervisor
label | Witness - C
checkpoint | Person(s) on site with authority to stop work if quality of final outcome is compromised for any reason
label | Controlling Documents - QMP
label | Acceptance Criteria - At least one nominated staff member on site at all times
label | Responsible Person - Site Supervisor, Quality Controller, Engineer
label | Verifying Document - Pre-start sheets, timesheets
label | Conduct - C or PE
label | Produce Record - PE
checkpoint | On site Prestart Meeting
label | Controlling Documents - Site design information - Earthworks plan - design drawings.
label | Acceptance Criteria - Visual confirmation and walk over - confirm associated works -verify extent of works - verify digouts or additonal items
label | Method - Visual inspection and recording- variation approval process
label | Frequency - Prior to any phyusical work engagement
label | Responsible Person - Supervisor
label | Verifying Document - Pre Strart Attendance sheet
label | Conduct - SC
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Highlight the extent for different pavement types
label | Controlling Documents - Reference from Project Drawing Sheet C 01, 02 & 03
label | Method - Survey/Mobile Roads, Marks with Dazzle
label | Frequency - Chainages for every different pavement sections
label | Responsible Person - Sub Contractor/ Supervisor
label | Verifying Document - Project Drawings
label | Conduct - SC
checkpoint | Records Management (i.e. it is known what documented records are to be kept)
label | Controlling Documents - ITP and QMP state what quality documentation is required
label | Acceptance Criteria - Filled in and Signed ITP
label | Method - Visual inspection, recording and approval
label | Frequency - As per hold points in collaboration with the programme
label | Responsible Person - Quality Controller
label | Verifying Document - ITP
label | Conduct - C
label | Produce Record - C
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
section | 2. Temporary Works (including Traffic Management, Environmental and Health and Safety Controls)
checkpoint | Traffic Management Approved / Implemented (copy in Job Pack on-site)
label | Controlling Documents - Site Specific TMP, COPTTM, Higgins TTM SOP, SCR Form
label | Acceptance Criteria - Passing SCR audits
label | Method - Visual inpsection and recording
label | Responsible Person - STMS
label | Verifying Document - Site Specific TMP, SCR
label | Conduct - C
label | Witness - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Environmental controls in place (Seal of Existing Catchpits or storm water line)
label | Controlling Documents - HSE Audit, JSEA
label | Responsible Person - Site Supervisor
label | Verifying Document - HSE Audit, JSEA
label | Conduct - C
label | Witness - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Health and Safety controls in place (e.g. Isolate work area)
label | Controlling Documents - HSE Audit, JSEA
label | Responsible Person - Site Supervisor
label | Verifying Document - HSE Audit, JSEA
label | Conduct - C
label | Witness - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Standard Operating Procedures / JSEAs available on site
label | Controlling Documents - HSE Audit
label | Responsible Person - Site Supervisor
label | Verifying Document - HSE Audit
label | Conduct - C
label | Witness - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Any service covers or utilities identified and protected to Service Authorities expectations
label | Controlling Documents - PTW Process, B4UDIG
label | Acceptance Criteria - Work always undertaken under live PTW
label | Method - Visual inpsection and recording
label | Frequency - Weekly
label | Responsible Person - Permit Issuer
label | Verifying Document - PTW
label | Conduct - SC
label | Witness - PE
label | Produce Record - SC
label | Approval - PE
label | Witness Point - Y
section | 3. Construction - Pre-treatment Digouts (for Type 1, 2 SB & 3 SB)
checkpoint | Open Digout Depth as per the Attachment 1
label | Controlling Documents - Pavement Rehabilitation Design Report 2019/20 030-0147-6900-7190 Rotorua Airport
label | Method - Install Geogrid 30/30, (Class C) Geoteextile on Floor
label | Responsible Person - Sub Contractor
label | Verifying Document - Photo Graphs with chaniange highlighted
label | Conduct - SC
label | Witness - PE
label | Produce Record - PE
label | Witness Point - Y
checkpoint | Excavation floor drainage
label | Controlling Documents - Higgins SOP 0128 - Digout Repair
label | Acceptance Criteria - 4-8% toward edge of seal
label | Method - Digital level
label | Frequency - As required
label | Responsible Person - Quality Controller/ Supervisor
label | Verifying Document - Dig out QA form
label | Conduct - PE
label | Witness - C
label | Produce Record - PE
label | Approval - C
checkpoint | Sub Grade material hardness (In case of undercut req. on Soft Patch)
label | Controlling Documents - Higgins SOP 0128 - Digout Repair
label | Acceptance Criteria - ≥45 Clegg
label | Method - Cleg Hammer
label | Frequency - 2 per patch
label | Responsible Person - Quality Controller/ Supervisor
label | Verifying Document - Cleg hammer form
label | Conduct - PE
label | Witness - C
label | Produce Record - PE
label | Approval - C
section | 4. Construction - Sub Soil Drainage
checkpoint | Subsoil depth and discharge point into SW system around As per the Cross section Attached with this ITP
label | Controlling Documents - Location as duirected by the principal engineer and methodology as per F/2 Specification
label | Acceptance Criteria - Slope to be confirmed on the site with visual inspection / Laser Level on Site, Blue Strip facing upward
label | Method - Visual inspection to confrim Sub soil draiange installed to the correct depth with pipe surrounded by BIDIM A14
label | Frequency - As required
label | Responsible Person - Sub Contractor
label | Verifying Document - Photo Graphs with Depth and position of blue strip
label | Conduct - SC
label | Witness - PE
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Bedding/ Surrounding material 20/40 drainage 5 round pebbles
label | Controlling Documents - Quarry Docket
label | Acceptance Criteria - Round Shape as per Drainage Specification F2. Depth under pipe & each layer should be min 75 MM
label | Method - Visual inspection
label | Frequency - As required
label | Responsible Person - Sub Contractor
label | Verifying Document - Photographs
label | Conduct - PE
label | Witness - C
label | Approval - E
holdpoint | HOLD POINT
section | 5. Construction - Granular make up and In-situ Modification (GAP 65 5% cement - 250 mm depth for Sub Base @ Pavement Type 1,2 SB & 3 SB) and (TNZ M/4 AP 40 2 % Cement 200 mm depth for Base Couse throughout)
checkpoint | Plant and Machinery Seletion
label | Controlling Documents - Plant and Equipment (6.0.0) - TNZ B/5: 2008
label | Acceptance Criteria - Cement Spreading Truck, Direct Injection Stabilising Mill, Vibratory Single Drum Roller, Pad Footed Roller and PTR
label | Method - Visual Inspection
label | Frequency - Pre-establishment
label | Responsible Person - Sub Contractor
label | Verifying Document - Daily Site Record
label | Conduct - SC
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Weather including temperature
label | Controlling Documents - Weather Limitations (7.1.1) - TNZ B/5: 2008
label | Acceptance Criteria - Ambient air temp ≥5˚ C, Wind speed ≤25km/h, Rainfall ≤0mm
label | Method - Visual Inspection, Met Service/Windy
label | Frequency - Throughout process
label | Responsible Person - Sub Contractor
label | Verifying Document - Daily Site Record, Metservice
label | Conduct - SC
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Spreading of Cement
label | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
label | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
label | Method - Mat test (1m² canvas) and Average Usage Test
label | Frequency - per 400m² and upon emptying the spreader
label | Responsible Person - Sub Contractor
label | Verifying Document - Mat Test Form and truck dockets
label | Conduct - SC
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Addition of Water
label | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
label | Acceptance Criteria - 90-100% OWC
label | Method - Nuclear Densometer Testing prior to Stabilisation
label | Frequency - ≥1 per 1000m² lot
label | Responsible Person - Sub Contractor
label | Verifying Document - NDM Record
label | Conduct - SC
label | Produce Record - PE
label | Approval - C
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Cut Depth
label | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
label | Acceptance Criteria - -5mm and +15mm of design stab depth
label | Method - Physical Measure and Visual Record
label | Frequency - ≥1 per 200m of cut length
label | Responsible Person - Sub Contractor
label | Verifying Document - Photographs and Daily Site Record
label | Conduct - SC
label | Produce Record - PE
label | Approval - C
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Tie in points
label | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, NZ3910 Variations TNZ State Highway Geometric Design Manual
label | Acceptance Criteria - Principal Approval
label | Method - Physical Measure and Visual Record
label | Frequency - Pre-physical work commencement
label | Responsible Person - Sub Contractor
label | Verifying Document - Design alteration variation ACCEPTANCE
label | Conduct - SC
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Longitudinal Joints
label | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
label | Acceptance Criteria - The greater of 100m or 50% of layer thickness
label | Method - Visual Record
label | Frequency - per sucessive cut
label | Responsible Person - Sub Contractor
label | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
label | Conduct - SC
label | Produce Record - PE
label | Approval - C
label | Witness Point - Y
checkpoint | Continuity of Layer
label | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
label | Acceptance Criteria - Longitudinal overlap 1m
label | Method - Visual Record
label | Frequency - per sucessive cut
label | Responsible Person - Sub Contractor
label | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
label | Conduct - SC
label | Produce Record - PE
label | Approval - C
label | Witness Point - Y
checkpoint | Stabilised Material Particle Size Dsictribution (On Base Course only)
label | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
label | Acceptance Criteria - NZTA B/^ Section 7.5.8
label | Method - Wet Sieve
label | Frequency - 3 Per Lot
label | Responsible Person - Lab Technician
label | Verifying Document - Test Report
label | Conduct - LT
label | Produce Record - PE or C
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Strength Test Conducted -ITS (On Base Course only)
label | Controlling Documents - TNZ B2 /NZTA Best Practice Guide/ NZTA T 19 Notes
label | Acceptance Criteria - NZTA T19 Table 1 for Cement Modified Base course with results min 300 KPA for ITS
label | Method - Lab Testing on Sample collected after hoeing
label | Frequency - 1 per lot
label | Responsible Person - Lab Technician
label | Verifying Document - Test Report
label | Conduct - LT
label | Produce Record - PE/C
label | Approval - E
holdpoint | HOLD POINT
checkpoint | Establish Compaction Target
label | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
label | Acceptance Criteria - Formal Agreement
label | Method - Plateau Density Testing
label | Frequency - 1 time, or additional tests when material changes visually (Recommend a minimum of 1-2 tests per section)
label | Responsible Person - Sub Contractor
label | Verifying Document - NDM Record
label | Conduct - LT/SC
label | Produce Record - PE or C
label | Approval - C
label | Witness Point - Y
checkpoint | Compaction Acceptance
label | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 -TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
label | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
label | Method - Nuclear Densometer Testing in Direct Transmission mode
label | Frequency - ≥ 5 tests per 1000m² lot
label | Responsible Person - Sub Contractor
label | Verifying Document - NDM Record
label | Conduct - PE or C
label | Produce Record - PE or C
label | Approval - C
label | Witness Point - Y
checkpoint | Control Testing
label | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
label | Acceptance Criteria - Nil
label | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
label | Frequency - when agreed
label | Responsible Person - Sub Contractor
label | Verifying Document - Test Report
label | Conduct - PE or C
label | Produce Record - PE or C
label | Approval - E
checkpoint | Surface Roughness
label | Controlling Documents - TNZ TM 7003 v1 2. Roughness Requirement
label | Acceptance Criteria - a. No 20 m reading in any lane shall exceed 70 NAASRA count/KM
label | Method - Measured in the Wheel paths of all lane surfaced under the contract in both directions
label | Frequency - On Completion Surface
label | Responsible Person - Sub Contractor/ Lab Technician
label | Verifying Document - Test Report
label | Conduct - LT
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Surface Shape
label | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 ;
label | Acceptance Criteria - Between -5mm and +15mm
label | Method - String lines or Survey Asbuilt
label | Frequency - during construction and prior to seal
label | Responsible Person - Sub Contractor
label | Verifying Document - String Sheet/Survey Asbuilts
label | Conduct - PE
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Cross Fall
label | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
label | Acceptance Criteria - 0.5% ≤ X ≤ ‐0.5%
label | Method - 3m straight edge or Survey Asbuilt
label | Frequency - during construction and prior to seal
label | Responsible Person - Sub Contractor
label | Verifying Document - Cross Fall Records/Survey Asbuilts
label | Conduct - PE
label | Witness - C
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Surface Finish
label | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
label | Acceptance Criteria - Tightly bound matrix post sweep
label | Method - Visual inspection
label | Frequency - prior to seal
label | Responsible Person - Sub Contractor
label | Verifying Document - Pre-seal inspection sheet
label | Conduct - C
label | Witness - C and E
label | Produce Record - C or PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Pre-sealing Requirements
label | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
label | Acceptance Criteria - ≤80%, however 65% is ideal
label | Method - Nuclear Densometer Testing
label | Frequency - if required, ≥5 tests per 1000m² lot
label | Responsible Person - Sub Contractor
label | Verifying Document - NDM Record
label | Conduct - C
label | Witness - E
label | Produce Record - PE
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
section | 5. Construction - Granular make up and In-situ Modification (GAP 65 5% cement - 250 mm depth for Sub Base @ Pavement Type 1,2 SB & 3 SB) and (TNZ M/4 AP 40 2 % Cement 200 mm depth for Base Couse throughout)
checkpoint | Binder - Penetration Grade
label | Controlling Documents - TNZ M/1
label | Acceptance Criteria - Table 1
label | Method - Property Test
label | Frequency - Annual
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
label | Witness Point - Y
checkpoint | Binder - Polymer Modified Emulsion
label | Controlling Documents - Higgins Internal Specification
label | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
label | Method - Property Test
label | Frequency - 1/100,000 litres supplied
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
label | Witness Point - Y
checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
label | Controlling Documents - TNZ M6, RNZ 9805:2009
label | Acceptance Criteria - <10% fines under 230kN minimum
label | Method - Sample Test - Crushing Resistance
label | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
label | Controlling Documents - TNZ M6, RNZ 9805:2009
label | Acceptance Criteria - AA or BA
label | Method - Weathering Quality Index
label | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Skid Resistance
label | Controlling Documents - NZTA T/10
label | Acceptance Criteria - Meet Skid performance Requirement
label | Method - Aggregate Perfomance Method
label | Frequency - Each Site
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Cleaness Value
label | Controlling Documents - NZTA P/17, M/6
label | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
label | Method - Sample Test - Cleaness Value
label | Frequency - Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Particle Size/Shape
label | Controlling Documents - NZTA P/17, M/6
label | Acceptance Criteria - As per Table 2 and 3 NZTA M/6
label | Method - Sample Test - Particle Size/Shape
label | Frequency - Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Broken Faces
label | Controlling Documents - NZTA P/17, M/6
label | Acceptance Criteria - 98%
label | Method - Sample Test - Broken Faces
label | Frequency - Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Chipseal Designs
label | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
label | Acceptance Criteria - Client Approval
label | Method - Review
label | Frequency - Annual
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - EBOP NOC Design Report Acceptance
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Finalise Sprayrate
label | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
label | Acceptance Criteria - N/A
label | Method - Review
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Site/Spray Instruction
label | Conduct - C
label | Produce Record - C
label | Approval - N
label | Witness Point - Y
checkpoint | Check weather
label | Controlling Documents - N/A
label | Acceptance Criteria - surface. Base Temp ≥ 10ºC and rising. No rain forecast
label | Method - Weather Forecast
label | Frequency - Prior to establishment each day
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - Daily Report, Chip Sealing Quality and Site Record
label | Conduct - PE
label | Produce Record - PE
label | Approval - C
label | Witness Point - Y
checkpoint | Ensure limits of site are marked
label | Controlling Documents - EBOP NOC Design Report
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Prior to start sealing each site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Establish TTM
label | Controlling Documents - TMP
label | Acceptance Criteria - Comply with TMP
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor / STMS
label | Verifying Document - Daily Diary / STMS Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Sweep surface clean of deleterious material
label | Controlling Documents - P/17
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Each site, prior to start of sealing
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Record ATP's on site
label | Controlling Documents - N/A
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Each site, prior to start of sealing
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Confirm correct treatment(s) and chip
label | Controlling Documents - EBOP NOC Design Report
label | Acceptance Criteria - Details/chip correct
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
holdpoint | HOLD POINT
checkpoint | Cutback Bitumen Blend
label | Controlling Documents - RNZ 9803_0513
label | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
label | Method - Sample and test
label | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
label | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Bitumen Application Rate
label | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
label | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
label | Method - Test, Review
label | Frequency - Per Sprayer, Per Site
label | Responsible Person - Surfacing Supervisor/ Supervisor
label | Verifying Document - E/2 Certificate. Spray Sheets
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Chip Application Rates
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - As per Chipping Guide
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor/ Supervisor
label | Verifying Document - check sheet. Chip Sealing Quality and
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Rolling
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor/ Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Cleanup
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Site including adjacent surfaces free of loose chip
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor/ Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
holdpoint | HOLD POINT
checkpoint | Post Sweeping
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Site including adjacent surfaces free of loose chip
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor/ Supervisor
label | Verifying Document - Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
holdpoint | HOLD POINT
checkpoint | Linemarking and RRPM Reinstated
label | Controlling Documents - MOTSAM
label | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
label | Method - Visual
label | Frequency - Each Site
label | Responsible Person - Surfacing Supervisor/ Supervisor
label | Verifying Document - Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Removal of TTM
label | Controlling Documents - TMP
label | Acceptance Criteria - Comply with TMP
label | Method - Record
label | Frequency - Each Site
label | Responsible Person - STMS/ Supervisor
label | Verifying Document - STMS Record / Daily Report
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Resurfacing Construction Completion report
label | Controlling Documents - NOC; MS 6.1.3
label | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
label | Method - Record
label | Frequency - Each Site
label | Responsible Person - Resurfacing Construction Completion report
label | Verifying Document - Daily Report / STMS Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Witness Point - Y
checkpoint | Chipseal Post-Verification Testing and Report
label | Controlling Documents - NOC; MS 6.1.3
label | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
label | Method - Record
label | Frequency - Each Site
label | Responsible Person - Surfacing Manager
label | Verifying Document - Chipseal Post- Verification Testing and Report
label | Conduct - C
label | Produce Record - C
label | Approval - C
holdpoint | HOLD POINT
section | 7. Close Out
checkpoint | Post Construction Walkover
label | Acceptance Criteria - Formal Agreement
label | Method - Visual Inspection
label | Frequency - Post seal sweep
label | Responsible Person - Quality Controller, Supervisor and Engineer
label | Verifying Document - Meeting Minutes
label | Conduct - C
label | Produce Record - C, PE and E
label | Witness - C
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT
checkpoint | Pavement Rehabilitation Construction Completion Report
label | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
label | Acceptance Criteria - Engineer Approval
label | Method - Visual Inspection
label | Frequency - ≤2 months of 1st Coat Seal
label | Responsible Person - Contract Manager/ Quality Control
label | Verifying Document - Signed Report
label | Conduct - C
label | Produce Record - C, PE and E
label | Witness - C
label | Approval - E
label | Witness Point - Y
holdpoint | HOLD POINT