## Folder Structure
SPEEDRAMP | Speedramp Elevation 1 | Grid R1/1-8 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
|  | Grid R1/9-14 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
|  | Grid R1/15-20 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
|  | Grid R1/21-26 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
| Speedramp Elevation 2 | Grid R2/1-8 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
|  | Grid R2/9-14 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
|  | Grid R2/15-20 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
|  | Grid R2/21-26 | B. External Sealant Checklist
D. Seismic Checklist
E. Waterstop Checklist
| Under Speedramp 1 | Ground / Level 1 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
| Under Speedramp 2 | Ground / Level 1 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
| Under Speedramp 3 | Level 1 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 2 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
| Under Speedramp 4 | Ground / Level 1 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
| Under Speedramp 5 | Ground / Level 1 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
STAIRS | Stair 1 | Level 1 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 2 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 3 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 4 | C. Internal Sealant Checklist
D Seismic Checklist
| Stair 2 | Level 1 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 2 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 3 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 4 | C. Internal Sealant Checklist
D Seismic Checklist
| Stair 3 | Level 1 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 2 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 3 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 4 | C. Internal Sealant Checklist
D Seismic Checklist
| Stair 4 | Level 1 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 2 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 3 | C. Internal Sealant Checklist
D Seismic Checklist
|  | Level 4 | C. Internal Sealant Checklist
D Seismic Checklist
| Stair 5 and 6 | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
| Stair 7 | Level 1 | C. Internal Sealant Checklist
D Seismic Checklist
OFFICE LIFTSHAFT | Grid C3/G-S3 | Level 2 | B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 3 | B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 4 | B. External Sealant Checklist
C. Internal Sealant Checklist
D Seismic Checklist
OFFICE BUILDING | Grid C4/A-E | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
| Grid C4/E-J | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
| Grid C3/S4-S3 | Level 2 | B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 3 | B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Level 4 | B. External Sealant Checklist
C. Internal Sealant Checklist
|  | Roof | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
LOBBY CONCOURSE WEST | Grid J/2-4 | Level 1 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
| Grid K/2-4 | Level 1 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
LOBBY CONCOURSE EAST | Grid J/13-16 | Level 1 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
| Grid K/13-16 | Level 1 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 2 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 3 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist
|  | Level 4 | A. Baffles Checklist
B. External Sealant Checklist
C. Internal Sealant Checklist
D. Seismic Checklist

## A.Baffles Checklist
Type | Name | Value
Checklist | Façade Baffle & Soaker Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Install Sika Facade Battle to vertical joints | Photo Required
Checkpoint | Install S/S pin into rebate and mechanically fix to panel | Photo Required
Checkpoint | Install SS soaker - beadseal with Sikaflex 11 FC & mechanically fixed to one panel | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## B. External Sealant Checklist
Type | Name | Value
Checklist | External Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install expansion tape to horizontal & vertical inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer to horizontal & vertical joints | Photo Required
Checkpoint | Apply Sikahyflex 250 to horizontal & vertical joints | Photo Required
Checkpoint | Write initials and date beside each joint | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## C. Internal Sealant Checklist
Type | Name | Value
Checklist | Internal Joint Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install expansion tape to horizontal & vertical inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer to horizontal & vertical joints | Photo Required
Checkpoint | Apply Sika Fire 400 sealant to horizontal & vertical joints | Photo Required
Checkpoint | Write initials and date beside each joint | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## D. Seismic Checklist
Type | Name | Value
Checklist | Emseal Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Apply Sikadur 31CF to vertical & horizontal joints | Photo Required
Checkpoint | Install Sika Emseal Seismic Colorseal to vertical & horizontal joints | Photo Required
Checkpoint | Install Sika Emseal WFR2 to vertical & horizontal joints | Photo Required
Checkpoint | Apply Sika WS-295 sealant to butt ends | Photo Required
Checkpoint | Apply corner beads using Sika WS-295 sealant | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## E. Waterstop Checklist
Type | Name | Value
Checklist | Waterbar Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install waterstop 101 RX to vertical stitch joints | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required