## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation | itp |  |  |  |  | ITP - Clearing and Grubbing, Earthworks - Cut, Fill and Subgrade Preparation Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using Issued for Construction (IFC) drawings
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: IFC drawings and drawing registers
note | INSPECTION/TEST METHOD: Document Review / Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSMP, EMP, TMP, SWMS & WP. Access and egress inspected and assessed for stability.
note | REFERENCE DOCUMENTS: OHSMP, EMP, TMP, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.3 Ground Penetration Permit
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: A ground penetration permit must be issued prior to excavation commencing.
note | ○ Plant and equipment must be appropriate for the task.
note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
note | REFERENCE DOCUMENTS: Ground Penetration Permit
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.4 Implementation of environmental measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
note | REFERENCE DOCUMENTS: Project Spec Cl176.A3, EMP
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.5 Flora and Fauna
note | FREQUENCY: Prior to removing vegetation
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits. Shall fence and sign all sites nominated as No-Go Zones.
note | REFERENCE DOCUMENTS: Cl176.I1
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 Protection of Existing Vegetation
note | FREQUENCY: Prior to comencement of any work
note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the Superintendent shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
note | ○ If directed by the Superintendent, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
note | ○ Protective fencing shall consist of, as a minimum, star pickets with three strands of wire and parawebbing.
note | REFERENCE DOCUMENTS: EMP Cl201.1
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer / Superintendent
textbox | DATE:
checkpoint | 1.7 Flora and Fauna
note | FREQUENCY: Prior to removal of vegetation
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
note | REFERENCE DOCUMENTS: EMP Cl176.J1
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 Authorisation for works
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Check that all relevant approvals have been granted including verification of the works area
note | ○ Ensure work pack is reviewed & signed
note | REFERENCE DOCUMENTS: Work Procedure
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.9 Utilities
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.10 Traffic Management
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS.
note | REFERENCE DOCUMENTS: TMS
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 2 - Clear & Grub
checkpoint | 2.1 Limits of work
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Limits of clearing and grubbing shall be the whole length between the following chainages:
note | REFERENCE DOCUMENTS: Cl201.03
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.2 Clear and grub trees and vegetation
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: The area within the specified limits shall be cleared of all vegetation, refuse and obstructions down to natural surface. The Contractor shall not undertake any clearing work or any type of disturbance outside of the specified limits of work unless approved by the Superintendent.
note | REFERENCE DOCUMENTS: Cl201.04
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.3 Clear and grub trees and vegetation
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
note | REFERENCE DOCUMENTS: Cl201.05
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.4 Clear and grub trees and vegetation (embankment areas)
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
note | REFERENCE DOCUMENTS: Cl201.05
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.5 Clear and grub trees and vegetation at culvert sites
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6 m2 (unless otherwise shown on drawings)
note | REFERENCE DOCUMENTS: Cl201.06
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.6 Backfill holes
note | FREQUENCY: After clearing
note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted to the same degree as the surrounding material
note | REFERENCE DOCUMENTS: Cl201.05
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.7 Dispose of Trees and vegetation
note | FREQUENCY: After clearing
note | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from site. Small tree branches, weeds and shrubs shall be disposed of by chipping and mulching.
note | REFERENCE DOCUMENTS: Cl201.07 (b)
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.8 Damage to Fencing
note | FREQUENCY: During Clearing
note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
note | REFERENCE DOCUMENTS: Cl201.09
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 3 - Earthworks
checkpoint | 3.1 Material Categorisation
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Prior to commencing excavation in any area and during excavation work, the contractor and Superintendent shall inspect and agree upon the type / category of material encountered
note | REFERENCE DOCUMENTS: Cl 204.06c
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Stripping of Topsoil
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
note | REFERENCE DOCUMENTS: Cl 204.05
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.3 Unsuitable Material
note | FREQUENCY: Each Lot containing unsuitable material
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ For unsuitable material, the proposed in-situ treatment or extent of excavation submitted to the Superintendent for review.
note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
note | REFERENCE DOCUMENTS: Cl 204.04b, Cl 204.07d
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 Subgrade Fill Material
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Fill material free of topsoil, deleterious and/or perishable matter.
note | ○ Type A material shall comply with the requirements of Table 204.041
note | ○ Type B material shall have minimum Assigned CBR of 4% and Assigned swell less than 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
note | ○ Type C material shall be capable of being spread in layers of not more than 500mm
note | REFERENCE DOCUMENTS: Cl 204.04, Table 204.041
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Test Report
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.5 Treatment of Rock Subgrade
note | FREQUENCY: Each Lot (prior to construction of regulating layer)
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
note | REFERENCE DOCUMENTS: Cl 204.06f
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 Groundwater
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
note | REFERENCE DOCUMENTS: Cl 204.06h, EMP
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Water Authorities and Superintendent Approval, This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 Surface finish of batters
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Surface of cut and fill batters to be topsoiled and textured by scarifying or horizontal grooving
note | REFERENCE DOCUMENTS: Cl 204.06i
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.8 Borrow Excavation
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Borrow Excavations within the road reservation are not permitted without prior approval of Superintendent
note | REFERENCE DOCUMENTS: Cl 204.09
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed, Correspondance with superintendent
note | HP
note | RESPONSIBILITY: Site Engineer / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 Areas upon which fills are to be constructed
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Areas where fill is to be constructed must be reviewed by the superintendent prior to the placement of any fill in the area
note | REFERENCE DOCUMENTS: Cl 204.10b
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
checkpoint | 3.10 Placing of Fill
note | FREQUENCY: Each Layer
note | ACCEPTANCE CRITERIA: Fill placed and spread in uniform layers. Each layer keyed into the next with a textured surface. Any rocky material uniformly distributed throughout the layer.
note | ○ Compacted layers do not exceed specified maximum thicknesses:
note | ○ Type A: Maximum compacted thickness 200mm (can be used in locations specified for Type B material)
note | ○ Type B: Maximum compacted thickness 200mm (can be used in locations specified for Type C material). Where > 25% rock by volume, loose layer thickness may equal 125% of typical maximum particle dimension up to max 500mm. No rocks > 80% of loose thickness of the layer.
note | ○ Type C: Maximum compacted thickness 300mm. Where > 25% rock by volume, loose thickness of each layer may equal the maximum particle dimension of the rock up to max 500mm. Reference table 204.111
note | REFERENCE DOCUMENTS: Cl 204.10d
note | INSPECTION/TEST METHOD: Visual Inspection / Measure
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 4 - Testing and Surface Preperation
checkpoint | 4.1 Test Rolling
note | FREQUENCY: Each layer
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Areas upon which fills are to be constructed, all layers of fill, material within 150 mm of the cut floor level in cuts, and all stabilisied material shall be test rolled in accordance with Section 173.
note | REFERENCE DOCUMENTS: Cl 173.03, Cl 204.12
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 Cut and Fill Tolerances
note | FREQUENCY: In accordance with Table 204.031. Lots < 4,000m²
note | ACCEPTANCE CRITERIA: Formation width and alignment: not less than the widths specified or shown on the drawings
note | ○ Formation level and shape: Verges match FSL at outer edge of shoulder or pavement (± 50mm from design level)
note | ○ Boxing width and alignment: not less than specified or design levels & no deviation > 50mm from designed offset from the centreline or design line.
note | ○ Type A Material: thickness and width not less than specified at any point.
note | ○ Type B material (immediately below capping / selected material): +15mm -30mm specified level
note | ○ Cut floor level (when capping layer required): +15mm -30mm specified level
note | ○ Cut floor level (no capping layer): same as subgrade tolerance
note | ○ Subgrade Scale A & B: random levelling Cl204.03(h). No point > 20mm below a 3m straightedge laid in any direction.
note | ○ Batter and slope: Not steeper than specified at any cross section.
note | ○ Batter line: Batter point < 10% of the batter height outside the calculated batter line.
note | ○ Surface Drains: Invert levels and side slopes ±50mm and free from depressions capable of retaining water.
note | ○ The contractor shall establish a procedure to verify that compacted layers do not exceed the specified thickness. Verification records must provide evidence of measurements taken every three layers.
note | REFERENCE DOCUMENTS: Cl 204.03, Table 204.031,
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | SCP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.3 Subgrade level conformity
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
note | ○ Level tolerances:
note | ○ Scale A - 80 measurements per lot
note | • Range = +5, -15mm
note | • Max S = 12 mm
note | ○ Scale B - 40 measurements per lot
note | • Range x = +5, -25mm
note | • Max S = 15 mm
note | REFERENCE DOCUMENTS: Cl 204.03
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed, Survey report
note | SCP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.4 Fill Material Compaction & Moisture Content Requirements
note | FREQUENCY: Each Lot as defined in Table 204.142.
note | ○ 6 tests per lot.
note | ○ Small area lots (<500m2) as per Cl173.04d.
note | ○ 3 test mean lots.
note | ○ +2% compaction req.
note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Tolerances, Properties and Testing Scales and subsequent Requirements.
note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
note | REFERENCE DOCUMENTS: Cl 204.13, Table 204.131, Table 204.161
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.5 Material Properties Testing (Scale B)
note | FREQUENCY: Once per lot or per material change, as per Table 204.141
note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
note | REFERENCE DOCUMENTS: Cl 204.14, Table 204.041, Table 204.161
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.6 Preparation and Maintenance of Final Earthwork Surface and Subgrade
note | FREQUENCY: Each Lot (Final Layer only)
note | ACCEPTANCE CRITERIA: Smooth, hard, tightly bound surface presented. Free from depressions capable of holding water.
note | ○ Material within 150mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to placement of pavement layer.
note | REFERENCE DOCUMENTS: Cl 204.15
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Add Signature
checkpoint-no-status | Table 204.031 Minimum Number of Level Measurements and Tolerances
label | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̅ Range (mm) ¦¦ Tolerance: Maximum S (mm)
label | – – – – – – – – – –
label | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
label | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
label | – – – – – – – – – –
label | Notes:
label | 1. x̅ is the mean value of all level readings taken in the lot
label | 2. S is the standard deviation of all level readings taken in the lot
label | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
checkpoint-no-status | Table 204.041
label | Location and Use of Type A Material ¦¦ Physical Properties: Assigned CBR (min) % (1) ¦¦ Physical Properties: Swell % (1) ¦¦ Physical Properties: Permeability (max) m/s (2)
label | – – – – – – – – – –
label | Capping Layer ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ 5 x 10^-9
label | Selected Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
label | Verge Material ¦¦ ##:6 ¦¦ ≤ 1.0 ¦¦ 5 x 10^-9
label | Structural Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
label | Other Type A Material ¦¦ ##:6 ¦¦ ≤ 1.5 ¦¦ Not Applicable
label | – – – – – – – – – –
label | Location and Use of Type A Material ¦¦ Limits of Grading (% passing by mass) :: Post Compaction Sieve Size AS (mm)
label | – – – – – – – – – –
label | Capping Layer ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | Selected Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | Verge Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | Structural Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | Other Type A Material ¦¦ 75.0 :: ##:100 ¦¦ 37.5 :: ##:- ¦¦ 4.75 :: ##:40-80 ¦¦ 0.425 :: ##:- ¦¦ 0.075 :: ##:10-40
label | – – – – – – – – – –
label | Notes:
label | (1) The Assigned CBR and percentage swell values are to be determined in accordance with VicRoads Code of Practice RC 500.20. Sampling for CBR testing shall be undertaken after field compaction.
label | (2) The permeability value is to be determined in accordance with VicRoads Code of Practice RC 500.16. The permeability value is to be determined on specimens manufactured from that fraction of material which passes a 19.0 mm AS sieve, compacted at optimum moisture content and 98% of maximum dry density as determined by testing using standard compactive effort for CBR and swell.
checkpoint-no-status | Table 204.111 Fill at Structures
label | Non Vibrating Rollers - Static Weight * (tonne) ¦¦ Vibrating Rollers - Total Applied Force ** (kN) ¦¦ Minimum Distance from Compaction Plant to Abutments, Retaining Walls and Wing Walls (m) ¦¦ Minimum Cover over Top of Culverts (m)
label | – – – – – – – – – –
label | Less than 2 ¦¦ Less than 20 ¦¦ 0.15 ¦¦ 0.15 ¦¦ 0.15
label | 2 - 5 ¦¦ 21 - 50 ¦¦ 0.3 ¦¦ 0.3 ¦¦ 0.15
label | 6 - 10 ¦¦ 51 - 100 ¦¦ 1.2 ¦¦ 1.2 ¦¦ 0.4
label | 11 - 20 ¦¦ 101 - 200 ¦¦ 2.4 ¦¦ 1.2 ¦¦ 0.4
label | 21 - 35 ¦¦ 201 - 350 ¦¦ 2.4 or height of structure (whichever is greater) ¦¦ 1.2 or height or structure (whichever is greater) ¦¦ 0.7
label | – – – – – – – – – –
label | * Includes vibrating rollers operating in non-vibrating mode.
label | ** Total Applied Force is the sum of the static weight and the vertical component of centrifugal force.
checkpoint-no-status | Table 204.131 Compaction Requirements
label | Material Type and Location ¦¦ Scale A: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale B: Minimum Characteristic Value of Density Ratio (%) ¦¦ Scale C: Minimum Characteristic Value of Density Ratio (%)
label | – – – – – – – – – –
label | All Type A Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
label | Type B Material placed within 400 mm of top of Type B Material ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
label | Ripped and re-compacted material below Cut Floor Level ¦¦ 99.0 ¦¦ 98.0 ¦¦ 100.0
label | Type B Material placed more than 400 mm below top of Type B Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
label | The top 150 mm of areas where fill is to be constructed ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
label | Type C Material ¦¦ 97.0 ¦¦ 95.0 ¦¦ 95.0
checkpoint-no-status | Table 204.142 Minimum Frequency of Testing for Compaction and Moisture Content
label | Material ¦¦ Acceptable Lot Size in a Single Layer of Work ¦¦ Minimum Testing Frequency
label | – – – – – – – – – –
label | Type A Material ¦¦ One day's production or 5,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
label | – – – – – – – – – –
label | Type B Material
label | • Ripped and re-compacted below Cut Floor Level ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every sercond lot of like material and work
label | • Placed within 400 mm of top of Type B Material ¦¦ One day's production or 10,000 m^2, whichever is the lesser ¦¦ Every second lot of like material and work
label | • Placed more than 400 mm below top of Type B Material ¦¦ One day's production ¦¦ Every third lot of like material and work
label | – – – – – – – – – –
label | Type C Material ¦¦ One day's production ¦¦ Every sixth lot of like material and work
checkpoint-no-status | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
label | Road Name ¦¦ Chainage / Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
label | – – – – – – – – – –
label | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
label | – – – – – – – – – –
label | Note: Where no level of testing is nominated, Scale A applies.