## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Linemarking & RRPM & Road Furniture and Signage | itp |  |  |  |  | ITP - Linemarking & RRPM & Road Furniture and Signage Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Document review
note | RECORD OF CONFORMITY: This ITP signed off
note | HP*
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP*
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | DATE:
checkpoint | 1.3 Signage Conformance
note | FREQUENCY: Before commencement of activity
note | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with contract drawings Road Signage Installation
note | REFERENCE DOCUMENTS: Drawings 2101-2116
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.4 Service Identification
note | FREQUENCY: Prior to start
note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation of posts (Road Sign Preparation)
note | REFERENCE DOCUMENTS: DBYD
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Ground penetration permit, This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 2 - Linemarking Works
checkpoint | 2.1 Set out of line markings; dimensions and spacings
note | FREQUENCY: Prior to commencing line marking works
note | ACCEPTANCE CRITERIA: Holding Point:
note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
note | (a) New pavement markings shall be positioned in accordance with the following requirements:
note | (i) set out by the Contractor in conformance with the appropriate standard required by Clause 721.A03
note | (ii) applied within the tolerances listed in Table 721.A101.
note | (b) Temporary Reflective Markers Temporary reflective markers for new works shall be placed at the following minimum spacings on all longitudinal lane lines, except that on any curve less than 500 m in radius the spacing shall not be more than 12 metre centres:
note | ○ AADT ≥5,000 and National Highway 12 metre centres
note | ○ AADT ≥1,000 and <5,000 24 metre centres
note | ○ AADT <1,000 48 metre centres
note | REFERENCE DOCUMENTS: Cl.721.B05
note | INSPECTION/TEST METHOD: Document review & Site inspection
note | RECORD OF CONFORMITY: Consent to proceed by Superintendent OR written exemption granted, This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Verification of line marking material
note | FREQUENCY: Prior to commencing line marking works
note | ACCEPTANCE CRITERIA: Line marking material is to comply with minimum requirements as specified in Spec Tables 721.D021 and 721.E021
note | REFERENCE DOCUMENTS: Cl.721.D02, Cl.721.E02
note | INSPECTION/TEST METHOD: Document review
note | RECORD OF CONFORMITY: Material compliance, This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 3 - RRPMs
checkpoint | 3.1 Materials
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Markers shall comply with the relevant requirements of AS 1906, Part 3.
note | ○ Epoxy adhesive shall be Standard Set or Rapid Set adhesive complying with the relevant requirements of AS 3554
note | REFERENCE DOCUMENTS: Cl 710.03
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.2 Preparing Adhesive
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Adhesive components shall be batched so that the mixed adhesive contains not less than 45% nor more than 55% by volume of either component. Before starting work each day, or when changing to a different batch of adhesive, a hand mixed colour standard shall be prepared for reference during the day.
note | ○ When hand-mixing is used not more than 500 g of each component shall be mixed at any time.
note | ○ The components shall be mixed on a flat surface and the mixed adhesive shall be used within 10 minutes of the time the two components are brought together.
note | ○ Hot melt bitumen adhesive shall not be used on days of total fire ban without the written approval of the Tasmanian Fire Service
note | REFERENCE DOCUMENTS: Cl 710.04, Cl 710.05
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.3 Pavement preparation
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: The Contractor shall sweep or air blast each marker site as necessary to remove loose material before placing markers. Markers shall only be placed at locations where the pavement is free from dirt, oil, grease, paint, or any other material
note | REFERENCE DOCUMENTS: Cl 710.06
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.4 Placing markers
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Markers shall not be placed in any of the following circumstances:
note | • when the pavement is wet;
note | • when the relative humidity is greater than 80%;
note | • when the ambient temperature or the temperature of the road surface is less than 15deg for standard set adhesive or 0deg for rapid set or hot melt adhesive.
note | ○ Where a marker is not positioned correctly within 10 seconds for hot melt bitumen adhesive, 2 minutes for rapid set machine mix adhesive, 4 minutes for standard set machine mix, or 10 minutes for standard set hand mix from the time mixing commences, it shall be discarded and a new marker placed.
note | REFERENCE DOCUMENTS: Cl 710.07
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.5 Tolerances
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: (a) Markers in Line with Broken Line Segments
note | ○ Transverse position within 25 mm of the centreline of the segments.
note | ○ Longitudinal position within 0.5 m of the specified position.
note | (b) Markers in a Longitudinal Group
note | ○ Transverse position of the centre of each marker within 25 mm of the specified position and within 10 mm of a line joining the centres of the end markers of the group.
note | (c) Markers Adjacent to Unbroken Line
note | ○ Clearance to edge of line within 5 mm of that specified.
note | ○ Longitudinal mismatch between markers in transverse pairs at barrier line not more than 25 mm.
note | (d) Orientation of Reflective Markers
note | ○ Lower edge of the reflective face at 85deg to 95deg to the centreline of the roadway or any adjacent line.
note | REFERENCE DOCUMENTS: Cl 710.02
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 4 - Testing
checkpoint | 4.1 Line Marking Tolerances
note | FREQUENCY: After completion of works
note | ACCEPTANCE CRITERIA: Line marking shall comply with the tolerances shown in Table 721.A101.
note | REFERENCE DOCUMENTS: Table 721.A131, Project Spec. Table 721.A101
note | INSPECTION/TEST METHOD: Document review & Site inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.2 Removal of Non-compliant marking
note | FREQUENCY: After completion of works
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Where the removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence
note | REFERENCE DOCUMENTS: Project Spec. Cl.721.A12
note | INSPECTION/TEST METHOD: Document review
note | RECORD OF CONFORMITY: Approval from Superintendent, This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Signage
checkpoint | 5.1 Setting Out
note | FREQUENCY: Prior to start
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
note | REFERENCE DOCUMENTS: Drawings 2101 to 2116
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.2 Conformity with drawings
note | FREQUENCY: Four weeks prior to installation
note | ACCEPTANCE CRITERIA: Witness Point
note | ○ If the Contractor proposes to use an alternative method of installation, the Contractor shall submit full details to the Superintendent for approval not later than four weeks before the commencement of sign installation
note | REFERENCE DOCUMENTS: Cl 714.04
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
checkpoint | 5.3 Post & Foundations
note | FREQUENCY: Prior to Start
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
note | REFERENCE DOCUMENTS: Cl 714.06
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 Signage Install
note | FREQUENCY: Each Sign
note | ACCEPTANCE CRITERIA: Sign to be installed as per most current project and DSG standard drawings, local council documentation, and to the correct height and position.
note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
note | REFERENCE DOCUMENTS: DSG standard drawings. Cl 714.07
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.5 Tolerances
note | FREQUENCY: Each Sign
note | ACCEPTANCE CRITERIA: Posts vertical with maximum deviation of 1 in 100
note | ○ Post tops 50mm +-10mm below top edge of sign
note | ○ Signs mounted level with maximum deviation of 1 in 100
note | ○ +-40mm of the height specified in the Sign and Post schedule
note | ○ +-100mm of the pegged sign location or specified location
note | REFERENCE DOCUMENTS: Cl 714.05, Cl 714.07
note | INSPECTION/TEST METHOD: Measure
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Add Signature
checkpoint-no-status | Table 721.A101 Tolerances on Pavement Markings
label | Markings ¦¦ Tolerance
label | – – – – – – – – – –
label | (A) Pavement Markings (1)
label | Distance between the centreline of the marking and the centreline of the set out mark ¦¦ < 30 mm
label | Distance between the centreline of the completed marking and the centreline of the previous marking ¦¦ < 15 mm
label | Width of completed painted markings ¦¦ ± 10 mm of the specified dimensions
label | Width of completed markings for long life materials ¦¦ 0 mm to +10 mm
label | Length of completed stripes and blocks ¦¦ 0% to +10% of the specified length
label | Gap between dobule lines ¦¦ -10 mm to +0 mm of the required 100 mm gap (2)
label | – – – – – – – – – –
label | (B) Raised pavement markers
label | (i) Markers in line with broken segments
label | Transverse position ¦¦ ±25 mm of the centreline of segments
label | Longitudinal position ¦¦ ±0.5 mm of the specified position
label | (ii) Markers in a longitudinal group
label | Transverse position ¦¦ ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | Longitudinal position ¦¦ ±0.5 mm
label | Spacing of markers within the group ¦¦ ±50 mm of specified spacing
label | (iii) Markers adjacent to an unbroken line
label | Clearance to edge line ¦¦ ±5 mm of the specified dimensions
label | Longitudinal mismatch between markers in transverse pairs ¦¦ <25 mm
label | (iv) Orientation of reflective markers ¦¦ Lower edge of the reflective face at 85° to 95° to centreline of roadway or adjacent line
label | – – – – – – – – – –
label | (C) Thermoplastic profiled lines
label | (i) Tolerances on dimension
label | Line width ¦¦ +20 mm, -5 mm
label | Line height ¦¦ +2 mm, -0 mm
label | Extrusion breadth ¦¦ +10 mm, -0 mm
label | Extrustion spacing ¦¦ ±15 mm
label | Extrustion shape ¦¦ ±25 mm at any point from rectangular shape
label | (ii) Tolerances on position
label | Distance between the centreline of the marking and the centreline of the setout ¦¦ <30 mm
label | Length of the completed lines ¦¦ -0% to +5% of the specified length
label | Longitudinal position of individual extrusions ¦¦ ±50 mm of any previously applied profiled lining
label | – – – – – – – – – –
label | (1) Apparent line of the markings is a smooth, continuous alignment when viewed in the direction of the line.
label | (2) Maintenance of pavement markings: If the gap between the existing lines is 90 mm or less the gap shall not be reduced by the maintenance application.
checkpoint-no-status | Table 721.A131 Acceptance of Retroreflectivity
label | Testing Period (1) ¦¦ Initial Measurement: 3 - 5 weeks ¦¦ Additional Measurement: 5 - 6 months
label | Minimum level of retroreflectivity on sprayed seal surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 220 mcd/lux/m^2
label | Minimum level of retroreflectivity on asphalt and all other surfaces ¦¦ Initial Measurement: 350 mcd/lux/m^2 ¦¦ Additional Measurement: 250 mcd/lux/m^2
label | – – – – – – – – – –
label | (1) Measured after application of the second/final coat of material.
checkpoint-no-status | Table 721.D021 Minimum Requirements - Paint and Glass Beads
label | Paint (1) ¦¦ Glass Beads (2)
label | – – – – – – – – – –
label | Linemarking
label | • New Markings (initial application only)
label | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
label | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
label | • Re-marking (including second application on new markings
label | 0.38 mm dft on sprayed seals ¦¦ Type D-HR (3)
label | 0.35 mm dft on asphalt and all other surfaces ¦¦ Type D-HR (3)
label | – – – – – – – – – –
label | Roadmarking
label | • All marking
label | 0.35 mm dft on sprayed seals ¦¦ Type B-HR
label | 0.30 mm dft on asphalt and all other surfaces ¦¦ Type B-HR
label | – – – – – – – – – –
label | (1) The minimum dry paint film thickness (dft) specified above shall be the end product thickness measured on a 200 mm x 100 mm sheet metal test plate without beads. Consideration shall be given to the texture of the road surface and the method of application used to achieve the requirements of this section.
label | (2) A minimum of 400 g/m^2 shall be retained in the painted marking for all glass beads.
label | (3) An alternative glass bead application rate shall be 300 g/m^2 of D-HR with a separate drop of 200 g/m^2 of B-HR provided that 75% minimum of the D-HR beads is retained at the 5 demonstrated by photographs at each test site.
checkpoint-no-status | Table 721.E021 Minimum Requirements - Long Life and Glass Beads
label | Material ¦¦ Applied Minimum Thickness, Glass Bead and Other Requirements
label | – – – – – – – – – –
label | Thermoplastic
label | Sprayed markings ¦¦ 2.0 mm minimum thickness on logitudinal lines contaiing internmix beads and with a minimum of 400 g/m^2 of Type D-HR or Type B-HR(3) drop-on glass beads retained on the marking surface
label | Extruded line markings (1) ¦¦ 2.0 mm minimum thickness on longitudinal lines containing internmix beads and a minimum of 400 g/m^2 of the Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | Extruded road markings (1) ¦¦ 3.0 mm minimum thickness on intersections containing internmix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | Preformed markings ¦¦ 2.3 mm with a minimum skidding resistance value of 45 BPN (British Pendulum Number) and retroreflective properties agreed with the Superintendent
label | Profiled lines (1) ¦¦ 8.0 mm minimum thickness with a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | – – – – – – – – – –
label | Cold-applied Plastic
label | Sprayed line markings (2) ¦¦ 1.0 mm minimum thickness for longitudinal line markings only with a minimum of 400 g/m^2 of Type D-HR or Type B-HR glass beads retained in and on the marking surface
label | Sprayed road markings (2) ¦¦ 2.0 mm minimum thickness for all road markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | Trowelled, screeded, or extruded markings (1) ¦¦ 2.0 mm minimum thickness of markings containing intermix beads and a minimum of 400 g/m^2 of Type D-HR or Type B-HR drop-on glass beads retained on the marking surface
label | – – – – – – – – – –
label | Pliant Polymer Tape
label | As approved by the Superintendent
label | – – – – – – – – – –
label | (1) The minimum thickness specified shall be the height above the upper road surface level or above the existing marking as appropriate.
label | (2) The minimum thickness specified shall be the height of the material between the glass beads on a metal test plate. All other thicknesses shall be as measured on a metal test plate including glass beads.
label | (3) Pristine drop-on Type B glass beads (Type B-HR), as per Clause 721.A05.