## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Stormwater and Subsurface Drainage | itp |  |  |  |  | ITP - Stormwater and Subsurface Drainage Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
note | REFERENCE DOCUMENTS: Drawings and drawing registers, Cl 175.03
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.3 Material Classification
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Pipes supplied shall be of the category and diameter shown on the drawings or specified in clause 702.12 and shall comply with the requirements of the appropriate Australian Standard in accordance with Section 175 or as follows:
note | ○ Category 1: Perforated plastics Class 1000;
note | ○ Precast concrete Class "2"
note | ○ Category 2: Perforated plastics Class 400
note | ○ Category 3: Geocomposite drains
note | ○ Granular material as per clause 702.05, Geotextile material as per clause 702.06
note | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Order acceptance certificate, This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 2 - Procurement of Materials
checkpoint | 2.1 Precast Reinforced Concrete Pipe Supply
note | FREQUENCY: Prior to works commencing
note | ACCEPTANCE CRITERIA: Pipe class and size and endwall type as per drawings and Cl 701.05
note | REFERENCE DOCUMENTS: Cl 701.05, Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed, Order acceptance certificate
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.2 Precast Reinforced Concrete Inlet and Outlet Structures supply
note | FREQUENCY: Prior to works commencing
note | ACCEPTANCE CRITERIA: The supply of precast inlet and outlet structures shall conform with D.S.G standard drawings
note | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
note | REFERENCE DOCUMENTS: 610, 611, standard drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.3 Bedding and Backfill Material Specification
note | FREQUENCY: Grading 1 test per 1,000t
note | ACCEPTANCE CRITERIA: Bedding and Backfill materials free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092
note | ○ Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091
note | REFERENCE DOCUMENTS: Cl 701.09(d), Table 701.091, Table 701.092
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.4 Setout of Works
note | FREQUENCY: Prior to works commencing
note | ACCEPTANCE CRITERIA: Hold Point
note | Prior to commencement of excavation for the culverts the contractor shall confirm the position of all culverts with the Superintendent
note | REFERENCE DOCUMENTS: Cl 701.10
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Installation of Underground Stormwater Drainage
checkpoint | 3.1 Excavation Permit
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
note | ○ Plant and equipment shall be appropriate for the task.
note | ○ Excavation operations shall not disturb areas outside the limit of excavation
note | REFERENCE DOCUMENTS: Excavation permit
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.2 Excavation for trench
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm;
note | ○ The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in comleted exacavations.The Superintendent shall be notified at least 24 hours prior to the inspection.
note | REFERENCE DOCUMENTS: Cl 701.15 Table 701.151, Cl 702.08
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | HP
note | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Trench Base Preparation / Bedding
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Bedding material placed in full width of trench and compacted to at least 100mm thick, or; where the culvert is to be placed without trenching, to a width of 0.8m greater than the overall width of the culvert.
note | ○ Bedding of granular filter material of thickness between 25 mm and 50mm shall be placed across bottom of trench and shall be tamped and screeded or graded to level.
note | REFERENCE DOCUMENTS: Cl 701.16, Cl 702.09 (c)
note | INSPECTION/TEST METHOD: Visual inspection / Measure
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.4 Laying/ Placing of pipes
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Laying of pipes to commence from the downstream end. Pipes to be laid with rebate or socket end facing upstream and be fully entered. Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
note | ○ Pipes shall be placed centrally in the trench on the prepared bedding and held firmly in place
note | REFERENCE DOCUMENTS: Cl 701.10d Cl 701.17, Cl 702.09 (d)
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.5 Jointing
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
note | REFERENCE DOCUMENTS: Cl 701.18
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.6 Tolerance
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
note | ○ Tolerance:
note | • Invert level of pipes at pits ± 50mm
note | • Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
note | REFERENCE DOCUMENTS: Cl '701.10
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | SCP
note | RESPONSIBILITY: Surveyor, Site Engineer
textbox | DATE:
section | 4 - Backfilling of Stormwater
checkpoint | 4.1 Filling
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
note | • The trench shall be backfilled to design subgrade level with selected material.
note | (ii) Culvert Under Area not to be Paved
note | • The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
note | REFERENCE DOCUMENTS: Cl 701.19
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.2 Placement of granular backfill
note | FREQUENCY: Prior to backfilling
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the submitted quality procedures
note | REFERENCE DOCUMENTS: Cl 702.09 (g)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 Placement of no fines backfill
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
note | REFERENCE DOCUMENTS: Cl 702.09 (g)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer/ QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 Testing and Acceptance of Fill Materials
note | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots tested
note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
note | Bedding shall be compacted to refusal using hand held mechanical equipment.
note | Backfill material with nominal size < 40mm after compaction shall be compacted to a mean density ratio of not less than 97% CDR.
note | Backfill material with a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
note | REFERENCE DOCUMENTS: Cl '701.20
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Compaction Test Result OR This ITP Signed
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.5 Access Points and Flushouts
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Access point installed at the beginning and end of the drainage run and inspection openings at intervals between 100m and 150m. Flushout risers have same diameter as pipe.
note | REFERENCE DOCUMENTS: Cl 702.10
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.6 Flushing Test
note | FREQUENCY: At completion of stage
note | ACCEPTANCE CRITERIA: Flushing test undertaken on each subsurface drainage line after completion of the drains, flushers and risers, and after completion of barriers and road furniture. The test should be witnessed by a representative nomitated by the superintendent. Record of flushing tests must be kept.
note | REFERENCE DOCUMENTS: Cl 702.09(h)
note | INSPECTION/TEST METHOD: Site inspection
note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
note | TP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
checkpoint | 4.7 Installation of Inlet or Outlet Structure
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
note | REFERENCE DOCUMENTS: Cl '701.10 Cl 701.25
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 4.8 Culvert Coverage
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for axle or track loading has been provided, construction traffic shall not be permitted to cross the culvert.
note | REFERENCE DOCUMENTS: Cl 701.14 Table 701.141
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 5 - Subsurface / Subsoil Drainage
checkpoint | 5.1 Excavation Permit
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
note | ○ Plant and equipment shall be appropriate for the task.
note | ○ Excavation operations shall not disturb areas outside the limit of excavation
note | REFERENCE DOCUMENTS: Excavation permit
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.2 Excavation of Trench
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
note | REFERENCE DOCUMENTS: 702.08
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP
note | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 Placement of bedding
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
note | REFERENCE DOCUMENTS: 702.09 (c)
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.4 Placing pipes and geofabric (if required)
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
note | ○ If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
note | REFERENCE DOCUMENTS: 702.09
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.5 Placement of granular backfill
note | FREQUENCY: Prior to backfilling
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
note | REFERENCE DOCUMENTS: 702.09
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP
note | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Placement of backfill
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
note | REFERENCE DOCUMENTS: 702.09 (g)
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.7 Install Pits and Flushouts
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
note | REFERENCE DOCUMENTS: 702.1
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.8 Flushing Test
note | FREQUENCY: At completion of stage
note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
note | REFERENCE DOCUMENTS: C702.09(h)
note | INSPECTION/TEST METHOD: Site inspection
note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
note | WP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 6 - Finishing and Commissioning
checkpoint | 6.1 Finishing and Rendering Pipes
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: All stormwater inlet and outlet connections shall be cut trimmed neat and finished with cementitious mortar.
note | REFERENCE DOCUMENTS: Work Procedure
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 6.2 Inspection of subsurface drainage lines
note | FREQUENCY: At completion of stage
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ All subsurface drainage lines constructed shall be inspected, after completion of the flushing test and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
note | REFERENCE DOCUMENTS: Cl 702.09(i)
note | INSPECTION/TEST METHOD: Site inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 Repair of Damaged Pipes
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures.
note | REFERENCE DOCUMENTS: Cl 701.31
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | HP
note | RESPONSIBILITY: Site Engineer / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 CCTV
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
note | REFERENCE DOCUMENTS: Cl 701.30 WSA 05-2013
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Add Signature
checkpoint-no-status | Table 701.091
label | Sieve Size - AS (mm) ¦¦ Percentage Passing (by mass)
label | – – – – – – – – – –
label | Material: Backfill
label | 75.0: - ¦¦ 37.5: - ¦¦ 19.0: 100 ¦¦ 2.36: - ¦¦ 0.075: 5-40
label | Material: Selected Backfill
label | 75.0: - ¦¦ 37.5: 100 ¦¦ 19.0: - ¦¦ 2.36: - ¦¦ 0.075: 5-40
label | Material: Ordinary backfill
label | 75.0: 100 ¦¦ 37.5: - ¦¦ 19.0: - ¦¦ 2.36: 40-100 ¦¦ 0.075: -
checkpoint-no-status | Table 701.092
label | Test ¦¦ Test Value
label | Plasticity Index (Max.) ¦¦ 20
checkpoint-no-status | Table 701.141
label | Required Cover Thickness (Metre) (Min.)
label | Type, Size, and Class of Culvert
label | – – – – – – – – – –
label | Range of Axle or Track Loading (tonne): 0 - 9
label | • Pipe 2
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Pipe 3
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Pipe 4
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | - ¦¦ 0.1
label | – – – – – – – – – –
label | Range of Axle or Track Loading (tonne): 9 - 20
label | • Pipe 2
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Pipe 3
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Pipe 4
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | 1.2 ¦¦ 0.6
label | – – – – – – – – – –
label | Range of Axle or Track Loading (tonne): 20 - 35
label | • Pipe 2
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.7 ¦¦ 0.4
label | • Pipe 3
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Pipe 4
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.4 ¦¦ 0.4
label | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | 1.5 ¦¦ 0.9
label | – – – – – – – – – –
label | Range of Axle or Track Loading (tonne): 35 - 50
label | • Pipe 2
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.9 ¦¦ 0.7
label | • Pipe 3
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.6 ¦¦ 0.5
label | • Pipe 4
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.5 ¦¦ 0.4
label | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | 1.8 ¦¦ 1.2
label | – – – – – – – – – –
label | Range of Axle or Track Loading (tonne): 50 - 60
label | • Pipe 2
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | # ¦¦ #
label | • Pipe 3
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.8 ¦¦ 0.8
label | • Pipe 4
label | Pipe Class D<1.2m ¦¦ Pipe Class D>1.2m
label | 0.7 ¦¦ 0.7
label | • Corrugated Metal: D 1200-3600 mm ¦¦ Box Culvert 90 kN Proof Load
label | 2.1 ¦¦ 1.5
label | – – – – – – – – – –
label | # This range of loading not permissible.
label | D Nominal Pipe Diameter
label | D less than 1200 mm not permitted, D more than 3600 mm as directed by the Superintendent.
checkpoint-no-status | Table 701.151
label | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench :: Min. (mm) / Max. (mm)
label | – – – – – – – – – –
label | Corrugated Metal Culvert ¦¦ All :: 300 / 1,000
label | Other ¦¦ All :: 300 / 600