## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Surfacing - Asphalt Placement & Spray Sealing | itp |  |  |  |  | ITP - Surfacing - Asphalt Placement & Spray Sealing Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 Submission of Mix Design
note | FREQUENCY: Prior to commencing paving
note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by the Victorian Department of Transport as 'General', unless otherwise approved by the Victorian Department of Transport.
note | ○ The registration for all mixes incorporated into the works shall be current at the time of their use. The contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
note | REFERENCE DOCUMENTS: Cl 407.09
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Mix registration & correspondence
note | HP
note | RESPONSIBILITY: FH Engineer/ Superintendent / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP*
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
checkpoint | 1.3 Site Inspection and Base Condition
note | FREQUENCY: Prior to commencing paving
note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
note | REFERENCE DOCUMENTS: Cl 407.17 (a), AS2150 10.1, AS2150 10.3
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Engineer / Superintendent
textbox | DATE:
checkpoint | 1.4 Ambient Conditions for Placing
note | FREQUENCY: Prior to commencing paving
note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when majority of the area to be paved has a surface temperature less than that detailed as follows:
note | ○ Base or Intermediate Courses: 5°C for specified binder class of C170 or C320; or 10°C for asphalt mixes with specified binder class of C600 or containing a PMB.
note | ○ Wearing Course: 10°C for specified binder class of C170 or C320; or 15°C for asphalt mixes with specified binder class of C600 or containing a PMB.
note | REFERENCE DOCUMENTS: Cl 407.17 (a) Table 407.171
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: FH Engineer / QAV
textbox | DATE:
section | 2 - Material Procurement for Spray Seal
checkpoint | 2.1 Adhesion Agent
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
note | REFERENCE DOCUMENTS: Cl 408.09 (a),
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.2 Aggregate Precoating Materials
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: Aggregate Precoating Materials shall be distillate, distillate based product, cutback bitumen, emulsion based product or proprietary product.
note | REFERENCE DOCUMENTS: Cl 408.09 (b)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.3 Bitumen
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: Bitumen shall be Class 170 complying with the requirements of AS 2008.
note | REFERENCE DOCUMENTS: Cl 408.08 (a), AS 2008
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.4 Bitumen Emulsion
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: Bitumen Emulsion shall comply with the requirements of AS 1160.
note | REFERENCE DOCUMENTS: Cl 408.08 (b), AS 1160
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.5 Cutback Bitumen
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: Cutback bitumen shall comply with the requirements of AS 2157.
note | REFERENCE DOCUMENTS: Cl 408.08 (c), AS 2157
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.6 Cutter
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: Cutters shall comply with the properties in the Table 408.091.
note | REFERENCE DOCUMENTS: Cl 408.09 (d) Table 408.091
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.7 Polymer Modified Binder (PMB)
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: The class of PMB shall comply with the requirements of Austroads Technical Specification ATS-3110. Alternative or 'ungraded' PMMBs which do not comply with the specified test requirements of ATS-3110 shall not be used without approval by the Superintendent and will be subject to the Contractor providing evidence that the product has delievered satisfactory fiels performance for a period of at least three years.
note | REFERENCE DOCUMENTS: Cl 408.08 (d), AST-3110
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.8 Primer
note | FREQUENCY: Test cert. upon request
note | ACCEPTANCE CRITERIA: The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.Bitumen emulsion alternative acceptable upon providing evidence that the emulsion product meets the same functional requirements.
note | REFERENCE DOCUMENTS: Cl 408.08 (e)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 3 - Aggregate
checkpoint | 3.1 Aggregate Specification
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Aggregate shall comply with sections:
note | ○ 801 - Source Rock for the Production of Crushed Rock and Aggregates
note | ○ 831 - Aggregate for Sprayed Bituminous Surfacing
note | REFERENCE DOCUMENTS: Cl 408.11 (a)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.2 Aggregate Precoating
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate or field precoated aggregate.
note | ○ Aggregate precoating shall be undertaken using a purpose-built item of plant to apply to the precoating material in a controlled manner that produces a uniform coating.
note | REFERENCE DOCUMENTS: Cl 408.11 (b)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.3 Removal of loose aggregate
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing as it is mfreeway and AADT is greater than 5000, as per table 408.141, unless otherwise agreed with the Superintendent.
note | ○ For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
note | REFERENCE DOCUMENTS: Table 408.141
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 4 - Asphalt Placement
checkpoint | 4.1 Tack Coat
note | FREQUENCY: Prior to commencing paving
note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder. From 1 July 2022 only trackles stack coat will be permitted. The contractor shall submit the details of the trackless tack coat proposed to be used in the works
note | REFERENCE DOCUMENTS: Cl 407.08 (d) AS2150 11
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Hold Point Release
note | HP
note | RESPONSIBILITY: FH Engineer/ Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 Application of Tack Coat
note | FREQUENCY: Prior to Asphalt placement
note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed. The tack coat shall achieve an effective bond between the asphalt and the underlying layer.
note | REFERENCE DOCUMENTS: Cl 407.19
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed off
note | IP
note | RESPONSIBILITY: FH Engineer / QAV
textbox | DATE:
checkpoint | 4.3 Commencement of Asphalt Placement
note | FREQUENCY: Prior to commencing Paving
note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent
note | REFERENCE DOCUMENTS: Cl 407.23
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Hold Point Release
note | HP
note | RESPONSIBILITY: FH Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 Delivery of Mix
note | FREQUENCY: Each load
note | ACCEPTANCE CRITERIA: Asphalt delivered to site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
note | REFERENCE DOCUMENTS: Cl 407.20 (a)
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: Delivery Docket /Asphalt Traceability Sheet
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
checkpoint | 4.5 Layer Thickness and Scale of Level
note | FREQUENCY: Regularly during paving
note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness and Scale for Level as specified on drawings or specifications
note | REFERENCE DOCUMENTS: Cl 407.30 Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Dips using ruler or dip stick
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
checkpoint | 4.6 Paver Stoppages
note | FREQUENCY: If paver stops
note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C , a transverse joint shall be constructed.
note | ○ Hand spreading shall only be used for small areas where it is not practical to use a paver
note | REFERENCE DOCUMENTS: Cl 407.25
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Thermometer
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
checkpoint | 4.7 Surface Finish of Wearing Course
note | FREQUENCY: During paving and after final roll
note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
note | REFERENCE DOCUMENTS: Cl 407.29 (i)
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
checkpoint | 4.8 Kerb and Channel
note | FREQUENCY: During paving and after final roll
note | ACCEPTANCE CRITERIA: Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5mm above the lip of the channel.
note | REFERENCE DOCUMENTS: Cl 407.29 (ii)
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
checkpoint | 4.9 Alignment of layers not placed against concrete edge
note | FREQUENCY: During paving and at completion of work
note | ACCEPTANCE CRITERIA: Where asphalt is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designated offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25mm in 10 m.
note | REFERENCE DOCUMENTS: Cl 407.29 (iv) Drawings
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
checkpoint | 4.10 Width of layers not placed against concrete edge
note | FREQUENCY: During paving and at completion of work
note | ACCEPTANCE CRITERIA: Where asphalt placement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300 m shall not be less than the design or specified width.
note | REFERENCE DOCUMENTS: Cl 407.29 (v)
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Foreman / FH Engineer
textbox | DATE:
section | 5 - Spray Sealing
checkpoint | 5.1 Rates of Application
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent.
note | REFERENCE DOCUMENTS: Cl 408.13 (a)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 Surface Pre-treatment
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Surface pre-treatments to correct variable surface texture shall be allowed for and carried out as part of the works to meet the requirements of Surface Texture and Aggregate Loss specified in Tables 408.152 and 408.153.
note | REFERENCE DOCUMENTS: Cl 408.13 (b)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.3 Calibration of Bitumen Sprayer
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads Test Methods AGPT-T530, and AGTP-T536 and renewed every 12 months.
note | REFERENCE DOCUMENTS: Cl 408.07
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.4 Commencement of seal works
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Work shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 hours prior to the works occuring. For Periodic Resurfacing and Maintenance Works this includes patching and other preparatory works, and for the Initial Seals on Construction Projects the requirements of Standard Section 310 shall be satisfied.
note | REFERENCE DOCUMENTS: Cl 408.04
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 Commencement of seal works
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ Written confirmation of the works that will be undertaken the following day and obtain agreement from the superintendent to any variation in the design rates of appliaction to those provided under clause 408.13(a).
note | REFERENCE DOCUMENTS: Cl 408.04
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Records
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Job completion report using the proforma included as Attachment A to Section 408, or an equivlant proforma as approved by the Superintendent, completed and submitted within 7 days of completion of sealing each job.
note | REFERENCE DOCUMENTS: Cl 408.17
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
checkpoint | 5.7 Binder application rates
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: The Contractor shall produce evidence to show that the actual rate of application complies with the design rates of application. Variation between the actual rates and the design rates will be assessed in accordance with Table 408.151.
note | REFERENCE DOCUMENTS: Cl 408.15 (a)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.8 Surface Texture
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Acceptance of work for surface texture and surface enrichment shall be based on visual assessment, or tested in accordance with VicRoads Test Method RC 317.01 and assessed in accordance with Table 408.152 if required by the Superintendent
note | REFERENCE DOCUMENTS: Cl 408.15 (b)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.9 Aggregate retention
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Acceptance of work for aggregate retention shall be based on visual assessment, or tested in accordance with the VicRoads Test Method RC 317.03 and assessed in accordance with Table 408.153 if required by the Superintendent.
note | REFERENCE DOCUMENTS: Cl 408.15 (c)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.10 Visual Uniformity
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
note | REFERENCE DOCUMENTS: Cl 408.15 (d)
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 5.11 Maintenance of seals
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Hold Point
note | ○ The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period. The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work
note | REFERENCE DOCUMENTS: Cl 408.16
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | HP
note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.12 Maintenance of seals
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: The Contractor shall obatin the agreement of the Superintendent of the proposed treatment before undertaking the work.
note | REFERENCE DOCUMENTS: Cl 408.16
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Signed ITP
note | HP
note | RESPONSIBILITY: FH Engineer / Spray Supervisor / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Testing
checkpoint | 6.1 Compaction of Asphalt layers
note | FREQUENCY: Per Lot
note | ACCEPTANCE CRITERIA: For layers <= 50mm, if characteristic density ration is:
note | • 95.0% or more - Accept Lot
note | • 94.9% to 93.0% - Lot may be accepted at reduced rate
note | ○ For layers >= 50mm, if characteristic density ratio is:
note | • 96.0% or more - Accept lot
note | • 94% to 95.9% Lot may be accepted at reduced rate
note | REFERENCE DOCUMENTS: Cl 407.27 Table 407.271 Cl 173.04
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Test Report
note | TP
note | RESPONSIBILITY: FH Engineer/ Lab Technician
textbox | DATE:
checkpoint | 6.2 Level Conformance for Asphalt layers
note | FREQUENCY: Per 4,000m2 at completion of work
note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of ±8mm (Scale B)
note | REFERENCE DOCUMENTS: Cl 407.29 Table 407.293
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Visual match existing / This ITP signed off
note | SCP
note | RESPONSIBILITY: FH Engineer/ Surveyor
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Add Signature
checkpoint-no-status | Table 407.171 Minimum Pavement Temperatures Prior to Laying Asphalt
label | Asphalt Type ¦¦ Intermediate or Base Courses ¦¦ Wearing Course
label | – – – – – – – – – –
label | All asphalt with a specified binder class of C170 or C320 ¦¦ 5°C ¦¦ 10°C
label | All asphalt with a specified binder class of C600 or containing a PMB ¦¦ 10°C ¦¦ 15°C
checkpoint-no-status | Table 407.271 Limits for Characteristic Density Ratio (Six Tests)
label | For layers less than 50 mm thick
label | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
label | – – – – – – – – – –
label | 95.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot
label | 94.9% to 93.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1325
label | 92.9% or less ¦¦ Remove and replace asphalt
label | – – – – – – – – – –
label | For layers 50 mm thick or greater
label | Characteristic Value of the Density Ratio (Rc) ¦¦ Assessment
label | – – – – – – – – – –
label | 96.0% or more ¦¦ Accept lot subject to no other nonconformances raised for the lot.
label | 95.9% to 94.0% ¦¦ Lot may be accepted at a reduced rate calculated by P = 15 Rc - 1340
label | 93.9% or less ¦¦ Remove and replace asphalt
checkpoint-no-status | Table 407.292 Minimum Number of Level Measurements per Lot
label | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements Per Lot
label | – – – – – – – – – –
label | Scale A ¦¦ 80
label | Scale B ¦¦ 40
checkpoint-no-status | Table 407.293 Mean Surface Level Tolerances for the Sub-base and Pavement Courses
label | Granular or Cement Treated Subbase: x̅ Range (mm) / Max. S (mm) ¦¦ Asphalt Layers: x̅ Range (mm) / Max. S (mm)
label | – – – – – – – – – –
label | Scale of Surface Level Measurement: Scale A
label | +4 to -8 / 8 ¦¦ ±5 / 8
label | – – – – – – – – – –
label | Scale of Surface Level Measurement: Scale B
label | +6 to -12 / 13 ¦¦ ±8 / 10
label | – – – – – – – – – –
label | Notes on Table 407.293
label | x̅ is the mean value of all level readings taken in the lot (a negative value designates a measured departure below the design level and positive value designates a surface level above the design level)
label | S is the standard deviation of all level readings taken in the lot.
checkpoint-no-status | Table 408.141 Maximum Time Limit for Removal of Loose Aggregate
label | Traffic Volume (AADT) * ¦¦ Maximum Time Limit
label | – – – – – – – – – –
label | >5000 and all Freeways ¦¦ Within 8 hours of sealing
label | >2000 to 5000 ¦¦ Within 24 hours of sealing
label | >500 to 2000 ¦¦ Within 48 hours of sealing
label | <500 ¦¦ Within 5 days of sealing
checkpoint-no-status | Table 408.152 Surface Texture Requirements
label | SINGLE/SINGLE TREATMENTS
label | Mean Texture Depth (mm)
label | Size 5 :: Size 7 :: Size 10 :: Size 14 ¦¦ Action Required
label | – – – – – – – – – –
label | Treatment: Seals (All Types) (1)
label | 1.0 to 1.6 :: 1.3 to 1.8 :: 1.5 to 2.5 :: 2.0 to 4.0 ¦¦ Accept
label | 0.8 to 1.0 or 1.6 to 1.8 :: 1.2 to 1.3 or 1.8 to 2.0 :: 1.3 to 1.5 or 2.5 to 3.0 :: 1.7 to 2.0 or 4.0 to 4.5 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
label | < 0.8 or > 1.8 :: < 1.2 or > 2.0 :: < 1.3 or > 3.0 :: < 1.7 or > 4.5 ¦¦ Work to be rectified
label | – – – – – – – – – –
label | Treatment: Initial Seals (2)
label | N/A :: 1.0 to 2.0 :: 1.2 to 3.0 :: N/A ¦¦ Accept
label | N/A :: < 1.0 or > 2.0 :: < 1.2 or > 3.0 :: N/A ¦¦ Work to be rectified
label | – – – – – – – – – –
label | Treatment: Surface Enrichment (1)
label | N/A :: N/A :: 0.8 :: 0.8 ¦¦ Accept
label | N/A :: N/A :: < 0.8 :: < 0.8 ¦¦ Work to be rectified
label | – – – – – – – – – –
label | DOUBLE/DOUBLE TREATMENTS
label | Mean Texture Depth (mm)
label | Size 10/5 :: Size 10/7 :: Size 14/5 :: Size 14/7 :: Size 20/7 ¦¦ Action Required
label | – – – – – – – – – –
label | Treatment: Seals (All Types) (1)
label | 1.3 to 2.1 :: 1.3 to 2.2 :: 1.3 to 2.4 :: 1.3 to 2.4 :: 1.4 to 2.5 ¦¦ Accept
label | 1.2 to 1.3 or 2.0 to 2.3 :: 1.2 to 1.3 or 2.1 to 2.4 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.2 to 1.3 or 2.4 to 2.7 :: 1.3 to 1.4 or 2.5 to 2.8 ¦¦ The Superintendent may require rectification of the works or elect to reduce payment for the lot by $1.00/m^2
label | < 1.1 or > 2.3 :: < 1.1 or > 2.4 :: < 1.2 or > 2.7 :: < 1.2 or > 2.7 :: < 1.3 or > 2.8 ¦¦ Work to be rectified
label | – – – – – – – – – –
label | Treatment: Initial Seals (2)
label | 1.0 to 2.0 :: 1.0 to 2.0 :: N/A :: N/A :: N/A ¦¦ Accept
label | < 1.0 or > 2.0 :: < 1.0 or > 2.0 :: N/A :: N/A :: N/A ¦¦ Work to be rectified
label | – – – – – – – – – –
label | Notes:
label | (1) Surface texture measurements for sprayed seals and surface enrichment may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.
label | (2) Surface texture measurements for initial seals shall be undertaken between 10 and 15 weeks after placement. If tests are not undertaken in this period and later test results require the works to be rectified, the later test results are to be used for acceptance of the works.
checkpoint-no-status | Table 408.153 Assessment of Aggregate Retention
label | Degree of Aggregate Stripping ¦¦ Action Required
label | – – – – – – – – – –
label | 0 to 2 ¦¦ Accept
label | 3 to 5 ¦¦ Work to be re-tested within one month prior to the end of the Defects Liability Period. If the Degree of Aggregate Stripping has increased since it was last tested, the work shall be rectified before the end of the Defects Liability Period.
label | Greater than 5 ¦¦ Work shall be rectified within 5 days.
label | – – – – – – – – – –
label | Note: Aggregate retention measures may be undertaken at any time during the Defects Liability Period, but final acceptance of works is not affected until the end of the Defects Liability Period.