## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Unbound Flexible Pavement Construction | itp |  |  |  |  | ITP - Unbound Flexible Pavement Construction Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.2 Material Classification
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Hold Point:
note | ○ All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads RC500.02 and conform to specified requirements applicable to that class of product
note | REFERENCE DOCUMENTS: 812.04 VicRoads RC500.02
note | INSPECTION/TEST METHOD: Document Review
note | RECORD OF CONFORMITY: This ITP signed
note | AP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
checkpoint | 1.3 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 1.4 Plant and Equipment
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
note | REFERENCE DOCUMENTS: N/A
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 2 - Placement
checkpoint | 2.1 The commencement of construction of base and subbase
note | FREQUENCY: Prior to placing subbase
note | ACCEPTANCE CRITERIA: Underlying ITP signed off
note | ○ Identifying and removing soft areas to a minimum of 200mm depth. Underlying layer shall be clean of all foreign matter. The edges of previously placed materials shall be watered. Proof roll underlying layer prior to commencing
note | REFERENCE DOCUMENTS: Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.2 Delivery Dockets
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Where material is scheduled for measurement by loose volume in delivery vehicles or by mass, a delivery docket for each load shall be issued to the Superintendent at the point of delivery.
note | REFERENCE DOCUMENTS: –
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.3 Layer Thickness
note | FREQUENCY: Each layer
note | ACCEPTANCE CRITERIA: Material is to be compacted to the overall thickness shown in the drawings (dependent on pavement type), subbase not less than the specified thickness by more than 15 mm
note | REFERENCE DOCUMENTS: Drawings and 304.06(c)
note | INSPECTION/TEST METHOD: Visual and Measure
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.4 Conformity with Drawing
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
note | ○ Where pavement is to be constructed to the lip level of kerb and channel, it shall be constructed flush with the lip of the channel or not more than 5 mm above.
note | ○ Any material that has been compacted and then trimmed from the compacted surface to conform
note | REFERENCE DOCUMENTS: –
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 2.5 Jointing
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: (a) material shall be spread in such a manner as to minimise the number of joints
note | (b) transverse joints shall be offset from one layer to the next by not less than 2m
note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150mm.
note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
note | REFERENCE DOCUMENTS: 304.07
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
section | 3 - Testing and Conformance
checkpoint | 3.1 Determine Testing Scale & Initial testing frequency
note | FREQUENCY: Prior to Testing
note | ACCEPTANCE CRITERIA: Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale B, the first lot of each pavement course shall be tested for post-compaction grading and PI.
note | ○ If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
note | REFERENCE DOCUMENTS: Table 204.161 304.10 (c or d) 304.10 (a) 304.10 (b)(ii) Table 304.101 Table 304.103 304.11 (c) (ii)
note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | AP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.2 Post Compaction Testing
note | FREQUENCY: Each Lot 304.10 (a) & (b)
note | ACCEPTANCE CRITERIA: If the first lot does not meet the requirements specified in Clause 304.10(a) and (b), the Contractor shall then seek approval from the Superintendent before work proceeds.
note | REFERENCE DOCUMENTS: 304.11 (c) (ii)
note | INSPECTION/TEST METHOD: PI
note | RECORD OF CONFORMITY: This ITP sIgned
note | HP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Test Rolling
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Hold Point:
note | ○ All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.
note | REFERENCE DOCUMENTS: 304.08
note | INSPECTION/TEST METHOD: Test Roll
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Site Engineer / QAV
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 Compaction Testing
note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modified compactive effort. The work shall be assessed for compliance with Scale B requirements for testing and acceptance of compaction as specified in the table below
note | – – – – – – – – – –
note | Characteristic Density Ratio % (six tests)
note | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
note | – – – – – – – – – –
note | ○ Compaction Scale: A
note | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
note | ○ Compaction Scale: B
note | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
note | – – – – – – – – – –
note | REFERENCE DOCUMENTS: 304.08 Table 304.061 304.11 (b) Table 304.111
note | INSPECTION/TEST METHOD: Test point
note | RECORD OF CONFORMITY: This ITP signed
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.5 Post Compaction Testing
note | FREQUENCY: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
note | ACCEPTANCE CRITERIA: If specified in Clause 304.10(c) or Clause 304.10(d), following completion of compaction, material shall be tested for post-compaction grading or Plasticity Index (PI) at the frequency specified in Clause 304.11 for the appropriate Scale of Testing specified in Clause 304.12(a).
note | REFERENCE DOCUMENTS: 304.10 Table 304.101
note | INSPECTION/TEST METHOD: Test point
note | RECORD OF CONFORMITY: This ITP signed
note | TP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.6 Shape
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall have no point deviation > 8mm from 3m straight edge. The subbase shall also not be less than the specified thickness by more than 15mm
note | REFERENCE DOCUMENTS: 304.06(b, d, i) Drawings Table 304.062
note | INSPECTION/TEST METHOD: Survey
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | 3.7 Completed Surface Level Compliance
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number specified in Table 304.061.
note | ○ The mean and standard deviation of the departures from the design surface level for the pavement courses at their respective levels within each lot shall meet the requirements of Table 304.062.
note | – – – – – – – – – –
note | Table 304.062 Surface Level Tolerances for the Pavement Courses
note | – – – – – – – – – –
note | Scale of Level Measurement: Scale A
note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
note | +6 to -10 ¦¦ 10
note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
note | +4 to -8 ¦¦ 8
note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
note | ±5 ¦¦ 8
note | – – – – – – – – – –
note | Scale of Level Measurement: Scale B
note | Lower Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
note | +8 to -16 ¦¦ 15
note | Upper Subbase: x̅ Range (mm) ¦¦ Max. S (mm)
note | +6 to -12 ¦¦ 13
note | Base: x̅ Range (mm) ¦¦ Max. S (mm)
note | ±8 ¦¦ 10
note | – – – – – – – – – –
note | Notes:
note | 1. x̅ is the mean value of all level readings taken in the lot
note | 2. S is the standard deviation of all level readings taken in the lot
note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
note | – – – – – – – – – –
note | REFERENCE DOCUMENTS: 304.06(b) Drawings Table 304.062
note | INSPECTION/TEST METHOD: Survey
note | RECORD OF CONFORMITY: This ITP signed
note | SCP
note | RESPONSIBILITY: Site Engineer
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
signoff | Add Signature
checkpoint-no-status | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
label | Road Name ¦¦ Chainage/Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B or C)
label | – – – – – – – – – –
label | Bruny Island Main Road ¦¦ Within Limits of Works ¦¦ B ¦¦ B ¦¦ B
checkpoint-no-status | Table 304.081 Acceptance Limits for Scale A and Scale B Standards of Compaction
label | Characteristic Density Ratio % (six tests)
label | Lower Subbase Layers ¦¦ Upper Subbase Layers ¦¦ Base Layers: Layer directly beneath the Bituminous Surfacing ¦¦ Base Layers: Other Layers
label | – – – – – – – – – –
label | Not less than 98.0 ¦¦ Not less than 98.0 ¦¦ Not less than 100.0 ¦¦ Not less than 99.0
label | Not less than 97.0 ¦¦ Not less than 97.0 ¦¦ Not less than 98.0 ¦¦ Not less than 98.0
checkpoint-no-status | Table 304.101 Post-Compaction Grading Requirements for Crushed Materials
label | Post-Compaction Grading Limits (% Passing by Mass)
label | – – – – – – – – – –
label | Class 1 or Class 2 Crushed Rock
label | Crushed Scoria Base
label | Class CC2 Crushed Concrete
label | – – – – – – – – – –
label | Sieve Size ¦¦ Nominal Size (mm): 20
label | – – – – – – – – – –
label | 53.0 ¦¦ -
label | 37.5 ¦¦ -
label | 26.5 ¦¦ 100
label | 19.0 ¦¦ 95 - 100
label | 13.2 ¦¦ 78 - 92
label | 9.5 ¦¦ 63 - 83
label | 4.75 ¦¦ 44 - 64
label | 2.36 ¦¦ 30 - 49
label | 0.425 ¦¦ 14 - 23
label | 0.075 ¦¦ 6 - 12
label | – – – – – – – – – –
label | Class 3 Crushed Rock
label | Crushed Scoria Upper Subbase
label | Crushed Concrete Class CC3
label | – – – – – – – – – –
label | Sieve Size ¦¦ Nominal Size (mm): 20 ¦¦ Nominal Size (mm): 40
label | 53.0 ¦¦ - ¦¦ 100
label | 37.5 ¦¦ - ¦¦ 95 - 100
label | 26.5 ¦¦ 100 ¦¦ 75 - 95
label | 19.0 ¦¦ 95 - 100 ¦¦ 64 - 90
label | 13.2 ¦¦ 75 - 95 ¦¦ -
label | 9.5 ¦¦ 60 - 90 ¦¦ 42 - 78
label | 4.75 ¦¦ 42 - 76 ¦¦ 27 - 64
label | 2.36 ¦¦ 28 - 61 ¦¦ 20 - 51
label | 0.425 ¦¦ 14 - 29 ¦¦ 10 - 24
label | 0.075 ¦¦ 6 - 14 ¦¦ 6 - 13
checkpoint-no-status | Table 304.103 Post-Compaction Requirements for Plasticity Index
label | Material ¦¦ Plasticity Index: Minimum ¦¦ Plasticity Index: Maximum
label | – – – – – – – – – –
label | Class 1 Crushed Rock ¦¦ 0 ¦¦ 6
label | Class 2 Crushed Rock ¦¦ 0 ¦¦ 6
label | Class 3 Crushed Rock ¦¦ 0 ¦¦ 10
checkpoint-no-status | Table 304.111 Maximum Lot Size and Minimum Frequency of Testing for Compaction, Post-compaction Grading and PI (after passing the minimum number of qualifying lots)
label | Maximum Allowable Lot Size for a Single Layer of Work ¦¦ Minimum Frequency of Testing for Compaction ¦¦ Minimum Frequency of Testing for Scale A Post-compaction Grading ¦¦ Minimum Frequency of Testing for Scale A Post-compaction PI
label | – – – – – – – – – –
label | Pavement Layer: Upper Base Layer
label | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 4 lots
label | – – – – – – – – – –
label | Pavement Layer: Lower Base Layer
label | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 2 lots ¦¦ One pair per 8 lots
label | – – – – – – – – – –
label | Pavement Layer: Upper Subbase
label | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ One per 4 lots ¦¦ One pair per 8 lots
label | – – – – – – – – – –
label | Pavement Layer: Lower Subbase
label | The lesser of 4000 m^2 or one day's production ¦¦ One per 2 lots ¦¦ – ¦¦ –
checkpoint-no-status | Table 310.032 Testing Schedule for Pavement Dryback and Embedment
label | Road ¦¦ Location/Chainage ¦¦ Testing Scale
label | – – – – – – – – – –
label | Bruny Island Main Road ¦¦ Within the limits of works ¦¦ B