## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 496ad6f2-797a-4b17-a0c0-69cd3b3dcd4a |  | checklist | Compliance Documentation |  |  |  |  | Yes | Compliance Documentation Checklist | f3e79d28-e6a7-4307-a43d-740ee207ed7e
checkpoint-status | f58889c0-5e6b-482f-bec0-0ae5a115ed21 |  | checkpoint | Concrete Test Results
label | 066d13f7-4c78-53cf-ae07-c6288d05b188 |  | note | Pass once all test results for this project are attached
text | 4fe06e26-34cc-58f5-876f-027f90ea4833 |  | textbox | Concrete test requirements for this project
checkpoint-status | a40742db-3201-4a72-ac32-2faed3ed3e97 |  | checkpoint | Mill Certification
label | 95c90d50-faae-57db-8f9a-9e8b3b1bada8 |  | note | Pass once all mill certs for this project are attached
checkpoint-status | 75aa4f73-99ce-4d2a-a05b-d954d6eb38ed |  | checkpoint | PS1 Attached (if applicable)
checkpoint-status | 49b1e850-1ca9-4741-8c28-ee80ef9b1a01 |  | checkpoint | PS3 Attached (if applicable)
checkpoint-status | 2e7a2ce4-b667-435d-b89d-f639ced12998 |  | checkpoint | PS4 Attached (if applicable)
checklist-sectioned | b724e883-46ad-4066-bbd6-7b76ba27a411 |  | checklist | P |  |  |  |  | Yes | 4. LR WT3 Panel | c2071aab-da87-42a4-90d5-d238a564bc58
checkpoint-group | d50a8d64-f42a-4db5-b00b-3607d2c2c06e |  | section | Precast Element Details
checkpoint-status | 65b85a6f-9b67-48b7-bc9c-07b4c68cb279 |  | checkpoint | Concrete Details Complete
text | f93de833-ccdc-5608-8629-2316fa7f600c |  | textbox | Concrete Volume
text | 56b56db4-c506-5a41-af40-aff036996a3d |  | textbox | Concrete Strength
text | 71a28364-61e6-5596-9258-cc7c6a059f71 |  | textbox | Enter Drawing Revision Number
text | ca0a00f4-d2b5-5553-934b-5fb566b8821c |  | textbox | Cast Date
checkpoint-group | 2eea5c2b-988c-49fd-a1a1-2184f840f926 |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 6aa62017-177a-49a9-b602-aac63163d958 |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | dab16392-35b2-4430-93c8-84582d427495 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | c87d5623-07e1-4a3a-8bff-1eb8f612c1f6 |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | f36abc39-4276-4da4-8ff9-78f0b57af286 |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 80fdf14f-f673-4f13-88e9-4631667290b3 |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | 21dbfe01-bcdb-47ed-9e1e-ce41e2379986 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 365be858-5d9b-4821-8ab1-b7839e899350 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | ca22ec0c-f64b-4f89-a8be-605c24dba9f1 |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 475dd75f-d023-44cd-a731-b873184a7b90 |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | 3d2304b6-a071-4e25-8d11-6b04a7db2bc3 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 7d1d72d5-d3b9-4b10-bb5e-703a48945d74 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 65c3dee1-1c73-44d1-adb4-b71fd464eff3 |  | checkpoint | Mould Face Clean
checkpoint-status | 15976424-d03d-42b9-895a-b892e17e10e4 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 750bbf26-1471-4adc-9d70-6eddaf1b923b |  | checkpoint | Edge Details & Rebates
checkpoint-status | d65eb75e-b297-48c5-8e07-66fd74f4e4c2 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 938ba8e7-c008-4d6b-83e7-dcd1572232c0 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 037c7b98-6806-4e63-b41d-08746a24ae4a |  | checkpoint | Main Reinforcing
checkpoint-status | fb844be8-a2ff-4b95-afe5-e3114de6f815 |  | checkpoint | Starters
checkpoint-status | 9c25e551-9e13-47ae-a999-f0aeabab3a0f |  | checkpoint | Stirrups
checkpoint-status | 79701048-ec04-45ef-b37e-57f82e191a7b |  | checkpoint | Lifters
checkpoint-status | 73384c8d-8264-49c4-8554-c6cc8ca43f48 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | 867a7f81-b555-4d55-914a-acd3754bb9a7 |  | checkpoint | Tie wire Trimmed
checkpoint-status | 07849838-9a99-4424-9340-00e8c72e10b6 |  | checkpoint | General Photos Attached
checkpoint-status | bc42d565-97da-49ad-998a-4ab978ee2f41 |  | checkpoint | Concrete Docket Attached
checkpoint-status | b8aff650-fc59-4d7a-9e70-b5dc861c4c62 |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | 4e6ccdfc-8afd-4618-96b8-9db0e9d8df2c |  | section | Post Pour (Table Supervisor)
checkpoint-status | 7515470f-9e12-4d1b-82f3-9cd28d6214f2 |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 9d6cef15-b237-44c9-919c-27805c00bb23 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | 24d944aa-177c-40ad-b4ff-dca6ba2e150c |  | checkpoint | Roughening Lines Correct
checkpoint-group | 8325d04d-03ec-43ba-85b5-17649266397d |  | section | Demould Inspection (Yard QA)
checkpoint-status | 15f0fed1-36ea-494a-a1ec-460dd0c1a81b |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | 4eec067d-b46a-43e3-983d-6ac1c56943ef |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | a2b7bc2e-8679-475c-ad65-7c991bac6342 |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 49ac45ca-9b4b-44ad-afaa-b8805c878eee |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | b5875386-cb18-4732-815a-db0774dcf43f |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | a9143544-3c2b-426b-8cbc-a55cea1060dc |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 8c25d55b-a3ea-43b4-a172-3cc622d1aa0c |  | checkpoint | MF roughening's jet washed
checkpoint-status | 3b4dc1f8-770b-4842-bf37-a2f5554725b0 |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 79e62c39-cec1-450d-872b-4142c70b3455 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | 76bd40bd-4dbc-4f68-a4a8-6e3bdc63fa65 |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 8877fc6f-598a-428b-a26f-722f98707bd1 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | 1f308c9f-0fea-4327-8361-6f146fe133a8 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 0e72cda3-ffe7-4754-85e0-d85e1a5eb587 |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | e79d0926-519e-4ec9-b9be-3e89379a972f |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | 00481297-cd25-4982-a44c-cae53b69ec57 |  | checkpoint | Shop drawing checked off
checkpoint-group | fb2ab45e-4f82-4ca9-a9f3-25d04fcb8fa5 |  | section | Panel Painting Checks (Yard Supervisor)
checkpoint-status | 70446044-3882-4bc3-a235-9676ee9f289b |  | checkpoint | Panel MF Sprayed with Tiltwash and rinsed off with waterblaster (2 passes)
checkpoint-status | 2a6cc8d9-0387-4612-816b-d2ed247becae |  | checkpoint | Window opening inspected and concrete finish acceptable
checkpoint-status | 05bfac8b-4c1d-47b6-ae64-a820991b3088 |  | checkpoint | Large Pinholes or honey combing repaired with Sikadur UA (if required)
checkpoint-status | 90148788-b82a-4ac0-b921-33c804eae774 |  | checkpoint | Ecotone colouring system applied as per quality plan
checkpoint-status | b45bf808-b4c0-4230-bbae-94607fb1ceb2 |  | checkpoint | Masking tape in window opening removed and edges of panel clear of any overspray
holdpoint | 619ab959-3519-4208-9f6b-ab145baa2a3c | Multiple signoffs are not allowed | signoff | Window installer accepted quality of concrete opening
holdpoint | 0f434652-fe71-4eb1-bb55-31bfb52b4599 | Multiple signoffs are not allowed | signoff | Window installer confirmed they have completed their works and panel can delivered to site
checkpoint-group | 0873e2ba-5b39-4b39-a886-d668e9fdc45d |  | section | Overall Panel Quality (Yard QA)
checkpoint-status | 35b5ff2e-40e9-48a1-b583-c19cca553477 |  | checkpoint | Overall Panel Quality Ratings Recorded Below
label | 89229089-abe6-556d-bcb8-02df20595fc2 |  | note | The higher the number the better the quality
label | 3bacc4db-f3cf-5268-874b-d204448de3fc |  | note | e.g. "1" is unacceptable
button | 5b5001e1-c681-5a8b-9851-93809a8aff02 |  | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
button | 9cff5aa3-a33b-530a-88d9-2392fdcc67f9 |  | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
button | 7eb9c059-7eb9-57df-89f8-d576c10a15f2 |  | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
button | f8d5cc93-b813-562b-9bbd-cfcb3ba1f551 |  | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
button | 2c2070d3-5446-51e8-8925-3b63dbebaac6 |  | button | MF Quality | 5 , 4 , 3 , 2 , 1
checkpoint-group | 8a0f5bcc-51f0-4431-9dbe-3b751f280f81 |  | section | Loading Out (Yard QA)
checkpoint-status | c7d434d8-2d96-4f8e-a016-62692ed9c804 |  | checkpoint | Load Docket Given to Driver
checkpoint-status | cdf7416b-3af7-4f4a-a649-27c4a72cff91 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | ac290861-b72d-4d6b-910f-4909161ca741 |  | checkpoint | No remedial work required on site
checkpoint-group | 07950d92-7d8b-4c72-8cb3-000353575e40 |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | 18c48cbd-61d7-49e9-a5c8-223bb3b5baf7 |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 649b75c9-8a0c-423e-af85-5e49c1cc2813 |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | 7eb796b1-08ee-4d6e-b922-1b858a23d03d |  | checkpoint | Upload Concrete test results
checklist-sectioned | 5c93fb5f-b61a-4357-8829-a2b817644768 |  | checklist | 3. LR WT2 Panel |  |  |  |  | Yes | 3. LR WT2 Panel | b4cf0324-2f36-4666-98b6-5a48540c67a1
checkpoint-group | 6f088471-5db4-478a-8d28-bf309b6a6bf1 |  | section | Precast Element Details
checkpoint-status | 6e9a2455-9873-428b-ae69-0c70778ea1ae |  | checkpoint | Concrete Details Complete
text | d36190de-c6c4-5076-83ae-e266b4aa0f17 |  | textbox | Concrete Volume
text | ab5d60e3-3ec2-5eb0-9d08-0c330f3ca6b4 |  | textbox | Concrete Strength
text | 5e2297eb-4354-5732-9668-aaf49961ae40 |  | textbox | Enter Drawing Revision Number
text | 2fa8ac20-9f58-5315-a403-5f5bcc21d5db |  | textbox | Cast Date
checkpoint-group | 4b6b42c8-324c-4998-886c-769bf6a964b3 |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 1cfa040a-5412-44c0-aa5a-edb08ef62baa |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | 3d593793-a7c7-40c6-a7d7-e276239582e3 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 9e0412d0-965c-4290-8633-e7e6b352b71a |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | f3959fa8-6b0a-4a8e-8039-3351e80160ad |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | f9eb675d-f8c0-489f-b070-34b74098efd3 |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | 7c2e024e-fdb4-4efd-82e0-1f25d2961284 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 84a23642-682d-4a7c-adb7-7fc42bfc126a |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | 2bd72e81-121d-4972-96f5-3deab0acc852 |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | bcedd380-12af-454a-8a05-97601f36a594 |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | 6cdae6de-e05d-4289-bb05-dba79751c8a1 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 93143dff-4123-4ede-86c6-a32158df4654 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 74878f7d-dd3b-4832-b0da-0db01909a29c |  | checkpoint | Mould Face Clean
checkpoint-status | 2ca2f0b2-55ee-4d36-bb8f-8b732ba85a88 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 88f20329-3495-41c4-8a51-efc8dad893b3 |  | checkpoint | Edge Details & Rebates
checkpoint-status | ac212024-7230-4b9a-b99d-3ea1105a0c38 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | c858fa41-ca5b-4d0f-ba7b-a0f02f1454d3 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 95d9408d-a008-4c94-b975-9747871e89eb |  | checkpoint | Main Reinforcing
checkpoint-status | bdac6b26-84f4-4764-8e9c-1b31275f74c7 |  | checkpoint | Starters
checkpoint-status | 6feca183-f9e4-48bc-9452-ef2411204e3b |  | checkpoint | Stirrups
checkpoint-status | 96f95bdf-c7a6-4289-8957-0c787d9bfe5b |  | checkpoint | Lifters
checkpoint-status | fb31b4ef-87d6-420c-9599-268ac1f3987a |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | d284b03e-6720-43fb-85f3-d37ddaec4931 |  | checkpoint | Tie wire Trimmed
checkpoint-status | a1203515-40c1-48d9-a3cd-f7cefea5d610 |  | checkpoint | General Photos Attached
checkpoint-status | 3e0483e6-6d34-4296-aa64-c5240b987c91 |  | checkpoint | Concrete Docket Attached
checkpoint-status | e778187c-8b54-4705-8b14-0fbcdbc50392 |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | 4516c37b-f67b-4a64-9e8f-edbb7cccc460 |  | section | Post Pour (Table Supervisor)
checkpoint-status | 6def30f3-6d78-4ce5-964f-cfabda6f5d03 |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 17f291a3-721d-43cb-8e5b-2cdd41a112c7 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | 5d27de29-2db8-4d62-9ce6-2449e5fdb579 |  | checkpoint | Roughening Lines Correct
checkpoint-group | adee160f-226a-4b21-b385-9d902bcb46f7 |  | section | Demould Inspection (Yard QA)
checkpoint-status | 42997e26-9829-4621-96b5-50f75262af6e |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | cd5926f9-7fa8-4253-815d-ab65123a2690 |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | b95a575c-d0a6-4e00-bf4f-61e659040cb2 |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 843f8376-6696-4e61-a702-1d2eb4090faa |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | 8f35b262-69aa-4359-ac21-ed918c60b575 |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 9b818bc7-5a6f-41fe-a6b7-684387085205 |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | dd902ac0-8622-4766-b886-275874b889f6 |  | checkpoint | MF roughening's jet washed
checkpoint-status | 60432691-81d1-4d49-b718-1b436e509ae7 |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | c4086058-5c31-4a51-a714-687127fb3444 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | ab62e6f5-834f-4c64-a77c-5419c6166088 |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 06bf7cfb-e3cb-4309-af04-a1e9bb855d57 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | e3633db2-8eee-41ca-ad8f-0d0726128d99 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 711eccd1-49b0-457e-ad5a-fc1658304f7a |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | 25071402-7fb7-4efb-9a1d-c490bbbc55d9 |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | d53f4229-a0f6-4441-b140-6956ecf7a051 |  | checkpoint | Shop drawing checked off
checkpoint-group | d763b10a-d2d1-4a07-a0dc-afd36844a4ae |  | section | Panel Painting Checks (Yard Supervisor)
checkpoint-status | 5f3ef837-c6e6-47dc-963d-abb4505abff3 |  | checkpoint | Panel MF Sprayed with Tiltwash and rinsed off with waterblaster (2 passes)
checkpoint-status | 7ca30d9a-f496-44b9-9506-13cc931d2210 |  | checkpoint | Window opening inspected and concrete finish acceptable
checkpoint-status | ff5ad1c6-97e1-4451-bf93-661f6ef5c957 |  | checkpoint | Large Pinholes or honey combing repaired with Sikadur UA (if required)
checkpoint-status | aff4f0b4-820a-4694-9633-5a6d239dfa57 |  | checkpoint | Panel allowed to cure for 48hours before applying primer
checkpoint-status | f9aaa4d5-8cbe-454e-be3d-b981a8743ab5 |  | checkpoint | Single coat of Dulux AcraTex Green Render Sealer applied (upload photo)
checkpoint-status | 80680ddb-dac4-4e2f-bdc6-fa89e6175a8a |  | checkpoint | Allow sealer coat to dry for 4 hours before applying topcoat
checkpoint-status | b509154a-84bb-40f5-940d-12ab6f664551 |  | checkpoint | 2 coats of Dulux AcraTex AcraShield Advance Matt topcoat (upload photo)
checkpoint-status | fe5bacc4-9ad0-472b-86bb-d1012303b616 |  | checkpoint | Masking tape in window opening removed and edges of panel clear of any overspray
holdpoint | c0188f1a-3da0-4996-a70a-47cdc1c56f07 |  | signoff | Window installer accepted quality of concrete opening
checkpoint-status | 400c3274-5018-4d28-a284-b39f9d6d8ea1 |  | checkpoint | Confirmation
holdpoint | 90a51107-ab38-4601-9f59-625ed62dd755 |  | signoff | Window installer confirmed they have completed their works and panel can delivered to site
checkpoint-group | d8ae2582-7359-4b88-bf2e-ca9d2a347137 |  | section | Loading Out (Yard QA)
checkpoint-status | 1e37e562-2ff6-4441-92db-39615c76e4ad |  | checkpoint | Load Docket Given to Driver
checkpoint-status | 96d13520-b30a-46d1-a15b-9966dbcc69df |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | a337ab2f-bbf9-4077-b169-99b6f341fe76 |  | checkpoint | No remedial work required on site
checkpoint-group | a22af8c2-c0f7-4efd-a3d3-6c1f3de88bef |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | 4f629c74-fe0c-4526-9493-e1314c98ec86 |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 9a783d0c-df54-47b8-8ad4-525595c76adf |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | d53cea49-063c-411f-ad33-a16528332da7 |  | checkpoint | Upload Concrete test results
checklist-sectioned | c9532baa-2661-46a0-81b6-9e05e793d95f |  | checklist | P |  |  |  |  | Yes | 2. Standard with Aquron2000 | ecaaba9e-5cb5-4411-b42f-c60215ea4b68
checkpoint-group | 3af0ed91-1a12-48d6-a8f8-8c0d94327c3d |  | section | Precast Element Details
checkpoint-status | 0d5daa81-d94e-4616-84ce-6d819a3e0693 |  | checkpoint | Concrete Details Complete
text | 3a85f9d4-703c-55f7-9b57-850154b27ffe |  | textbox | Concrete Volume
text | c8382481-315a-5d69-b033-00bfe99a280b |  | textbox | Concrete Strength
text | 44df4941-b51a-5c4f-b1da-1c81d7e8811f |  | textbox | Enter Drawing Revision Number
text | cbbe92d7-0e2f-55f3-bc1b-4274259dd7b5 |  | textbox | Cast Date
checkpoint-group | 82807428-795d-4908-b30e-16add4baed73 |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | 15df543a-6261-42b2-808e-30624be1003c |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | 6a432f5b-40b0-4358-96fc-bfe523f2e3ef |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 6c88ff88-bd04-4fbc-af87-8ced9cad3f5b |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | e9e7a835-8e09-48cc-9bf6-f4af47e011fd |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | 82a7a611-592d-4544-8794-6da04b7e5ddd |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | d10b12dd-5a81-4dc6-8156-e909d18a7194 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 54c5301b-9ed2-47ec-8dfb-a6e809ad1ba3 |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | 2002d92f-add1-4de1-916b-87c8c3a0eca7 |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 1ae09b2c-6b32-4da5-977f-db85e7f89f1b |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | f60fafe9-b006-4b9a-96a0-df64a825b0f6 |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 443a97be-3cbf-4341-873a-47e672c264c7 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 568de151-9781-4959-afd6-41b5903bfce6 |  | checkpoint | Mould Face Clean
checkpoint-status | 7d64f16f-4416-4c90-92d2-780e61232f90 |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 2aebe6a9-c12e-449d-b9c0-1668625fef22 |  | checkpoint | Edge Details & Rebates
checkpoint-status | 25d63464-79b5-4b8b-8e9c-a06025518391 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | 04d564f0-6e3c-4f47-b513-898742360659 |  | section | Prepour Checks (Tables QA)
checkpoint-status | 7d35586f-8a4b-4fcb-8875-30beb46d51d2 |  | checkpoint | Main Reinforcing
checkpoint-status | 4e481b78-33cc-4123-b6f3-6312ead1bea6 |  | checkpoint | Starters
checkpoint-status | b8559d72-a035-43c7-9567-5303c25a2e83 |  | checkpoint | Stirrups
checkpoint-status | 7014fec5-99a0-49ba-b8fb-357d386aa585 |  | checkpoint | Lifters
checkpoint-status | 260f757f-12db-463a-b474-896499452a70 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | 4b890473-b1a7-4c3b-80dc-6087a3a05646 |  | checkpoint | Tie wire Trimmed
checkpoint-status | 2abea4b5-6d6e-4759-b9bf-8c8283b6cb81 |  | checkpoint | General Photos Attached
checkpoint-status | 02a6f973-348c-487e-9599-f04a177b5d83 |  | checkpoint | Concrete Docket Attached
checkpoint-status | 5f938220-45ed-4398-bc03-244528d68d6d |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | a057cf1e-23da-4f2f-9114-b73cec5e5ff2 |  | section | Post Pour (Table Supervisor)
checkpoint-status | ca997259-066e-4475-bbd7-1dde1eef7efd |  | checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint-status | 5a2b9d3f-41cf-42ef-9030-77d64866c9c6 |  | checkpoint | Face lifters placed in correct location
checkpoint-status | 488d0deb-c0fc-491e-b88b-de7a137ce37c |  | checkpoint | Roughening Lines Correct
checkpoint-group | c92f3d80-ce2f-4db7-8884-7faf173e1b0a |  | section | Demould Inspection (Yard QA)
checkpoint-status | bac95f8e-cf57-43dc-adde-518a6f248c56 |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | a3eba977-f22d-4e9c-b47d-0c8691f8b8ea |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | 277f257e-e4d4-4336-953f-96bf6a060971 |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | 0bfdfc50-4e9b-4bc6-8cc0-5f6a5be8f406 |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | dbe2576f-fca6-4798-a37e-b7ea152107f6 |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 1461a022-4a3c-499e-8ffa-f6873665fb42 |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 17d0b46a-c24a-440e-838f-e230a569205c |  | checkpoint | MF roughening's jet washed
checkpoint-status | 864d8a8a-0a4a-42f0-b853-cd00a783cb7d |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 2bb34f40-b43f-432d-b6d3-bb78fcd74a81 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | e46bddd3-c149-4771-8e2c-49ef868740da |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 5f6d402e-29ff-4e83-8243-47d545b6e27b |  | checkpoint | Grade 500 starters are straight
checkpoint-status | e43d11ce-0752-4e30-9276-05601eef0884 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 48ae86a5-fb44-4184-a054-f368f2531cc6 |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | e45cc533-1903-4bd8-91db-611bdc3eade4 |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | c7596507-8e7f-4877-b407-d81759f11abd |  | checkpoint | Shop drawing checked off
checkpoint-status | c19c76fe-0b9e-4233-8f1f-141d20da1e93 |  | checkpoint | Aquron2000 applied to Mould Face of Panel
checkpoint-status | d6a6b1a2-61f5-499c-a32a-ef6557767030 |  | checkpoint | Upload photo of Batch no. for Aquron2000 applied to this panel
checkpoint-group | 9f009d2e-39d5-4ef1-8039-f98384cc9e93 |  | section | Overall Panel Quality (Yard QA)
checkpoint-status | 4986d13e-6244-4871-8b84-bf20b9c71151 |  | checkpoint | Overall Panel Quality Ratings Recorded Below
label | 2ff8b1cb-7ac1-53df-af46-78eb6d1693e9 |  | note | The higher the number the better the quality
label | 2c634f88-35d0-50a6-944e-55beebe44330 |  | note | e.g. "1" is unacceptable
button | f555994b-e225-5071-87e6-61d4a819a6e5 |  | button | Vibrating Quality | 5 , 4 , 3 , 2 , 1
button | 869a6493-be6c-565b-b276-f7c6dfec15cc |  | button | Trowelling Quality | 5 , 4 , 3 , 2 , 1
button | 8a798ac1-df4f-54dc-8a03-dee910cd0530 |  | button | Silicone Quality | 5 , 4 , 3 , 2 , 1
button | 30c0d8c2-31b5-5af4-9239-19f5b3ad476f |  | button | Chamfer Quality | 5 , 4 , 3 , 2 , 1
button | 05f8b9dd-c82b-5037-b1a8-d55a9c3592fb |  | button | MF Quality | 5 , 4 , 3 , 2 , 1
checkpoint-group | 5ed06998-d37e-4ae4-9da9-20c7c201c1db |  | section | Loading Out (Yard QA)
checkpoint-status | 410ca20a-5c94-4256-9575-dd334e21776b |  | checkpoint | Load Docket Given to Driver
checkpoint-status | b46c5ecb-24dc-4e79-a878-d3f206d09000 |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | e43f0833-e66e-4a54-9d52-95f5ef05c416 |  | checkpoint | No remedial work required on site
checkpoint-group | e889270a-5643-4398-a04e-1e3cd1a34b63 |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | ad32e840-80a9-4714-8d4a-82539d67487e |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 19a2f2db-d835-40e2-97a6-67c0eb10cf82 |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | b21cbe19-abb3-4760-a152-648e03328ad8 |  | checkpoint | Upload Concrete test results
checklist-flat | 3a2edcf7-94ef-451e-b661-8c2c021a9af7 |  | checklist | Remedial - |  |  |  |  | Yes | Add Defect/Remedial | a28654fb-28bf-4f39-bc8d-85fca885653a
checkpoint-status | e970f2e8-38be-47ea-88e8-55a317040604 |  | checkpoint | Defect Details Inputted
select | 02fb74a6-9297-5b69-8d8f-5d0c48b9c66b |  | dropdown | What is the Defect | Chip in panel, Crack in the panel, Level of finish inadequate, Incorrect Location of Cast in Items, Missing Cast In Items, Other Remedial - Specify below
text | 5643327d-d65b-5388-9530-86f7463e6f6b |  | textbox | Other Defect (specify here if applicable)
text | 0a0c215a-1923-5c54-9bd7-a2a864f6723e |  | textbox | Defect Location on Panel (Attach Photo)
text | 7152a2c6-2eb2-5247-8f3c-096388865e18 |  | textbox | Remedial Work Required
checkpoint-status | 502296f5-6918-4b50-a34e-45b8d43935b1 |  | checkpoint | Panel Location Inputted
text | 96be865a-2544-5cb4-9d0c-5574d44c5bb8 |  | textbox | Panel Location
checkpoint-status | 98dc4c4e-edbc-4b97-8033-8b15d5166725 |  | checkpoint | NCR Raised if Required
checkpoint-status | 883a5a98-2c88-4d02-aa0d-e0db0e558895 |  | checkpoint | Remedial completed - (Attach Photo)
checklist-flat | cb39f9e7-7e8f-4740-8ac4-ef68fc245ea4 |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist | ed41acee-d06d-4515-84d2-177bddfc14a8
checkpoint-status | 3d098030-e418-4675-b5b1-7520caf5ee77 |  | checkpoint | Project details entered below
text | 8724734a-b967-59e4-b175-c5c6f1db0e60 |  | textbox | Job File Number
text | 45b6015f-22e3-5b0c-8117-3a27221048ee |  | textbox | Project Name
text | ef1b5d06-622a-5aca-84c2-8a00931e8d8a |  | textbox | Site Address
text | 31c83e66-7544-5cd3-a918-a8f6baca03e9 |  | textbox | Main Contractor (e.g. Teak)
text | b1590901-5990-5ddc-9dee-19725346ccbb |  | textbox | Main Contractor POC
text | 04d29bad-dab1-5357-9860-e83c0c02444f |  | textbox | Structural Engineer
text | 78611fa4-7a52-594c-8bc7-427229a97b3c |  | textbox | Architect
checklist-sectioned | 86f8f365-588a-4a1f-98fd-7495c9190d1e |  | checklist | 1. Standard |  |  |  |  | Yes | 1. Standard | 51e4dca4-048a-4f3b-84ea-913976231d06
checkpoint-group | f71100fd-a7fa-44fc-8f74-9d56b8d53283 |  | section | Precast Element Details
checkpoint-status | 1b933215-c507-41db-b205-ce47736001b1 |  | checkpoint | Concrete Details Complete
text | efe39546-000b-58ed-859c-7f771062249f |  | textbox | Concrete Volume
text | 0cf46f33-9cbb-5d97-b4e6-9451957bb3a0 |  | textbox | Concrete Strength
text | 7bd99f9e-eadf-568a-84d9-481dbba7cb7a |  | textbox | Enter Drawing Revision Number
text | 4acc4ac6-074c-5063-a0f2-5b7e55354bef |  | textbox | Cast Date
checkpoint-group | 7f029b61-65c1-44eb-9200-1d526c75745d |  | section | Reinforcing Yard Checks (Reo QA)
checkpoint-status | aedd4c5b-9e7f-4d00-994c-5acdf004cfc9 |  | checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint-status | 926ae2f9-ac1d-41b8-8921-9340b5d6c338 |  | checkpoint | Cut and bent bars checked off against detail sheet
checkpoint-status | 0d3ce625-b05a-4bf6-b4cf-85f02d43ab52 |  | checkpoint | Perimeter bars and spacing marks confirmed
checkpoint-status | 7b82878b-5eb8-4e2d-b946-e8f580016e4a |  | checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint-status | d20574b1-6e69-49b8-b41e-d6e8b4f76ab3 |  | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint-status | 1d43601b-3e13-48e6-87eb-9e3ce48db5c6 |  | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint-status | 5474f4f7-821f-425f-aafd-d358403766ce |  | checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint-status | 3b9a338b-1f2b-4953-b521-4205bc1e8cdb |  | checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint-status | 40488736-7109-430a-91f7-f813e40f40f9 |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
checkpoint-group | f26ea5c9-30d6-4542-b7bf-fa5737d8ddee |  | section | Formwork Set Up Checks (Tables QA)
checkpoint-status | 904d0cbe-333a-4def-b143-74a97a03f2b4 |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status | 75b3e26e-6472-4107-a397-26c8c05b4975 |  | checkpoint | Mould Face Clean
checkpoint-status | b1f5a271-0bb9-49ea-98af-7f1bf138abcb |  | checkpoint | Length/Width/Thickness/Cutouts
checkpoint-status | 2a743ef9-bc63-481b-86ac-cf9c3c6c45e0 |  | checkpoint | Edge Details & Rebates
checkpoint-status | ea426651-470b-46d6-83bb-88a5db4cb961 |  | checkpoint | MF Weld plates in correct location and siliconed to table
checkpoint-group | cf54c35e-5164-442f-b0c4-d1a0b7d41269 |  | section | Prepour Checks (Tables QA)
checkpoint-status | e2b6dbd1-8bb1-42db-a2e9-38d6d03abae1 |  | checkpoint | Main Reinforcing
checkpoint-status | 072ad4eb-720d-483f-b373-182c3787478d |  | checkpoint | Starters
checkpoint-status | cb741fc2-4e54-427b-8e95-06c4d550aafd |  | checkpoint | Stirrups
checkpoint-status | e5859140-ac93-4dd7-a65c-949e9d6d412f |  | checkpoint | Lifters
checkpoint-status | 0ae2bc4c-4e04-4b5c-8441-28b3227ac284 |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status | 482c54b1-4d12-4d84-9657-e3f8e7888580 |  | checkpoint | Tie wire Trimmed
checkpoint-status | ffa7e3b1-4416-4985-aed8-1091c753187f |  | checkpoint | General Photos Attached
checkpoint-status | 0b3c73be-9361-4e2d-a260-9c84d9f4e083 |  | checkpoint | Concrete Docket Attached
checkpoint-status | 06d3d864-f96d-4a38-81a5-be13ef9438d9 |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group | fe55d931-2f9b-42fe-b76d-cc309b5a13c3 |  | section | Demould Inspection (Yard QA)
checkpoint-status | f0cf69d3-04aa-46f5-b55f-66d13903f05d |  | checkpoint | Panel correctly labeled (check against shop drawing)
checkpoint-status | 15ffdf9c-af53-467b-a420-a10663078551 |  | checkpoint | Grout holes for Drossbach Ducts have been drilled (top and bottom)
checkpoint-status | 8f25fca8-6c0b-41ee-8278-94f9e296e09d |  | checkpoint | Bottom of Drossbach Duct is clear (any slurry/grout has been removed)
checkpoint-status | dc19c577-e451-46aa-b34f-8f99f25eb355 |  | checkpoint | All lifters have been cleared/cleaned out (including top lifters for install)
checkpoint-status | 1caa1b49-4b14-4b96-aa47-f009f6f961a5 |  | checkpoint | All Inserts have been exposed and nail plates removed (caps that came with Ancon fixings should be put back on)
checkpoint-status | 1e412ff6-d7c9-42f2-82b2-e0218415560e |  | checkpoint | Stitch joints have been jet washed
checkpoint-status | 64a4040f-c13e-4863-9dc3-96bd0cb13139 |  | checkpoint | MF roughening's jet washed
checkpoint-status | 7dd64f63-fa4e-4b0a-bdae-c3484c3bec80 |  | checkpoint | NF chamfers and square edges rounded with cup stone
checkpoint-status | 944a0dbc-e2c0-4b07-bcb4-4fa813ba9201 |  | checkpoint | Weld plates cleaned (NF weld plates to be cleaned with cup stone)
checkpoint-status | 75cbb1ae-17c8-4f70-8095-7052ebe287c8 |  | checkpoint | Grade 300 starters bent up for transport (only bend starter down if transport height is increased by bending up)
checkpoint-status | 368d7ad1-9796-41c9-a32f-6b23d39ab248 |  | checkpoint | Grade 500 starters are straight
checkpoint-status | 4df75124-ab50-470e-8d94-875b1f5efb10 |  | checkpoint | NF Quality acceptable (attach photo)
checkpoint-status | 23ff0ca5-aedf-40fb-a0de-e5894b325c0b |  | checkpoint | MF Quality acceptable (attach photo)
checkpoint-status | 21fc41b2-af7a-4653-875b-66393feaa89c |  | checkpoint | Structural repairs required (if yes photograph before)
checkpoint-status | b2640d1e-6d91-4441-80e7-b558e30d1006 |  | checkpoint | Shop drawing checked off
checkpoint-group | ba97502f-2524-4657-be74-4567cb28ec3f |  | section | Loading Out (Yard QA)
checkpoint-status | d2565aa2-663d-4431-94ec-91423eed8d32 |  | checkpoint | Load Docket Given to Driver
checkpoint-status | a93eef2d-8c17-49e8-9b1b-1d5d70fbe3ff |  | checkpoint | Photo take of Panel on Truck
checkpoint-status | 031f8038-ac03-44e4-9a76-a4228426daf6 |  | checkpoint | No remedial work required on site
checkpoint-group | 29ae6473-1a11-4111-bc71-4fca2d0bad7b |  | section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint-status | c6b0ee27-1b9d-4f9f-a363-ab6f10b4d8a7 |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status | 26ba50b2-8cca-432f-9a92-6576e0c2f71a |  | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint-status | a94545ec-a584-4b5a-adf7-b277d4065155 |  | checkpoint | Upload Concrete test results