## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
20b17b2d-f8cb-4f37-9e86-24a543e2347b | checklist | Exterior balustrade |  | Exterior balustrade
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7328389c-48b4-484b-9d88-95b8a5d2830e | checkpoint | Holes drilled to correct depth and cleaned out
d0b22e85-ce0a-4572-ab69-19678b64be5a | checkpoint | Pull test to 10% of rods and meets KN rating in PS1
4f06f2a5-6474-4e0f-b609-67b99aed1f23 | checkpoint | Balustrade plumb and level
c8e2447d-8f12-4305-bc0c-641a0229c62b | checkpoint | Balustrade has no gaps bigger then 100mm
dcb7ece9-e064-405c-853f-86801b32c87a | checkpoint | Balustrade to correct height
3ac17f3f-a848-4005-810b-7d2eb2f378a5 | checkpoint | Balustrade has no scratches or been touched up
99cb88a2-2e06-4e87-9ed1-48e2bdcc086a | checkpoint | Balustrade installed as per shop drawings
963a84d9-f672-44d6-86a4-8771998a8ac8 | checkpoint | Balustrade has protection tape over capping and corner posts if exposed
932a9adb-96eb-4130-863b-72d905d19484 | checkpoint | Balustrade finished and ready for review by client
f4e33924-4548-4717-9957-a9396f054c31 | checklist | Exterior screens |  | Exterior screens
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f4ef56d9-ae21-4b13-bfe6-d4adb4b62ff6 | checkpoint | Holes drilled to correct depth and cleaned out
b54daea9-5664-4a9e-ac46-bb61526b0761 | checkpoint | Pull test to 10% of rods and meets KN rating in PS1
f761ff78-a78b-4c04-817a-a94c32bd28bc | checkpoint | Screens plumb and level
db4fb551-123e-492a-ad2e-8ff105d98cea | checkpoint | Screens have no scratches or been touched up
f66e0beb-8125-419a-853c-1bfa774ad120 | checkpoint | Screens installed as per shop drawings
1c28a3a5-d92e-484d-a9d4-5af077dc90bb | checkpoint | Screens finished and ready for review by client