## Table 1
Sub-Soil Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 007 - Rev 00
SECTION 1 – GENERAL DETAILS
Project Name: |  |  |  | Wellesley St Bus Interchange - WSBI | [6 empty] | ITP Number: |  |  | 7
Project Number: |  |  |  | DN1211 | [6 empty] | ITP Status: |  |  | IFC
ITP Description: |  |  |  | Subsoil Drainage | [6 empty] | Revision: |  |  | 0
Contract Number: |  |  |  |  | WSBI - DN1211 | [5 empty] | Drawing Sets: | [5 empty] | Stormwater and Kerbing
Customer: |  |  |  |  | Auckland Transport | [5 empty] | Specification: | [5 empty] | WSBI Technical Specification, Ref: 522356-W00001-SPE-MC-0001
Quality Specified:
Review / Update History | [14 empty] | Verification Activity
Rev: |  | Status: | Date: |  |  | Reviewed By: |  | Revision Details: | [6 empty] | Activity Key | [6 empty] | Responsibilities Key
IFC |  | Draft for Review | 2024-09-17 |  |  | R.Collier |  | Sub-Soil ITP | [6 empty] | A |  | Action |  |  |  |  | ENG |  | Engineer / Engineer's Rep
[15 empty] | B |  | Report by Breach |  |  |  |  | CR |  | Customer Rep
[15 empty] | C |  | Check |  |  |  |  | DES |  | Designer
[15 empty] | D |  | Dimension Inspection |  |  |  |  | PM |  | Project Manager
[15 empty] | E |  | Examine |  |  |  |  | OP |  | Operations Manager
[15 empty] | HP |  | Hold Point (Engineer) |  |  |  |  | HSE |  | HSE Manager / Rep
[15 empty] | H |  | Hold Point (Internal) |  |  |  |  | QM |  | QA Manager / Rep
[15 empty] | I |  | Inspection |  |  |  |  | PE |  | Project Engineer
[15 empty] | M |  | Monitor on Random Basis |  |  |  |  | SE |  | Site Engineer
[15 empty] | O |  | Operation |  |  |  |  | QE |  | Quality Engineer
[15 empty] | R |  | Review |  |  |  |  | SUP |  | Superintendent / Supervisor
[15 empty] | S |  | Subcontractor |  |  |  |  | SV |  | Surveyor
[15 empty] | V |  | Visual Verification |  |  |  |  | ITP |  | Third Party Inspector
[15 empty] | W |  | Witness Point |  |  |  |  | SPEC |  | Specialist
SECTION 2A – Master ITP Approval | [10 empty] | SECTION 2B – ITP CLOSEOUT
Position |  |  | Name: |  |  |  | Signature: |  | Date: |  | Position |  |  |  | Name: |  |  |  |  | Signature: | [5 empty] | Date:
Downer PM |  |  | Glen Maria |  |  |  | Glen Maria |  | 2024-07-17 |  | Downer PM
Downer QM | [10 empty] | Downer QM
Client (If Applicable) | [10 empty] | Client (If Applicable)
Sub-Soil Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 007 - Rev 00
Item No. | Inspection and Test Point |  |  |  | Acceptance / Conformance Criteria |  |  |  |  | Standard / Specification |  | Verifying Document | Frequency |  |  | Verification Activity |  |  | Downer Conformance of Compliance Signoff
[16 empty] | Activity |  | By | Downer Signature |  | Date |  | MSQA signature (Blank as Req.) |  | Engineer Rep Signature (Blank as req.) |  | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01.01 | Construction Pack |  |  |  | Submit a Construction Pack including a Methodology and JSEA to the Engineer before works |  |  |  |  | Downer |  | Construction Pack | Submit 5 days prior to commencement of works |  |  | H |  | PE | H | [5 empty] | R
3.02.02 | Survey Setout |  |  |  | Survey Set out as per contract drawings and specification, capturing pre- construction levels where needed. |  |  |  |  | Downer |  | Survey Records | Prior to Works |  |  | H |  | SV | H
3.01.02 | Service Location |  |  |  | Complete the Excavation permit process to identify, locate and protect all services. |  |  |  |  | Downer |  | Excavation Permit | Prior to Excavation |  |  | H |  | SE | H
3.02.03 | Internal Permits |  |  |  | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. |  |  |  |  | Downer |  | Internal Permits | Prior to Excavation |  |  | H |  | SE | H
3.01.03 | External Permits |  |  |  | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. |  |  |  |  | Downer |  | External Permits | Prior to Excavation |  |  | H |  | PE | H | [5 empty] | R
3.02.04 | Approved Construction Drawings |  |  |  | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. |  |  |  |  | Downer |  | IFC Drawings | Prior to works start |  |  | H |  | PE | H
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01.01 | Material Properties |  |  |  | Filter Aggregate, pipes and filter fabric shall comply with TNZ F/2 for non‐wrapped drains and TNZ F/6 for fabric wrapped drains. Filter aggregates specified in TNZ F/5 shall not be used. Pipes supplied and installed as specified in drawings |  |  |  |  | Aurecon Civil Spec Section 16.5 TNZ F/2, F/6 ATCoP |  | Supplier Records | Prior to use Checked on Delivery |  |  | H |  | PE | H |  |  |  | R |  | R
4.01.02 | Drainage Aggregate |  |  |  | Shall be NZTA F/2 or F/6 Drainage Aggregate chip (20/7mm) DN1211-DOW-RFI - 0048 |  |  |  |  | Aurecon Civil Spec Section 16.6.3 RFI-0048 |  | MAR record | Pior to Use Delivery Dockets |  |  | H |  | PE | H |  |  |  | R
4.01.03 | No-Fines Concrete |  |  |  | As per TfNSW 3222, for aggregate size distribution to be 26.5 mm @ 100 % 19 mm @ 95 - 100% 9.5 mm @ 0 - 5% |  |  |  |  | Aurecon Civil Spec Section 14,17.11.7 |  | Supplier Records Concrete Dockets | As required |  |  | H |  | PE | H |  |  |  | R
SECTION 5 – CONSTRUCTION ACTIVITY – DRAINAGE INSTALLATION
5.01.01 | Subsoil trenching |  |  |  | Construct subsoil trenches as per TNZ F/2 or Approved 20/7 drainage chip, falling towards drainage outlet. Install Geotextile filter fabric at base of trench where specified. Drainage aggregate bedding installed at trench base; 75mm thick for Ø=75mm pipe and 100mm thick for Ø=100mm pipe. Suvey Set-out position as per deign unless design clash changes required |  |  |  |  | Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP |  | QA Checksheet | Inspect on regular intervals |  |  | I |  | SE | I
5.01.02 | Subsoil installation |  |  |  | In absence of subsoil depths in drawings: Install subsoils at 600mm below FL forsealed roads and traffickable areas, and at 450mm for non‐trafficked areas. Subsoils laid straight, falling towards drainage outlet as per TNZ F/2 and drawing |  |  |  |  | Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP |  | QA Checksheet | Inspect on regular intervals |  |  | W |  | SE | W |  |  |  | R |  | I
5.01.03 | Trench Dimensions |  |  |  | Excavate trench to lines, levels, width and gradients shown on drawings. Trench of sufficient width to permit installation of all materials and fittings. Pipes minimum 100mm from trench wall. |  |  |  |  | Aurecon Civil Spec Section 16.6.2 |  | QA Checksheet | Inspect on regular intervals |  |  | W |  | SE | W
5.01.04 | Backfill Placement |  |  |  | Backfill with 150mm + 150mm depth of drainage filter material above pipe, hand tamped Backfill and plate compact remainder to FL as specified in drawing |  |  |  |  | Aurecon Civil Spec 18.6.3 TNZ F/2 ATCoP |  | QA Checksheet | Inspect on regular intervals |  |  | I |  | SE | I
5.01.05 | Flow Test |  |  |  | Visual inspection of water flow. |  |  |  |  | Visual Inspection |  | ITP Sign off | Once per Zone |  |  | H |  | SE | H |  |  |  | R |  | R
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01.01 | Construction Record Compilation |  |  |  | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. |  |  |  |  | Downer |  | Records | Post construction |  |  | H |  | SE | H |  |  |  | R |  | H
6.01.02 | Survey Records |  |  |  | Ensure all items have been surveyed and records are assembled for asbuilting. Asbuilts to include type, size, quantity, location and level of subsoil laid. |  |  |  |  | Downer |  | Records | Post construction |  |  | H |  | SV | H |  |  |  | R |  | H
6.01.03 | Redline Drawings |  |  |  | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Relevant change correspondence to be included. |  |  |  |  | Downer |  | Redlines | Post construction |  |  | H |  | PE | H |  |  |  | R |  | H
6.01.04 | Defect, Snag and Punch List |  |  |  | Update the project Defect, Snag and Punch List Register |  |  |  |  | Downer |  | Register | Post construction |  |  | H |  | PE | H |  |  |  | R |  | H