## ITP Cover Page - Kerb & Channel
Northern Access Road & Carpark - Kerb & Channel Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-006-005 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | SP2-006-005
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Approved - IFC
ITP Description: |  |  | Northern Access Road & Carpark - Kerb & Channel |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 26.7 Kerb and Channel
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-26 |  | Cordelia Girdler-Brown |  | Draft for Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved /IFC | 2025-02-17 |  | Cordelia Girdler-Brown & Nick Adams |  | AS per GCO 0116 1. 3.1.1 crushing resistance change from >80KN to >100KN. 2. 4.1.2 Clegg values change from Min 22, ave 25 to min 18 and ave 20. 3. Section 5 name change from semi mountable kerb to Nib kerb with footing. |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS |  |  | #VALUE! |  | 17/02/2025 | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 17/02/2025 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Kerb & Channel
Kerb & Channel Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-006-005 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: 17/02/2025 | DOWNER RESPONSE - Date: 17/02/2025
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | MATERIAL APPROVALS: IMPORTED MATERIAL TESTING - AP40-1 - BASECOURSE FOR KERB PREP - SOURCE PROPERTY TESTS FOR TYPE A1 IMPORTED STRUCTURAL FILL - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Project Specifications Appendix XVIII | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG |  |  |  | Crushing resistance should be >100kN | Changes made
3.1.2 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | Project Specifications Appendix XVIII | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.3 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 37.5mm 100% passing 19.0mm 60-75% passing 9.5mm 37-50% passing 4.75mm 20-35% passing 2.36mm 12-28% passing 1.18mm 9-20% passing 0.600mm 7-12% Passing 0.300mm 3-10% Passing 0.150mm 0-5% passing 0.075mm 0-5% passing | Project Specifications Appendix XVIII Tauranga Council IDC - Table IT-4.7 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
SECTION 4 – CONSTRUCTION - KERB & CHANNEL PREPARATION
4.1 | BASECOURSE (AP40)
4.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | -0mm + 20mm | NZTA B/06 8.2.2 - Table 3 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.1.2 | Compaction - Clegg | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | PS Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE |  |  |  | Clegg values to be as per testing schedule - min CIV =18, ave CIV = 20 | Changes made
SECTION 5 – CONSTRUCTION - KERB & CHANNEL PREPARATION
5.1 | VERTICAL KERB & CHANNEL
5.1.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | Project Specifications 21.7.6 | Kerb construction record | During construction - Before every pour | I | SE
5.1.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | Project Specifications 26.7.3 | Concrete Delivery dockets Concrete Test Results | During construction - Every pour | I | SE
5.1.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Project Specifications 27.4.5 (c) | Post-Pour Checksheet | During construction - Every pour | I | SE
5.1.4 | Final Finish | Slip form kerb and channel | Slip form kerb and channel | Project Specifications 26.7.3 | Post-Pour Checksheet | After every pour | I | SE
5.2 | SEMI MOUNTABLE KERB & CHANNEL
5.2.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | Project Specifications 21.7.6 | Kerb construction record | During construction - Before every pour | I | SE
5.2.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | Project Specifications 26.7.3 | Concrete Delivery dockets Concrete Test Results | During construction - Every pour | I | SE
5.2.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Project Specifications 27.4.5 (c) | Post-Pour Checksheet | During construction - Every pour | I | SE
5.2.4 | Final Finish | Slip form kerb and channel | Slip form kerb and channel | Project Specifications 26.7.3 | Post-Pour Checksheet | After every pour | I | SE
5.3 | NIB KERB WITH FOOTING | [10 empty] | Please update ITP to include NIB kerb with footing | Changes made
5.3.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | Project Specifications21.7.6 | Kerb construction record | During construction - Before every pour | I | SE
5.3.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | Project Specifications 26.7.3 | Concrete Delivery dockets Concrete Test Results | During construction - Every pour | I | SE
5.3.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Project Specifications 27.4.5 (c) | Post-Pour Checksheet | During construction - Every pour | I | SE
5.3.4 | Final Finish | Slip form kerb and channel | Slip form kerb and channel | Project Specifications 26.7.3 | Post-Pour Checksheet | After every pour | I | SE
5.4 | MOUNTABLE KERB & CHANNEL
5.4.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | Project Specifications21.7.6 | Kerb construction record | During construction - Before every pour | I | SE
5.4.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | Project Specifications 26.7.3 | Concrete Delivery dockets Concrete Test Results | During construction - Every pour | I | SE
5.4.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Project Specifications 27.4.5 (c) | Post-Pour Checksheet | During construction - Every pour | I | SE
5.4.4 | Final Finish | Slip form kerb and channel | Slip form kerb and channel | Project Specifications 26.7.3 | Post-Pour Checksheet | After every pour | I | SE
5.5 | CYCLE MOUNTABLE KERB
5.5.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | Project Specifications21.7.6 | Kerb construction record | During construction - Before every pour | I | SE
5.5.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | Project Specifications 26.7.3 | Concrete Delivery dockets Concrete Test Results | During construction - Every pour | I | SE
5.5.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Project Specifications 27.4.5 (c) | Post-Pour Checksheet | During construction - Every pour | I | SE
5.5.4 | Final Finish | Slip form kerb and channel | Slip form kerb and channel | Project Specifications 26.7.3 | Post-Pour Checksheet | After every pour | I | SE
5.6 | KASSEL KERB
5.6.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | Project Specifications21.7.6 | Kerb construction record | During construction - Before every pour | I | SE
5.6.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | Project Specifications 26.7.3 | Concrete Delivery dockets Concrete Test Results | During construction - Before every pour | I | SE
5.6.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Project Specifications 27.4.5 (c) | Post-Pour Checksheet | During construction - Every pour | I | SE
5.6.4 | Final Finish | Hand poured and formed concrete kerbs | F3 Surface Finish / Slip form kerb and channel | Project Specifications 22.10.2 | Post-Pour Checksheet | After every pour | I | SE
SECTION 6 – CONCRETE ISLAND
6.1 | BASECOURSE (AP40)
6.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface 75mm from finish concrete level | -0mm + 20mm | NZTA B/06 8.2.2 - Table 3 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
6.1.2 | Compaction - Clegg | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | PS Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
6.2 | CONCRETE
6.3.1 | Concrete | 20 MPa coloured with 2.5% black oxide | 28 days concrete strength test of 20MPa | 232735.02-WSP-DR-UDL-0405 | Concrete Delivery dockets and test reports | During construction | I | SE
6.3.2 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m | PS 27.4.5 | Post Pour Checksheet | During construction - Every pour | I | SE
6.3.3 | Final Finish | Trowelled | U3 Finish | 232735.02-WSP-DR-UDL-0405 | Post-Pour Checksheet | After pour | I | SE
SECTION 7 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7.1 | Final Inspection | Final inspection of all concrete work. | All works meet project specifications and standards. | NZTA P39: 2013 | Final inspection report | 100% Completion of works | HP | ENG
7.1 | As-Builts | Final inspection of all concrete work. | All works meet project specifications and standards. - any changes to be added to redpen markuProject Specifications | Project Specifications 16.7.6 | Redpen markuProject Specifications | 100% Completion of works | D | SV