## ITP Cover Page
Northern Access Road & Carpark - Vehicle Crossings - Inspection & Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - SP2-006-006 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | SP2-006-006
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | Approved - IFC
ITP Description: |  |  | Northern Access Road & Carpark - Vehicle Crossings |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 27.4 Hard Landscaping
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 28/01/2025 |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved /IFC | 17/02/2025 |  | Cordelia Girdler-Brown & Nick Adams |  | AS per GCO 0116 1.ITP 4.1.2 scalas change from 2blows/100mm to 3blows /100mm |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 17/02/2025 | Downer PM |  | Nick Adams
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 17/02/2025 | Downer QM |  | Cordelia Girdler-Brown
Client (If Applicable) | [7 empty] | Client (If Applicable)

## NAR Vehicle Crossings
Northern Access Road & Carpark - Vehicle Crossings - Inspection & Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - SP2-006-006 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: 17/02/2025 | DOWNER RESPONSE - Date: 17/02/2025
SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | MATERIAL APPROVALS: IMPORTED MATERIAL TESTING - AP40-1 - SOURCE PROPERTY TESTS FOR TYPE A1 IMPORTED STRUCTURAL FILL - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 130kN | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >80% | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.1.3 | Accelerated Weathering | NZTAT/20 Ethylene Glycol Accelerated Weathering Test | ≤ 30% increase in fines | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.1.4 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.2 | MATERIAL APPROVALS: IMPORTED MATERIAL TESTING - AP40-1 - PRODUCTION PROPERTY TESTS FOR TYPE A1 IMPORTED STRUCTURAL FILL - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.2.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 37.5mm 100% passing 19.0mm 60-75% passing 9.5mm 37-50% passing 4.75mm 20-35% passing 2.36mm 12-28% passing 1.18mm 9-20% passing 0.600mm 7-12% Passing 0.300mm 3-10% Passing 0.150mm 0-5% passing 0.075mm 0-5% passing | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.2 | Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 28-48% 19.0 – 4.75 14-34% 9.5 – 2.36 7-27% 4.75 – 1.18 6-22% 2.36 – 0.6 2-20% 1.18 – 0.3 5-19% 0.6 – 0.15 2-14% | Project Specifications 20.9 TCC-IDC IT-4..8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.3 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | ≥ 40 | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.4 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | Plasticity Index ≤ 8 | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.5 | Cone Penetrometer Limit | NZS4407:2015, Test 3.2 Cone Penetration | Cone Penetrometer ≤ 30 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.6 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | ≤ 5 | Project Specifications 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.8 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, Per Source | HP | ENG
3.3 | MATERIAL APPROVALS: STEEL REINFORCING
3.3.1 | Reinforcing Mesh | 661 Reinforcing mesh (Commerical Vehicle Crossing) | 661 Reinforcing mesh (Commerical Vehicle Crossing) | 232735.02-WSP-DR-RSA-0305 | Material Data Sheet Engineer's Approval | Prior to Construction | W | SE
3.3.2 | Reinforcing Ties | R6 Ties (For commercial crossing only) | R6 Ties at 600 centres with 60 mm (For commercial crossing only) | 232735.02-WSP-DR-RSA-0305 | Material Data Sheet Engineer's Approval | Prior to Construction | W | SE
3.3.3 | Reinforcing Bars | 4-D12 Bars (For commerical crossing only) | 4-D12 Bars with 50 mm Cover (For commerical crossing only) | 232735.02-WSP-DR-RSA-0305 | Material Data Sheet Engineer's Approval | Prior to Construction | W | SE
3.4 | MATERIAL APPROVALS: CONCRETE
3.4.1 | Concrete Mix Design | 20.0 MPA concrete. 4kg/m3 black oxide (2.5%) | 28 days concrete strength test of 20MPA | 232735.02-WSP-DR-UDL 0405 | Material Data Sheet Engineer's Approval | Prior to Construction | HP | ENG
SECTION 4 - CONSTRUCTION
4.1 | GENERAL
4.1.1 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa CBR: >3 Single Test Minimum SU: >50kPa | Project Specifications Appendix XVIII | Shear Vane Report | 1 test per 100m2 | I | SE
4.1.2 | Cut Subgrade Testing - Granular Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Project Specifications Appendix XVIII | Scala Report | 4 test per 400m2 | I | SE |  |  |  | Scalas to be min 3 blows/100mm | Changes made
4.1.3 | Proof Roll Subgrade | Visual Inspection of Proof Roll | Visual Inspection | Project Specifications Appendix XVIII | Visual Inspection/Photos | Across Finished Area | I | SE
4.1.4 | Hold point | Subgrade signoff | Conqa signoff |  | Conqa signoff | Each area | HP | ENG
SECTION 5 - CONSTRUCTION - RESIDENTIAL AND COMMERICAL VEHICLE CROSSINGS
5.1 | BASECOURSE (AP40)
5.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | Hight '+15mm/0mm Width –20 mm +100 mm | NZTA B/06 8.2.2 - Table 3 | Surveyor Records | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.2.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | H | SE
5.1.2 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | NZTA B/02 7.6 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
5.1.3 | Hold point | Basecourse signoff | Conqa signoff |  | Conqa signoff | Each area | HP | ENG
5.3 | FORMWORK
5.3.1 | Surveyor check | Equivalent to check the position of the formwork | +\- 100mm of design | Project Specifications 27.4.5 (b) | Surveyor Records | 1 Set Every 20m Centres 1 set = 5 tests | HP | ENG
5.3.2 | Surveyor check | Equivalent to check finished height of framework | +\- 10mm of design | Project Specifications 27.4.5 (b) | Surveyor Records | 1 Set Every 20m Centres 1 set = 5 tests | H | SE
5.4 | REINFORCING MESH
5.4.1 | Reinforcing Mesh Check | 661 Reinforcing mesh (Commerical Vehicle Crossing) | 661 Reinforcing mesh (Commerical Vehicle Crossing) | 232735.02-WSP-DR-RSA-0305 | Delivery Dockets Visual Inspection/Photos | Before Pour During Construction | H | SE
5.4.2 | Reinforcing Mesh | Ensure that overlap and cover above and beneath mesh | Reinforcing mesh to be placed centrally in the concrete layer | 232735.02-WSP-DR-RSA-0305 | Visual Inspection/Photos | Before Pour During Construction | H | SE
5.5 | REINFORCING STEEL (COMMERICAL VEHICLE CROSSING ONLY)
5.5.1 | Reinforcing Ties | R6 Ties at 600 centres with 60 mm (For commercial crossing only) | R6 Ties at 600 centres with 60 mm (For commercial crossing only) | 232735.02-WSP-DR-RSA-0305 | Delivery Dockets Visual Inspection/Photos | Before Pour During Construction | H | SE
5.5.2 | Reinforcing Bars | 4-D12 Bars with 50 mm Cover (For commerical crossing only) | 4-D12 Bars with 50 mm Cover (For commerical crossing only) | 232735.02-WSP-DR-RSA-0305 | Delivery Dockets Visual Inspection/Photos | Before Pour During Construction | H | SE
5.6 | CONCRETE
5.6.1 | Concrete | 20.0 MPA concrete. 4kg/m3 black oxide (2.5%) | 28 days concrete strength test of 20MPA | 232735.02-WSP-DR-UDL 0405 | Concrete Delivery Dockets Test Results | Before Pour During Construction | H | SE
5.6.2 | Concrete Layer Thickness | Concrete layer thickness to be 150 mm for Residential Vehicle Crossings Concrete layer thickness to be 200 mm for Commerical Vehicle Crossings | Concrete layer thickness to be 150 mm for Residential Vehicle Crossings Concrete layer thickness to be 200 mm for Commerical Vehicle Crossings | 232735.02-WSP-DR-RSA-0305 | Pre-Pour CheckSheet | Before Pour | H | SE
5.6.3 | Final Finish | Rough broom finish | U5 | 232735.02-WSP-DR-UDL 0405 | Post-Pour CheckSheet | After Pour | H | SE
5.6.4 | Saw Cuts | Saw cut expansion joints at 4m centres maximum each way | Saw cut expansion joints at 4m centres maximum each way | 232735.02-WSP-DR-RSA-0305 | Post-Pour CheckSheet | After Pour | D | SE
SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.1 | As-Builts | Final inspection of all concrete work. Red Pen Mark up | All works meet project specifications and standards. any changes to be noted on redpen markuProject Specifications | Project Specifications 16.7.6 | Red Pen Markup | 100% Completion of works | D | SV
Note on D23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Jeremy Martin - add this information to the detail as well. I do not see any mesh as a material above to be approved, remember all materials used need to be pre-approved by the Engineer, as a line item with the verifying document been the material data sheet and RFI or NTC approval, and once the construction works start, we will add the delivery dockets and photos as proof of the correct material been used.
Note on D44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Jeremy Martin - add this information to the detail as well. I do not see any mesh as a material above to be approved, remember all materials used need to be pre-approved by the Engineer, as a line item with the verifying document been the material data sheet and RFI or NTC approval, and once the construction works start, we will add the delivery dockets and photos as proof of the correct material been used.
Note on F50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Jeremy Martin - testing of concrete? we need to add concrete test results here Reply: @Jeremy Martin - also no approval in materials for this - please add - even if it's an already approved concrete mix on site we need to add it with this pack
Note on F51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: should this not be pre-pour?