## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-011-002 ITP Northern Access Road WW | itp |  |  |  |  | DN1210-SP2-011-002 ITP Northern Access Road WW Rev 1
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL , PERSONNEL & THIRD PARTY APPROVLS (P&G / ESTABLISHMENT)
checkpoint | 3.1.1 - Pipe Laying
label | Detail - Method statement
label | Acceptance / Conformance Criteria - As Per Specification and IFC Drawings
label | Standard / Specification - PS- 22.3 Appendix V
label | Verifying Document - Wastewater Construction Work Pack Sign off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Pipeline Pressure Testing
label | Detail - Method statement
label | Acceptance / Conformance Criteria - As Per Specification and IFC Drawings
label | Standard / Specification - PS- 22.3 Appendix V
label | Verifying Document - Wastewater Pipeline Pressure Testing Work Pack Sign off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Extent of Line Setout
label | Detail - Ensure line and level of Wastewater has been marked out and agreed with Engineer in accordance with Waste water drawings.
label | ○ Identify any clashes before construction.
label | ○ LOT - markup
label | Acceptance / Conformance Criteria - As Per Drawings & Markup drawing
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off / Mark-up
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction & Every Revision of IFC Drawings/Data.
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Material grading: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - No Particles >200mm
label | ○ Maximum fines 10% passing 75micron sieve
label | Standard / Specification - PS 22.13.1 Appendix XVIII, PS 16.5.5 Appendix V
label | Verifying Document - Lab Test Report NZS 4407.3.8.1
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Weathering index: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - Crushing Resistance: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.1 - Material grading: Materials (GAP20/AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 19.0mm ¦¦ 100% passing
label | 13.2mm ¦¦ 80-95% passing
label | 9.5mm ¦¦ 64-76% passing
label | 4.75mm ¦¦ 37-58% passing
label | 2.36mm ¦¦ 30-40% passing
label | 1.18mm ¦¦ 18-28% passing
label | 0.600mm ¦¦ 12-22% passing
label | 0.300mm ¦¦ 6-14% passing
label | 0.150mm ¦¦ 2-7% passing
label | 0.075mm ¦¦ 0-3% passing
label | Standard / Specification - PS-22.4.5, PS-21.5.7, PS-21.7.2 Table 21.2
label | Verifying Document - Lab Test Report NZS 4407.2015 Test 3.8.1
label | Testing Quantity Required (based from schedule qtys) - 0-400m3 ¦¦ 2 Test
label | 400-1500m3 ¦¦ 3 Test
label | 1500-4000m3 ¦¦ 4 Test
label | >4000 ¦¦ 1 Test Additional 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - Weathering index: Materials (AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.3
label | Verifying Document - Lab Test Report NZS 4407.3.11
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - Crushing Resistance: Materials (AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - >100kN
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.4
label | Verifying Document - Lab Test Report NZS 4407:1991 Test.3.10
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 21.7.2, PS16.5.12, IFC Drawing WST-0320
label | Verifying Document - Lab Test Report NZS 4407.3.8.1
label | Testing Quantity Required (based from schedule qtys) - 1 Test for each additional 1000m3
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.2 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 21.7.2, PS16.5.12, IFC Drawing WST-0321
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test for each additional 1000m3
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.1 - Pipes (PE/ PVC)
label | Detail - Manufacturer's record and location of extrusion plants.
label | ○ Name of the proposed PE resin, the manufacturer, production information on the properties of resin.
label | ○ Full Traceability information and certification of analysis for the resin batch.
label | Acceptance / Conformance Criteria - Full Traceability information and certification of Material and resin.
label | Standard / Specification - PS-22.4.1 (d)
label | Verifying Document - Full Traceability information and certification of Material and resin, Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.2 - Green Dome Odour Filter
label | Detail - A Green Dome Odour Filter (Model GDOF36) complete with DN150 ducting.
label | Acceptance / Conformance Criteria - IFC Drawing 0324-1
label | Standard / Specification - Model GDOF30
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.3 - Valves, Adaptors, Flanges and Fittings
label | Detail - Have a pressure rating no less than the designed pressure.
label | ○ Mechanically, chemically and electrically compatible with the class and material of the pipe.
label | ○ Current Water Services Association of Australia (WSAA) appraisal certificate or approved independent proof of fitness-for-purpose.
label | Acceptance / Conformance Criteria - Engineer approval, AS/NZS 4129
label | Standard / Specification - PS-22.4.2
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.1 - Pipe and fittings. (PE100- DN250 PN10 RM, DN300 PVC SN16)
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Acceptance / Conformance Criteria - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Standard / Specification - Design Drawings
label | Verifying Document - Delivery Dockets / Inspection Checksheet (DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.2 - Valves, Adaptors, Flanges and Fittings
label | Detail - Confirm class and type as shown on the drawings, and that the fittings are correct and in good condition.
label | Acceptance / Conformance Criteria - Confirm class and type as shown on the drawings, and that the fittings are correct and in good condition.
label | Standard / Specification - PS-22.4.2
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.3 - Granular Material (Imported Sand, GAP20/AP20, GAP65/AP65)
label | Detail - Confirm Specification and material in good condition.
label | Acceptance / Conformance Criteria - Confirm Specification and material in good condition.
label | Standard / Specification - PS-22.4.1
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.4 - Bidim/Geogrid
label | Detail - BIDIM A29, Durogrid 30/30 or similar.
label | Acceptance / Conformance Criteria - Site Engineer Approval
label | Standard / Specification - PS-22.4.1
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.5 - Manhole WWMH 01
label | Detail - Confirm the class and type as shown in the drawings, and fittings required for MH is same
label | Acceptance / Conformance Criteria - Confirm the class and type as shown in the drawings, and fittings required for MH is same
label | Standard / Specification - Design Drawings
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.6 - Manhole WWMH 02
label | Detail - Confirm the class and type as shown in the drawings, and fittings required for MH is same
label | Acceptance / Conformance Criteria - Confirm the class and type as shown in the drawings, and fittings required for MH is same
label | Standard / Specification - Design Drawings
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6.7 - Manhole WWMH 03
label | Detail - Confirm the class and type as shown in the drawings, and fittings required for MH is same
label | Acceptance / Conformance Criteria - Confirm the class and type as shown in the drawings, and fittings required for MH is same
label | Standard / Specification - Design Drawings
label | Verifying Document - Delivery Dockets / Inspection Checksheet(DG-QA-TP019)
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION ACTIVITY
checkpoint | 4.1.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | (Or)
label | ○ Cohesive Material: Vane Shear Strength min50kpa, ave>60kpa
label | Standard / Specification - Appendix V Table 21:11
label | Verifying Document - Scala/Shear test result
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | Verification Activity: Activity - W
label | Review of text reports/records or other evidence of compliance
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Undercut approval
label | Detail - Trench Foundation
label | Acceptance / Conformance Criteria - 300mm Max cut
label | ○ IFC Drawing Sheet 320
label | (Or)
label | ○ Engineers approval
label | Standard / Specification - IFC Drawing WST 0320. AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Undercut Backfill Compliance (PAP5)
label | Detail - On Granular Material / On each layer as per specification / on the trench foundation.
label | Acceptance / Conformance Criteria - Visiual Inspection
label | Standard / Specification - IFC Drawing WST 0320
label | Verifying Document - Lab Test Report / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - Every Undercut
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Bedding Zone Compaction Testing
label | Detail - On Granular Material / On each layer as per specification (Imported Sand or GAP20)
label | Acceptance / Conformance Criteria - Bedding Zone: 100mm minimum thickness (compacted) over the bottom of the trench.
label | ○ Minimum Compaction- 85%MDD
label | OR
label | ○ 12% CIV
label | Standard / Specification - IFC Drawing 0320-1, AS/NZS 2566.2/2002
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - As per SW Specification.
label | ○ One test per 10m evenly spaced intervals.
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.1.5 - Laying of Pipes
label | Detail - Lay in straight lines, beginning at the lower end of the line.
label | ○ Lay all pipe with manufacturing codes and class markings facing upwards.
label | Acceptance / Conformance Criteria - As Per Drawings, Facing upwards
label | Standard / Specification - PS22.7.1 C
label | Verifying Document - Visual Inspection / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - Every Line
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.1.6 - Pipe Installation on Curved Alignments
label | Detail - All Industry Guideline PVC, PP AND PE PIPE INSTALLATION ON CURVED ALIGNMENTS (POP202)
label | Acceptance / Conformance Criteria - AS Per POP 202
label | Standard / Specification - PS 22.7.1 D
label | Verifying Document - Visual Inspection / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - Every Line
label | Verification Activity: Activity - M
label | Monitor on Random Basis
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Flanges
label | Detail - Manufacturer specifies their own bolt tightening torque and sequence, it should override the project specification.
label | Acceptance / Conformance Criteria - Flanges to AS/NZS 4087
label | Standard / Specification - PS 22.7.5
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - First flanged joint
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.2 - Bends
label | Detail - PE 100 butt fusion welded segmented bends only where specifically indicated on the Drawings.
label | ○ Fitting must meets the same PN rating as the adjacent PE 100.
label | ○ Fittings must be suitable for producing the joints shown on the Drawings.
label | Acceptance / Conformance Criteria - PIPA POP 006 and AS/NZS 4129
label | Standard / Specification - PS 22.4.2
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - As per the IFC drawing
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.3.1 - Butt-Fusion pre construction weld test
label | Detail - One weld on the most common size of pipes used for the project.
label | ○ One weld on the thickest wall (highest PN) pipe
label | Acceptance / Conformance Criteria - ISO 13953 for tensile strength and failure mode, WMS Report
label | Standard / Specification - PS 22.9.6 (a)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Two test welds per operative(Welder)
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.2 - Butt-Fusion Welding
label | Detail - Use only semi-automatic or automatic welding machines.
label | ○ Maintain a site record for all butt-fusion welds.
label | ○ The lead welder or supervisor must verify on the site record form that all welds have been made in accordance with the WMS and that the information on the record form is correct.
label | Acceptance / Conformance Criteria - Site Butt Fusion Welding record to be filled out. (Refer to CWP), WMS Report
label | Standard / Specification - Appendix 22. PS 22.9.4 C
label | Verifying Document - Visual Inspection / Butt Fusion welding records checklist, WMS Report
label | Testing Quantity Required (based from schedule qtys) - Every Welding Point
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.3 - Butt-Fusion Construction weld test
label | Detail - Test at least two welds from the first 50 welds.
label | ○ One of the welds to be selected by the Engineer for satisfactory result.
label | Acceptance / Conformance Criteria - Tensile testing and ductility of welds.
label | Standard / Specification - PS- 22.9.6 (a) (iv)
label | Verifying Document - Test report
label | Testing Quantity Required (based from schedule qtys) - Two welds for the first 50 welds
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.4 - Survey
label | Detail - Inspection of Pipeline Inverts
label | Acceptance / Conformance Criteria - Vertical design Setout:
label | — Pipes ≤ 1% grade: +/- 10mm variance
label | — Pipes > 1% grade: +/- 20mm variance
label | ○ Horizontal design Setout:
label | — +/-30mm variance
label | Standard / Specification - PS- 21.7.6 Table 21.15
label | Verifying Document - Survey Data / As-built record
label | Testing Quantity Required (based from schedule qtys) - Pipeline invert to be surveyed at chainages as indicated in the drawings.
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.4.1 - Electrofusion (EF) pre construction weld test
label | Detail - Use the designated welding equipment and the approved WMS.
label | ○ On the largest size of PE pipe used in this Contract
label | Acceptance / Conformance Criteria - ISO 21751 (strip-Bend test) or ISO 13954 (Peel-decohesion test), WMS Report
label | Standard / Specification - PS 22.9.6 (b)
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - One test welds per operative(Welder)
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.2 - Electrofusion (EF) Welding
label | Detail - Required if Butt fusion welding cannot be perform.
label | ○ EF Jointing in accordance with PIPA POP 001.
label | ○ The lead welder or welding supervisor must verify on the site record form.
label | Acceptance / Conformance Criteria - WMS Report, Checklist (refer to CWP).
label | Standard / Specification - PS 22.9.5 Appendix 22
label | Verifying Document - Visual Inspection / Electrofusion (EF) welding record checklist, WMS Report
label | Testing Quantity Required (based from schedule qtys) - Every Welding Point
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.4.3 - Electrofusion (EF) construction weld test
label | Detail - EF weld quality to be maintained.
label | Acceptance / Conformance Criteria - EF coupler and EF saddle testing
label | Standard / Specification - PS- 22.9.6 (b) (iv)
label | Verifying Document - Test report
label | Testing Quantity Required (based from schedule qtys) - 1 in 10 test
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.4 - Survey
label | Detail - Inspection of Pipeline Inverts
label | Acceptance / Conformance Criteria - Vertical design Setout:
label | — Pipes ≤ 1% grade: +/- 10mm variance
label | — Pipes > 1% grade: +/- 20mm variance
label | ○ Horizontal design Setout:
label | — +/-30mm variance
label | Standard / Specification - PS- 21.7.6 Table 21.15
label | Verifying Document - Survey Data / As-built record
label | Testing Quantity Required (based from schedule qtys) - Pipeline invert to be surveyed at chainages as indicated in the drawings.
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.5.1 - Emebment Zone - (Side Haunch Overlay)
label | Detail - Granular Sand backfill Compacted in 200mm Layers.
label | ○ NDM/CleggTesting to be completed on maximum 200mm lifts of overlays.
label | ○ NDM BS to be Carried Out
label | Acceptance / Conformance Criteria - in 200mm layers.
label | ○ More than 85% of MDD.
label | OR
label | ○ 12% CIV
label | Standard / Specification - IFC Drawing 0320-1
label | Verifying Document - Lab Report / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals. 200mm lift
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.5.2 - Pipe Markers
label | Detail - Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings.
label | ○ Mark fire hydrant positions in accordance with SNZ PAS 4509
label | Acceptance / Conformance Criteria - AS Per Drawings.
label | Standard / Specification - PS 22.7.3 a
label | Verifying Document - Visual Inspection / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - Every Line
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.5.3 - Backfill Compaction Testing
label | Detail - GAP65/AP65 Backfill Compacted in 200mm Layers.
label | ○ NDM Testing to be completed on maximum 200mm lifts of backfill.
label | Acceptance / Conformance Criteria - GAP65/AP65 Backfill Compacted in 200mm layers.
label | ○ Testing to be completed on maximum 200mm lifts of backfill.
label | ○ 95% NDM on Shared and Carriageway.
label | OR
label | ○ 28% CIV
label | Standard / Specification - PS- 22.13.5, NDM Standerd 25832 NZS 4402 Test 4.1.3, IFC Drawing 0320-1
label | Verifying Document - Lab Report / Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - As per SW Specification. One test per 10m evenly spaced intervals.
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.6.1 - Pipe Inspection
label | Detail - Inspection of Drainage line
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - Internal
label | Verifying Document - Wastewater line record
label | Testing Quantity Required (based from schedule qtys) - Continious 1 per Line
label | Verification Activity: Activity - I
label | Formal inspection activity to be undertaken and recorded.
label | Verification Activity: By - SE
checkpoint | 4.7.1 - Pressure Acceptance Testing
label | Detail - Backfill/cover with embedment before testing
label | ○ End caps in place, provision for filling the pipeline and bleeding air.
label | Acceptance / Conformance Criteria - Wastewater Rising Main Pipelines – 800kPa
label | ○ Ensure the STP is not more than 25% above the rated pressure of any pipeline component.
label | Standard / Specification - PS 22.7.12(d), PS 22.7.13(b)
label | Verifying Document - Test Report, Pressure Log in.csv or .xlsx format
label | Testing Quantity Required (based from schedule qtys) - All Pipeline, All valves
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength min50kpa, ave>60kpa
label | Standard / Specification - Appendix V Table 21:11
label | Verifying Document - Shear vane or Scala test result
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 4.8.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 21.5
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8.3 - Undercut Backfill Compliance AP65
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Undercut
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.8.4 - Bedding Compaction Testing AP65
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12, PS- 21.6.11
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.8.5 - Survey
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm.
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SV
checkpoint | 4.8.6 - Sidefill Compaction Testing
label | Detail - From the bedding layer to the overlay layer of pipe.
label | Acceptance / Conformance Criteria - AP20/GAP20
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 85% MDD
label | OR
label | ○ GAP20-Clegg12% CIV
label | Standard / Specification - PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 4 Density test per layer at Quarter Points around the Structure.
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.8.7 - Backfill Compaction Testing
label | Detail - From Overlay layer to the subgrade layer
label | Acceptance / Conformance Criteria - AP65
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | ○ AP65-Clegg28%CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 4 Density test per layer at Quarter Points around the Structure.
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.8.8 - MH joints inspection
label | Detail - Inspection of joints
label | Acceptance / Conformance Criteria - Right joint type used, no visual leak or breakage
label | Standard / Specification - PS 22.7.10
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - HP
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8.9 - Inspection
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure.
label | Standard / Specification - PS- 21.6.11
label | Verifying Document - Manhole/Catchpit Record
label | Testing Quantity Required (based from schedule qtys) - 1 Checksheet per manhole/catchpit
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.8.10 - Plumb
label | Detail - The maximum permitted installed out of plumb is 25 mm of horizontal deviation in 1 m of vertical rise.
label | Acceptance / Conformance Criteria - The maximum permitted installed out of plumb is 25 mm of horizontal deviation in 1 m of vertical rise.
label | Standard / Specification - PS-22.7.10
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SV
checkpoint | 4.8.11 - Step Rungs
label | Detail - Step rungs evenly spaced at nominal 300mm vertical intervals
label | Acceptance / Conformance Criteria - Lowest rung more than 450mm above floor highest rung not more than 600mm below the top surface of MH cover
label | Standard / Specification - PS-22.7.11
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.8.12 - Manhole frame and covers
label | Detail - Make up the height between the manhole roof slab or precast lid and the finished surface level using concrete riser rings. Set the manhole frame and cover in concrete so it finishes flush with the finished ground or roadway level. Finish the concrete in a way that allows the final surface to be brought close to the cover frame.
label | Acceptance / Conformance Criteria - Make up the height between the manhole roof slab or precast lid and the finished surface level using concrete riser rings. Set the manhole frame and cover in concrete so it finishes flush with the finished ground or roadway level. Finish the concrete in a way that allows the final surface to be brought close to the cover frame.
label | Standard / Specification - PS-22.7.12
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | 4.8.13 - Manhole lateral connection
label | Detail - DN150 PVCu connection for future lateral.
label | ○ 800mm above manhole outlet invert
label | ○ DN150PVCu end cap
label | Acceptance / Conformance Criteria - DN150 PVCu connection for future lateral.
label | ○ 800mm above manhole outlet invert
label | ○ DN150PVCu end cap
label | Standard / Specification - IFC Drawing 0320-Rev 03
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Per connection
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Survey As-Builts
label | Detail - Quality Check on Nee pipeline and structure based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec as per drawings and capture any NCR or change to design.
label | Standard / Specification - Project Specifications
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-006-005 ITP Kerb & Channel | itp |  |  |  |  | DN1210-006-005 ITP Kerb & Channel Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONNEL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% Passing
label | 0.300mm ¦¦ 3-10% Passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - Project Specifications Appendix XVIII, Tauranga Council IDC - Table IT-4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION - KERB & CHANNEL PREPARATION
checkpoint | 4.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - NZTA B/06 8.2.2 - Table 3
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Compaction - Clegg
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - PS Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION - KERB & CHANNEL PREPARATION
checkpoint | 5.1.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications 21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications 21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.4 - Final Finish
label | Detail - Hand poured and formed concrete kerbs
label | Acceptance / Conformance Criteria - F3 Surface Finish / Slip form kerb and channel
label | Standard / Specification - Project Specifications 22.10.2
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – CONCRETE ISLAND
checkpoint | 6.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface 75mm from finish concrete level
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - NZTA B/06 8.2.2 - Table 3
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.2 - Compaction - Clegg
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - PS Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.1 - Concrete
label | Detail - 20 MPa coloured with 2.5% black oxide
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPa
label | Standard / Specification - 232735.02-WSP-DR-UDL-0405
label | Verifying Document - Concrete Delivery dockets and test reports
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.2 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m
label | Standard / Specification - PS 27.4.5
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.3 - Final Finish
label | Detail - Trowelled
label | Acceptance / Conformance Criteria - U3 Finish
label | Standard / Specification - 232735.02-WSP-DR-UDL-0405
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 7 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 7.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - As-Builts
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards. - any changes to be added to redpen markuProject Specifications
label | Standard / Specification - Project Specifications 16.7.6
label | Verifying Document - Redpen markuProject Specifications
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-006-006 ITP Vehicle Crossings | itp |  |  |  |  | DN1210-006-006 ITP Vehicle Crossings Rev 1
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONNEL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >80%
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Accelerated Weathering
label | Detail - NZTAT/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% Passing
label | 0.300mm ¦¦ 3-10% Passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 28-48%
label | 19.0 – 4.75 ¦¦ 14-34%
label | 9.5 – 2.36 ¦¦ 7-27%
label | 4.75 – 1.18 ¦¦ 6-22%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 5-19%
label | 0.6 – 0.15 ¦¦ 2-14%
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4..8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 40
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 30
label | Standard / Specification - PS 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - ≤ 5
label | Standard / Specification - Project Specifications 20.9, TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.1 - Reinforcing Mesh
label | Detail - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Acceptance / Conformance Criteria - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Material Data Sheet, Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.2 - Reinforcing Ties
label | Detail - R6 Ties (For commercial crossing only)
label | Acceptance / Conformance Criteria - R6 Ties at 600 centres with 60 mm (For commercial crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Material Data Sheet, Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.3 - Reinforcing Bars
label | Detail - 4-D12 Bars (For commerical crossing only)
label | Acceptance / Conformance Criteria - 4-D12 Bars with 50 mm Cover (For commerical crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Material Data Sheet, Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.4.1 - Concrete Mix Design
label | Detail - 20.0 MPA concrete. 4kg/m3 black oxide (2.5%)
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Material Data Sheet, Engineer's Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - CONSTRUCTION
checkpoint | 4.1.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU:
label | — > 60kPa
label | — CBR: >3
label | ○ Single Test Minimum SU:
label | — >50kPa
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 test per 100m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Cut Subgrade Testing - Granular Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Proof Roll Subgrade
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Across Finished Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Hold point
label | Detail - Subgrade signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Standard / Specification -
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 - CONSTRUCTION - RESIDENTIAL AND COMMERICAL VEHICLE CROSSINGS
checkpoint | 5.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - Height '+15mm/0mm
label | ○ Width –20 mm +100 mm
label | Standard / Specification - NZTA B/06 8.2.2 - Table 3
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.1.2 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.3 - Hold point
label | Detail - Basecourse signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Standard / Specification -
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.1 - Surveyor check
label | Detail - Equivalent to check the position of the formwork
label | Acceptance / Conformance Criteria - +\- 100mm of design
label | Standard / Specification - Project Specifications 27.4.5 (b)
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.2 - Surveyor check
label | Detail - Equivalent to check finished height of framework
label | Acceptance / Conformance Criteria - +\- 10mm of design
label | Standard / Specification - Project Specifications 27.4.5 (b)
label | Verifying Document - Surveyor Records
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.4.1 - Reinforcing Mesh Check
label | Detail - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Acceptance / Conformance Criteria - 661 Reinforcing mesh (Commerical Vehicle Crossing)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Delivery Dockets, Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.4.2 - Reinforcing Mesh
label | Detail - Ensure that overlap and cover above and beneath mesh
label | Acceptance / Conformance Criteria - Reinforcing mesh to be placed centrally in the concrete layer
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.5.1 - Reinforcing Ties
label | Detail - R6 Ties at 600 centres with 60 mm (For commercial crossing only)
label | Acceptance / Conformance Criteria - R6 Ties at 600 centres with 60 mm (For commercial crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Delivery Dockets, Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.5.2 - Reinforcing Bars
label | Detail - 4-D12 Bars with 50 mm Cover (For commerical crossing only)
label | Acceptance / Conformance Criteria - 4-D12 Bars with 50 mm Cover (For commerical crossing only)
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Delivery Dockets, Visual Inspection/Photos
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.6.1 - Concrete
label | Detail - 20.0 MPA concrete. 4kg/m3 black oxide (2.5%)
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Concrete Delivery Dockets, Test Results
label | Testing Quantity Required (based from schedule qtys) - Before Pour, During Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.6.2 - Concrete Layer Thickness
label | Detail - Concrete layer thickness to be 150 mm for Residential Vehicle Crossings
label | ○ Concrete layer thickness to be 200 mm for Commerical Vehicle Crossings
label | Acceptance / Conformance Criteria - Concrete layer thickness to be 150 mm for Residential Vehicle Crossings
label | ○ Concrete layer thickness to be 200 mm for Commerical Vehicle Crossings
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Pre-Pour CheckSheet
label | Testing Quantity Required (based from schedule qtys) - Before Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.6.3 - Final Finish
label | Detail - Rough broom finish
label | Acceptance / Conformance Criteria - U5
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Post-Pour CheckSheet
label | Testing Quantity Required (based from schedule qtys) - After Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.6.4 - Saw Cuts
label | Detail - Saw cut expansion joints at 4m centres maximum each way
label | Acceptance / Conformance Criteria - Saw cut expansion joints at 4m centres maximum each way
label | Standard / Specification - 232735.02-WSP-DR-RSA-0305
label | Verifying Document - Post-Pour CheckSheet
label | Testing Quantity Required (based from schedule qtys) - After Pour
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
section | SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.1 - As-Builts
label | Detail - Final inspection of all concrete work.
label | ○ Red Pen Mark up
label | Acceptance / Conformance Criteria - All works meet project specifications and standards. any changes to be noted on redpen markuProject Specifications
label | Standard / Specification - Project Specifications 16.7.6
label | Verifying Document - Red Pen Markup
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-011-004 ITP NAR Car Park Utilities | itp |  |  |  |  | DN1210-011-004 ITP NAR Car Park Utilities Rev 0
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINT - MATERIAL, PERSONNEL AND THIRD PARTY APPROVALS (P&G / ESTABLISHMENT)
checkpoint | 3.1.1 - Trench Profile
label | Detail - Tolerance of +/- 100 mm of the planned horizontal alignment and the maximum deviation shall be 1 in 20 in both the horizontal and vertical planes.
label | Acceptance / Conformance Criteria - Survey Set out
label | Standard / Specification - PS 25.13.2 a (1)
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | ○ Review existing service location drawing supplied by WSP.
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
checkpoint | 3.1.2 - Underground Services
label | Detail - Pothole all services within traffic management prior to commencement of trenching. Accurately record the location and reduced level of each service and forward Engineer.
label | Acceptance / Conformance Criteria - Surevy Data/Existing utilities Drawings
label | Standard / Specification - Appendix V
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction, Review existing service location drawing supplied by WSP.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.2.1 - Bedding and Overlay Material: Sand
label | Detail - Material grading:PSD
label | Acceptance / Conformance Criteria - Free of larger sharp particles conforming to GAP 7
label | Standard / Specification - PS 25.13.2 g) & h)
label | Verifying Document - Delivery Dockets/Material Certification
label | Testing Quantity Required (based from schedule qtys) - NA
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Material grading: Materials (GAP20/AP20)
label | Detail - Material grading:PSD
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 19.0mm ¦¦ 100% passing
label | 13.2mm ¦¦ 80-95% passing
label | 9.5mm ¦¦ 64-76% passing
label | 4.75mm ¦¦ 37-58% passing
label | 2.36mm ¦¦ 30-40% passing
label | 1.18mm ¦¦ 18-28% passing
label | 0.600mm ¦¦ 12-22% passing
label | 0.300mm ¦¦ 6-14% passing
label | 0.150mm ¦¦ 2-7% passing
label | 0.075mm ¦¦ 0-3% passing
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.2
label | Verifying Document - Lab Test Report NZS 4407.2015 Test3.8.1
label | Testing Quantity Required (based from schedule qtys) - 0-400m3 ¦¦ 2 Test
label | ○ 400-1500m3 ¦¦ 3 Test
label | ○ 1500-4000m3 ¦¦ 4 Test
label | ○ >4000 ¦¦ 1 Test Additional 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - Weathering index: Materials (AP20)
label | Detail - Weathering index:
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.3
label | Verifying Document - Lab Test Report NZS 4407.3.11
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Crushing Resistance: Materials (AP20)
label | Detail - Crushing Resistance
label | Acceptance / Conformance Criteria - >100kN
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.4
label | Verifying Document - Lab Test Report NZS 4407:1991 Test.3.10
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - Material grading: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - No Particles >200mm
label | ○ Maximum fines 10% passing 75micron sieve
label | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - Weathering index: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Crushing Resistance: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Materials Approvals
label | Detail - All works and materials are to comply with the National Code of Practice for Utilities Operators' Access to Transport Corridors, and Individual Utility Providers Requirements
label | Acceptance / Conformance Criteria - Prior to Commencement and throughout construction
label | Standard / Specification - Project Specifications
label | Verifying Document - Utilities Providers Approval/Material Certification /Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Pipe and fittings. Ducts
label | Detail - Duct Pipes shall be of the size, material and class nominated in Drawings.
label | ○ Ducts shall be high impact uPVC
label | ○ Duct colours shall be to local authorities requirements.
label | ○ Duct colours for the different Utility Structures must be in accordance with the guidelines.
label | Acceptance / Conformance Criteria - Duct Pipes shall be of the size, material and class nominated in Drawings.
label | ○ Ducts shall be high impact uPVC
label | ○ Duct colours shall be to local authorities requirements.
label | ○ Duct colours for the different Utility Structures must be in accordance with the guidelines.
label | Standard / Specification - PS 25.13.6 b)
label | Verifying Document - Delivery Dockets/Material Certification
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.2 - Bedding material
label | Detail - Free of larger sharp particles conforming sand
label | Acceptance / Conformance Criteria - Free of larger sharp particles conforming to sand
label | Standard / Specification - PS 25.13.2 g) & h)
label | Verifying Document - Delivery Dockets/Material Certification
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.3 - Backfill Material
label | Detail - Under roads, driveways and footpath - refer to pavement section for appropriate materials and layer thickness.
label | ○ Under berm or grass areas - site Won materials to be approved by Engineer or GAP65 to be used if site material does not meet Specs
label | Acceptance / Conformance Criteria - Comply with Project Specifications
label | Standard / Specification - PS 25.13.4 a)
label | Verifying Document - Delivery Dockets/Lab Test reports
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.4 - Pits Covers
label | Detail - Jointing and pulling pits shall have slip resistant surfaces complying with AS/NSZ 3661-1-1993. the cover set load rating shall be in compliance with AS3996.
label | Acceptance / Conformance Criteria - Class A-10kN loading - footways and areas only accessible to pedestrian and cyslists.
label | ○ Class B - 80kN loading - footways that may be mounted by vehicle or livestock and light tractor paths. (Light duty)
label | ○ Class C - 150kN loading - grass verges or other areas open to slow moving commercial vehicles such as tractor mowers etc (medium duty)
label | ○ Class D - 120kN loading - Carriageway of roads and areas open to commercial vehicles (heavy duty)
label | Standard / Specification - PS 25.13.6 c) AS/NZS 3661-1-1993.
label | Verifying Document - Material Certifications.Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 4 – CONSTRUCTION ACTIVITY
checkpoint | 4.1.1 - Trench Excavation
label | Detail - To be excavated to within a tolerance.
label | ○ Not more than 100 metres of trench associated with each site shall remain open at one time.
label | Acceptance / Conformance Criteria - +/- 100 mm of the planned horizontal.
label | ○ The maximum deviation shall be 1 in 20 in both the horizontal and vertical planes.
label | ○ Less than 100m
label | Standard / Specification - PS 25.13.2 a) i
label | Verifying Document - Survey
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Unsuitable Materials
label | Detail - All confirmed unsuitable material shall be excavated down to suitable materials.
label | Acceptance / Conformance Criteria - Dig Down to Get Suitable Materials or get Engineers Approval.
label | Standard / Specification - PS 25.13.2 b) ii
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Foundation Compliance
label | Detail - It shall be de-watered prior to installation of bedding material.
label | ○ If the bottom of the trench is naturally occurring rock, or has stones, gravel or other sharp material in occurrence
label | Acceptance / Conformance Criteria - 50mm granular layer shall be laid and compacted before the bedding layer is laid.
label | Standard / Specification - PS 25.13.2 c) and g)
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Bedding
label | Detail - The floor of the trench shall be clear of any obstacles and shall be as flat as possible.
label | Acceptance / Conformance Criteria - Clean Imported Sand or SAP 7 to be placed 50mm minimum thickness (compacted) over the bottom of the trench.
label | Standard / Specification - PS 25.13.2 g)
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.5 - Installation of Ducts
label | Detail - If more than 2 ducts are being placed.
label | Acceptance / Conformance Criteria - Must have 50 mm bedding material between the two ducts.
label | Standard / Specification - PS 25.13.7 b) iii
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.6 - Draw Wires
label | Detail - A draw wire shall be intalled in all ducts and within all sub-ducts to facilitate the hauling-in of cable after the completion of the ducting.
label | Acceptance / Conformance Criteria - Pigmented, stranded polypropylene or equivalent rot-proof material draw wire of 5kN breaking load.
label | ○ ≥20 years design life.
label | ○ The ends of draw wires shall be made fast within the pits and be secured to the duct plugs.
label | ○ Blue colour wire
label | Standard / Specification - PS 25.13.7 e) ii to iv
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.7 - Caps
label | Detail - All duct ends shall be capped
label | Acceptance / Conformance Criteria - Capped ducts
label | Standard / Specification - PS 25.13.7 e) v
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.8 - Warning Tape
label | Detail - Warning tape to be placed above services.
label | Acceptance / Conformance Criteria - Warning Tape to be placed no more than 300mm above the topmost duct
label | Standard / Specification - PS 25.13.7 b) iii & f)
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.9 - Overlay
label | Detail - 99 mm minimum sand placed on top of duct.
label | ○ No mechanical compaction will caarry out till 300mm drom top of duct.
label | Acceptance / Conformance Criteria - 100 mm minimum sand placed on top of duct.
label | Standard / Specification - PS 25.13.7 b) ii
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Cable
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.10 - Backfill
label | Detail - GAP65 to be used if site material is not approved.
label | Acceptance / Conformance Criteria - Clegg Test every 200mm compacted layer of GAP65
label | ○ clegg >28CIV
label | Standard / Specification - PS 25.13.10 a) modified
label | Verifying Document - Lab report
label | Testing Quantity Required (based from schedule qtys) - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.11 - Pit Installation Location
label | Detail - Locations shall be avoided where running water can flow over the lid or where mud and debris can fall or be washed onto the lid .
label | Acceptance / Conformance Criteria - Pit lid and concrete apron shall be flush with ground level in grass, concrete or asphalt areas.
label | ○ When pit is located on a slope of 10 to 30 degrees, the lid shall be flush with ground on the upper side.
label | ○ When slope is greater than 30 degrees, the lid shall be up to 100mm above the ground level on the upper side.
label | Standard / Specification - PS 25.13.8 a) i and ii
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pit Location
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.12 - Pit Installation Bedding
label | Detail - Bedding with 150mm compacted GAP20 hard-fill coverd with 20mm compacted sand. Pits shall be carefully lifted into place and lined up with the ducts to penetrate the chamber.
label | Acceptance / Conformance Criteria - 150mm compacted GAP20 hard-fill covered with 20mm of compacted sand
label | Standard / Specification - PS 25.13.8 d)
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pit Location
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.13 - Pit Installation Sidefill concrete
label | Detail - Plactic pits shall be cast into the ground with 150mm concrete surround
label | Acceptance / Conformance Criteria - Plactic pits shall be cast into the ground with 150mm concrete surround
label | Standard / Specification - PS 25.13.8 d)
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pit Location
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.14 - Pit Installation Backfilling
label | Detail - Backfill and compact the ground around concrete pits. Extra care to be taken to avoid damaging the ducts in 200mm layers of GAP 65.
label | Acceptance / Conformance Criteria - Min 92% compaction rate and Average of 95%.
label | Standard / Specification - PS 25.13.10 a) modified
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pit Location
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.15 - Pit Installation Concrete
label | Detail - Top 300mm of pit shall be concreted around with a with of 150mm with a 20MpA concrete.
label | Acceptance / Conformance Criteria - 20 mPa
label | Standard / Specification - PS 25.13.8 d) iv.
label | Verifying Document - Concrete Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Pit Location
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.16 - Pit Installation Clean up
label | Detail - Clean out all pit after completion of the work
label | Acceptance / Conformance Criteria - Pit are free of dirty, mud,water and foreign materials
label | Standard / Specification - PS 25.13.8 e)
label | Verifying Document - Checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pit Location
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.1.17 - Survey As Built
label | Detail - As Built every ducts joint before backfill
label | Acceptance / Conformance Criteria - Completed as per drawings
label | Standard / Specification - Standard Practise
label | Verifying Document - Survey
label | Testing Quantity Required (based from schedule qtys) - On going
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1.1 - Survey As-Builts
label | Detail - Quality Check on New Works based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - PS-21.7.7
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature