## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP016 - Asphalt Production (Airport Mix) | itp |  |  |  |  | FH-ZU2-QU-ITP016 - Asphalt Production (Airport Mix) - Rev 0
section | 1.0 - General
checkpoint | 1.1 - Submission of ITP
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All relevant ITPs to be submitted to the Principal’s Representative.
label | Reference Documents - AfPA Sec 4.3 Cl 14-18
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Change in Mix Design
label | Frequency - During the works
label | Acceptance Criteria - Any change in the constituent materials or mixture design must be immediately reported to the Principal’s Representative. The Contractor must detail the proposed mixture design verification testing to ensure that the performance of the asphalt has not been adversely impacted by the change.
label | Reference Documents - AfPA Sec 6.2 Cl 75-77
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - Hold Point Release Form
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Manufacture of Asphalt
checkpoint | 2.1 - Monitor and Control Asphalt Manufacture
label | Frequency - During the works
label | Acceptance Criteria - The Contractor must produce asphalt to be consistent and uniform in temperature, and composition, consistent with the approved Construction Procedure.
label | Reference Documents - AfPA Sec 9.1 Cl 138 - 142
label | Inspection/Test Method - Plant Process Controls
label | Record of conformity - Process Control Records
label | TP
label | Responsibility - Laboratory manager
date | Date Completed:
checkpoint | 2.2 - Conformance of manufactured asphalt
label | Frequency - For each truck load of Asphalt
label | Acceptance Criteria - Segregated or not fully coated asphalt must not be used in the works. If required, the Principal’s Representative is to be advised of steps to be taken to remedy the non- conformance.
label | Reference Documents - AfPA Sec 9.1 Cl 142
label | Inspection/Test Method - Visual
label | Record of conformity - Delivery Docket
label | HP
label | Responsibility - Quality manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Sampling and Testing during Asphalt Production
checkpoint | 3.1 - Coarse Aggregate Testing
label | Frequency - During the works at prescribed frequency
label | Acceptance Criteria -
label | – – – – – – – – –
label | Test property ¦¦ Test method ¦¦ Test frequency
label | – – – – – – – – –
label | Particle size distribution (grading) ¦¦ AS 1141.11.1 ¦¦ 1 test per 500 tonnes aggregate
label | Material Finer than 0.075 mm in Aggregates (by washing) ¦¦ AS 1141.11.1 ¦¦ 1 test per 500 tonnes aggregate
label | Flakiness Index ¦¦ AS 1141.15 ¦¦ 1 test per 1000 tonnes aggregate
label | Weak particles (including clay lumps, soft and friable particles) in coarse aggregate ¦¦ AS 1141.32 ¦¦ 1 test per 1000 tonnes aggregate
label | Particle density ¦¦ AS 1141.6.1 or AS 1141.6.2 ¦¦ 1 test per 2000 tonnes aggregate
label | Water absorption ¦¦ AS 1141.6.1 or AS 1141.6.2 ¦¦ 1 test per 2000 tonnes aggregate
label | – – – – – – – – –
label | Reference Documents - AfPA Sec 11.2.1 Cl 187 - 190
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.2 - Fine Aggregate Testing
label | Frequency - During the works at prescribed frequency
label | Acceptance Criteria -
label | – – – – – – – – –
label | Test property ¦¦ Test method ¦¦ Test frequency
label | – – – – – – – – –
label | Particle size distribution (grading) ¦¦ AS 1141.11.1 ¦¦ 1 test per 500 tonnes aggregate
label | Particle density ¦¦ AS 1141.5 ¦¦ 1 test per 2000 tonnes aggregate
label | Water absorption ¦¦ AS 1141.5 ¦¦ 1 test per 2000 tonnes aggregate
label | – – – – – – – – –
label | Reference Documents - AfPA Sec 11.2.2 Cl 192 - 195
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.2 - Fine Aggregate Testing
label | Frequency - During the works at prescribed frequency
label | Acceptance Criteria -
label | – – – – – – – – –
label | Test property ¦¦ Test method ¦¦ Test frequency
label | – – – – – – – – –
label | Plasticity index ¦¦ AS 1289.3.3.1 ¦¦ 1 test per 2000 tonnes aggregate
label | – – – – – – – – –
label | Reference Documents - AfPA Sec 11.2.2 Cl 196
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.3 - Binder Compliance Certificate
label | Frequency - Every Delivery to Production Plant
label | Acceptance Criteria - A test certificate to be supplied for every delivery to the asphalt mixing plant.
label | Reference Documents - AfPA Sec 11.2.4.1 Cl 200 - 201
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.4 - Binder – Binder Consistency Testing or Confirmation
label | Frequency - Every Delivery to Production Plant
label | Acceptance Criteria - For every batch of polymer modified binder production either:
label | a. Provide written confirmation that the raw ingredients are consistent with the modified binder used to produce the asphalt mixture.
label | b. Sample and test the binder according to Clause Cl 204.
label | Reference Documents - AfPA Sec 11.2.4.1 Cl 202 - 206
label | Inspection/Test Method - Written Confirmation/ Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.5 - Binder – Point of Production Testing
label | Frequency - Every Production Batch
label | Acceptance Criteria - Every production batch of binder must be sampled at the point of production and tested by the Contractor, for:
label | a. Viscosity at 165°C according to ATM-111.
label | b. Torsional recovery at 25°C, 30 s according to ATM-122.
label | c. Softening point according to AG: PT/T131.
label | Reference Documents - AfPA sec 11.2.4.1 Cl 207 - 208
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.6 - Binder – Addition Production Testing
label | Frequency - Every Ten modified production batches
label | Acceptance Criteria - Additional production testing must be performed at least once every ten modified binder production batches, or once every 250 tonnes of modified binder production, whichever is more often.
label | Reference Documents - AfPA sec 11.2.4.1 Cl 209 - 212
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.7 - Binder – Point of Delivery Sampling
label | Frequency - Prior to the commencement of asphalt production
label | Acceptance Criteria - Binder must be sampled for each delivery vessel/tank, not more than four hours prior to the commencement of asphalt production or transfer of binder to the asphalt product plant binder storage tank.
label | ○ A minimum of two samples, each not less than 0.5 L in volume, must be obtained in accordance with ATM-101.
label | Reference Documents - AfPA Sec 11.2.4.5 Cl. 213 - 219
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - Sampling Process Control Charts
label | WP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.8 - Point of Delivery Binder Testing
label | Frequency - Before each production shift
label | Acceptance Criteria - The point of delivery sample, to be retained for point of delivery testing, must be tested by the Contractor, prior to the commencement of asphalt production for the work period, for:
label | a. Viscosity at 165°C according to ATM-111.
label | b. Torsional recovery at 25°C, 30 s according to ATM-122.
label | c. Softening point according to AG:PT/T131.
label | Reference Documents - AfPA Sec 11.2.4.6 Cl 220 - 221, Sec 12.2.4. Cl 275
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | HP
label | Responsibility - Laboratory Manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Point of Delivery Binder Testing
label | Frequency - If binder test results nonconforming
label | Acceptance Criteria - If required, the Contractor must prepare and submit a disposition regarding the binder point of delivery test result for approval by the Principal’s Representative.
label | Reference Documents - AfPA Sec 12.2.4.6 Cl 220
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | HP
label | Responsibility - Laboratory Manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Tack Coat Testing
label | Frequency - Every Delivery to Site
label | Acceptance Criteria - A test certificate which demonstrates that the tack coat complies with AS 1160 or approved modified tack coat production properties, must be supplied for every delivery to site
label | Reference Documents - AfPA Sec 11.2.5 Cl 222
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.11 - Asphalt Production Testing
label | Frequency - During each production shift as prescribed by Table 16
label | Acceptance Criteria -
label | – – – – – – – – –
label | Tonnes of Asphalt in the Lot ¦¦ Number of test sets
label | – – – – – – – – –
label | Not greater than 300 tonnes ¦¦ 2
label | 300 to 600 tonnes ¦¦ 3
label | 600 to 1,000 tonnes ¦¦ 4
label | Greater than 1,000 tonnes ¦¦ 5
label | – – – – – – – – –
label | Reference Documents - AfPA Sec 11.3 Cl. 222 - 223
label | Inspection/Test Method - Test Method and Results
label | Record of conformity - NATA Test Report
label | TP
label | Responsibility - Laboratory Manager
date | Date Completed:
checkpoint | 3.12 - Shift Usage Calculations
label | Frequency - For each Production Shift
label | Acceptance Criteria - For each production Lot calculate; bitumen usage, mass of asphalt produced & average bitumen content
label | Reference Documents - AfPA Sec 11.3 Cl. 231
label | Inspection/Test Method - Test Method and Results
label | Record of conformity -
label | TP
label | Responsibility - Quality Manager
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality/System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: