## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Preparation
checkpoint | Check Area clear of all other trades and their materials
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Grind Floor
button | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply feather coat
holdpoint | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving location/type - 150mm to all walls and units as required
checkpoint | Confirm aluminium cove capping as required
checkpoint | Glue out floors
checkpoint | Copper tape for anti-static vinyl
checkpoint | Install vinyl or anti-static vinyl as required
checkpoint | Install coving & capping/sealant as applicable
checkpoint | Install sheet vinyl to stair treads as required with AA125 nosings
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
holdpoint | SEND TO CLIENT FOR QUALITY APPROVAL