## Sheet1
Type | Name | Values | Prompting Name
checklist | QA - Alpha |  | QA - Alpha
section | Details
checkpoint | Plasterboard installed
checkpoint | Stopping complete
checkpoint | Aconex field issues (defects) closed
signoff | Send to Leighs once completed
checklist | QA - Contract Coatings |  | QA - Contract Coatings
section | Details
checkpoint | Sealer Coat
checkpoint | First Coat
checkpoint | Aconex field issues (defects) closed
signoff | Send to Leighs once completed
checklist | QA - Data Talk |  | QA - Data Talk
section | Details
checkpoint | Installation completed
checkpoint | Junction box installed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed
signoff | Send to Leighs once completed
checklist | QA - Gilcom |  | QA - Gilcom
section | Details
checkpoint | Installation completed
checkpoint | Testing completed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed
checklist | QA - Hanlon Plumbing |  | QA - Hanlon Plumbing
section | Details
checkpoint | Installation completed
checkpoint | Testing completed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed
checklist | QA - HelRimu |  | QA - HelRimu
section | Details
checkpoint | Installation completed
checkpoint | Testing completed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed
checklist | QA - LCL |  | QA - LCL
section | Details
checkpoint | Framing completed
tickbox | Insulation
tickbox | Blocking
checkpoint | Framing straight and flush
checkpoint | Fixings complete
checkpoint | Moisture content <20%
checkpoint | Aconex field issues (defects) closed
checkpoint | Room data sheet check completed
checkpoint | Check for grab rail nogs (A07 drawings)
checkpoint | Services complete and no outstanding work or changes
checklist | QA - Premier Fire |  | QA - Premier Fire
section | Details
checkpoint | Installation completed
checkpoint | Testing completed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed
checklist | QA - Rauland |  | QA - Rauland
section | Details
checkpoint | Installation completed
checkpoint | Testing completed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed
checklist | QA - VAE |  | QA - VAE
section | Details
checkpoint | Installation completed
checkpoint | Testing completed
checkpoint | Acoustic treatment completed
checkpoint | Aconex field issues (defects) closed