## Sheet1
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JSEA to the Engineer before works | Downer | Construction Pack | Submit 5 days prior to commencement of works | H | PE | 0 |  | R | 3.01.01 - Construction Pack | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works | Standard / Specification - Downer | Verifying Document - Construction Pack | Frequency - Submit 5 days prior to commencement of works | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - 0 | MSQA signature - | Engineer Rep Signature - R | 3.01.01 - Construction Pack
3.02.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre- construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV | H |  |  | 3.02.02 - Survey Setout | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre- construction levels where needed. | Standard / Specification - Downer | Verifying Document - Survey Records | Frequency - Prior to Works | Verification Activity: Activity - H | Verification Activity: By - SV | Downer Signature - H | MSQA signature - | Engineer Rep Signature - | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
3.01.02 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE | H |  |  | 3.01.02 - Service Location | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services. | Standard / Specification - Downer | Verifying Document - Excavation Permit | Frequency - Prior to Excavation | Verification Activity: Activity - H | Verification Activity: By - SE | Downer Signature - H | MSQA signature - | Engineer Rep Signature - | Standard / Specification - Downer
3.02.03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE | H |  |  | 3.02.03 - Internal Permits | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Standard / Specification - Downer | Verifying Document - Internal Permits | Frequency - Prior to Excavation | Verification Activity: Activity - H | Verification Activity: By - SE | Downer Signature - H | MSQA signature - | Engineer Rep Signature - | Verifying Document - Construction Pack
3.01.03 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE | H |  | R | 3.01.03 - External Permits | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Standard / Specification - Downer | Verifying Document - External Permits | Frequency - Prior to Excavation | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - | Engineer Rep Signature - R | Frequency - Submit 5 days prior to commencement of works
3.02.04 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE | H |  |  | 3.02.04 - Approved Construction Drawings | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Standard / Specification - Downer | Verifying Document - IFC Drawings | Frequency - Prior to works start | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - | Engineer Rep Signature - | Verification Activity: Activity - H
4.01.01 | Material Properties | Filter Aggregate, pipes and filter fabric shall comply with TNZ F/2 for non‐wrapped drains and TNZ F/6 for fabric wrapped drains. Filter aggregates specified in TNZ F/5 shall not be used. Pipes supplied and installed as specified in drawings | Aurecon Civil Spec Section 16.5 TNZ F/2, F/6 ATCoP | Supplier Records | Prior to use Checked on Delivery | H | PE | H | R | R | 4.01.01 - Material Properties | Acceptance / Conformance Criteria - Filter Aggregate, pipes and filter fabric shall comply with TNZ F/2 for non‐wrapped drains and TNZ F/6 for fabric wrapped drains. Filter aggregates specified in TNZ F/5 shall not be used. Pipes supplied and installed as specified in drawings | Standard / Specification - Aurecon Civil Spec Section 16.5 TNZ F/2, F/6 ATCoP | Verifying Document - Supplier Records | Frequency - Prior to use Checked on Delivery | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - R | Verification Activity: By - PE
4.01.02 | Drainage Aggregate | Shall be NZTA F/2 or F/6 Drainage Aggregate chip (20/7mm) DN1211-DOW-RFI - 0048 | Aurecon Civil Spec Section 16.6.3 RFI-0048 | MAR record | Pior to Use Delivery Dockets | H | PE | H | R |  | 4.01.02 - Drainage Aggregate | Acceptance / Conformance Criteria - Shall be NZTA F/2 or F/6 Drainage Aggregate chip (20/7mm) DN1211-DOW-RFI - 0048 | Standard / Specification - Aurecon Civil Spec Section 16.6.3 RFI-0048 | Verifying Document - MAR record | Frequency - Pior to Use Delivery Dockets | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - | Downer Signature - 0
4.01.03 | No-Fines Concrete | As per TfNSW 3222, for aggregate size distribution to be 26.5 mm @ 100 % 19 mm @ 95 - 100% 9.5 mm @ 0 - 5% | Aurecon Civil Spec Section 14,17.11.7 | Supplier Records Concrete Dockets | As required | H | PE | H | R |  | 4.01.03 - No-Fines Concrete | Acceptance / Conformance Criteria - As per TfNSW 3222, for aggregate size distribution to be 26.5 mm @ 100 % 19 mm @ 95 - 100% 9.5 mm @ 0 - 5% | Standard / Specification - Aurecon Civil Spec Section 14,17.11.7 | Verifying Document - Supplier Records Concrete Dockets | Frequency - As required | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - | MSQA signature -
5.01.01 | Subsoil trenching | Construct subsoil trenches as per TNZ F/2 or Approved 20/7 drainage chip, falling towards drainage outlet. Install Geotextile filter fabric at base of trench where specified. Drainage aggregate bedding installed at trench base; 75mm thick for Ø=75mm pipe and 100mm thick for Ø=100mm pipe. Suvey Set-out position as per deign unless design clash changes required | Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP | QA Checksheet | Inspect on regular intervals | I | SE | I |  |  | 5.01.01 - Subsoil trenching | Acceptance / Conformance Criteria - Construct subsoil trenches as per TNZ F/2 or Approved 20/7 drainage chip, falling towards drainage outlet. Install Geotextile filter fabric at base of trench where specified. Drainage aggregate bedding installed at trench base; 75mm thick for Ø=75mm pipe and 100mm thick for Ø=100mm pipe. Suvey Set-out position as per deign unless design clash changes required | Standard / Specification - Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP | Verifying Document - QA Checksheet | Frequency - Inspect on regular intervals | Verification Activity: Activity - I | Verification Activity: By - SE | Downer Signature - I | MSQA signature - | Engineer Rep Signature - | Engineer Rep Signature - R
5.01.02 | Subsoil installation | In absence of subsoil depths in drawings: Install subsoils at 600mm below FL forsealed roads and traffickable areas, and at 450mm for non‐trafficked areas. Subsoils laid straight, falling towards drainage outlet as per TNZ F/2 and drawing | Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP | QA Checksheet | Inspect on regular intervals | W | SE | W | R | I | 5.01.02 - Subsoil installation | Acceptance / Conformance Criteria - In absence of subsoil depths in drawings: Install subsoils at 600mm below FL forsealed roads and traffickable areas, and at 450mm for non‐trafficked areas. Subsoils laid straight, falling towards drainage outlet as per TNZ F/2 and drawing | Standard / Specification - Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP | Verifying Document - QA Checksheet | Frequency - Inspect on regular intervals | Verification Activity: Activity - W | Verification Activity: By - SE | Downer Signature - W | MSQA signature - R | Engineer Rep Signature - I | 3.02.02 - Survey Setout
5.01.03 | Trench Dimensions | Excavate trench to lines, levels, width and gradients shown on drawings. Trench of sufficient width to permit installation of all materials and fittings. Pipes minimum 100mm from trench wall. | Aurecon Civil Spec Section 16.6.2 | QA Checksheet | Inspect on regular intervals | W | SE | W |  |  | 5.01.03 - Trench Dimensions | Acceptance / Conformance Criteria - Excavate trench to lines, levels, width and gradients shown on drawings. Trench of sufficient width to permit installation of all materials and fittings. Pipes minimum 100mm from trench wall. | Standard / Specification - Aurecon Civil Spec Section 16.6.2 | Verifying Document - QA Checksheet | Frequency - Inspect on regular intervals | Verification Activity: Activity - W | Verification Activity: By - SE | Downer Signature - W | MSQA signature - | Engineer Rep Signature - | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre- construction levels where needed.
5.01.04 | Backfill Placement | Backfill with 150mm + 150mm depth of drainage filter material above pipe, hand tamped Backfill and plate compact remainder to FL as specified in drawing | Aurecon Civil Spec 18.6.3 TNZ F/2 ATCoP | QA Checksheet | Inspect on regular intervals | I | SE | I |  |  | 5.01.04 - Backfill Placement | Acceptance / Conformance Criteria - Backfill with 150mm + 150mm depth of drainage filter material above pipe, hand tamped Backfill and plate compact remainder to FL as specified in drawing | Standard / Specification - Aurecon Civil Spec 18.6.3 TNZ F/2 ATCoP | Verifying Document - QA Checksheet | Frequency - Inspect on regular intervals | Verification Activity: Activity - I | Verification Activity: By - SE | Downer Signature - I | MSQA signature - | Engineer Rep Signature - | Standard / Specification - Downer
5.01.05 | Flow Test | Visual inspection of water flow. | Visual Inspection | ITP Sign off | Once per Zone | H | SE | H | R | R | 5.01.05 - Flow Test | Acceptance / Conformance Criteria - Visual inspection of water flow. | Standard / Specification - Visual Inspection | Verifying Document - ITP Sign off | Frequency - Once per Zone | Verification Activity: Activity - H | Verification Activity: By - SE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - R | Verifying Document - Survey Records
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE | H | R | H | 6.01.01 - Construction Record Compilation | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Standard / Specification - Downer | Verifying Document - Records | Frequency - Post construction | Verification Activity: Activity - H | Verification Activity: By - SE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - H | Frequency - Prior to Works
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting. Asbuilts to include type, size, quantity, location and level of subsoil laid. | Downer | Records | Post construction | H | SV | H | R | H | 6.01.02 - Survey Records | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting. Asbuilts to include type, size, quantity, location and level of subsoil laid. | Standard / Specification - Downer | Verifying Document - Records | Frequency - Post construction | Verification Activity: Activity - H | Verification Activity: By - SV | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - H | Verification Activity: Activity - H
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Relevant change correspondence to be included. | Downer | Redlines | Post construction | H | PE | H | R | H | 6.01.03 - Redline Drawings | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Relevant change correspondence to be included. | Standard / Specification - Downer | Verifying Document - Redlines | Frequency - Post construction | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - H | Verification Activity: By - SV
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE | H | R | H | 6.01.04 - Defect, Snag and Punch List | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register | Standard / Specification - Downer | Verifying Document - Register | Frequency - Post construction | Verification Activity: Activity - H | Verification Activity: By - PE | Downer Signature - H | MSQA signature - R | Engineer Rep Signature - H | Downer Signature - H
MSQA signature -
Engineer Rep Signature -
3.01.02 - Service Location
Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
Standard / Specification - Downer
Verifying Document - Excavation Permit
Frequency - Prior to Excavation
Verification Activity: Activity - H
Verification Activity: By - SE
Downer Signature - H
MSQA signature -
Engineer Rep Signature -
3.02.03 - Internal Permits
Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
Standard / Specification - Downer
Verifying Document - Internal Permits
Frequency - Prior to Excavation
Verification Activity: Activity - H
Verification Activity: By - SE
Downer Signature - H
MSQA signature -
Engineer Rep Signature -
3.01.03 - External Permits
Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
Standard / Specification - Downer
Verifying Document - External Permits
Frequency - Prior to Excavation
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature -
Engineer Rep Signature - R
3.02.04 - Approved Construction Drawings
Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
Standard / Specification - Downer
Verifying Document - IFC Drawings
Frequency - Prior to works start
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature -
Engineer Rep Signature -
4.01.01 - Material Properties
Acceptance / Conformance Criteria - Filter Aggregate, pipes and filter fabric shall comply with TNZ F/2 for non‐wrapped drains and TNZ F/6 for fabric wrapped drains. Filter aggregates specified in TNZ F/5 shall not be used. Pipes supplied and installed as specified in drawings
Standard / Specification - Aurecon Civil Spec Section 16.5 TNZ F/2, F/6 ATCoP
Verifying Document - Supplier Records
Frequency - Prior to use Checked on Delivery
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature - R
4.01.02 - Drainage Aggregate
Acceptance / Conformance Criteria - Shall be NZTA F/2 or F/6 Drainage Aggregate chip (20/7mm) DN1211-DOW-RFI - 0048
Standard / Specification - Aurecon Civil Spec Section 16.6.3 RFI-0048
Verifying Document - MAR record
Frequency - Pior to Use Delivery Dockets
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature -
4.01.03 - No-Fines Concrete
Acceptance / Conformance Criteria - As per TfNSW 3222, for aggregate size distribution to be 26.5 mm @ 100 % 19 mm @ 95 - 100% 9.5 mm @ 0 - 5%
Standard / Specification - Aurecon Civil Spec Section 14,17.11.7
Verifying Document - Supplier Records Concrete Dockets
Frequency - As required
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature -
5.01.01 - Subsoil trenching
Acceptance / Conformance Criteria - Construct subsoil trenches as per TNZ F/2 or Approved 20/7 drainage chip, falling towards drainage outlet. Install Geotextile filter fabric at base of trench where specified. Drainage aggregate bedding installed at trench base; 75mm thick for Ø=75mm pipe and 100mm thick for Ø=100mm pipe. Suvey Set-out position as per deign unless design clash changes required
Standard / Specification - Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP
Verifying Document - QA Checksheet
Frequency - Inspect on regular intervals
Verification Activity: Activity - I
Verification Activity: By - SE
Downer Signature - I
MSQA signature -
Engineer Rep Signature -
5.01.02 - Subsoil installation
Acceptance / Conformance Criteria - In absence of subsoil depths in drawings: Install subsoils at 600mm below FL forsealed roads and traffickable areas, and at 450mm for non‐trafficked areas. Subsoils laid straight, falling towards drainage outlet as per TNZ F/2 and drawing
Standard / Specification - Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP
Verifying Document - QA Checksheet
Frequency - Inspect on regular intervals
Verification Activity: Activity - W
Verification Activity: By - SE
Downer Signature - W
MSQA signature - R
Engineer Rep Signature - I
5.01.03 - Trench Dimensions
Acceptance / Conformance Criteria - Excavate trench to lines, levels, width and gradients shown on drawings. Trench of sufficient width to permit installation of all materials and fittings. Pipes minimum 100mm from trench wall.
Standard / Specification - Aurecon Civil Spec Section 16.6.2
Verifying Document - QA Checksheet
Frequency - Inspect on regular intervals
Verification Activity: Activity - W
Verification Activity: By - SE
Downer Signature - W
MSQA signature -
Engineer Rep Signature -
5.01.04 - Backfill Placement
Acceptance / Conformance Criteria - Backfill with 150mm + 150mm depth of drainage filter material above pipe, hand tamped Backfill and plate compact remainder to FL as specified in drawing
Standard / Specification - Aurecon Civil Spec 18.6.3 TNZ F/2 ATCoP
Verifying Document - QA Checksheet
Frequency - Inspect on regular intervals
Verification Activity: Activity - I
Verification Activity: By - SE
Downer Signature - I
MSQA signature -
Engineer Rep Signature -
5.01.05 - Flow Test
Acceptance / Conformance Criteria - Visual inspection of water flow.
Standard / Specification - Visual Inspection
Verifying Document - ITP Sign off
Frequency - Once per Zone
Verification Activity: Activity - H
Verification Activity: By - SE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature - R
6.01.01 - Construction Record Compilation
Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
Standard / Specification - Downer
Verifying Document - Records
Frequency - Post construction
Verification Activity: Activity - H
Verification Activity: By - SE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature - H
6.01.02 - Survey Records
Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting. Asbuilts to include type, size, quantity, location and level of subsoil laid.
Standard / Specification - Downer
Verifying Document - Records
Frequency - Post construction
Verification Activity: Activity - H
Verification Activity: By - SV
Downer Signature - H
MSQA signature - R
Engineer Rep Signature - H
6.01.03 - Redline Drawings
Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Relevant change correspondence to be included.
Standard / Specification - Downer
Verifying Document - Redlines
Frequency - Post construction
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature - H
6.01.04 - Defect, Snag and Punch List
Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
Standard / Specification - Downer
Verifying Document - Register
Frequency - Post construction
Verification Activity: Activity - H
Verification Activity: By - PE
Downer Signature - H
MSQA signature - R
Engineer Rep Signature - H