## 2100 Culvert
INSPECTION & TEST PLAN
Contract No 7/21/186 |  | Contract Name: |  |  |  |  | Rev: | Originator | Date | Approved | Date
|  | Ruapekapeka Road Seal Extension |  |  | 2100dia Culvert |  | 0 | Cam Wood | 2021-02-24
ITP No: | [6 empty] | 1
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | HOLD POINT (H) OR WITNESS POINT (W) | SIGNATURE | DATE | COMMENTS
2100 Culvert Pipe Installation
Pre Construction
Review Drawings | IFC Drawings | Review |  | Before Starting Onsite | For Construction | W
Supply of Materials
Supply Bedding/Backfill Material | IFC Drawing DE9 |  |  | For Culvert | Within grading parameters: | W
2100 Culvert Pipes | IFC Drawing DE9 | Visual | UCC Rep | Each Pipe | To be In-Wall-Jointed 2100dia Internal Diameter Class 4: photos/visual inspection | W
Construction
Setout | IFC Drawing DE9 | Visual | UCC Rep | Before construction | To be agreed with Engineer if different to Drawings | W
Installation of Pipes | IFC Drawing DE9 | Visual | UCC Rep | On Completion | To Match the design drawings and Hynds installation Technical Specification | W
RenoMatress | IFC Drawing DE9 | Visual | PM/PE/Supervisor | At Completion | To match Drawings & design: | W
Asbuilt | Specification |  |  | On Completion | Asbuilt of invert on completion