## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - 2100 Culvert Pipe Installation | itp |  |  |  |  | ITP - 2100 Culvert Pipe Installation
checkpoint | Review Drawings
note | SPECIFICATION REFERENCE - IFC Drawings
note | TEST REQUIRED - Review
note | TASK TIMING OR TASK FREQUENCY - Before Starting Onsite
note | ACCEPTANCE CRITERIA - For Construction
note | W
checkpoint | Supply Bedding/Backfill Material
note | SPECIFICATION REFERENCE - IFC Drawing DE9
note | TASK TIMING OR TASK FREQUENCY - For Culvert
note | ACCEPTANCE CRITERIA - Within grading parameters:
note | – – – – – – – – – – – – – – – – – – –
note | GRADING LIMITS
note | – – – – – – – – – – – – – – – – – – –
note | BED & HAUNCH:BED & HAUNCH ZONES:
note | SEIVE SIZE (MM) ¦¦ WEIGHT PASSING (%)
note | – – – – – – – – – – – – – – – – – – –
note | 19.0 MM ¦¦ 100%
note | 2.36 MM ¦¦ 100 - 50%
note | 0.60 MM ¦¦ 90 - 20%
note | 0.30 MM ¦¦ 60 - 10%
note | 0.15 MM ¦¦ 25 - 0%
note | 0.075 MM ¦¦ 10 - 0%
note | – – – – – – – – – – – – – – – – – – –
note | SIDE ZONES:
note | SEIVE SIZE (MM) ¦¦ WEIGHT PASSING (%)
note | – – – – – – – – – – – – – – – – – – –
note | 75.0 MM ¦¦ 100%
note | 9.5 MM ¦¦ 100 - 50%
note | 2.36 MM ¦¦ 100 - 30%
note | 0.60 MM ¦¦ 50 - 15%
note | 0.075 MM ¦¦ 25 - 0%
note | – – – – – – – – – – – – – – – – – – –
note | W
checkpoint | 2100 Culvert Pipes
note | SPECIFICATION REFERENCE - IFC Drawing DE9
note | TEST REQUIRED - Visual
note | INSPECTION BY - UCC Rep
note | TASK TIMING OR TASK FREQUENCY - Each Pipe
note | ACCEPTANCE CRITERIA - To be In-Wall-Jointed 2100dia Internal Diameter Class 4: photos/visual inspection
note | W
checkpoint | Setout
note | SPECIFICATION REFERENCE - IFC Drawing DE9
note | TEST REQUIRED - Visual
note | INSPECTION BY - UCC Rep
note | TASK TIMING OR TASK FREQUENCY - Before construction
note | ACCEPTANCE CRITERIA - To be agreed with Engineer if different to Drawings
note | W
checkpoint | Installation of Pipes
note | SPECIFICATION REFERENCE - IFC Drawing DE9
note | TEST REQUIRED - Visual
note | INSPECTION BY - UCC Rep
note | TASK TIMING OR TASK FREQUENCY - On Completion
note | ACCEPTANCE CRITERIA - To Match the design drawings and Hynds installation Technical Specification
note | W
checkpoint | RenoMatress
note | SPECIFICATION REFERENCE - IFC Drawing DE9
note | TEST REQUIRED - Visual
note | INSPECTION BY - PM/PE/Supervisor
note | TASK TIMING OR TASK FREQUENCY - At Completion
note | ACCEPTANCE CRITERIA - To match Drawings & design:
note | – – – – – – – – – – – – – – – – – – –
note | RENO MATTRESSES
note | – – – – – – – – – – – – – – – – – – –
note | 6000mm WIDE X 6000mm LONG X 300mm THICK
note | FILL:
note | DIAMETER:
note | MINIMUM 75mm
note | MAX 200mm
note | (NO MORE THAN 5% BY MASS BEING FINER THAN 75mm)
note | MATTRESS TO BE OVER GEOTEXTILE
note | (DURAFORCE AS410 OR SIMILAR APPROVED)
note | – – – – – – – – – – – – – – – – – – –
note | W
checkpoint | Asbuilt
note | SPECIFICATION REFERENCE - Specification
note | TASK TIMING OR TASK FREQUENCY - On Completion
note | ACCEPTANCE CRITERIA - Asbuilt of invert on completion