## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-001
2024-02-15
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Ballarto Road |  | Clearing and Grubbing |  | Name: | Ruby Lewis | Name: | Nikhil Patil |  | Name: | Nikhil Patil
Contract No: |  | DOT28757 |  | Specifications: VicRoads Specifications Section 201
|  |  |  | Structure / Component: Earthworks/Civil |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | 2024-02-15 |  | Date : | 2024-02-15 |  | Date : | 2024-02-15
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check current drawings are used on site for works |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP | PSP, CEMP, TMP, JSEA, SWMS, | Visual Inspection | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.4 | Flora & Fauna |  | Prior to commencing clearing | A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required. | Construction Environmental Management Plan Appendix 2 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman |  |  | N/A
1.5 | Permit to distrurb flora & fauna |  | Prior to commencing clearing | VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works. | Condition Plans endorsement | Visual Inspection | This ITP Signed off | IP | Project Engineer | N/A |  | N/A
2 | Clear & Grub
2.1 | Define work area |  | Prior to commencing clearing | The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site. | 201.1 | Inspect | This ITP Signed off | HP | Project Engineer/ Superintendent
2.2 | Cultural Heritage and Areas of Significance |  | Prior to commencing clearing | Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing. Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction. Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage. | CHMP | Inspect | This ITP Signed off | HP | Project Engineer/ Superintendent
2.3 | Joint Inspection to Mark vegetation or habitat to be removed |  | Prior to commencing clearing | Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist | Drawings CEMP Tree Management Plan 176.I1 | Visual Inspection | This ITP Signed off | HP | Project Engineer/ Superintendent |  |  | N/A
2.4 | Felling of Trees |  | Prior to commencing clearing | Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared | 201.04 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A
2.5 | Backfill holes |  | After clearing | Any holes produced from grubbing operations have been backfilled with similar material and compacted | 201.05 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.6 | Dispose of Trees and vegetation |  | After clearing | Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works. Noxious weeds shall not be mulched. | 201.07 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.7 | Dispose of concrete, bituminous and other recyclable materials. |  | After clearing | Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments. | 201.07 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.8 | Stripping of topsoil |  | Prior and after commencement of any ground disturbing activities | Topsoil shall be stripped for the full width of the formation.Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable. | VicRoads Spec. Cl.204.05 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.9 | Removal of abandoned services |  | Prior to commencing works | Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort. | VicRoads Spec. Cl.201.05 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.1 | Clearing of Trees and Vegetation |  | During clearin works | Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used. | VicRoads Spec. Cl.201.04 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.11 | Grubbing of vegetation |  | Prior and after commencement of any ground disturbing activities | In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment. Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material | CEMP VicRoads Spec. Cl.201.05 | Visual Inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.