## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-003
2024-02-15
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Ballarto Road |  | Easrthworks Foundation |  | Name: | Ruby Lewis | Name: | Nikhil Patil |  | Name: | Nikhil Patil
Contract No: |  | DOT28757 |  | Specifications: VicRoads Specifications Section 204, 205 and 173
|  |  |  | Structure / Component: Earthworks/Civil |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | 2024-02-15 |  | Date : | 2024-02-15 |  | Date : | 2024-02-15
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing Work | All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site | Induction Register | Document Review | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | PSP, CEMP, TMP, JSEA, SWMS, | Document Review | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Excavation Permit issued |  | Prior to commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document Review | Excavation Permit No. | IP | Site Engineer & Superintendent | N/A |  | N/A
1.4 | Check that current revision drawings are being used |  | Prior to Commencing Work | Issued For Construction (IFC) and latest available revision used | IFC Drawings | Document Review | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.5 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing Work | All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document Review | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A
1.6 | Verification of Site Clearing |  | Prior to Commencing | In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. | VicRoads Spec. Cl.201.05 ITP-001 | Visual Inspection | This ITP Signed off | IP | Project Engineer | N/A |  | N/A
1.7 | Material Category |  | Prior and During Excavation | Prior to commencing excavation in any area and during excavation work, the Superintendent shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of material in accordance with Clause 204.04 | VicRoads Spec. Cl.204.04 Cl.204.06(c) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.8 | Placing Fill |  | Prior to Commencing Fill | Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent | VicRoads Spec. Cl. 204.10(b) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.9 | Rock Subgrade |  | During Excavation | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review. | VicRoads Spec. Cl. 204.06(f) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.1 | Ground Water |  | During Excavation | The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted . | VicRoads Spec. Cl. 204.06(h) | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
1.11 | Unsuitable Material |  | During Excavation | Where unsuitable material is encountered, actions shall be: a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent | IFC Drawings | Visual Inspection | This ITP Signed off | IP | Project Engineer |  |  | N/A
2 | Construction Works
2.1 | Survey set-out |  | Prior to Commencing | The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings. | IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP | Project Engineer/ Superintendent | N/A |  | N/A
2.2 | Surface Preparation |  | During Excavation | For areas where the subgrade height is less than one metre above cut height, the cut should be scarified to 150mm and recompacted with Type B material | VicRoads Spec. Cl. 204.04 Cl. 204.06 | Site Inspection | Signed ITP | HP | Project Engineer/ Superintendent | N/A |  | N/A
2.3 | Foundation Treatment (if required) |  | Prior to Treatment (if required) | Proposed method reviewed, refer relevant ITP | Relevant ITP | Document review | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Survey set-out |  | Prior to Commencing | The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings. | IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP | Project Engineer/ Superintendent | N/A |  | N/A
2.1 | Survey set-out |  | Prior to Commencing | The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings. | IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP | Project Engineer/ Superintendent | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.