## MFU-FH-ITP-008
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-004
Client: | DTP |  | Construction Process: | Fill with Material Type B |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Ballarto Road |  |  |  |  | Name | Ruby Lewis | Name: | Nikhil Patil |  | Name: | Nikhil Patil
Contract No: | DOT28757 |  | Specifications: | VicRoads Specification Sections 173 and 204
|  |  | Structure / Component: | Earthworks/Civil
|  |  | Location: |  |  | Date : | 2024-02-15 | Date : | 2024-02-15 |  | Date : | 2024-02-15
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site | Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken |  | Prior to commencing | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP | Site Engineer, Site Foreman & Superintendent
1.3 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A
1.5 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.6 | Verify Material |  | Prior to Commencing | Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material. Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products. | VicRoads Spec. Cl. 204.06(c) Cl.204.04(c) | Site Inspection | TestResults Material Ctegory agreed with Superintendent | HP | Site Engineer & Superintendent |  |  | N/A
2 | Placing Type B Material
2.1 | Survey set-out |  | Prior to Commencing Excavation | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used | Latest IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP | Site Engineer & Surveyor | N/A |  | N/A
2.2 | Fill Construction |  | Prior to Commencing Excavation | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent | VicRoads Spec. Cl. 204.10(b) | Site Inspection | Area reviewed by Superintendent Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.3 | Keyed fill layers |  | During Excavation | Placement surface textured to ensure layers keyed into each other. | VicRoads Spec. Cl. 204.10(d)(i) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Layer thickness |  | During Excavation | Layers placed and spread in uniform compacted layers not thicker than 200mm. A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records. | VicRoads Spec. Cl. 204.10(d)(ii) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.5 | Proof Roll |  | Each Lot (one day's production or 5,000m2, whichever is lesser) | Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling. | VicRoads Spec. Cl. 204.12 Cl.173.03 | Site Inspection | Proof Roll Form completed & signed. | WP | Site Engineer & Superintendent |  |  | N/A
2.6 | Preparation of final surface |  | Prior to construction of subgrade layer | The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water). | VicRoads Spec. Cl. 204.15 Cl. 204.03(g) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.7 | Conformity with Drawings |  | Prior to construction of subgrade layer | Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings | VicRoads Spec. Table 204.03(f) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3 | Testing
3.1 | Compaction Testing |  | Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent. | Type B Material placed more than 400 mm below top of Type B Material should be compacted to 97% of MDD. Type B Material placed within 400 mm of top of Type B Material should be compacted to 99% MDD. | VicRoads Spec. Cl.204.13(a) Cl.204.13(b) Table 204.131 Table 204.142 | Site Inspection | Compaction Test Records | TP | Site Engineer | N/A |  | N/A
3.2 | Maximum Particle Size |  | Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. | Maximum particle size should be 150mm when soil is within 400mm of the top of Type B soil, and 400 mm at depths greater than 400 mm below the top of Type B material. | VicRoads Spec. Cl. 204.04(c) Cl.204.14(a) | Site Inspection | Maximum Particle Size Test Records | TP | Site Engineer | N/A |  | N/A
3.3 | CBR/Swell |  | The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frecuency (every 8 lots) for future lots shall be agreed with the Superintendent | CBR: ≥ 2%, Swell: < 2.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent). | VicRoads Spec. Cl. 204.14 Cl. 204.04(c) Table 204.141 | Site Inspection | CBR/Swell Test Records | TP | Site Engineer | N/A |  | N/A
3.4 | Atterberg Limit Tests |  | 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frecuency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent | Ensure that soil post-compaction is not classified as silt | VicRoads Spec. Cl. 204.14 Table 204.141 | Site Inspection | PI Test Records | TP | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent