## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004 - Fill with Material Type B | itp |  |  |  |  | ITP-004 - Fill with Material Type B
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior to Commencing
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Verify Material
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material.
label | ○ Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(c), Cl.204.04(c)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results, Material Ctegory agreed with Superintendent
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Placing Type B Material
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Fill Construction
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Keyed fill layers
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Layer thickness
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
label | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Proof Roll
label | FREQUENCY: Each Lot (one day's production or 5,000m2, whichever is lesser)
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 2.6 - Preparation of final surface
label | FREQUENCY: Prior to construction of subgrade layer
label | ACCEPTANCE CRITERIA: The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03(g)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Conformity with Drawings
label | FREQUENCY: Prior to construction of subgrade layer
label | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction Testing
label | FREQUENCY: Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent.
label | ACCEPTANCE CRITERIA: Type B Material placed more than 400 mm below top of Type B Material should be compacted to 97% of MDD. Type B Material placed within 400 mm of top of Type B Material should be compacted to 99% MDD.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.13(a), Cl.204.13(b) Table 204.131, Table 204.142
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compaction Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Maximum Particle Size
label | FREQUENCY: Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements.
label | ACCEPTANCE CRITERIA: Maximum particle size should be 150mm when soil is within 400mm of the top of Type B soil, and 400 mm at depths greater than 400 mm below the top of Type B material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c), Cl.204.14(a)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Maximum Particle Size Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - CBR/Swell
label | FREQUENCY: The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frecuency (every 8 lots) for future lots shall be agreed with the Superintendent
label | ACCEPTANCE CRITERIA: CBR: ≥ 2%, Swell: < 2.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent).
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14, Cl. 204.04(c) Table 204.141
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: CBR/Swell Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Atterberg Limit Tests
label | FREQUENCY: 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frecuency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent
label | ACCEPTANCE CRITERIA: Ensure that soil post-compaction is not classified as silt
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14 Table 204.141
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: PI Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: