## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-006 - Subgrade Preparation | itp |  |  |  |  | ITP-006 - Subgrade Preparation
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Excavation Permit No.
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | REFERENCE DOCUMENTS: Project Spec.Cl.1190.07 Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compliance with latest IFC drawings, Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Unsuitable Material
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Material Category
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior excavation, Superintendent and Fulton Hogan responsible shall inspect each type of material encountered and, subject to verification by laboratory testing, agree on category of material in accordance with VicRoads Spec Section 204.04
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06(c)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendent agreement, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Trimming and level conformity
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping not differ by more than 5 mm above or 15 mm below the specified level.
label | ○ Level at any point of sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns.
label | ○ Water shall not pond at any point.
label | ○ The mean and standard deviation of the departures from the theoretical surface level within each lot shall meet the requirements of Table 204.031.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Cut to Fill Zones
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(g)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing for Compaction and Material Properties
checkpoint | 3.1 - Proof Rolling
label | FREQUENCY: Each Lot (one day's production), prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Test rolling of all fill layers and subgrade shall be in accordance with Section 173 and 204 of the VicRoads Standard Specification.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.03, Cl. 204.12
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Proof Rolling Register signed.
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 3.2 - Testing for Compaction and Material Properties
label | FREQUENCY: Testing as per table 204.141 of VicRoads Spec. for Roadworks and Bridgeworks
label | ACCEPTANCE CRITERIA: Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level= minimum compaction 99% MDD.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of cuts= minimum compaction 97% MDD.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.04, Cl. 204.13, Cl. 204.14, Table 204.131, Table 204.141
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: