## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-007 - Guardrail Installation | itp |  |  |  |  | ITP-007 - Guardrail Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Approval of Guardrail System
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | REFERENCE DOCUMENTS: RDN 06-04
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP/Email
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Approvals
checkpoint | 2.1 - Approved steel supply
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(b)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved), Material Test Certificates
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Approved Galvanisation records
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(d)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance, Test Certificates
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Installation of Guardrail & Maintenance strip
checkpoint | 3.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | SCP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Service Location
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
label | REFERENCE DOCUMENTS: Services file & Current DBYD notifications
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Services marked on the ground
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Approval of location and length
label | FREQUENCY: Prior to Installation
label | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the superintendent the required location and length of all guard fence.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Install posts, rails and terminations
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Tolerances
label | W-beam guard fence shall be erected to the following tolerances:
label | (i) Variation from true plan position of posts ±20 mm
label | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
label | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
label | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
label | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
label | (vi) Dimension of holes -0 mm, +50 mm
label | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
label | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(d)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Construct crushed rock base for maintenance strip
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.6 - Construct concrete maintenance strip
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam.
label | ○ Separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative), full depth expansion joints 200mm either side of posts.
label | ○ Fresh concrete to be protected from rain or other damage until hard set.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Concrete dockets/Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
section | 4 - Testing
checkpoint | 4.1 - Compliance Audit of Barrier System Installation
label | FREQUENCY: Prior the issue of the Certificate of Practical Completion
label | ACCEPTANCE CRITERIA: Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract and the Contractor shall complete and submit to the superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.10
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Safety barrier compliance audit, Manufacturer compliance certificate
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Completion
checkpoint | 5.1 - Delineators
label | FREQUENCY: Once installation of assets is completed
label | ACCEPTANCE CRITERIA: The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see:
label | ○ red delineators on the left side of one-way and two-way roadways;
label | ○ white delineators on the right side of two-way roadways; and
label | ○ yellow delineators on the right side of one-way roadways.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.11
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Site Photos/Signed ITP
label | IP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 5.2 - Survey data captured for As-Builts
label | FREQUENCY: Completion of Works
label | ACCEPTANCE CRITERIA: As-Built drawings to be submitted to client
label | REFERENCE DOCUMENTS: VicRoads Spec. 708
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: As-Builts, Survey reports
label | IP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: