## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-018-A2-LOT-XXX - Desc | itp |  |  |  |  | ITP 0018 - Protective and-or Decorative Concrete Coatings
section | 1 - Preliminaries
checkpoint | 1.1 - Anti-graffiti System Selection
label | Frequency: Once, for each coating system, 14 days prior to application
label | - - - - - - - - -
label | Acceptance Criteria:
label | i. be either a film-forming or a penetrant system
label | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | iv. be non-yellowing, colour-fast and not subject to fading or discolouration
label | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | vi. application thicknesses (film-forming):
label | WFT total = 175µm min. OR
label | WTF per coat = 88µm min.
label | DFT total = 100µm min.
label | vii. adhesion to substrate (film-forming):
label | 0.75MPa min.
label | viii. application rate (penetrants)
label | as per the minimum thickness on the manufacturer's TDS
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & €
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Decorative & Anti-carbonation System Selection
label | Frequency: Once, for each coating system, 21 days prior to application
label | - - - - - - - - -
label | Acceptance Criteria: The system shall be selected based on the following criteria:
label | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | iv. be non-yellowing, colour-fast and not subject to fading or discolouration
label | v. be guaranteed to last for 10 years of outdoor exposure
label | vi. application thicknesses:
label | WFT per coat = enough to achieve the total DFT
label | DFT total = 150µm min.
label | vii. adhesion to substrate:
label | 0.75MPa min.
label | viii. able to bridge cracks up to 0.3mm wide
label | ix. able to be re-coated within 24 hours
label | x. have a minimum pot life of 1 hour
label | xi. compatibility to an alkaline surface
label | xii. equivalent air thickness >150m
label | xiii. equivalent concrete thickness >450mm
label | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | xv. Water vapour equivalent air layer <4m
label | - - - - - - - - -
label | Reference Documents: IFC Drawings Coating System TDS, Surface Cleaner TDS, 686.04, 686.05 (a) & (b) Table 686.051
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
label | Frequency: Once, for each coating system, 21 days prior to application
label | - - - - - - - - -
label | Acceptance Criteria: The system shall be selected based on the following criteria:
label | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | iv. be non-yellowing, colour-fast and not subject to fading or discolouration
label | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | vi. application thicknesses:
label | WFT per coat = enough to achieve the total DFT
label | DFT total = 150µm min.
label | vii. adhesion to substrate:
label | 0.75MPa min.
label | viii. able to bridge cracks up to 0.3mm wide
label | ix. able to be re-coated within 24 hours
label | x. have a minimum pot life of 1 hour
label | xi. compatibility to an alkaline surface
label | xii. equivalent air thickness >150m
label | xiii. equivalent concrete thickness >450mm
label | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | xv. Water vapour equivalent air layer <4m
label | - - - - - - - - -
label | Reference Documents: IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
label | Frequency: Once, for each coating system, 21 days prior to application
label | - - - - - - - - -
label | Acceptance Criteria: The system shall be selected based on the following criteria:
label | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
label | ii. all coats to be compatible with each other
label | Penetrants:
label | iii. active ingredients:
label | Silane = at least 95%
label | Solid silane & silane cream = at least 80%
label | Silane-siloxane & siloxane = product shall only be used if approved by the Superintendent
label | iv. application rates:
label | Silane = 2 applications of 0.3L/m² min.
label | Solid silane & silane cream = 1 application of 0.4L/m² min.
label | Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
label | Film-forming coat:
label | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
label | vi. to be water or acrylic based, solvent-free
label | vii. to be non-yellowing, colour-fast and not subject to fading or discolouration
label | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | ix. application thicknesses:
label | WFT per coat = enough to achieve the total DFT
label | DFT total = 200µm min.
label | x. adhesion to substrate:
label | 0.75MPa min.
label | xi. able to bridge cracks up to 0.3mm wide
label | xii. able to be re-coated within 24 hours
label | xiii. have a minimum pot life of 1 hour
label | xiv. compatibility to an alkaline surface
label | xv. equivalent air thickness >150m
label | xvi. equivalent concrete thickness >450mm
label | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | xviii. Water vapour equivalent air layer <4m
label | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
label | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
label | - - - - - - - - -
label | Reference Documents: IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051, 686.05 (c) (i) & (iii)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Work Procedures
label | Frequency: Once, for each coating system, 21 days prior to application
label | - - - - - - - - -
label | Acceptance Criteria: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents: 685.05, 686.04
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Coating Personnel & Equipment
label | Frequency: Once, prior to application.
label | - - - - - - - - -
label | Acceptance Criteria: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | - - - - - - - - -
label | Reference Documents: Coating System TDS, Surface Cleaner TDS 685.16, 686.19
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 1.7 - Protection of Adjacent Works & Property
label | Frequency: Where applicable, 2 days prior to application.
label | - - - - - - - - -
label | Acceptance Criteria: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents: 685.17, 686.10
label | - - - - - - - - -
label | Inspection / Test Method: Visual, Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Minimum Concrete Curing Period
label | Frequency: Once, prior to application.
label | - - - - - - - - -
label | Acceptance Criteria: Concrete shall not be coated until the minimum concrete curing times have elapsed:
label | ○ Standard cured concrete = 28 days, or 14 days with moisture content less than 10%,.
label | ○ Accelerated cured concrete = 14 days
label | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | - - - - - - - - -
label | Reference Documents: 685.08, 686.16
label | - - - - - - - - -
label | Inspection / Test Method: Visual, Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 1.9 - Trial Application (or Past Performance) Inspection
label | Frequency: Once, for each coating system, 7 days prior to full coating application
label | - - - - - - - - -
label | Acceptance Criteria: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively & subject to approval, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | ○ Attach: Inspection Photographs
label | - - - - - - - - -
label | Reference Documents: 685.11, 686.13
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Nominated Authority
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Pre-application activities
checkpoint | 2.1 - Material Records
label | Frequency: Prior to application
label | - - - - - - - - -
label | Acceptance Criteria: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
label | ○ the manufacturer's name & address
label | ○ product reference
label | ○ batch number
label | ○ quantity manufactured in the batch
label | ○ date of manufacture
label | – Product beyond the manufacturer's shelf life shall not be used.
label | – Each product shall be traced to final location.
label | - - - - - - - - -
label | Reference Documents: Coating System TDS, Surface Cleaner TDS 685.10, 686.12
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 2.2 - Weather Conditions
label | Frequency: Prior to application and every 4 hours per shift
label | - - - - - - - - -
label | Acceptance Criteria: Coating systems shall not be applied under any of the following conditions:
label | i. windy conditions where spray/splatter may be generated
label | ii. when wind-borne debris is likely to contaminate the uncured surface
label | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | – Weather conditions are to be recorded.
label | - - - - - - - - -
label | Reference Documents: Coating System TDS, Surface Cleaner TDS 685.09, 685.12 (a), 686.11, 686.14 (a) (iii)
label | - - - - - - - - -
label | Inspection / Test Method: Visual, Measure
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 2.3 - Surface Preparation
label | Frequency: Once, prior to application.
label | - - - - - - - - -
label | Acceptance Criteria: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | - - - - - - - - -
label | Reference Documents: Surface Cleaner TDS, Coating System TDS 685.05, 686.06
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 2.4 - Surface Moisture Testing
label | Frequency: Immediately prior to application, test 1m2
label | - - - - - - - - -
label | Acceptance Criteria: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
label | - - - - - - - - -
label | Reference Documents: 685.12 (a), 686.14 (a) (iii)
label | - - - - - - - - -
label | Inspection / Test Method: Test
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
section | 3 - Application activities
checkpoint | 3.1 - Method of Application
label | Frequency: Each coat
label | - - - - - - - - -
label | Acceptance Criteria: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | ○ Attach: Coating Application Record
label | - - - - - - - - -
label | Reference Documents: Coating System TDS 685.07, 686.07, 686.09
label | - - - - - - - - -
label | Inspection / Test Method: Visual, Measure
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 3.2 - Wet Film Thickness (WFT) Testing
label | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
label | - - - - - - - - -
label | Acceptance Criteria: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | ○ Attach: WFT Test Results
label | - - - - - - - - -
label | Reference Documents: Coating System TDS 685.12 (b) (ii), 686.14 (b) (ii)
label | - - - - - - - - -
label | Inspection / Test Method: Test
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 3.3 - Inspection & Defect Identification
label | Frequency: After each coat
label | - - - - - - - - -
label | Acceptance Criteria: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | - - - - - - - - -
label | Reference Documents: 685.07, 685.13 (d), 686.07, 686.15
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 3.4 - Drying and Curing
label | Frequency: After each coat
label | - - - - - - - - -
label | Acceptance Criteria: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | - - - - - - - - -
label | Reference Documents: Coating System TDS 685.17, 686.09, 686.10
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
section | 4 - Post application activities
checkpoint | 4.1 - Clean-up & Waste Disposal
label | Frequency: At completion of Works
label | - - - - - - - - -
label | Acceptance Criteria: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | - - - - - - - - -
label | Reference Documents: 685.09 (c), 686.10
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.2 - Dry Film Thickness (DFT) Testing
label | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
label | - - - - - - - - -
label | Acceptance Criteria: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
label | i. Anti-graffiti system = 100µm
label | Ii. Decorative & anti-carbonation = 150µm
label | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
label | iv. Atmospheric & splash zone (dual protective) = 200µm
label | – No more than 15% of the readings shall be less than 90% of the required thickness.
label | Attach: DFT Test Results
label | - - - - - - - - -
label | Reference Documents: 685.12 (b) (iii), 686.14 (b) (iii)
label | - - - - - - - - -
label | Inspection / Test Method: Test
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.3 - Adhesion Bond Strength Testing
label | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
label | - - - - - - - - -
label | Acceptance Criteria: A minimum of 14 days after application, the bond-strengths between:
label | i. the coating system to the substrate, and
label | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
label | ○ The subsequent results shall be greater than 0.75MPa.
label | ○ Attach: Adhesive Bond Strength Testing Results
label | - - - - - - - - -
label | Reference Documents: 685.12 (b) (i), 686.14 (b) (i)
label | - - - - - - - - -
label | Inspection / Test Method: Test
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.4 - Penetration Depth Testing
label | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
label | - - - - - - - - -
label | Acceptance Criteria: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
label | The subsequent results shall be:
label | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
label | ii. Silane, Solid Silane or Silane Cream = 5mm min.
label | iii. Silane-Siloxane or Siloxane = 3mm min.
label | ○ Attach: Penetration Depth Testing Results
label | - - - - - - - - -
label | Reference Documents: 685.12 (b) (v), 686.14 (b) (v)
label | - - - - - - - - -
label | Inspection / Test Method: Test
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.5 - Non-conforming Coatings
label | Frequency: Where required
label | - - - - - - - - -
label | Acceptance Criteria: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | - - - - - - - - -
label | Reference Documents: 685.14, 686.17
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.6 - Coating Application Guarantee
label | Frequency: At completion of Works
label | - - - - - - - - -
label | Acceptance Criteria: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | ○ Attach: Coating Application Guarantee
label | - - - - - - - - -
label | Reference Documents: 685.06 (b), 686.05 (a)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | SP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.7 - Repair to Damaged Coating
label | Frequency: Where required
label | - - - - - - - - -
label | Acceptance Criteria: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | - - - - - - - - -
label | Reference Documents: 686.17
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.8 - Non-conformance Report (NCR) Closure
label | Frequency: Once, prior to closure of this lot / element / Work area
label | - - - - - - - - -
label | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | - - - - - - - - -
label | Reference Documents: Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
date | Work Completed On