## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP 1 Delivery Checklist | itp |  |  |  |  | ITP 1 Delivery Checklist
section | Details
checkpoint | Durra panel sizes to match order
checkpoint | Durra panel quantities to match order
checkpoint | Durra panel layers to match order
checkpoint | T bars quantities to match order
checkpoint | T bars have no damage
checkpoint | Beam size to match order
checkpoint | Beam quantities to match order
checkpoint | All panels have no damage
checkpoint | All beams have no damage
checkpoint | Wedge quantities to match order
checkpoint | Correct paperwork with delivery
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 2 Module Assembly | itp |  |  |  |  | ITP 2 Module Assembly
section | Details
checkpoint | All Durra layers are installed as per location mark up
checkpoint | All spacings are to match install area
checkpoint | All T bars are secured
checkpoint | All Durra panels are in place with correct minimum spacings
checkpoint | All wedges are in place
checkpoint | All Durra panels are taped to all edges
checkpoint | All panels have no damage
checkpoint | Infill panels are secured ready for lift
checkpoint | Infill T bars are secured ready for lift
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 3 Module Install | itp |  |  |  |  | ITP 3 Module Install
section | Details
checkpoint | All Durra layers are installed as per location mark up
checkpoint | All angles are secured correctly to pre cast
checkpoint | All angles have correct amount of bolts
checkpoint | All T bars are secured
checkpoint | All Durra panels are in place with correct minimum spacings
checkpoint | All wedges are in place
checkpoint | All Durra panels are taped to all edges
checkpoint | All infill panels are in place and wedged
checkpoint | All beams are bolted
checkpoint | All bolts are correct length and size
checkpoint | All bolts have been tensioned
checkpoint | All panels have no damage
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 4 Fire Draft Walls | itp |  |  |  |  | ITP 4 Fire Draft Walls
section | Details
checkpoint | All Durra layers are installed as per location mark up
checkpoint | All T bars are secured
checkpoint | All Durra panels are in place with correct minimum spacings
checkpoint | All Durra panels are taped to all edges
checkpoint | Any gaps bigger than 3mm have been caulked
checkpoint | All frames are securely fastened
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 5 Durra Panels Top Layer | itp |  |  |  |  | ITP 5 Durra Panels Top Layer
section | Details
checkpoint | All Durra layers are installed as per location mark up
checkpoint | All T bars are secured
checkpoint | All bolts are in place and tensioned
checkpoint | All bolts used are correct length and size
checkpoint | All Durra panels are in place with correct minimum spacings
checkpoint | All wedges are installed
checkpoint | All Durra panels are taped to all edges
checkpoint | All infill pieces are in place and wedged completely
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 6 Roof Layers | itp |  |  |  |  | ITP 6 Roof Layers
section | Details
checkpoint | All roof layers are installed as per location mark up
checkpoint | Safety mesh installed as per manufactures tech data
checkpoint | Layer of sarking with tape to joins no gaps in tape
checkpoint | Sarking taped with correct sarking tape
checkpoint | 2 layers of cement sheeting with no gaps
checkpoint | Correct thickness cement sheeting to suit area as per mark up attached
checkpoint | Correct size insulation blanket to suit area as per mark up attached
checkpoint | Correct size roof spacers to suit insulation as per mark up attached
checkpoint | Thermal break tape to roof spacers to be consistent runs
checkpoint | Vapour barrier installed with minimum 150mm lap
checkpoint | Vapour barrier taped with correct tape
checkpoint | Vapour barrier taped with no gaps or breaks in taping
checkpoint | Any holes have been taped over
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 7 Gutters | itp |  |  |  |  | ITP 7 Gutters
section | Details
checkpoint | Gutters have correct fall
checkpoint | Gutters have expansions joins(where necessary)
checkpoint | Gutters have compliant overflow precautions
checkpoint | Gutters/sumps clean of swarf
checkpoint | Eaves gutters have correct bracket spacings to suit manufacturers tech data
checkpoint | Downpipe clip spacings as per regulations
checkpoint | Spreaders include ½ stop ends where needed
checkpoint | Downpipes are located as per Hydraulic plans
checkpoint | Overflows are located as per Hydraulic plans
checkpoint | Sumps installed where located on Hydraulic plans
checkpoint | Correct size outlets to match Hydraulic plans
checkpoint | Correct size overflows to match Hydraulic plans
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | ITP 8 Roof | itp |  |  |  |  | ITP 8 Roof
section | Details
checkpoint | Roof profile is compliant with roof pitch
checkpoint | Roof sheets minimum 50mm into gutter
checkpoint | Roof sheets turned up (and down if required)
checkpoint | Roof screwed off correctly
checkpoint | Flashings correctly screwed off/riveted
checkpoint | Flashings cover 150mm or 2 ribs
checkpoint | Penetrations backtrays correctly screwed/riveted/oversealed
checkpoint | Dektites screwed/oversealed
checkpoint | Ensure ponding is not present in or around dektite
checkpoint | Cappings screwed off every 500mm
checkpoint | Roof clean of swarf
checkpoint | Gutters have correct fall
checkpoint | Gutters have expansions joins
checkpoint | Gutters have compliant overflow precautions
checkpoint | Gutters/sumps clean of swarf
checkpoint | Downpipe clip spacings as per regulations
checkpoint | Spreaders include ½ stop ends where needed
checkpoint | All works have been carried out in accordance with above ITP
label | Attach Faulkner Roofing representative signature
holdpoint | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
checklist | Safety Mesh Checklist | [5 empty] | Safety Mesh Checklist
section | Details
checkpoint | This is to certify that the safety mesh used has been installed correctly and to specified guidelines
textbox | Safety mesh used
textbox | Leading Hand
holdpoint | Signed
checklist | Safety Rail Checklist | [5 empty] | Safety Rail Checklist
section | Details
checkpoint | This is to certify that the hand rail system used has been installed correctly and to specified guidelines
textbox | Safety rail system used
textbox | Leading Hand
holdpoint | Signed
checkpoint | This is to certify that the access tower has been installed by a competent scaffolder to meet Australian Standards: AS/NZS 1576 Scaffolding - General requirements and AS/NZS 4576 - Guidelines for Scaffolding, and has been signed off.
textbox | Scaffolder
textbox | Licence Number
date | Expiry
holdpoint | Signed
checklist | Wall Cladding ITP | itp |  |  |  |  | Wall Cladding ITP
section | Details
checkpoint | Wall cladding sheets/panels have been installed as per manufacturer’s instructions
checkpoint | Wall cladding sheets/panels have been screwed off properly (if required)
checkpoint | Wall cladding sheets/panels penetrations have been flashed properly
checkpoint | Wall cladding sheets/panels clean
checkpoint | Wall cladding sheets/panels free of dints
checkpoint | Wall cladding sheets/panels free of scratches
checkpoint | Toe moulds are free from metal swarf/filings
checkpoint | Toe moulds free of dints
checkpoint | Toe moulds free of scratches
checkpoint | All works have been carried out in accordance with above ITP
holdpoint | Faulkner Roofing representative to sign off
checkpoint | Inspection and test plan was conducted and signed by Faulkner Roofing on this date
holdpoint | Builder representative to sign off
checklist | Roofing ITP 1.0 | itp |  |  |  |  | Roofing ITP 1.0
section | Details
checkpoint | Structural steel pre-check
checkpoint | Safety mesh installed
checkpoint | Handrail Installed
checkpoint | Hold Point: Builder to sign
holdpoint | Builder Signature
checkpoint | Hold Point: FR PM to sign
holdpoint | Faulkner Roofing PM Signature
checkpoint | Roof profile is compliant with roof pitch
checkpoint | Roof sheets minimum 50mm into gutter
checkpoint | Insulation installed correctly
checkpoint | Roof sheets turned up (and down if required)
checkpoint | Roof screwed off correctly
checkpoint | Foam profile infill strips inserted (if required)
checkpoint | Flashings correctly screwed off/riveted
checkpoint | Flashings cover 150mm or 2 ribs
checkpoint | Penetrations backtrays correctly screwed/riveted/over sealed
checkpoint | Dektites screwed/over sealed
checkpoint | Ensure ponding is not present in or around dektite
checkpoint | Cappings screwed off every 500mm
checkpoint | Roof clean of metal swarf/filings
checkpoint | All works have been carried out in accordance with above ITP
holdpoint | Faulkner Roofing representative to sign off
checkpoint | Inspection and test plan was conducted and signed by Faulkner Roofing on this date
holdpoint | Builder representative to sign off
checklist | Roofing Vent Ridge ITP | itp |  |  |  |  | Roofing Vent Ridge ITP
section | Details
checkpoint | Check Roof opening Confirms to the nominated throat width of the ridge vent being installed
checkpoint | Check that the Purlins are in the correct position for screwing down Vent Ridge
checkpoint | Ensure the Roof sheets are weather correctly
checkpoint | Vent ridge is inspected for damage or missing components upon delivery
checkpoint | Hold Point: Builder to sign
holdpoint | Builder Signature
checkpoint | Hold Point: FR PM to sign
holdpoint | Faulkner Roofing PM Signature
checkpoint | Worker has a copy of the installation guide
checkpoint | Infill foam installed (if required)
checkpoint | Main frames and Stack Flashing installed square and straight
checkpoint | Stack flashing notched to suit roof profile and fix with roofing screws
checkpoint | Lap joints sealed correctly
checkpoint | Stack Cap correctly installed with correct main frame clearance
checkpoint | Inbuilt gutter and drains attached correctly
checkpoint | Diaphragms installed correctly
checkpoint | Guidevane Blades installed and are at correct spacings
checkpoint | Stop end cut and installed correctly
checkpoint | All guidevance blades installed
checkpoint | Windband installed
checkpoint | Birdwire installed
checkpoint | Final check of Screw fixings, laps and joins sealed, panels are correctly installed, fitted and lapped
checkpoint | Metal swarf/filings has been cleaned
checkpoint | All works have been carried out in accordance with above ITP
holdpoint | Faulkner Roofing representative to sign off
checkpoint | Inspection and test plan was conducted and signed by Faulkner Roofing on this date
holdpoint | Builder representative to sign off
checklist | Wall Cladding ITP 2.0 | itp |  |  |  |  | Wall Cladding ITP 2.0
section | Details
checkpoint | Sarking/Sislation fixed with no sags, joints lapped and taped
checkpoint | Sarking product used
checkpoint | Top hats fixed and installed level
checkpoint | Toe moulds installed level and as documented
checkpoint | Toe moulds free of scratches
checkpoint | Hold Point: Builder to sign
holdpoint | Builder Signature
checkpoint | Hold Point: FR PM to sign
holdpoint | Faulkner Roofing PM Signature
checkpoint | Wall cladding sheets/panels have been installed as per manufacturer’s
checkpoint | instructions
checkpoint | Infill foam installed (if required)
checkpoint | Wall Insulation installed (if required)
checkpoint | Wall cladding sheets/panels have been screwed as per manufacturer’s
checkpoint | instructions
checkpoint | Wall cladding sheets/panels penetrations have been flashed properly
checkpoint | Wall cladding sheets/panels clean
checkpoint | Wall cladding sheets/panels free of dints and scratches
checkpoint | Wall cladding sheets/panels free of scratches
checkpoint | Toe moulds are free from metal swarf/filings
checkpoint | All works have been carried out in accordance with above ITP
holdpoint | Faulkner Roofing representative to sign off
checkpoint | Inspection and test plan was conducted and signed by Faulkner Roofing on this date
holdpoint | Builder representative to sign off
checklist | Gutter ITP | itp |  |  |  |  | Gutter ITP
section | Details
checkpoint | Gutters have correct fall
checkpoint | Gutters have expansions joins
checkpoint | Gutters have compliant overflow precautions
checkpoint | Gutters/sumps clean of metal swarf/filings
checkpoint | Downpipe clip spacings as per regulations
checkpoint | All works have been carried out in accordance with above ITP
holdpoint | Faulkner Roofing representative to sign off
checkpoint | Inspection and test plan was conducted and signed by Faulkner Roofing on this date
holdpoint | Builder representative to sign off