## ITP-003
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # DTM-ITP-008
[11 empty] | Revision : 0 |  | Date: 04/10/24
Client: Department of State Growth |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Davey to Macquarie Street |  |  |  | Underground Stormwater Drainage |  | Name: | Mileva Savic | Name: | Patrick Schurink-Moeller |  | Name: | Sam Arnold
Contract No: |  | C3741 |  | Specifications: Specifications Section 610, 620, 701, AS4058, AS1646, DSG Standard Drawings,
|  |  |  | Structure / Component: Drainage Pipes, Pits and Headwalls |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | QAV | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | OHSMP, EMP, TMS, SWMS, WP | Visual Inspection | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
2 | Procurement of Materials
2.1 | Precast Reinforced Concrete Pipe Supply |  | Prior to works commencing | All portland cement-based precast reinforced concrete pipes shall be produced in accordance with AS4058. Rubber ring joints shall comply with the requirements of AS 1646. Pipes shall arrive onsite free from defect or deformity. | 701.05 AS4058 AS1646 | Verify | This ITP Signed Recievable Inspection Checklist | HP* | Site Engineer | N/A |  | N/A
2.2 | Precast Reinforced Concrete Pit Supply and Inlet and Outlet Structure |  | Prior to works commencing | The supply of precast pits and inlet and outlet structures shall conform with the requirements of the specification section 705. Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611. | 610.474 611 705.07 | Verify | This ITP Signed Recievable Inspection Checklist | HP* | Site Engineer | N/A |  | N/A
2.3 | Covers, Lintels and Grates |  | Prior to works commencing | Covers, Lintels and Grates shall be as shown on DSG standard drawings | DSG Standard Drawings 3402-9 P20 to P30 | Verify | This ITP Signed Recievable Inspection Checklist | IP | Site Engineer | N/A |  | N/A
2.4 | Provision for Stormwater Connections in Pits |  | Prior to works commencing | Precast pits must allow 150mm diameter holes for subsurface drains and holes of sufficient diameter to allow for connections of stormwater culverts as shown on the drawings with the holes not greater than 50mm larger than required. | 705.09 705.11 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
2.5 | Bedding and Backfill Material Specification |  | Grading 1 test per 1,000t | Bedding and Backfill materials to conform to sieve requirements of Table 701.091 in the specification. Select Backfill shall also conform to the plasticity requirements of table 701.092 | Table 701.091 Table 701.092 | Verify | This ITP Signed, Quarry test report | HP* | Site Engineer | N/A |  | N/A
2.6 | Setout of Works |  | Prior to works commencing | Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent. Works to be setout to true line and level by a surveyor. | 701.10 | Verify | Survey records, pegs on ground & this ITP Signed | HP | Site Engineer / QAV | N/A
3 | Installation of Underground Stormwater Drainage
3.1 | Excavation for pipe |  | Each Lot | Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm | 701.15 Table 701.151 | Visual Inspection | This ITP Signed | IP | Site Engineer | N/A |  | N/A
3.2 | Trench Base Preparation / Bedding |  | Each Lot | Treat or replace all soft, wet or unstable material below the level required.The compacted thickness of bedding material following any shaping necessary shall be not less than 100mm where D < 1500 mm. | 701.16 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
3.3 | Laying of pipes |  | Each Lot | Pipes to be laid with rebate or socket end facing upstream, design grade tolerance of +- 10mm in 10m and +-50mm invert level of pipes at pits. Multiple pipes to be laid with a horizontal spacing of 0.3m for pipes under 600mm diameter and D/2 for pipes with a diameter of 600mm or greater. | 701.17 Table 701.171 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
3.4 | Jointing |  | Each Lot | Reinforced concrete pipes shall be wrapped with a 200mm wide external joint rubber band. Rubber rings shall be kept undisturbed, clean and free from dirt and other foreign materials. Rubbers are to be inspected afer each connection and in place before proceeding to next section. | 701.18 | Verify | This ITP Signed | IP | Site Engineer / Foreman | N/A |  | N/A
3.5 | Haunching |  | Each Lot | Haunching layer to be reaching a height equal to 30% of nominal diameter. Layer thickness shown below: DN600 Pipe Bedding above = 200MM DN525 Pipe Bedding above = 175MM DN450 Pipe Bedding above = 150MM DN300 Pipe Bedding above = 100MM DN225 Pipe Bedding above = 100MM | 701.20 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
3.6 | Pit Connections |  | Each Lot | Weepholes or holes installed on site shall be cut and not broken out. Pits shall be replaced if cracking occurs as a result of installing holes or if the hole exceeds the pipe dia by more than 50mm. | 705.11 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
3.7 | Culverts |  | Each Lot | Prior to commencement of any excavation for culverts the position shall be confirmed with the superintendant | 701.10 | Verify | Hold point release | HP | QAV | N/A |  | N/A
3.8 | Tolerance |  | Each Lot | Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings. Tolerance: Offset of entry pits required to match lines of kerbs or barriers ± 20mm Plan location of pits other than offsets to kerb lines or barriers ± 100mm Invert level of pipes at pits ± 50mm Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250 | 701.10 | Verify | This ITP Signed | SCP | Surveyor, Site Engineer | N/A |  | N/A
4 | Backfilling of Stormwater
4.1 | Filling |  | Each Lot | (i) Culvert Under Area to be Paved The trench shall be backfilled as per requirements from Table 701.091 and 701.092. Above subgrade level, materials as per pavement design. (ii) Culvert Under Area not to be Paved The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level. Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment. | 701.19 705.18 | Verify | This ITP Signed, Particle size distribution certificate of selected backfill material | IP | Site Engineer | N/A |  | N/A
4.2 | Testing and Acceptance of Fill Materials |  | 3 Tests per Lot tested with 20% of all Lots for each culvert tested | Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content. Bedding shall be compacted to refusal using hand held mechanical equipment. Backfill material (nominal size < 40mm after compaction) shall be compacted to a mean density ratio of not less than 97% SDR. Backfill (nominal size > 40mm after compaction) material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. | 701.20 | Verify | Compaction Test Result | TP | Site Engineer | N/A |  | N/A
4.3 | Installation of Inlet or Outlet Structure |  | Each Lot | Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas. | 701.10 701.25 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
4.4 | Culvert Coverage |  | Each Lot | Until the minimum compacted thickness of cover in Table 701.141 for each type of vehicle are met, construction shall not be allow to travel over the culvert | 701.14 Table 701.141 | Visual inspection | This ITP Signed | IP | Site Engineer | N/A |  | N/A
5 | Finishing and Commissioning
5.1 | Finishing and Rendering Pipes |  | Each Lot | All stormwater connections and subsurface drain connections shall be cut trimmed neat and finished with cementitious mortar. | 705.11 705.15 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
5.2 | Repair of Damaged Pipes |  | Each Lot | Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval. Repairs to be in accordance with relevant ITP. | 701.31 | Verify | This ITP Signed | HP | Superintendent / Site Engineer/ QAV
5.3 | CCTV |  | Each Lot | All drainage lines constructed beneath pavements shall be inspected after earthworks to subgrade level are complete and prior to the construction of pavement layers by an indpendent organisation using CCTV in accordance with WSA 05-2013 - Conduit Inspection Reporting Code of Australia. Verify that the flow of water is not obstructed by waste construction material and check for visible signs of defects | 701.30 WSA 05-2013 | Verify | This ITP Signed | HP | Site Engineer / QAV | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent