## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-008- Stormwater Drainage | itp |  |  |  |  | DTM-ITP-008- Stormwater Drainage Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Procurement of Materials
checkpoint | 2.1 - Precast Reinforced Concrete Pipe Supply
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: All portland cement-based precast reinforced concrete pipes shall be produced in accordance with AS4058. Rubber ring joints shall comply with the requirements of AS 1646.
label | ○ Pipes shall arrive onsite free from defect or deformity.
label | REFERENCE DOCUMENTS: 701.05, AS4058, AS1646
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Precast Reinforced Concrete Pit Supply and Inlet and Outlet Structure
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: The supply of precast pits and inlet and outlet structures shall conform with the requirements of the specification section 705.
label | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
label | REFERENCE DOCUMENTS: 610.474, 611, 705.07
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Covers, Lintels and Grates
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: Covers, Lintels and Grates shall be as shown on DSG standard drawings
label | REFERENCE DOCUMENTS: DSG Standard Drawings 3402-9 P20 to P30
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Provision for Stormwater Connections in Pits
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: Precast pits must allow 150mm diameter holes for subsurface drains and holes of sufficient diameter to allow for connections of stormwater culverts as shown on the drawings with the holes not greater than 50mm larger than required.
label | REFERENCE DOCUMENTS: 705.09, 705.11
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Bedding and Backfill Material Specification
label | FREQUENCY: Grading 1 test per 1,000t
label | ACCEPTANCE CRITERIA: Bedding and Backfill materials to conform to sieve requirements of Table 701.091 in the specification. Select Backfill shall also conform to the plasticity requirements of table 701.092
label | REFERENCE DOCUMENTS: Table 701.091, Table 701.092
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Setout of Works
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ○ Works to be setout to true line and level by a surveyor.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Installation of Underground Stormwater Drainage
checkpoint | 3.1 - Excavation for pipe
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm
label | REFERENCE DOCUMENTS: 701.15, Table 701.151
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Trench Base Preparation / Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Treat or replace all soft, wet or unstable material below the level required.The compacted thickness of bedding material following any shaping necessary shall be not less than 100mm where D < 1500 mm.
label | REFERENCE DOCUMENTS: 701.16
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Laying of pipes
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes to be laid with rebate or socket end facing upstream, design grade tolerance of +- 10mm in 10m and +-50mm invert level of pipes at pits.
label | ○ Multiple pipes to be laid with a horizontal spacing of 0.3m for pipes under 600mm diameter and D/2 for pipes with a diameter of 600mm or greater.
label | REFERENCE DOCUMENTS: 701.17, Table 701.171
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Jointing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforced concrete pipes shall be wrapped with a 200mm wide external joint rubber band. Rubber rings shall be kept undisturbed, clean and free from dirt and other foreign materials.
label | ○ Rubbers are to be inspected afer each connection and in place before proceeding to next section.
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Foreman
date | Date Completed:
checkpoint | 3.5 - Haunching
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Haunching layer to be reaching a height equal to 30% of nominal diameter. Layer thickness shown below:
label | ○ DN600 Pipe Bedding above = 200MM
label | ○ DN525 Pipe Bedding above = 175MM
label | ○ DN450 Pipe Bedding above = 150MM
label | ○ DN300 Pipe Bedding above = 100MM
label | ○ DN225 Pipe Bedding above = 100MM
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.6 - Pit Connections
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Weepholes or holes installed on site shall be cut and not broken out. Pits shall be replaced if cracking occurs as a result of installing holes or if the hole exceeds the pipe dia by more than 50mm.
label | REFERENCE DOCUMENTS: 705.11
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.7 - Culverts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencement of any excavation for culverts the position shall be confirmed with the superintendant
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Hold point release
label | HP
label | RESPONSIBILITY: QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Tolerance
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
label | ○ Tolerance:
label | – Offset of entry pits required to match lines of kerbs or barriers ± 20mm
label | – Plan location of pits other than offsets to kerb lines or barriers ± 100mm
label | – Invert level of pipes at pits ± 50mm
label | – Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | SCP
label | RESPONSIBILITY: Surveyor, Site Engineer
date | Date Completed:
section | 4 - Backfilling of Stormwater
checkpoint | 4.1 - Filling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
label | – The trench shall be backfilled as per requirements from Table 701.091 and 701.092. Above subgrade level, materials as per pavement design.
label | (ii) Culvert Under Area not to be Paved
label | – The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
label | – Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | REFERENCE DOCUMENTS: 701.19, 705.18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Particle size distribution certificate of selected backfill material
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.2 - Testing and Acceptance of Fill Materials
label | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots for each culvert tested
label | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
label | ○ Bedding shall be compacted to refusal using hand held mechanical equipment.
label | ○ Backfill material (nominal size < 40mm after compaction) shall be compacted to a mean density ratio of not less than 97% SDR.
label | ○ Backfill (nominal size > 40mm after compaction) material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Compaction Test Result
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.3 - Installation of Inlet or Outlet Structure
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
label | REFERENCE DOCUMENTS: 701.10, 701.25
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.4 - Culvert Coverage
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for each type of vehicle are met, construction shall not be allow to travel over the culvert
label | REFERENCE DOCUMENTS: 701.14, Table 701.141
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 5 - Finishing and Commissioning
checkpoint | 5.1 - Finishing and Rendering Pipes
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All stormwater connections and subsurface drain connections shall be cut trimmed neat and finished with cementitious mortar.
label | REFERENCE DOCUMENTS: 705.11, 705.15
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.2 - Repair of Damaged Pipes
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval. Repairs to be in accordance with relevant ITP.
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer/ QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - CCTV
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements shall be inspected after earthworks to subgrade level are complete and prior to the construction of pavement layers by an indpendent organisation using CCTV in accordance with WSA 05-2013 - Conduit Inspection Reporting Code of Australia. Verify that the flow of water is not obstructed by waste construction material and check for visible signs of defects
label | REFERENCE DOCUMENTS: 701.30, WSA 05-2013
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature