## ITP -1
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authorityv C – Contractor, S – Subcontractor,E – Engineer/Principal Representative, Sp – Supplier |  |  |  | Hold Point | Witness Point | Quality Controller Sign Off | Date | Engineer Sign-off | Date | Compliance Manager Sign off | Date
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) |  |  |  |  | Y/N | Y/N | Name / Signature | Date All Records verified complete | Name / Signature | Date All Records verified complete | Name / Signature | Date All Records verified complete
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
1. Procurement
Pre-construction tasks. e.g. approval of materials | Design
| Pavement Treatment Design | Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Principal Approval | Contractor and Principal peer review | per design |  | Pavement Rehabilitation Design Report | C or S |  | C | E | Y
Materials: GAP 65 Pre-treatment Material
| Materials: GAP 65 Pre-treatment Material - Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | C or S |  |  | S
| Materials: GAP 65 Pre-treatment Material - Source Property Test | CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Soaked CBR ≥ 40 | Soaked CBR test (NZS:4407:2015:3.15) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y
| Materials: GAP 65 Pre-treatment Material - Production Property Test | Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Sand Equivalent Test (NZS:4407:2015, 3.6) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y
Materials: M/4 AP40 Material
| Materials: M/4 AP40 Material - Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet
| Materials: M/4 AP40 Material - Source Property Test (1) | Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | less than 10% fines passing 2.36mm sieve size under a load of 130kN | Curshing Resistance Test (NZS 4407:1991, Test 3.10) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
| Materials: M/4 AP40 Material - Source Property Test (2) | Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | AA, AB, AC, BA, BB or CA | Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
| Materials: M/4 AP40 Material - Source Property Test (3) | California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Soaked CBR ≥ 80% | California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
| Materials: M/4 AP40 Material - Production Property Test (1) | Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
| Materials: M/4 AP40 Material - Production Property Test (2) | Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Broken Face Test (NZS:4407: 1991, Test 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
| Materials: M/4 AP40 Material - Production Property Test (3) | Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y
Materials: Geotextile
| Materials: Geotextile - Geotextile (Strength Class C) A29 or greater | TNZ F7 Specification | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S |  | Sp or S | C |  | Y
2. Pre-Implementation
| Production Testing of stabilised material - OMC/MDD | TNZ B/2 section 7.5 | To obtain OMC & MDD | NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Once on commencement and then each stablilised layer at one test per 5000m2 | Quality Controller | Test report | S or C | C | S or C | C |  | Y
| Production Testing of stabilised material - Solid Density | TNZ B/2 section 7.5 | For info. and use in MDD calculation | NZS 4407; test 3.7.1 | Once on commencement and if any materials change | Quality Controller | Test report | S or C | C | S or C | C |  | Y
| Project survey setting out | Reference from Project Drawings |  | Survey/Mobile Roads, Marks with Dazzle | Chainages for every different pavement sections | Subcontractor/ Engineer | Construction drawings | S or C | C | S or C | C |  | Y
3. Construction - Pre-treatment Digouts
Construction phase - Digouts | Pre-treatment Repair Method Selection | Site specifics to be confirmed | Confirm scala acceptance criteria based on treatment type | Scala Penetrometer on Excavation Floor | As required | Quality Controller | Agreed treatment plan | S | C | S | E |  | Y
| Digout of Patches to repair | Higgins SOP 0128 - Digout Repair | 340mm deep | Visual inspection | As required | Quality Controller | Dig out site records/ Asbuilt | S | C | S | C |  | Y
| Subgrade material hardness Check base of excavation | Higgins SOP 0128 - Digout Repair | Scala > 3 blows per 100mm or Proof roll <5mm | Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful | As required depending on size of digout | Quality Controller | Test report | S/C | C | S/C | E |  | Y
| Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | TNZ F7 Specification | Meet TNZ F7 Spec. | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S |  | C | C |  | Y
| Place and compact GAP65 in digout area | Higgins SOP 0128 - Digout Repair | Clegg value > 45 | Clegg Test | Min. 2 per digout | Quality Controller | Test report | S/C | C | S/C | E |  | Y
4. Construction - Granular make up and In-situ Modification
Construction phase - Rehab | Place M/4 AP40 Material | TNZ B/2 (section 7.2) | Evenly spread, no segregation, placed near optimium moisture content | Visual Inspection | On completion of placement | Quality Controller | Photographs and Daily Site Record | S or C |  | S or C | C |  | Y
| Addition of Water | TNZ B/2 (section 7.5) | 90-100% OWC | Nuclear Densometer Testing prior to Stabilisation | ≥1 per 1000m² lot | Quality Controller | NDM Record | S or C |  | S | S or C |  | Y
| Compaction Acceptance | Compaction (7.6) - TNZ B/2 | Mean value ≥ 98% and Minimum Value ≥ 95% | Nuclear Densometer Testing | ≥ 5 tests per 1000m² lot | Quality Controller | NDM Record | S or C |  | S or C | E | Y
| Surface Shape | Compaction (7.7) - TNZ B/2 | ± 10mm deviation along a 3m straight edge, No water ponding | 3m Straight Edge | during construction and prior to seal | Supervisor | Photographs | S or C | C and E | S or C | E |  | Y
| Cross Fall | Compaction (5.1) - TNZ B/2 | 0.5% ≤ X ≤ -0.5% | 3m straight edge or Survey Asbuilt | during construction and prior to seal | Supervisor | Cross Fall Records/Survey Asbuilts | S or C | C and E | S or C | E |  | Y
| Degree of Saturation, DOS | , Pre-sealing requirements (12) - TNZ B/2 Notes: 2005 | ≤80%, however 65% is ideal | Nuclear Densometer Testing | ≥5 tests per 1000m² lot | Quality Controller | NDM Record | S or C | C and E | S or C | E |  | Y
5. Structural Asphlat- A separate ITP shall be submitted
6. Close Out
Final Closeout and Handover | Pavement Rehabilitation Construction Completion Report | Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Engineer Approval | Visual Inspection | ≤2 months of 1st Coat Seal | Quality Controller/ Contract Manager | Signed Report | C | C, S and E | C | E | Y
S – Subcontractor |  | C – Contractor |  | E – Engineer/Principal Representative |  | Sp – Supplier
Quality Control Records Compiled by: |  | Name: | Liju Mathew |  |  | Reviewed / Approved by: |  | Name: |  | Steve Elvy
|  | Role: | Project Engineer |  |  |  |  | Role: |  | Maintenance Contract Manager
|  | Signature: | [5 empty] | Signature:
|  | Date: | [5 empty] | Date