## Sheet1
Pavement Treatment Design | Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Principal Approval | Contractor and Principal peer review | per design |  | Pavement Rehabilitation Design Report | C or S |  | C | E | Y |  | Pavement Treatment Design | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Acceptance Criteria - Principal Approval | Method - Contractor and Principal peer review | Frequency - per design | Responsible Person - | Verifying Document - Pavement Rehabilitation Design Report | Conduct - C or S | Witness - | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Pavement Treatment Design
Materials: GAP 65 Pre-treatment Material - Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | C or S |  |  | S |  |  | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide | Acceptance Criteria - | Method - | Frequency - | Responsible Person - | Verifying Document - Sampling Worksheet | Conduct - C or S | Witness - | Produce Record - | Approval - S | Hold Point Y/N - | Witness Point Y/N - | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
Materials: GAP 65 Pre-treatment Material - Source Property Test | CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Soaked CBR ≥ 40 | Soaked CBR test (NZS:4407:2015:3.15) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: GAP 65 Pre-treatment Material - Source Property Test | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Acceptance Criteria - Soaked CBR ≥ 40 | Method - Soaked CBR test (NZS:4407:2015:3.15) | Frequency - | Responsible Person - Supervisor | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Acceptance Criteria - Principal Approval
Materials: GAP 65 Pre-treatment Material - Production Property Test | Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Sand Equivalent Test (NZS:4407:2015, 3.6) |  | Supervisor | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: GAP 65 Pre-treatment Material - Production Property Test | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Acceptance Criteria - Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Method - Sand Equivalent Test (NZS:4407:2015, 3.6) | Frequency - | Responsible Person - Supervisor | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Method - Contractor and Principal peer review
Materials: M/4 AP40 Material - Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide |  |  |  |  | Sampling Worksheet | [6 empty] | Materials: M/4 AP40 Material - Aggregate Sampling | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide | Acceptance Criteria - | Method - | Frequency - | Responsible Person - | Verifying Document - Sampling Worksheet | Conduct - | Witness - | Produce Record - | Approval - | Hold Point Y/N - | Witness Point Y/N - | Frequency - per design
Materials: M/4 AP40 Material - Source Property Test (1) | Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | less than 10% fines passing 2.36mm sieve size under a load of 130kN | Curshing Resistance Test (NZS 4407:1991, Test 3.10) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Material - Source Property Test (1) | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10) | Frequency - One test for every 10,000m³ of source material | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Responsible Person -
Materials: M/4 AP40 Material - Source Property Test (2) | Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | AA, AB, AC, BA, BB or CA | Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Material - Source Property Test (2) | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | Acceptance Criteria - AA, AB, AC, BA, BB or CA | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | Frequency - One test for every 10,000m³ of source material | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Verifying Document - Pavement Rehabilitation Design Report
Materials: M/4 AP40 Material - Source Property Test (3) | California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Soaked CBR ≥ 80% | California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Material - Source Property Test (3) | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Acceptance Criteria - Soaked CBR ≥ 80% | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | Frequency - One test for every 10,000m³ of source material | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Conduct - C or S
Materials: M/4 AP40 Material - Production Property Test (1) | Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Material - Production Property Test (1) | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Witness -
Materials: M/4 AP40 Material - Production Property Test (2) | Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Broken Face Test (NZS:4407: 1991, Test 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Material - Production Property Test (2) | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Method - Broken Face Test (NZS:4407: 1991, Test 3.4) | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Produce Record - C
Materials: M/4 AP40 Material - Production Property Test (3) | Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S |  | Sp or S | E | Y |  | Materials: M/4 AP40 Material - Production Property Test (3) | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Responsible Person - Quality Controller | Verifying Document - Test Report | Conduct - Sp or C or S | Witness - | Produce Record - Sp or S | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Approval - E
Materials: Geotextile - Geotextile (Strength Class C) A29 or greater | TNZ F7 Specification | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S |  | Sp or S | C |  | Y | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater | Controlling Documents - TNZ F7 Specification | Acceptance Criteria - Details on Docket | Method - Visual inspection | Frequency - Per Delivery | Responsible Person - Quality Controller | Verifying Document - MDS | Conduct - Sp or S | Witness - | Produce Record - Sp or S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Hold Point Y/N - Y
Production Testing of stabilised material - OMC/MDD | TNZ B/2 section 7.5 | To obtain OMC CHAR(AMP) MDD | NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Once on commencement and then each stablilised layer at one test per 5000m2 | Quality Controller | Test report | S or C | C | S or C | C |  | Y | Production Testing of stabilised material - OMC/MDD | Controlling Documents - TNZ B/2 section 7.5 | Acceptance Criteria - To obtain OMC CHAR(AMP) MDD | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2 | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S or C | Witness - C | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Witness Point Y/N -
Production Testing of stabilised material - Solid Density | TNZ B/2 section 7.5 | For info. and use in MDD calculation | NZS 4407; test 3.7.1 | Once on commencement and if any materials change | Quality Controller | Test report | S or C | C | S or C | C |  | Y | Production Testing of stabilised material - Solid Density | Controlling Documents - TNZ B/2 section 7.5 | Acceptance Criteria - For info. and use in MDD calculation | Method - NZS 4407; test 3.7.1 | Frequency - Once on commencement and if any materials change | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S or C | Witness - C | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Materials: GAP 65 Pre-treatment Material - Aggregate Sampling
Project survey setting out | Reference from Project Drawings |  | Survey/Mobile Roads, Marks with Dazzle | Chainages for every different pavement sections | Subcontractor/ Engineer | Construction drawings | S or C | C | S or C | C |  | Y | Project survey setting out | Controlling Documents - Reference from Project Drawings | Acceptance Criteria - | Method - Survey/Mobile Roads, Marks with Dazzle | Frequency - Chainages for every different pavement sections | Responsible Person - Subcontractor/ Engineer | Verifying Document - Construction drawings | Conduct - S or C | Witness - C | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
Pre-treatment Repair Method Selection | Site specifics to be confirmed | Confirm scala acceptance criteria based on treatment type | Scala Penetrometer on Excavation Floor | As required | Quality Controller | Agreed treatment plan | S | C | S | E |  | Y | Pre-treatment Repair Method Selection | Controlling Documents - Site specifics to be confirmed | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type | Method - Scala Penetrometer on Excavation Floor | Frequency - As required | Responsible Person - Quality Controller | Verifying Document - Agreed treatment plan | Conduct - S | Witness - C | Produce Record - S | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Acceptance Criteria -
Digout of Patches to repair | Higgins SOP 0128 - Digout Repair | 340mm deep | Visual inspection | As required | Quality Controller | Dig out site records/ Asbuilt | S | C | S | C |  | Y | Digout of Patches to repair | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - 340mm deep | Method - Visual inspection | Frequency - As required | Responsible Person - Quality Controller | Verifying Document - Dig out site records/ Asbuilt | Conduct - S | Witness - C | Produce Record - S | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Method -
Subgrade material hardness Check base of excavation | Higgins SOP 0128 - Digout Repair | Scala > 3 blows per 100mm or Proof roll CHAR(LESS)5mm | Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful | As required depending on size of digout | Quality Controller | Test report | S/C | C | S/C | E |  | Y | Subgrade material hardness Check base of excavation | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll CHAR(LESS)5mm | Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful | Frequency - As required depending on size of digout | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S/C | Witness - C | Produce Record - S/C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Frequency -
Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | TNZ F7 Specification | Meet TNZ F7 Spec. | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S |  | C | C |  | Y | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | Controlling Documents - TNZ F7 Specification | Acceptance Criteria - Meet TNZ F7 Spec. | Method - Visual inspection | Frequency - Per Delivery | Responsible Person - Quality Controller | Verifying Document - Certificate of conformance | Conduct - Sp or S | Witness - | Produce Record - C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Responsible Person -
Place and compact GAP65 in digout area | Higgins SOP 0128 - Digout Repair | Clegg value > 45 | Clegg Test | Min. 2 per digout | Quality Controller | Test report | S/C | C | S/C | E |  | Y | Place and compact GAP65 in digout area | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - Clegg value > 45 | Method - Clegg Test | Frequency - Min. 2 per digout | Responsible Person - Quality Controller | Verifying Document - Test report | Conduct - S/C | Witness - C | Produce Record - S/C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Verifying Document - Sampling Worksheet
Place M/4 AP40 Material | TNZ B/2 (section 7.2) | Evenly spread, no segregation, placed near optimium moisture content | Visual Inspection | On completion of placement | Quality Controller | Photographs and Daily Site Record | S or C |  | S or C | C |  | Y | Place M/4 AP40 Material | Controlling Documents - TNZ B/2 (section 7.2) | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content | Method - Visual Inspection | Frequency - On completion of placement | Responsible Person - Quality Controller | Verifying Document - Photographs and Daily Site Record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - C | Hold Point Y/N - | Witness Point Y/N - Y | Conduct - C or S
Addition of Water | TNZ B/2 (section 7.5) | 90-100% OWC | Nuclear Densometer Testing prior to Stabilisation | ≥1 per 1000m² lot | Quality Controller | NDM Record | S or C |  | S | S or C |  | Y | Addition of Water | Controlling Documents - TNZ B/2 (section 7.5) | Acceptance Criteria - 90-100% OWC | Method - Nuclear Densometer Testing prior to Stabilisation | Frequency - ≥1 per 1000m² lot | Responsible Person - Quality Controller | Verifying Document - NDM Record | Conduct - S or C | Witness - | Produce Record - S | Approval - S or C | Hold Point Y/N - | Witness Point Y/N - Y | Witness -
Compaction Acceptance | Compaction (7.6) - TNZ B/2 | Mean value ≥ 98% and Minimum Value ≥ 95% | Nuclear Densometer Testing | ≥ 5 tests per 1000m² lot | Quality Controller | NDM Record | S or C |  | S or C | E | Y |  | Compaction Acceptance | Controlling Documents - Compaction (7.6) - TNZ B/2 | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95% | Method - Nuclear Densometer Testing | Frequency - ≥ 5 tests per 1000m² lot | Responsible Person - Quality Controller | Verifying Document - NDM Record | Conduct - S or C | Witness - | Produce Record - S or C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Produce Record -
Surface Shape | Compaction (7.7) - TNZ B/2 | ± 10mm deviation along a 3m straight edge, No water ponding | 3m Straight Edge | during construction and prior to seal | Supervisor | Photographs | S or C | C and E | S or C | E |  | Y | Surface Shape | Controlling Documents - Compaction (7.7) - TNZ B/2 | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding | Method - 3m Straight Edge | Frequency - during construction and prior to seal | Responsible Person - Supervisor | Verifying Document - Photographs | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Approval - S
Cross Fall | Compaction (5.1) - TNZ B/2 | 0.5% ≤ X ≤ -0.5% | 3m straight edge or Survey Asbuilt | during construction and prior to seal | Supervisor | Cross Fall Records/Survey Asbuilts | S or C | C and E | S or C | E |  | Y | Cross Fall | Controlling Documents - Compaction (5.1) - TNZ B/2 | Acceptance Criteria - 0.5% ≤ X ≤ -0.5% | Method - 3m straight edge or Survey Asbuilt | Frequency - during construction and prior to seal | Responsible Person - Supervisor | Verifying Document - Cross Fall Records/Survey Asbuilts | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Hold Point Y/N -
Degree of Saturation, DOS | , Pre-sealing requirements (12) - TNZ B/2 Notes: 2005 | ≤80%, however 65% is ideal | Nuclear Densometer Testing | ≥5 tests per 1000m² lot | Quality Controller | NDM Record | S or C | C and E | S or C | E |  | Y | Degree of Saturation, DOS | Controlling Documents - , Pre-sealing requirements (12) - TNZ B/2 Notes: 2005 | Acceptance Criteria - ≤80%, however 65% is ideal | Method - Nuclear Densometer Testing | Frequency - ≥5 tests per 1000m² lot | Responsible Person - Quality Controller | Verifying Document - NDM Record | Conduct - S or C | Witness - C and E | Produce Record - S or C | Approval - E | Hold Point Y/N - | Witness Point Y/N - Y | Witness Point Y/N -
Pavement Rehabilitation Construction Completion Report | Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Engineer Approval | Visual Inspection | ≤2 months of 1st Coat Seal | Quality Controller/ Contract Manager | Signed Report | C | C, S and E | C | E | Y |  | Pavement Rehabilitation Construction Completion Report | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Acceptance Criteria - Engineer Approval | Method - Visual Inspection | Frequency - ≤2 months of 1st Coat Seal | Responsible Person - Quality Controller/ Contract Manager | Verifying Document - Signed Report | Conduct - C | Witness - C, S and E | Produce Record - C | Approval - E | Hold Point Y/N - Y | Witness Point Y/N - | Materials: GAP 65 Pre-treatment Material - Source Property Test
Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
Acceptance Criteria - Soaked CBR ≥ 40
Method - Soaked CBR test (NZS:4407:2015:3.15)
Frequency -
Responsible Person - Supervisor
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: GAP 65 Pre-treatment Material - Production Property Test
Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
Acceptance Criteria - Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
Frequency -
Responsible Person - Supervisor
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Material - Aggregate Sampling
Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
Acceptance Criteria -
Method -
Frequency -
Responsible Person -
Verifying Document - Sampling Worksheet
Conduct -
Witness -
Produce Record -
Approval -
Hold Point Y/N -
Witness Point Y/N -
Materials: M/4 AP40 Material - Source Property Test (1)
Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
Frequency - One test for every 10,000m³ of source material
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Material - Source Property Test (2)
Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
Acceptance Criteria - AA, AB, AC, BA, BB or CA
Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
Frequency - One test for every 10,000m³ of source material
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Material - Source Property Test (3)
Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
Acceptance Criteria - Soaked CBR ≥ 80%
Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
Frequency - One test for every 10,000m³ of source material
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Material - Production Property Test (1)
Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Material - Production Property Test (2)
Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: M/4 AP40 Material - Production Property Test (3)
Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
Responsible Person - Quality Controller
Verifying Document - Test Report
Conduct - Sp or C or S
Witness -
Produce Record - Sp or S
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
Controlling Documents - TNZ F7 Specification
Acceptance Criteria - Details on Docket
Method - Visual inspection
Frequency - Per Delivery
Responsible Person - Quality Controller
Verifying Document - MDS
Conduct - Sp or S
Witness -
Produce Record - Sp or S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Production Testing of stabilised material - OMC/MDD
Controlling Documents - TNZ B/2 section 7.5
Acceptance Criteria - To obtain OMC CHAR(AMP) MDD
Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S or C
Witness - C
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Production Testing of stabilised material - Solid Density
Controlling Documents - TNZ B/2 section 7.5
Acceptance Criteria - For info. and use in MDD calculation
Method - NZS 4407; test 3.7.1
Frequency - Once on commencement and if any materials change
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S or C
Witness - C
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Project survey setting out
Controlling Documents - Reference from Project Drawings
Acceptance Criteria -
Method - Survey/Mobile Roads, Marks with Dazzle
Frequency - Chainages for every different pavement sections
Responsible Person - Subcontractor/ Engineer
Verifying Document - Construction drawings
Conduct - S or C
Witness - C
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Pre-treatment Repair Method Selection
Controlling Documents - Site specifics to be confirmed
Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
Method - Scala Penetrometer on Excavation Floor
Frequency - As required
Responsible Person - Quality Controller
Verifying Document - Agreed treatment plan
Conduct - S
Witness - C
Produce Record - S
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Digout of Patches to repair
Controlling Documents - Higgins SOP 0128 - Digout Repair
Acceptance Criteria - 340mm deep
Method - Visual inspection
Frequency - As required
Responsible Person - Quality Controller
Verifying Document - Dig out site records/ Asbuilt
Conduct - S
Witness - C
Produce Record - S
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Subgrade material hardness Check base of excavation
Controlling Documents - Higgins SOP 0128 - Digout Repair
Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll CHAR(LESS)5mm
Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful
Frequency - As required depending on size of digout
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S/C
Witness - C
Produce Record - S/C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
Controlling Documents - TNZ F7 Specification
Acceptance Criteria - Meet TNZ F7 Spec.
Method - Visual inspection
Frequency - Per Delivery
Responsible Person - Quality Controller
Verifying Document - Certificate of conformance
Conduct - Sp or S
Witness -
Produce Record - C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Place and compact GAP65 in digout area
Controlling Documents - Higgins SOP 0128 - Digout Repair
Acceptance Criteria - Clegg value > 45
Method - Clegg Test
Frequency - Min. 2 per digout
Responsible Person - Quality Controller
Verifying Document - Test report
Conduct - S/C
Witness - C
Produce Record - S/C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Place M/4 AP40 Material
Controlling Documents - TNZ B/2 (section 7.2)
Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
Method - Visual Inspection
Frequency - On completion of placement
Responsible Person - Quality Controller
Verifying Document - Photographs and Daily Site Record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - C
Hold Point Y/N -
Witness Point Y/N - Y
Addition of Water
Controlling Documents - TNZ B/2 (section 7.5)
Acceptance Criteria - 90-100% OWC
Method - Nuclear Densometer Testing prior to Stabilisation
Frequency - ≥1 per 1000m² lot
Responsible Person - Quality Controller
Verifying Document - NDM Record
Conduct - S or C
Witness -
Produce Record - S
Approval - S or C
Hold Point Y/N -
Witness Point Y/N - Y
Compaction Acceptance
Controlling Documents - Compaction (7.6) - TNZ B/2
Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
Method - Nuclear Densometer Testing
Frequency - ≥ 5 tests per 1000m² lot
Responsible Person - Quality Controller
Verifying Document - NDM Record
Conduct - S or C
Witness -
Produce Record - S or C
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -
Surface Shape
Controlling Documents - Compaction (7.7) - TNZ B/2
Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
Method - 3m Straight Edge
Frequency - during construction and prior to seal
Responsible Person - Supervisor
Verifying Document - Photographs
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Cross Fall
Controlling Documents - Compaction (5.1) - TNZ B/2
Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
Method - 3m straight edge or Survey Asbuilt
Frequency - during construction and prior to seal
Responsible Person - Supervisor
Verifying Document - Cross Fall Records/Survey Asbuilts
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Degree of Saturation, DOS
Controlling Documents - , Pre-sealing requirements (12) - TNZ B/2 Notes: 2005
Acceptance Criteria - ≤80%, however 65% is ideal
Method - Nuclear Densometer Testing
Frequency - ≥5 tests per 1000m² lot
Responsible Person - Quality Controller
Verifying Document - NDM Record
Conduct - S or C
Witness - C and E
Produce Record - S or C
Approval - E
Hold Point Y/N -
Witness Point Y/N - Y
Pavement Rehabilitation Construction Completion Report
Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
Acceptance Criteria - Engineer Approval
Method - Visual Inspection
Frequency - ≤2 months of 1st Coat Seal
Responsible Person - Quality Controller/ Contract Manager
Verifying Document - Signed Report
Conduct - C
Witness - C, S and E
Produce Record - C
Approval - E
Hold Point Y/N - Y
Witness Point Y/N -