## QA Folder Structure
QA Folder Structure | [5 empty] | Checklists
Job Details
Site QA | Rough-In
|  | Ground Floor |  | GEF-G
Duct Installation Check list [F]
Sign Off
|  |  |  | CPEF-G.1 |  | Duct Installation Check list [F]
Sign Off
|  |  |  | PRSF-G |  | Duct Installation Check list [F]
Sign Off
|  |  |  | PREF-G |  | Duct Installation Check list [F]
Sign Off
|  |  |  | TEF-G.1 |  | Duct Installation Check list [F]
Sign Off
|  |  |  | TEF-G.2 |  | Duct Installation Check list [F]
Sign Off
OAF-G
Duct Installation Check list [F]
Sign Off
Level-1
|  |  |  | A1.01 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.02 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.03 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.04 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.05 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.06 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.07 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.08 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A1.09 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | Lower Communal Space |  | Duct Installation Check list [F]
Sign Off
|  |  |  | Upper Communal Space |  | Duct Installation Check list [F]
Sign Off
Level-2
|  |  |  | A2.01 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.02 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.03 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.04 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.05 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.06 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.07 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.08 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.09 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.10 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.11 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A2.12 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
Level-3
|  |  |  | A3.01 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.02 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.03 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.04 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.05 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.06 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.07 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.08 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.09 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.10 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.11 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A3.12 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
Level-4
|  |  |  | A4.01 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.02 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.03 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.04 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.05 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.06 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.07 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.08 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.09 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.10 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A4.11 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  | Level-5 |  | A5.01 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.02 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.03 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.04 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.05 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.06 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.07 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.08 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.09 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
|  |  |  | A5.10 |  | Ventilation Checklist 1 Rough In [C]
Flatpack Installation Checklist [O]
Access Panel 1 Rough In [D]
Sign Off
Apartment Ceiling Closure
| Fit-Off |  | Ground Floor |  | GEF-G
Base building Fit-Off Checklist [G]
Sign Off
[5 empty] | CPEF-G.1 |  | Base building Fit-Off Checklist [G]
Sign Off
[5 empty] | PRSF-G |  | Base building Fit-Off Checklist [G]
Sign Off
[5 empty] | PREF-G |  | Base building Fit-Off Checklist [G]
Sign Off
[5 empty] | TEF-G.1 |  | Base building Fit-Off Checklist [G]
Sign Off
[5 empty] | TEF-G.2 |  | Base building Fit-Off Checklist [G]
Sign Off
OAF-G
Duct Installation Check list [F]
Sign Off
Level-1
[5 empty] | A1.01 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.02 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.03 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.04 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.05 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.06 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.07 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.08 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A1.09 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | Lower Communal Space |  | Base building Fit-Off Checklist [G]
Sign Off
[5 empty] | Upper Communal Space |  | Base building Fit-Off Checklist [G]
Sign Off
Level-2
[5 empty] | A2.01 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.02 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.03 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.04 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.05 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.06 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.07 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.08 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.09 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.10 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.11 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A2.12 |  | Apartment Fit-Off Checklist [H]
Sign Off
Level-3
[5 empty] | A3.01 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.02 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.03 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.04 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.05 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.06 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.07 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.08 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.09 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.10 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.11 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A3.12 |  | Apartment Fit-Off Checklist [H]
Sign Off
Level-4
[5 empty] | A4.01 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.02 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.03 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.04 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.05 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.06 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.07 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.08 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.09 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.10 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A4.11 |  | Apartment Fit-Off Checklist [H]
Sign Off
|  |  | Level-5 |  | A5.01 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.02 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.03 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.04 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.05 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.06 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.07 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.08 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.09 |  | Apartment Fit-Off Checklist [H]
Sign Off
[5 empty] | A5.10 |  | Apartment Fit-Off Checklist [H]
Sign Off
Commissioning
|  |  | Ground Floor |  | GEF-G
Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | CPEF-G.1 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | PRSF-G |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | PREF-G |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | TEF-G.1 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | TEF-G.2 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | OAF-G |  | Ventilation Checklist Commissioning [ J]
Sign Off
Level-1
[5 empty] | A1.01 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.02 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.03 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.04 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.05 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.06 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.07 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.08 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A1.09 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | Lower Communal Space |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | Upper Communal Space |  | Ventilation Checklist Commissioning [ J]
Sign Off
Level-2
[5 empty] | A2.01 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.02 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.03 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.04 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.05 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.06 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.07 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.08 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.09 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.10 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.11 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A2.12 |  | Ventilation Checklist Commissioning [ J]
Sign Off
Level-3
[5 empty] | A3.01 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.02 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.03 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.04 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.05 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.06 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.07 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.08 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.09 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.10 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.11 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A3.12 |  | Ventilation Checklist Commissioning [ J]
Sign Off
Level-4
[5 empty] | A4.01 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.02 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.03 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.04 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.05 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.06 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.07 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.08 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.09 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.10 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A4.11 |  | Ventilation Checklist Commissioning [ J]
Sign Off
|  |  | Level-5 |  | A5.01 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.02 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.03 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.04 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.05 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.06 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.07 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.08 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.09 |  | Ventilation Checklist Commissioning [ J]
Sign Off
[5 empty] | A5.10 |  | Ventilation Checklist Commissioning [ J]
Sign Off
| Penetrations |  | Ground Floor | FD-G.01 (Communal Waste bins) |  | Fire Damper Checklist -Intumecent FD [K]
|  |  |  | FD-G.02 (Residential Waste Room) |  | Fire Damper Checklist -Intumecent FD [K]
|  |  |  | FD-G.03 (Bulky Waste) |  | Fire Damper Checklist -Intumecent FD [K]
|  |  |  | FD-G.04 (Main switch Room) |  | Fire Damper Checklist -Intumecent FD [K]
|  |  |  | FD-G.05 (Main Switch room) |  | Fire Damper Checklist -Intumecent FD [K]
OHS |  |  |  |  | prepopulate | Prestart OH&S Documents
[5 empty] | Ability to Add | Toolbox meeting
[5 empty] | Ability to Add | Toolbox meeting
[5 empty] | Ability to Add | Toolbox meeting
[5 empty] | Ability to Add | Toolbox meeting
[5 empty] | Ability to Add | Toolbox meeting
| OH&S - Accident/Incident Reports |  |  |  | Ability to Add | Incident Report - Checklist
Variations
[5 empty] | Ability to Add | Variation
[5 empty] | Ability to Add | Variation
[5 empty] | Ability to Add | Variation
[5 empty] | Ability to Add | Variation
[5 empty] | Ability to Add | Variation

## Checklists
checklist | Ventilation Checklist 1 Rough In [C]
| Is the installation area unobstructed? | Pass/Fail / N/A
| Fans installed within ceiling areas are in the correct location as per Mechanical Drawings | Pass/Fail / N/A
| Fans Installed correctly with rubber isolation pads | Pass/Fail / N/A
| All Flex has been run to correct location | Pass/Fail / N/A
| All flex are hung independent of other services and supported by intact load spreaders | Pass/Fail / N/A
| Butterfly dampers are installed on the PODs grille neck and they are in a fully opened position and air tight sealed | Pass/Fail / N/A
Pass/Fail / N/A
section | Sign Off |  | Sign off required
Sign-Off Completed as per below (Pass once complete)
Contract/Subcontractor Assessor Sign Off
Builder Representative Sign Off
Request Sign-Off(s) + Click to Add Signature(s)
Inspection Date:
checklist | Access Panel 1 Rough In [D]
| Access Panel location has been marked on floor as per RCP | Pass/Fail / N/A
| Access panel location allows sufficient access equipment | Pass/Fail / N/A
| All other other services do not impede access | Pass/Fail / N/A
section | Sign Off |  | Sign off required
Sign-Off Completed as per below (Pass once complete)
Contract/Subcontractor Assessor Sign Off
Builder Representative Sign Off
Request Sign-Off(s) + Click to Add Signature(s)
Inspection Date:
checklist | Duct Installation Check List [F]
| Is the installation area unobstructed? | Pass/Fail / N/A
| Are drawings on site the latest issue | Pass/Fail / N/A
| Are plant and equipment location correct | Pass/Fail / N/A
| Duct size and location correct | Pass/Fail / N/A
| Material and gauge correct | Pass/Fail / N/A
| Is correct support method being used - Risers are supported at each level. | Pass/Fail / N/A
| Is correct jointing method being used | Pass/Fail / N/A
| Are joints completed and cleated installed on flanges | Pass/Fail / N/A
| Is correct joint sealant being used | Pass/Fail / N/A
| Are fire dampers installed and break away joint complete | Pass/Fail / N/A
| Are canvas connections to equipment sealed and aligned | Pass/Fail / N/A
| Is ductwork fire rating complete | Pass/Fail / N/A
| Are all spigots installed and dampers fully open | Pass/Fail / N/A
| Are all access panels for fire damper access installed and closed | Pass/Fail / N/A
| Are the correct fixings used for fan installation? | Pass/Fail / N/A
| Is the fan secured correctly to hanging equipment? | Pass/Fail / N/A
| Is the hanging equipment correctly installed and secured? | Pass/Fail / N/A
| Is the ductwork connected to the fan as specified in workshop drawings? | Pass/Fail / N/A
| Are the cables connected as per electrical drawings and manufacturer's specifications? | Pass/Fail / N/A
| Is ductwork installation complete | Pass/Fail / N/A
checklist | Base building Fit-Off Checklist [G]
| Supply grilles fitted | Pass/Fail / N/A
| VCD is installed | Pass/Fail / N/A
| Exhaust grilles fitted | Pass/Fail / N/A
| All fire dampers provided with an access panel as per mechanical drawings | Pass/Fail / N/A
Sign-Off Completed as per below (Pass once complete)
Inspection Date
Contract/Subcontractor Assessor Sign Off
Builder Representative Sign Off
Request Sign-Off(s) + Click to Add Signature(s)
checklist | Apartment Fit-Off Checklist [H]
| Ensuite exhaust grilles installed | Pass/Fail / N/A
| Toilet exhaust grilles installed | Pass/Fail / N/A
| Range hood duct connected and taped to ensure air tight | Pass/Fail / N/A
| Access panels placed as per drawings | Pass/Fail / N/A
| "External louvers installed all gaps sealed between plenum box and wall/ louver flange to wall , photo evidence provided for below 1.Box sealed internally and the gap between the box and wall is sealed 2.Louver flanges sealed to the external box " | Pass/Fail / N/A
Sign-Off Completed as per below (Pass once complete)
Inspection Date
Contract/Subcontractor Assessor Sign Off
Builder Representative Sign Off
Request Sign-Off(s) + Click to Add Signature(s)
checklist | Ventilation Checklist Commissioning [ J]
| Fan has been tested and is operational? | Pass/Fail / N/A
| Adequate flow has been achieved in areas the fan is serving to? | Pass/Fail / N/A
| Does the fan interlocking working correctly with lights ? | Pass/Fail / N/A
| Range hood has been tested and is operational? | Pass/Fail / N/A
| Provide evidence of airflow reading | Pass/Fail / N/A
| Visual Survey | Pass/Fail / N/A
Sign-Off Completed as per below (Pass once complete)
Inspection Date
Contract/Subcontractor Assessor Sign Off
Builder Representative Sign Off
Request Sign-Off(s) + Click to Add Signature(s)
checklist | Fire Damper Checklist -Intumecent FD [K]
Fire damper is mechanically fixed to the casing with min 1 screw per side and min 200mm spacing betwwen screws
| Penetration details have been captured | Pass/Fail
| Gaps between the fire damper and wall no greater than 25mm and is filled with Killargo Intumescent Sealant with no cracking visible | Pass/Fail
| Killargo fire rated mastic has been applied to entire perimeter of fire damper cell on both sides. No evidence of cracking. | Pass/Fail
| Casing perimeter is sealed with Killargo intumescent sealant. No evidence of cracking. | Pass/Fail
| Sheet metal thickness is 0.7mm or greater. | Pass/Fail
| Ductwork is connected to either side of the casing with nylon bolts on the flanges as per the AS1682.2 break away joint method. Bolts do not exceed an 8mm diameter. | Pass/Fail
| Access panel is provided to conveniently access fire damper for visual and/or maintenance inspections. | Pass/Fail
| Fire damper labelling in accordance with AS1682.2 has been placed and clearly identifies the fire damper | Pass/Fail
| Pictures attached | Pass/Fail
| Signature (Contract/Subcontractor Assessor) | Pass/Fail
| Signature (Builder Representative) | Pass/Fail
Pictures/Comments attached below
Notes/Additional Comments
Sign-Off Completed as per below (Pass once complete)
Contract/Subcontractor Assessor Sign Off
Builder Representative Sign Off
Request Sign-Off(s) + Click to Add Signature(s)
checklist | Flatpack Installation Checklist [O]
| Flatpack duct is installed as per approved mechanical shop drawings | Pass/Fail
| Internal side of flatpack duct and fittings are clear from debris and dust | Pass/Fail
| Is flatpack supported from ceiling using metal hangers or metal support clips at every 2m intervals so that the flatpacks are not sagging? | Pass/Fail
| Wherever the flatpacks are screwed into, ensure properly sealed | Pass/Fail
| Flatpack joints & fittings are properly sealed. | Pass/Fail
| Are correct type of fittings used? | Pass/Fail
| Visual inspection | Pass/Fail

## OH&S - Miscellaneous Checklists
type | name | value
checklist | Job Details
checkpoint | Site Info |  | Dep True
text | Site Address
text | Builders Details
text | Project Managers Details
text | Site Managers Details
checkpoint | latest drawings (attached or referenced) |  | Dep True
checkpoint | Scope of Works Attached |  | Dep True
checkpoint | Additional Pre-Start Docs (attached or referenced) |  | Dep True
type | name | value
checklist | Prestart OH&S Documents
checkpoint | All Pre-start OH&S Documentation Completed, Reviewed & Attached
label | Public Liability and Work Cover Insurances
label | Company Safety Plan
label | SWMS & MSDS (Attached below)
label | Additional Prestart OH&S Documents
type | name | value
checklist | Toolbox meeting
checkpoint | Toolbox meeting completed & Specific Document(s) attached
text | Date
text | Site Address
text | Toolbox meeting topic
text | Toolbox Item 1 - (Add any resolutions below item)
text | Toolbox Item 2 - (Add any resolutions below item)
text | Toolbox Item 3 - (Add any resolutions below item)
text | Toolbox Item 4 - (Add any resolutions below item)
checkpoint | Toolbox meeting pdf attached (Add below)
label | Broad Air takes safety seriously and we encourage all persons representing the company to speak up if something is not right. If you find yourself unsure about something when it comes to safety, ASK! There is no such thing as a stupid question.
checkpoint | Sign Off – By signing this page you acknowledge your attendance of this toolbox meeting and your co-operation with our policies & procedures
holdpoint | Click to 'Add' signature's of each attendee
type | name | value
checklist | Variation (21/05/2020)
checkpoint | Variation Details Complete (Pass once inputted)
text | Variation Name
text | Variation Description
text | Materials & labour breakdown (Names, Hours & Material(s)/Quantities)
text | Acknowledgement (Who requested the work to be done)
text | Signature/Reference Mail (Who to send the variation too)
checkpoint | Supporting Documentation (Attached or Referenced)
label | Add Photos/Comments of variation work below
checkpoint | Variation Sign-Off - Click to Add signatures below
button | Broad Air Representative Signature Added below | Yes, No
button | Builder Representative Signature Added below | Yes, No
holdpoint | Click to Add Signatures of Wilson & Builder's Representative
type | name | values | prefix | postfix
checklist | Incident Report - Checklist
section | Injured Workers Details
checkpoint | Injured Worker
text | Name of Employer of injured Person(s) (If any):
text | Business address of Person/Organisation in charge of the equipment:
text | Full name of Employee:
text | Date of Birth:
button | Sex: | Female, Male
text | Residential address and telephone number (if known):
text | Occupation of Employee:
section | Incident Details
checkpoint | Incident
text | Date of Birth:
text | Place/Location where incident occurred:
text | Work/activity being performed at time of incident and equipment being used:
text | Brief description of incident:
text | Treatment given/action taken at the time of the incident: (Attach Statements below)
text | Name of Witnesses or Name of Person(s) who first attended the scene: (Attach Statements below)
text | Action taken/intended, if any, to prevent recurrence of the incident:
label | Add diagram or picture of incident below
section | Treatment Details
checkpoint | Details
button | Did the injury necessitate loss of time? | No, Yes
label | If "Yes" selected
text | Name the clinic/medical centre attended:
label | Attach WorkCover Certificate of Capacity (Attach below)
button | Was an ambulance required? | No, Yes
button | Was the incident reported to WorkSafe Victoria? | No, Yes
label | If "Yes" selected
text | WorkSafe Incident notification number is:
section | Form Details
checkpoint | Details of Person submitting this form
text | Name:
text | Position/Title:
text | Date:
button | Type of Injury (Filled out by OHS Manager): | LTI, MTI, FAI