## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Removal of Non-Compliant Cladding |  |  |  |  | Yes | Removal of Non-Compliant Cladding Checklist | 292bc74d-d39f-49ab-8c15-ad94fc112c68
checkpoint-status |  |  | checkpoint | Write panel number on existing panel to be removed
label | f8a659df-fa50-5d90-81e4-edf732a62298 |  | note | Photo's lodged to CONQA of panel to be removed with panel number visable to face
checkpoint-status |  |  | checkpoint | Removal of Non-Compliant comustable cladding panel
checkpoint-status |  |  | checkpoint | Check Latent condition of existing framing condition, consistent with IFC drawings
checkpoint-status |  |  | checkpoint | Check existing framing for compliant fasteners and fixings, as per IFC drawings
checkpoint-status |  |  | checkpoint | Check existing galvanised backpan and insulation is installed and present and free of damage
label | f774e60c-0da4-516e-a01f-262c80b3a081 |  | note | Photo's lodged to CONQA of removed combustable panel with framing present
checklist-flat |  |  | checklist | Fabrication |  |  |  |  | Yes | Fabrication Checklist | 307872a4-856b-4b11-9d84-7b13e3df4606
checkpoint-status |  |  | checkpoint | Panel Supplied by others is free of damage, no visable scratches to protective etc prior to processing
checkpoint-status |  |  | checkpoint | Panel Supplied by others delivery docket and labelling match colour nominated within the architectural elevation drawings (A-1204 to A-1209)
checkpoint-status |  |  | checkpoint | Panels routered and folded as per dimension in production drawings
checkpoint-status |  |  | checkpoint | Silicone used for stiffener is Dowsil XXX cartridge cylinder as per DOWSIL XXXX.PDF as nominited in BG&E XXXXX.PDF
checkpoint-status |  |  | checkpoint | Stiffener installed is 24x25x1.6mm RHS (soffit panels) & 40x40x3mm RHS (wall panels) as per BG&E structural assessment - Mondoclad solid aluminium cladding Rev 00
checkpoint-status |  |  | checkpoint | Fasteners for Z Angles installed as per BG&E structural assessment - Mondoclad solid aluminium cladding Rev 00
checkpoint-status |  |  | checkpoint | Panels loaded on truck free of damage
label | cec3f703-671d-5f12-afb4-a28302d40543 |  | note | Photo's lodged to CONQA of back of panel including installed stiffener with panel number in view
label | 1cb95a99-fd79-59c5-bada-97bf7a425070 |  | note | Photo's lodged to CONQA of front of panel with intact protective film with panel number in view
checklist-flat |  |  | checklist | Receival of Panels Onsite |  |  |  |  | Yes | Receival of Panels Onsite Checklist | befd7415-a2e4-4d16-be79-72f01a008d68
checkpoint-status |  |  | checkpoint | Delivered panels have protective film and are free of damage, no scratches on protective film
checkpoint-status |  |  | checkpoint | Confirm panel size aligns with panel tracking sheet - corect colour, size and nominated location
checkpoint-status |  |  | checkpoint | Confirm stiffener installed as per design document BG&E structural assessment - Mondoclad solid aluminium cladding Rev 00
checkpoint-status |  |  | checkpoint | Delivery Docket provided
label | 7e3257b5-671c-53eb-b3fe-6a448fe2bf4e |  | note | Photo's lodged to CONQA of delivery docket
checklist-flat |  |  | checklist | Installation of Panels |  |  |  |  | Yes | Installation of Panels Checklist | e38ffa57-a8e9-4151-8ebc-9e46718f92e8
checkpoint-status |  |  | checkpoint | Substrate (Top hat, angles, box sections etc) Compliant - Modified where required
checkpoint-status |  |  | checkpoint | Panel is installed as documented in BG&E structural assessment - Mondoclad solid aluminium cladding Rev 00
checkpoint-status |  |  | checkpoint | Fasteners used and installed correctly as documented in BG&E structural assessment - Mondoclad solid aluminium cladding Rev 00
checkpoint-status |  |  | checkpoint | Final check - Express joints have consistent gap within design tolerance
checkpoint-status |  |  | checkpoint | Panels are free of damages / scratches
checkpoint-status |  |  | checkpoint | Remove Protective Film
label | 426294d3-176b-5223-b234-6d411e6363dd |  | note | Photo's lodged to CONQA of installed panel
checkpoint-status |  |  | checkpoint | Caulking installed as per colour and product nominated in BG&E structural assessment - Mondoclad solid aluminium cladding Rev 00
checklist-flat |  |  | checklist | Document Upload |  |  |  |  | Yes | Document Upload Checklist | f38d1517-8049-4e65-b67c-77c204498dc3
checkpoint-status |  |  | checkpoint | Document type selected and uploaded below
select | 520f2114-2eb0-576e-9fc6-c6b0f259f73f |  | dropdown | document type uploaded | Butterfly Test Record,Sealant Inspection Record,Sealant Deglazing Checklist,Sealant Silicone Application Checklist
text | 68933493-88c7-5a81-ac65-e300f38f9298 |  | textbox | date