## Sheet3
Inspection and Test Plan Te Ara o Te Ata Fill 15 & 16 - ITP - 011
This ITP has been prepared by |  |  | Reviewed by [as applicable] |  |  | Reviewed by DSR | [7 empty] | Approved by [as applicable]
Rev Number | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date |  |  | Name |  | Signature |  | Date
Rev 01 | Libby Whyte | L.W | 2022-10-18 | William McCracken | W.M | 2022-10-18
Rev 02
Rev 03
Rev 04
ITP NO: XXX |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref: |  |  | Rev.A
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Earthworks Fill | [7 empty] | Area Location / Work Breakdown: XXXX
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates |  | Site Engineer approved | DSR Engineer verification | Certified Complete (Date, relevant checklist title/lab report number etc)
Responsible [tick]
[5 empty] | Method/Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.1.0 Pre-construction approvals
1.1.1 | Construction Environmental Management Plan |  | MMA-ENV-RMP-RPT-15631 |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CEMP | H |  |  |  | Signed CEMP
1.1.2 | Construction Work Plan |  | CWP |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.1.3 | IANZ accredited testing organisation |  | Details of proposed testing organisation |  | Document Review | Once prior to works commencing |  | Designer review and approval required on all test equipment calibration certificates and frequency on testing | H | H |  |  | Test and supplier certificates
1.1.4 | IFC's specification |  | MMA-GES-GEO-E1-SPC-3859 |  | Document Review | Once prior to works commencing |  | Obtain copy of the earthworks specification and ground instrumetnation and monitoring plan | H | H |  |  | IFCspecifications or Written approval from PAB
1.1.5 | IFC drawings |  | Obtain IFC drawings |  | Document Review | Once prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC drawings or Written approval from PAB
1.1.6 | Approved earthworks model |  |  |  | Document Review | Every new Earthworks Model and prior to work commencing |  | Designer to confirm and approve models to be loaded on the equipment | H | H |  |  | ?
1.1.7 | Approval of stockpile location |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review & Approval | Prior to works commencing |  | Approved stockpile location | H | H |  |  | ?
1.2.0 Material compliance
1.2.1 | Structural fill |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4 Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8 | 1 test per 20,000m3 |  | Report Only | H | W |  | I | Test Report
1.2.2 | Buttress Fill |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4 | 1 test per 20,000m3 |  | Report Only | H | W |  | I | Test Report
1.2.3 | GAP 65 |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer Laboratory Triaxial Hydraulic Conductivity - ASTM D5084 – 16a Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus) | Determination of the dry density/water content - 3 tests per source. PSD - 3 no. tests per source + 1 test per 2,000m3. Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source |  | Report Only | H | W |  | I | Test Report
1.2.4 | GAP 65 |  | MMA-DES-GEO-E1-SPC-3859 |  | PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2) | 3 no. tests per source and 1 test per 2000m3 |  | Report Only | H | W |  | I | Test Report
1.2.5 | MSE Fill |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4 Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8 | 1 test per 2,500m3 |  | Report Only | H | W |  | I | Test Report
1.2.6 | MSE Fill |  | MMA-DES-GEO-E1-SPC-3859 |  | PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2) | 3 no. tests per source and 1 test per 2500m3 |  | Report Only | H | W |  | I | Test Report
1.2.7 | Drainage blanket and AP 7 |  | Covered in subsoil drainage ITP |  | NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer Laboratory Triaxial Hydraulic Conductivity - ASTM D5084 – 16a | PSD - 3 no. tests per source and 1 test per 1000m3 Hydraulic conductivity - 3 no. tests per source |  |  | H | W |  | I
1.2.8 | Cement stabilised GAP 65 |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1. | Determination of the dry density/water content - 3 nos. tests per source PSD - 3 no. tests per source + 1 test per 2,000 m3 UCS - 3 no. tests per source at adopted cement ratio. |  | Report Only | H | W |  | I | Test Report
1.2.9 | Cement stabilised structural fill |  | MMA-DES-GEO-E1-SPC-3859 |  | Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4 Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1. | Determination of the dry density/water content - 3 nos. tests per source Atterberg limit - 1 test per source and 1 test per 500 m3 UCS - 3 no. tests per source at adopted cement ratio. |  | Report Only | H | W |  | I | Test Report
1.3.0 Geosynthetics, geogrid and basal reinforcement - pre-construction
1.3.1 | Product name Name and address of producer/supplier Manufacturer’s compliance certificate |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review | Check each lot (1 roll) |  | Report Only | H | W |  |  | Supplier certificate
1.3.2 | Tensile strength (machine direction) - geogrid and basal reinforcement |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review | 1 test per production batch |  | Report Only | H | W |  |  | Test certificate
1.3.3 | Visual inspection - separation geotextiles, basal reinforcement |  | MMA-DES-GEO-E1-SPC-3859 |  | To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration. | Check each lot (1 roll) |  | Report Only | H | H |  |  | Approval checklist
1.3.4 | Visual inspection - geogrids |  | MMA-DES-GEO-E1-SPC-3859 |  | To inspect geogrid is the proper type and no tears, rips or other signs of deterioration. | Check each lot (1 roll) |  | Report Only | H | H |  |  | Approval checklist
1.4.0 Monitoring - pre-construction
1.4.1 | Monitoring prior to preload |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 |  | Baseline readings | Settlement marker, extensometer, profilometer, inclinometer and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month |  | Baseline Recorded and Submitted to the Designer; Within 24 hours of site inspection/observation/ measurement | H | H |  |  | Designer site diary - confirming baseline readings satisfactory
2.0 Construction
2.1.0 Pre-filling
2.1.1 | Set out extents of fill and check against design |  | Earthworks geometrics model |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
2.1.2 | Vegetation Clearance |  | MMA-DES-GEO-E1-SPC-3859 |  | Survey/visual | Fill area foot print |  | Ensure stripping of all organics, topsoil roots and the like is completed or in accordance with Designer advice. | H | H |  |  | Subgrade approval checksheet Designer site report (where advise given)
2.1.4 | Designer witness of in-situ subgrade prior to filling |  | MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection | Prior to Filling |  |  | H | H | W |  | Subgrade approval checksheet
2.1.5 | General Undercuts |  | MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection | Prior to Filling |  | Unsuitable material shall be undercut and tested as per specification or designers instruction | I |  |  |  | Subgrade approval checksheet
2.1.6 | Required undercuts for basal reinforcement installation |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection | Prior to Filling |  | Required undercut for basal reinforcement installation or designers instruction | H | H
2.1.7 | Basal reinforcement installation |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection of directional placement, panel length, laps, and damage | During basal reinforcement installation and every 100m² of geotextile installed. |  | Ensure geotextile used is the correct type, and directional placement, tensioning, laps, and spacing are correct | H | H
2.1.8 | Drainage blanket installation |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection | Prior to filling, and every 100m2 of geotextile installed. |  | Ensure drainage blanket has the correct thickness, geotextile type and laps are correct | H | H
2.1.9 | Construction of wick drains |  | IFC drawings and MMA-DES-GEO-E1-SPC-8804 |  | Visual inspection and subcontractor record review | During wick drain construction |  | Ensure wick drains are constructed in accordance with design | I | W |  |  | Wick drain check list
2.1.10 | Sub soil drainage |  | MMA-DES-GEO-E1-SPC-3859 |  | Inspection | During subsoil construction |  | Ensure all additional areas that require either primary or secondary collector drains are identified | I | I |  |  | Sub soil drainage ITP,
2.1.11 | Monitoring Equipment |  | MMA-DES-GEO-E1-SPC-8510 |  | Survey/ data logging | As outlined in MMA-DES-GEO-E1-SKT-4077 |  | install all monitoring equipment as outline in drawings specific to area. Ensure monitoring of data is recored and supplied to designers | W |  |  |  | Drill logs
2.2.0 Fill construction
2.2.1 | Filling operations |  | MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection | Daily |  | Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately | W
2.2.2 | Filling operations |  | MMA-DES-GEO-E1-SPC-3859 |  | Survey/visual | Daily |  | Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge | W
2.2.3 | insitu fill testing |  | MMA-DES-GEO-E1-SPC-3859 |  | Plateau Test | Structural Fill - 1 test per material type per earthworks zone, Buttress Fill - 1 test per material type per earthworks zone GAP65 - 1 test per material type per structure / location Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location |  | Reviewed by designer | W |  |  | I | Test report
2.2.4 | insitu fill testing |  | MMA-DES-GEO-E1-SPC-3859 |  | In situ moisture content and density | Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level Buttress fill - 1 test per 200m length, approx 1 per 6000 m3 GAP65 - 4 tests per lift per structure Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length |  | Structural Fill - average > 95% MDD All tests > 92%, Buttress fill - Average > 92 MDD All tests > 90%, GAP65 - Average > 98% MDD All tests > 95%, Cement Stabilised GAP65 - Average > 98% MDD All tests > 95%, Cement Stabilised Structural fill - average > 95% MDD All tests > 92% | W |  |  | I | Test report
2.2.5 | insitu fill testing |  | MMA-DES-GEO-E1-SPC-3859 |  | Undrained shear Strength | Structural fill - 1 test per layer per 1000m2 Buttress Fill - 1 Test per layer per 2000m2 Cement Stabilised Structural Fill - 1 test per layer per 500m2 | Structural fill - 1 test per layer per 1000m2 Average > 150kPa all tests > 120kPa Buttress Fill - 1 Test per layer per 2000m2 Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - 1 test per layer per 500m2 Average > 150kPa all tests > 120kPa | Structural fill - Average > 150kPa all tests > 120kPa Buttress Fill - Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - Average > 150kPa all tests > 120kPa | W |  |  | I | test report
2.2.6 | Subgrade Fill Testing |  | MMA-DES-GEO-E1-SPC-3859 |  | in situ moisture content and density (and/ or air voids) testing of compacted fill material | Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth |  | Surcharged Fills - 1 test at subgrade formation level per 50m length, Average > 95% mdd All tests > 92% MDD Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth, Average > 95% mdd All tests > 92% MDD | W |  |  | I | Test report
2.2.7 | Subgrade Fill Testing |  | MMA-DES-GEO-E1-SPC-3859 |  | Scala Penetrometer Surcharged Fills | 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width |  |  | W |  |  | I | Test report
2.2.8 | Subgrade Fill Testing |  | MMA-DES-GEO-E1-SPC-3859 |  | Benkelman beam and FWD Testing | Surcharged Fills - At subgrade formation level 10m interval in each wheel path Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path |  | Benkelman beam, 90th percentile D0 target :1.2mm No D0 deflection exceeding 1.40mm. FWD, 90th percentile D0 target:2.0mm No D0 deflection exceeding 2.2mm | W |  |  | I | Test report
2.2.9 | Subgrade Fill Testing |  | MMA-DES-GEO-E1-SPC-3859 |  | Laboratory Soaked CBR | Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level |  | Surcharged Fills, Fill 12 & 13, Cut Fill Transitions - ≥ CBR 7% | W |  |  | I | Test report
2.2.10 | Confirm testing requirements are meet for insitu fill |  | MMA-DES-GEO-E1-SPC-3859 |  | Summarise, interpret and review test records | Every test result |  | Summarised, interpreted and reviewed test records | H | H |  |  | Review of testing records
2.2.11 | Failed test result and remedial approval |  |  |  | Review and approval of remedial action | Every failed test and prior to remedial works |  | Approved remedial action | H | H
2.3.0 Preload/Surcharge (for embankments requiring preload)
2.3.1 | Visual inspection for rate of filling |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Inspection of fill height, rate of filling as per IFC drawing | To be monitored daily |  | Ensure maximum rate of filling is adhered to | H | W
2.3.2 | After 1m of fill placement. Await approval from Designer before placing more fill. |  | Instrumentation spec MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Review data and TARP levels before releasing HOLD. | Before releasing hold periods and allowing filling to continue. |  | In accordance with design | H | H |  |  | Designer site diary
2.3.3 | Removal of preload/surcharge |  | IFC drawings and ground instrumentation plan |  | Assessment of monitoring and instrumentation data | After completion of proposed hold period |  | Hold period of preload or surcharge should not be released until monitoring data has been reviewed and confirmed by Designer. | H | H
2.3.4 | Removal of preload/surcharge |  | IFC drawings and ground instrumentation plan |  | Preparation of preload/surcharge report | Every four weeks during earthworks operations and at the end and commencement of each earthworks season |  | Acceptance of report |  |  | H
2.4.0 Monitoring
2.4.1 | During earth filling/preloading/surcharging |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring during earth filling/preloading/surcharging | Plate settlement marker, extensometer, profilometer, water standpipe, inclinometer, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download |  | Monitoring data submitted to the Designer; Within 24 hours of site inspection/observation/ measurement |  | W
2.4.2 | During preload or surcharge hold period |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring during preloading or surcharge hold period | Plate settlement marker, extensometer and profilometer, water standpipe and inclinometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download |  | Monitoring data submitted to the Designer; Within 24 hours of site inspection/observation/ measurement |  | W
2.4.3 | At surcharge removal or hold period release |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring at surcharge removal or hold period release | Plate settlement marker, extensometer and profilometer, water standpipe, inclinometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following. |  | Monitoring data submitted to the Designer; Within 24 hours of site inspection/observation/ measurement |  | W
2.4.4 | Post-surcharge or post preload |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring post-surcharge or post preload | Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - weekly for one month then monthly |  | Monitoring data submitted to the Designer; Within 24 hours of site inspection/observation/ measurement |  | W
2.4.5 | After asphalt and barrier construction or culvert construction |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring after asphalt and barrier construction or culvert construction | Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - weekly for one month then monthly
2.5.0 Monitoring reports
2.5.1 | Preliminary inspection/monitoring report |  | MMA-DES-GEO-E1-SPC-8510 |  | Summary of site inspection / observation / measurement | Within one working day of site inspection/observation/measurement |  | Recorded and submitted to the Designer |  | W
2.5.2 | Final inspection/monitoring report |  | MMA-DES-GEO-E1-SPC-8510 |  | Full and certified results of monitoring data | Within five working day of reading the particular instrument |  | Recorded and submitted to the Designer |  | W
2.5.3 | Trigger level report |  | MMA-DES-GEO-E1-SPC-8510 |  | Details of trigger level exceedance or increasing trend Possible cause of exceedance or increasing trend Suggested response (e.g. increased frequency of monitoring) | Initial report within 24 hours of observation; Interrim report within 5 working days incorporating all additional monitoring records; Final report once the situation has been resolved through ongoing monitoring / mitigation to acceptable levels |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager |  | W
2.5.4 | Detailed monitoring report |  | MMA-DES-GEO-E1-SPC-8510 |  | Ground movements Groundwater and pore water pressures Variation in characteristics, including strength gain in underlying materials Comparison monitored results against baseline design predictions in both table and graphical format | Every 3 months during earthworks operations and at the end of each earthworks season |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager |  | W
2.5.5 | Preload report |  | MMA-DES-GEO-E1-SPC-8510 |  | Comparison between monitored results and baseline design predictions in both table and graphical format | Every 4 weeks during earthworks operations and at the end and commencement of each earthworks season |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager |  | W
2.5.6 | Completion report |  | MMA-DES-GEO-E1-SPC-8510 |  | Including all results for all instruments throughout construction period and inventory of which instruments have been decommissioned and those that can continue to be monitored beyond handover. | End of Defects Liability Period |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager |  | W
3.0 Post Construction
3.1 | Monitoring - Post construction to practical completion |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring - Post construction to practical completion | Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - weekly for one month then monthly |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager | H
3.2 | Monitoring - At practical completion |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring - At practical completion | Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - one reading |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager | H
3.3 | Monitoring - During defects liability period |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring - During defects liability period | Surface settlement marker - tri-monthly |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager | H
3.4 | Monitoring - End of defects liability |  | Instrumentation drawings and MMA-DES-GEO-E1-SPC-8510 Trigger action response plan Doc. MMA-DES-GEO-E1-ITP-31384 |  | Monitoring - End of delfection liability | Surface settlement marker - one reading within one month of end of defect liability period |  | Reviewed and accepted by Principals advisor, Design Manager, Construction Manager, Geotechnical Manager | H
3.2 | Survey As-builts |  |  |  |  | During construction and at end |  | Ensure all features and buried items are captured. | H |  |  |  | CAD files
3.3 | As-builts |  |  |  | Mark up of construction drawings to reflect completed works | End of Construction or after completion of preload/surcharge works |  | Approved draft As-built records | H | H |  |  | Red pen mark ups
Note on J46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Whats the purpose of this Fill 12 & 13 - can we delete this red text? Reply: Not sure have removed
Note on L46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this being done? Reply: Will be done alongside 2.1.3
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add in new row for construction of wick drains
Note on H54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Whats this? Reply: Geotech Montiroing Location Drawings
Note on H61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed references to cut 12 and 13
Note on B69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added to clarify design requirements for filling
Note on E73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest we add the TARP reference in here? And rows below down to 2.4.4
Note on E86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added in TARP to all these rows
Note on H89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adjusted text to match spec.