## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 011 - Fill 15 |  |  |  |  | Yes | ITP - 011 - Fill 15 | 56cfed4c-fc80-4fa7-9f5f-38e8f24799d6
section | 1.1.0 Pre-construction Approvals
checkpoint | 1.1.1 - Construction Environmental Management Plan
note | Method/Description - Document Review
note | Test frequency - Prior to work starting
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CEMP
checkpoint | 1.1.2 - Construction Work Plan
note | Method/Description - Document Review
note | Test frequency - Prior to personal starting
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.1.3 - IANZ accredited testing organisation
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - IFC's specification
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - IFC drawings
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Approved earthworks model
note | Method/Description - Document Review
note | Test frequency - Every new Earthworks Model and prior to work commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - ?
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Approval of stockpile location
note | Method/Description - Document Review & Approval
note | Test frequency - Prior to works commencing
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - ?
section | 1.2.0 Material Compliance
checkpoint | 1.2.1 - Structural fill
note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
note | • Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
note | Test frequency - 1 test per 20,000m³
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Buttress Fill
note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
note | Test frequency - 1 test per 20,000m3
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.3 - GAP 65
note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
note | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
note | • Laboratory Triaxial Hydraulic Conductivity - ASTM D5084 – 16a
note | • Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus)
note | Test frequency - Determination of the dry density/water content - 3 tests per source.
note | • PSD - 3 no. tests per source + 1 test per 2,000m3.
note | • Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.4 - GAP 65
note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
note | Test frequency - 3 no. tests per source and 1 test per 2000m3
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.5 - MSE Fill
note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
note | • Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
note | Test frequency - 1 test per 2,500m3
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.6 - MSE Fill
note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
note | Test frequency - 3 no. tests per source and 1 test per 2500m3
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.7 - Drainage blanket and AP 7
note | Method/Description - NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
note | • Laboratory Triaxial Hydraulic Conductivity - ASTM D5084 – 16a
note | Test frequency - PSD - 3 no. tests per source and 1 test per 1000m3
note | • Hydraulic conductivity - 3 no. tests per source
note | Contractor - H
note | Designer - H
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.2.8 - Cement stabilised GAP 65
note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
note | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
note | • PSD - 3 no. tests per source + 1 test per 2,000 m3
note | • UCS - 3 no. tests per source at adopted cement ratio.
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.9 - Cement stabilised structural fill
note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
note | • Atterberg limit - 1 test per source and 1 test per 500 m3
note | • UCS - 3 no. tests per source at adopted cement ratio.
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
section | 1.3.0 Geosynthetics, geogrid and basal reinforcement - Pre-construction
checkpoint | 1.3.1 - Product name Name and address of producer/supplier Manufacturer’s compliance certificate
note | Method/Description - Document Review
note | Test frequency - Check each lot (1 roll)
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
checkpoint | 1.3.2 - Tensile strength (machine direction) - geogrid and basal reinforcement
note | Method/Description - Document Review
note | Test frequency - 1 test per production batch
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
checkpoint | 1.3.3 - Visual inspection - separation geotextiles, basal reinforcement
note | Method/Description - To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration.
note | Test frequency - Check each lot (1 roll)
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.3.4 - Visual inspection - geogrids
note | Method/Description - To inspect geogrid is the proper type and no tears, rips or other signs of deterioration.
note | Test frequency - Check each lot (1 roll)
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
signoff | AUTHORITY HOLDPOINT
section | 1.4.0 Monitoring - Pre-construction
checkpoint | 1.4.1 - Monitoring prior to preload
note | Method/Description - Baseline readings
note | Test frequency - Settlement marker, extensometer, profilometer, and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary - confirming baseline readings satisfactory
signoff | AUTHORITY HOLDPOINT
section | 2.1.0 Pre-filling
checkpoint | 2.1.1 - Set out extents of fill and check against design
note | Method/Description - Survey/visual
note | Test frequency - Prior to Commencement
note | Contractor - W
checkpoint | 2.1.2 - Vegetation Clearance
note | Method/Description - Survey/visual
note | Test frequency - Fill area foot print
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet Designer site report (where advise given)
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.1.4 - Designer witness of in-situ subgrade prior to filling
note | Method/Description - Visual inspection
note | Test frequency - Prior to Filling
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.1.5 - General Undercuts
note | Method/Description - Visual inspection
note | Test frequency - Prior to Filling
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
checkpoint | 2.1.6 - Required undercuts for basal reinforcement installation
note | Method/Description - Visual inspection
note | Test frequency - Prior to Filling
note | Contractor - H
note | Designer - H
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.1.7 - Basal reinforcement installation
note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
note | Contractor - H
note | Designer - H
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.1.8 - Drainage blanket installation
note | Method/Description - Visual inspection
note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
note | Contractor - H
note | Designer - H
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.1.9 - Construction of wick drains
note | Method/Description - Visual inspection and subcontractor record review
note | Test frequency - During wick drain construction
note | Contractor - I
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Wick drain check list
checkpoint | 2.1.10 - Sub soil drainage
note | Method/Description - Inspection
note | Test frequency - During subsoil construction
note | Contractor - I
note | Designer - I
note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint | 2.1.11 - Monitoring Equipment
note | Method/Description - Survey/ data logging
note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
section | 2.2.0 Fill Construction
checkpoint | 2.2.1 - Filling operations
note | Method/Description - Visual inspection
note | Test frequency - Daily
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.2 - Filling operations
note | Method/Description - Survey/visual
note | Test frequency - Daily
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint | 2.2.3 - Insitu fill testing
note | Method/Description - Plateau Test
note | Test frequency - Structural Fill - 1 test per material type per earthworks zone,
note | • Buttress Fill - 1 test per material type per earthworks zone
note | • GAP65 - 1 test per material type per structure / location
note | • Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.4 - Insitu fill testing
note | Method/Description - In situ moisture content and density
note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level
note | • Buttress fill - 1 test per 200m length, approx 1 per 6000 m3
note | • GAP65 - 4 tests per lift per structure
note | • Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
note | • Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.5 - Insitu fill testing
note | Method/Description - Undrained shear Strength
note | Test frequency - Structural fill - 1 test per layer per 1000m2
note | • Buttress Fill - 1 Test per layer per 2000m2
note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.6 - Subgrade Fill Testing
note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.7 - Subgrade Fill Testing
note | Method/Description - Scala Penetrometer Surcharged Fills
note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.8 - Subgrade Fill Testing
note | Method/Description - Benkelman beam and FWD Testing
note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
note | • Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.9 - Subgrade Fill Testing
note | Method/Description - Laboratory Soaked CBR
note | Test frequency - Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
note | Contractor - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.10 - Confirm testing requirements are meet for insitu fill
note | Method/Description - Summarise, interpret and review test records
note | Test frequency - Every test result
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.2.11 - Failed test result and remedial approval
note | Method/Description - Review and approval of remedial action
note | Test frequency - Every failed test and prior to remedial works
note | Contractor - H
note | Designer - H
signoff | AUTHORITY HOLDPOINT
section | 2.3.0 Preload/Surcharge (for embankments requiring preload)
checkpoint | 2.3.1 - Visual inspection for rate of filling
note | Method/Description - Inspection of fill height, rate of filling of 200mm/day (1m per week)
note | Test frequency - To be monitored daily
note | Contractor - H
note | Designer - W
checkpoint | 2.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
note | Method/Description - Review data and TARP levels before releasing HOLD.
note | Test frequency - Before releasing hold periods and allowing filling to continue.
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.3.3 - Removal of preload/surcharge
note | Method/Description - Assessment of monitoring and instrumentation data
note | Test frequency - After completion of proposed hold period
note | Contractor - H
note | Designer - H
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.3.4 - Removal of preload/surcharge
note | Method/Description - Preparation of preload/surcharge report
note | Test frequency - Every four weeks during earthworks operations and at the end and commencement of each earthworks season
section | 2.4.0 Monitoring
checkpoint | 2.4.1 - During earth filling/preloading/surcharging
note | Method/Description - Monitoring during earth filling/preloading/surcharging
note | Test frequency - Plate settlement marker, extensometer, profilometer, water standpipe, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download
note | Contractor - W
checkpoint | 2.4.2 - During preload or surcharge hold period
note | Method/Description - Monitoring during preloading or surcharge hold period
note | Test frequency - Plate settlement marker, extensometer and profilometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download
note | Contractor - W
checkpoint | 2.4.3 - At surcharge removal or hold period release
note | Method/Description - Monitoring at surcharge removal or hold period release
note | Test frequency - Plate settlement marker, extensometer and profilometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following.
note | Contractor - W
checkpoint | 2.4.4 - Post-surcharge or post preload
note | Method/Description - Monitoring post-surcharge or post preload
note | Test frequency - Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - weekly for one month then monthly
note | Contractor - W
checkpoint | 2.4.5 - After asphalt and barrier construction or culvert construction
note | Method/Description - Monitoring after asphalt and barrier construction or culvert construction
note | Test frequency - Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - weekly for one month then monthly
section | 2.5.0 Monitoring reports
checkpoint | 2.5.1 - Preliminary inspection/monitoring report
note | Method/Description - Summary of site inspection / observation / measurement
note | Test frequency - Within one working day of site inspection/observation/measurement
note | Contractor - W
checkpoint | 2.5.2 - Final inspection/monitoring report
note | Method/Description - Full and certified results of monitoring data
note | Test frequency - Within five working day of reading the particular instrument
note | Contractor - W
checkpoint | 2.5.3 - Trigger level report
note | Method/Description - Details of trigger level exceedance or increasing trend Possible cause of exceedance or increasing trend Suggested response (e.g. increased frequency of monitoring)
note | Test frequency - Initial report within 24 hours of observation; Interrim report within 5 working days incorporating all additional monitoring records; Final report once the situation has been resolved through ongoing monitoring / mitigation to acceptable levels
note | Contractor - W
checkpoint | 2.5.4 - Detailed monitoring report
note | Method/Description - Ground movements Groundwater and pore water pressures Variation in characteristics, including strength gain in underlying materials Comparison monitored results against baseline design predictions in both table and graphical format
note | Test frequency - Every 3 months during earthworks operations and at the end of each earthworks season
note | Contractor - W
checkpoint | 2.5.5 - Preload report
note | Method/Description - Comparison between monitored results and baseline design predictions in both table and graphical format
note | Test frequency - Every 4 weeks during earthworks operations and at the end and commencement of each earthworks season
note | Contractor - W
checkpoint | 2.5.6 - Completion report
note | Method/Description - Including all results for all instruments throughout construction period and inventory of which instruments have been decommissioned and those that can continue to be monitored beyond handover.
note | Test frequency - End of Defects Liability Period
note | Contractor - W
section | 3.0 Post Construction
checkpoint | 3.1 - Monitoring - Post construction to practical completion
note | Method/Description - Monitoring - Post construction to practical completion
note | Test frequency - Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - weekly for one month then monthly
note | Contractor - H
checkpoint | 3.2 - Monitoring - At practical completion
note | Method/Description - Monitoring - At practical completion
note | Test frequency - Surface settlement marker, plate settlement marker, extensometer, vibrating wire piezometer - one reading
note | Contractor - H
checkpoint | 3.3 - Monitoring - During defects liability period
note | Method/Description - Monitoring - During defects liability period
note | Test frequency - Surface settlement marker - tri-monthly
note | Contractor - H
checkpoint | 3.4 - Monitoring - End of defects liability
note | Method/Description - Monitoring - End of delfection liability
note | Test frequency - Surface settlement marker - one reading within one month of end of defect liability period
note | Contractor - H
checkpoint | 3.2 - Survey As-builts
note | Test frequency - During construction and at end
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint | 3.3 - As-builts
note | Method/Description - Mark up of construction drawings to reflect completed works
note | Test frequency - End of Construction or after completion of preload/surcharge works
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
signoff | AUTHORITY HOLDPOINT